## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Telecom System Agnes | 1 |  |  | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 | 58.375
1 | order license | 1.1 |  | FS2 | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2.375
2 | final order | 1.2 | 1FS | FS3;FS4;FS6 | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 0.375
3 | ordering equipment | 1.3 | 2FS | FS8 | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 0.375
4 | discussion list | 1.4 | 2FS | FS5 | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 3
5 | final discussion list | 1.5 | 4FS | FS13 | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 3
6 | key technical area | 1.6 | 2FS | FS7 | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 0.041667
7 | technische ruimte klaar and DECT meting | 1.7 | 6FS | FS8 | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 0.20833
8 | installing 19" cabinets | 1.8 | 3FS;7FS | FS9 | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 | 0.375
9 | delivering and installing glassfiber | 1.9 | 8FS | SS10+3d;SS11+3d | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 | 25.375
10 | putting 69 UTP cables in resident rooms | 1.10 | 9SS+3d | FS12;FS14 | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 | 9.375
11 | putting UTP cables with DECT and MIVA toilet | 1.11 | 9SS+3d | FS12;FS14 | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 | 6.9583
12 | delivering and installing I55 PABX | 1.12 | 10FS;11FS | FS13 | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 | 6.375
13 | programming telephone exchange (PABX) | 1.13 | 5FS;12FS | FS17 | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 | 6.375
14 | delivering and installing NOVAbox, IMS, alarmconverter | 1.14 | 10FS;11FS | FS15;FS16 | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 | 6.375
15 | assemble nurse call units 69 pieces | 1.15 | 14FS | FS17 | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 | 20.375
16 | assembly and installation other components regarding nurse call units | 1.16 | 14FS | FS17 | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 | 20.375
17 | installing control location OSPC | 1.17 | 13FS;15FS;16FS | FS18 | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 | 3.375
18 | testing control location OSPC | 1.18 | 17FS | FS19;FS20 | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 | 0.375
19 | nurses training 2 days | 1.19 | 18FS | FS21 | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 | 1.375
20 | prepare delivery | 1.20 | 18FS | FS21 | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 | 1.375
21 | final delivery | 1.21 | 19FS;20FS |  | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | project leader | Renewable | 1 #persons | 0 | 100 | 1;2;4;5;20;21; | 7200
2 | procurement manager | Renewable | 1 #persons | 0 | 55 | 3; | 440
3 | technician | Renewable | 3 #persons | 0 | 46 | 7[2.00 technician];8[3.00 technician];9[3.00 technician];12[3.00 technician];17[3.00 technician];18;20; | 30176
4 | programmer | Renewable | 1 #persons | 0 | 80 | 13;17;18;19; | 6400
5 | steeplejack | Renewable | 1 #persons | 200 | 0 | 12; | 200
6 | subcontracted technicians | Renewable | 9 #persons | 0 | 55.2 | 10[3.00 subcontracted technicians];11[3.00 subcontracted technicians];14[3.00 subcontracted technicians];15[3.00 subcontracted technicians];16[3.00 subcontracted technicians]; | 63590.3984

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Telecom System Agnes | 344h |  |  |  |  | 99 | 100 | 101
1 | order license | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | final order | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | ordering equipment | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | discussion list | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | final discussion list | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | key technical area | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | technische ruimte klaar and DECT meting | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | installing 19" cabinets | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | delivering and installing glassfiber | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | putting 69 UTP cables in resident rooms | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | putting UTP cables with DECT and MIVA toilet | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | delivering and installing I55 PABX | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | programming telephone exchange (PABX) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | delivering and installing NOVAbox, IMS, alarmconverter | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | assemble nurse call units 69 pieces | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | assembly and installation other components regarding nurse call units | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | installing control location OSPC | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | testing control location OSPC | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | nurses training 2 days | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | prepare delivery | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | final delivery | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-05-24 17:00 |  | TP Name | 24/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Telecom System Agnes | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 |  | 5d | [5 empty] | 13526.6396 |  | 7.495% |  | 13526.6396 | 13526.6396
1 | order license | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2011-05-18 08:00 | 3d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
2 | final order | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-05-23 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
3 | ordering equipment | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 2011-05-24 08:00 | 1d | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 440 | 440 | 100 | 100 | 100 | 100 | 100 | 100
4 | discussion list | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | final discussion list | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | key technical area | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-05-24 09:00 | 1h | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
7 | technische ruimte klaar and DECT meting | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 2011-05-24 10:00 | 4h | 9885.6396 | 0 | 0 | 0 | 0 | 9885.6396 | 0 | 100% | Finished | 9885.6396 | 9885.6396 | 100 | 100 | 100 | 100 | 100 | 100
8 | installing 19" cabinets | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 |  | 0 | 0 | 8826.6001 | 1d | 0 | 0 | 0 | 8826.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | delivering and installing glassfiber | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 |  | 0 | 0 | 20750.05 | 18d | 0 | 0 | 0 | 20750.05 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | putting 69 UTP cables in resident rooms | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 |  | 0 | 0 | 11012.4 | 8d | 0 | 0 | 0 | 11012.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | putting UTP cables with DECT and MIVA toilet | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 |  | 0 | 0 | 6660 | 5d | 0 | 0 | 0 | 6660 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | delivering and installing I55 PABX | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 |  | 0 | 0 | 14027.2803 | 5d | 0 | 0 | 0 | 14027.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | programming telephone exchange (PABX) | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 |  | 0 | 0 | 4550 | 5d | 0 | 0 | 0 | 4550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | delivering and installing NOVAbox, IMS, alarmconverter | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 |  | 0 | 0 | 15825 | 5d | 0 | 0 | 0 | 15825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | assemble nurse call units 69 pieces | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 |  | 0 | 0 | 42642 | 15d | 0 | 0 | 0 | 42642 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | assembly and installation other components regarding nurse call units | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 |  | 0 | 0 | 29760 | 15d | 0 | 0 | 0 | 29760 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | installing control location OSPC | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 |  | 0 | 0 | 5881.3 | 2d | 0 | 0 | 0 | 5881.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | testing control location OSPC | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 |  | 0 | 0 | 1008 | 1d | 0 | 0 | 0 | 1008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | nurses training 2 days | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 |  | 0 | 0 | 1280 | 2d | 0 | 0 | 0 | 1280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | prepare delivery | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 |  | 0 | 0 | 2336 | 2d | 0 | 0 | 0 | 2336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | final delivery | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-06-20 17:00 |  | TP Name | 20/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Telecom System Agnes | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 |  | 24d | [5 empty] | 115357.8897 |  | 63.92% |  | 115357.89 | 115357.8897
1 | order license | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2011-05-18 08:00 | 3d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
2 | final order | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-05-23 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
3 | ordering equipment | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 2011-05-24 08:00 | 1d | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 440 | 440 | 100 | 100 | 100 | 100 | 100 | 100
4 | discussion list | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-10 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
5 | final discussion list | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | key technical area | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-05-24 09:00 | 1h | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
7 | technische ruimte klaar and DECT meting | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 2011-05-24 10:00 | 4h | 9885.6396 | 0 | 0 | 0 | 0 | 9885.6396 | 0 | 100% | Finished | 9885.6396 | 9885.6396 | 100 | 100 | 100 | 100 | 100 | 100
8 | installing 19" cabinets | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 | 2011-05-25 08:00 | 1d | 8826.6001 | 0 | 0 | 0 | 0 | 8826.6001 | 0 | 100% | Finished | 8826.6001 | 8826.6001 | 100 | 100 | 100 | 100 | 100 | 100
9 | delivering and installing glassfiber | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 | 2011-05-26 08:00 | 18d | 20750.05 | 0 | 0 | 0 | 0 | 20750.05 | 0 | 100% | Finished | 20750.05 | 20750.05 | 100 | 100 | 100 | 100 | 100 | 100
10 | putting 69 UTP cables in resident rooms | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 | 2011-05-31 08:00 | 8d | 11012.4 | 0 | 0 | 0 | 0 | 11012.4 | 0 | 100% | Finished | 11012.4 | 11012.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | putting UTP cables with DECT and MIVA toilet | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 | 2011-06-01 13:00 | 5d | 6660 | 0 | 0 | 0 | 0 | 6660 | 0 | 100% | Finished | 6660 | 6660 | 100 | 100 | 100 | 100 | 100 | 100
12 | delivering and installing I55 PABX | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 |  | 0 | 0 | 14027.2803 | 5d | 0 | 0 | 0 | 14027.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | programming telephone exchange (PABX) | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 |  | 0 | 0 | 4550 | 5d | 0 | 0 | 0 | 4550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | delivering and installing NOVAbox, IMS, alarmconverter | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 | 2011-06-10 08:00 | 5d | 15825 | 0 | 0 | 0 | 0 | 15825 | 0 | 100% | Finished | 15825 | 15825 | 100 | 100 | 100 | 100 | 100 | 100
15 | assemble nurse call units 69 pieces | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 | 2011-06-17 08:00 | 2d | 25419.6 | 17222.4 | 13d | 0 | 0 | 25419.6 | 17222.4 | 13.33% | Started | 25419.6001 | 25419.6 | 100 | 13.3333 | 13.3333 | 100 | 59.6117 | 13.3333
16 | assembly and installation other components regarding nurse call units | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 | 2011-06-17 08:00 | 2d | 12537.6 | 17222.4 | 13d | 0 | 0 | 12537.6 | 17222.4 | 13.33% | Started | 12537.6001 | 12537.6 | 100 | 13.3333 | 13.3333 | 100 | 42.129 | 13.3333
17 | installing control location OSPC | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 |  | 0 | 0 | 5881.3 | 2d | 0 | 0 | 0 | 5881.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | testing control location OSPC | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 |  | 0 | 0 | 1008 | 1d | 0 | 0 | 0 | 1008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | nurses training 2 days | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 |  | 0 | 0 | 1280 | 2d | 0 | 0 | 0 | 1280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | prepare delivery | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 |  | 0 | 0 | 2336 | 2d | 0 | 0 | 0 | 2336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | final delivery | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-06-27 17:00 |  | TP Name | 27/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Telecom System Agnes | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 |  | 29d | [5 empty] | 129405.8897 |  | 71.7% |  | 129405.8898 | 143433.17
1 | order license | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2011-05-18 08:00 | 3d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
2 | final order | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-05-23 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
3 | ordering equipment | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 2011-05-24 08:00 | 1d | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 440 | 440 | 100 | 100 | 100 | 100 | 100 | 100
4 | discussion list | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-10 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
5 | final discussion list | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-24 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
6 | key technical area | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-05-24 09:00 | 1h | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
7 | technische ruimte klaar and DECT meting | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 2011-05-24 10:00 | 4h | 9885.6396 | 0 | 0 | 0 | 0 | 9885.6396 | 0 | 100% | Finished | 9885.6396 | 9885.6396 | 100 | 100 | 100 | 100 | 100 | 100
8 | installing 19" cabinets | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 | 2011-05-25 08:00 | 1d | 8826.6001 | 0 | 0 | 0 | 0 | 8826.6001 | 0 | 100% | Finished | 8826.6001 | 8826.6001 | 100 | 100 | 100 | 100 | 100 | 100
9 | delivering and installing glassfiber | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 | 2011-05-26 08:00 | 18d | 20750.05 | 0 | 0 | 0 | 0 | 20750.05 | 0 | 100% | Finished | 20750.05 | 20750.05 | 100 | 100 | 100 | 100 | 100 | 100
10 | putting 69 UTP cables in resident rooms | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 | 2011-05-31 08:00 | 8d | 11012.4 | 0 | 0 | 0 | 0 | 11012.4 | 0 | 100% | Finished | 11012.4 | 11012.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | putting UTP cables with DECT and MIVA toilet | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 | 2011-06-01 13:00 | 5d | 6660 | 0 | 0 | 0 | 0 | 6660 | 0 | 100% | Finished | 6660 | 6660 | 100 | 100 | 100 | 100 | 100 | 100
12 | delivering and installing I55 PABX | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 |  | 0 | 0 | 14027.2803 | 5d | 0 | 0 | 0 | 14027.2803 | 0% | Not Started | 0 | 14027.2803 | 100 |  | 0 | 100 |  | 0
13 | programming telephone exchange (PABX) | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 |  | 0 | 0 | 4550 | 5d | 0 | 0 | 0 | 4550 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | delivering and installing NOVAbox, IMS, alarmconverter | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 | 2011-06-10 08:00 | 5d | 15825 | 0 | 0 | 0 | 0 | 15825 | 0 | 100% | Finished | 15825 | 15825 | 100 | 100 | 100 | 100 | 100 | 100
15 | assemble nurse call units 69 pieces | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 | 2011-06-17 08:00 | 7d | 32043.6 | 10598.4 | 8d | 0 | 0 | 32043.6 | 10598.4 | 46.67% | Started | 32043.6 | 32043.6 | 100 | 46.6667 | 46.6667 | 100 | 75.1456 | 46.6667
16 | assembly and installation other components regarding nurse call units | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 | 2011-06-17 08:00 | 7d | 19161.6 | 10598.4 | 8d | 0 | 0 | 19161.6 | 10598.4 | 46.67% | Started | 19161.6 | 19161.6 | 100 | 46.6667 | 46.6667 | 100 | 64.3871 | 46.6667
17 | installing control location OSPC | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 |  | 0 | 0 | 5881.3 | 2d | 0 | 0 | 0 | 5881.3 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | testing control location OSPC | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 |  | 0 | 0 | 1008 | 1d | 0 | 0 | 0 | 1008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | nurses training 2 days | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 |  | 0 | 0 | 1280 | 2d | 0 | 0 | 0 | 1280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | prepare delivery | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 |  | 0 | 0 | 2336 | 2d | 0 | 0 | 0 | 2336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | final delivery | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-07-12 17:00 |  | TP Name | 12/07, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Telecom System Agnes | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 |  | 40d | [5 empty] | 166619.97 |  | 92.32% |  | 166619.97 | 176069.2701
1 | order license | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2011-05-18 08:00 | 3d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
2 | final order | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-05-23 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
3 | ordering equipment | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 2011-05-24 08:00 | 1d | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 440 | 440 | 100 | 100 | 100 | 100 | 100 | 100
4 | discussion list | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-10 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
5 | final discussion list | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-24 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
6 | key technical area | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-05-24 09:00 | 1h | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
7 | technische ruimte klaar and DECT meting | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 2011-05-24 10:00 | 4h | 9885.6396 | 0 | 0 | 0 | 0 | 9885.6396 | 0 | 100% | Finished | 9885.6396 | 9885.6396 | 100 | 100 | 100 | 100 | 100 | 100
8 | installing 19" cabinets | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 | 2011-05-25 08:00 | 1d | 8826.6001 | 0 | 0 | 0 | 0 | 8826.6001 | 0 | 100% | Finished | 8826.6001 | 8826.6001 | 100 | 100 | 100 | 100 | 100 | 100
9 | delivering and installing glassfiber | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 | 2011-05-26 08:00 | 18d | 20750.05 | 0 | 0 | 0 | 0 | 20750.05 | 0 | 100% | Finished | 20750.05 | 20750.05 | 100 | 100 | 100 | 100 | 100 | 100
10 | putting 69 UTP cables in resident rooms | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 | 2011-05-31 08:00 | 8d | 11012.4 | 0 | 0 | 0 | 0 | 11012.4 | 0 | 100% | Finished | 11012.4 | 11012.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | putting UTP cables with DECT and MIVA toilet | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 | 2011-06-01 13:00 | 5d | 6660 | 0 | 0 | 0 | 0 | 6660 | 0 | 100% | Finished | 6660 | 6660 | 100 | 100 | 100 | 100 | 100 | 100
12 | delivering and installing I55 PABX | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 | 2011-07-05 08:00 | 5d | 14027.2803 | 0 | 0 | 0 | 0 | 14027.2803 | 0 | 100% | Finished | 14027.2803 | 14027.2803 | 100 | 100 | 100 | 100 | 100 | 100
13 | programming telephone exchange (PABX) | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 | 2011-07-12 08:00 | 1d | 1990 | 2560 | 4d | 0 | 0 | 1990 | 2560 | 20% | Started | 1990 | 4550 | 100 | 20 | 20 | 100 | 43.7363 | 20
14 | delivering and installing NOVAbox, IMS, alarmconverter | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 | 2011-06-10 08:00 | 5d | 15825 | 0 | 0 | 0 | 0 | 15825 | 0 | 100% | Finished | 15825 | 15825 | 100 | 100 | 100 | 100 | 100 | 100
15 | assemble nurse call units 69 pieces | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 | 2011-06-17 08:00 | 15d | 42642 | 0 | 0 | 0 | 0 | 42642 | 0 | 100% | Finished | 42642 | 42642 | 100 | 100 | 100 | 100 | 100 | 100
16 | assembly and installation other components regarding nurse call units | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 | 2011-06-17 08:00 | 15d | 29760 | 0 | 0 | 0 | 0 | 29760 | 0 | 100% | Finished | 29760 | 29760 | 100 | 100 | 100 | 100 | 100 | 100
17 | installing control location OSPC | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 |  | 0 | 0 | 5881.3 | 2d | 0 | 0 | 0 | 5881.3 | 0% | Not Started | 0 | 5881.3 | 100 |  | 0 | 100 |  | 0
18 | testing control location OSPC | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 |  | 0 | 0 | 1008 | 1d | 0 | 0 | 0 | 1008 | 0% | Not Started | 0 | 1008 | 100 |  | 0 | 100 |  | 0
19 | nurses training 2 days | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 |  | 0 | 0 | 1280 | 2d | 0 | 0 | 0 | 1280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | prepare delivery | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 |  | 0 | 0 | 2336 | 2d | 0 | 0 | 0 | 2336 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | final delivery | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 1d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-07-29 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Telecom System Agnes | 2011-05-18 08:00 | 2011-07-15 17:00 | 43d |  |  | 72478.8701 |  |  | 180485.2701 |  | 53d | [5 empty] | 180485.2701 |  | 100% |  | 180485.2701 | 180485.2701
1 | order license | 2011-05-18 08:00 | 2011-05-20 17:00 | 3d | project leader | 2400 | 0 | 0 | 0 | 2400 | 2011-05-18 08:00 | 3d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 2400 | 2400 | 100 | 100 | 100 | 100 | 100 | 100
2 | final order | 2011-05-23 08:00 | 2011-05-23 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-05-23 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
3 | ordering equipment | 2011-05-24 08:00 | 2011-05-24 17:00 | 1d | procurement manager | 440 | 0 | 0 | 0 | 440 | 2011-05-24 08:00 | 1d | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 440 | 440 | 100 | 100 | 100 | 100 | 100 | 100
4 | discussion list | 2011-06-10 10:00 | 2011-06-13 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-10 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
5 | final discussion list | 2011-06-24 10:00 | 2011-06-27 10:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-06-24 10:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100
6 | key technical area | 2011-05-24 09:00 | 2011-05-24 10:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2011-05-24 09:00 | 1h | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
7 | technische ruimte klaar and DECT meting | 2011-05-24 10:00 | 2011-05-24 15:00 | 4h | technician[2.00 #3] | 368 | 9517.6396 | 0 | 0 | 9885.6396 | 2011-05-24 10:00 | 4h | 9885.6396 | 0 | 0 | 0 | 0 | 9885.6396 | 0 | 100% | Finished | 9885.6396 | 9885.6396 | 100 | 100 | 100 | 100 | 100 | 100
8 | installing 19" cabinets | 2011-05-25 08:00 | 2011-05-25 17:00 | 1d | technician[3.00 #3] | 1104 | 7722.6001 | 0 | 0 | 8826.6001 | 2011-05-25 08:00 | 1d | 8826.6001 | 0 | 0 | 0 | 0 | 8826.6001 | 0 | 100% | Finished | 8826.6001 | 8826.6001 | 100 | 100 | 100 | 100 | 100 | 100
9 | delivering and installing glassfiber | 2011-05-26 08:00 | 2011-06-20 17:00 | 18d | technician[3.00 #3] | 19872 | 878.05 | 0 | 0 | 20750.05 | 2011-05-26 08:00 | 18d | 20750.05 | 0 | 0 | 0 | 0 | 20750.05 | 0 | 100% | Finished | 20750.05 | 20750.05 | 100 | 100 | 100 | 100 | 100 | 100
10 | putting 69 UTP cables in resident rooms | 2011-05-31 08:00 | 2011-06-09 17:00 | 8d | subcontracted technicians[3.00 #9] | 10598.4 | 414 | 0 | 0 | 11012.4 | 2011-05-31 08:00 | 8d | 11012.4 | 0 | 0 | 0 | 0 | 11012.4 | 0 | 100% | Finished | 11012.4 | 11012.4 | 100 | 100 | 100 | 100 | 100 | 100
11 | putting UTP cables with DECT and MIVA toilet | 2011-06-01 13:00 | 2011-06-08 12:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 36 | 0 | 0 | 6660 | 2011-06-01 13:00 | 5d | 6660 | 0 | 0 | 0 | 0 | 6660 | 0 | 100% | Finished | 6660 | 6660 | 100 | 100 | 100 | 100 | 100 | 100
12 | delivering and installing I55 PABX | 2011-06-21 08:00 | 2011-06-27 17:00 | 5d | steeplejack;technician[3.00 #3] | 5720 | 8307.2803 | 0 | 0 | 14027.2803 | 2011-07-05 08:00 | 5d | 14027.2803 | 0 | 0 | 0 | 0 | 14027.2803 | 0 | 100% | Finished | 14027.2803 | 14027.2803 | 100 | 100 | 100 | 100 | 100 | 100
13 | programming telephone exchange (PABX) | 2011-06-28 08:00 | 2011-07-04 17:00 | 5d | programmer | 3200 | 1350 | 0 | 0 | 4550 | 2011-07-12 08:00 | 5d | 4550 | 0 | 0 | 0 | 0 | 4550 | 0 | 100% | Finished | 4550 | 4550 | 100 | 100 | 100 | 100 | 100 | 100
14 | delivering and installing NOVAbox, IMS, alarmconverter | 2011-06-10 08:00 | 2011-06-16 17:00 | 5d | subcontracted technicians[3.00 #9] | 6624 | 9201 | 0 | 0 | 15825 | 2011-06-10 08:00 | 5d | 15825 | 0 | 0 | 0 | 0 | 15825 | 0 | 100% | Finished | 15825 | 15825 | 100 | 100 | 100 | 100 | 100 | 100
15 | assemble nurse call units 69 pieces | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 22770 | 0 | 0 | 42642 | 2011-06-17 08:00 | 15d | 42642 | 0 | 0 | 0 | 0 | 42642 | 0 | 100% | Finished | 42642 | 42642 | 100 | 100 | 100 | 100 | 100 | 100
16 | assembly and installation other components regarding nurse call units | 2011-06-17 08:00 | 2011-07-07 17:00 | 15d | subcontracted technicians[3.00 #9] | 19872 | 9888 | 0 | 0 | 29760 | 2011-06-17 08:00 | 15d | 29760 | 0 | 0 | 0 | 0 | 29760 | 0 | 100% | Finished | 29760 | 29760 | 100 | 100 | 100 | 100 | 100 | 100
17 | installing control location OSPC | 2011-07-08 08:00 | 2011-07-11 17:00 | 2d | programmer;technician[3.00 #3] | 3488 | 2393.3 | 0 | 0 | 5881.3 | 2011-07-22 08:00 | 2d | 5881.3 | 0 | 0 | 0 | 0 | 5881.3 | 0 | 100% | Finished | 5881.3 | 5881.3 | 100 | 100 | 100 | 100 | 100 | 100
18 | testing control location OSPC | 2011-07-12 08:00 | 2011-07-12 17:00 | 1d | programmer;technician | 1008 | 0 | 0 | 0 | 1008 | 2011-07-26 08:00 | 1d | 1008 | 0 | 0 | 0 | 0 | 1008 | 0 | 100% | Finished | 1008 | 1008 | 100 | 100 | 100 | 100 | 100 | 100
19 | nurses training 2 days | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | programmer | 1280 | 0 | 0 | 0 | 1280 | 2011-07-27 08:00 | 2d | 1280 | 0 | 0 | 0 | 0 | 1280 | 0 | 100% | Finished | 1280 | 1280 | 100 | 100 | 100 | 100 | 100 | 100
20 | prepare delivery | 2011-07-13 08:00 | 2011-07-14 17:00 | 2d | project leader;technician | 2336 | 0 | 0 | 0 | 2336 | 2011-07-27 09:00 | 2d | 2336 | 0 | 0 | 0 | 0 | 2336 | 0 | 100% | Finished | 2336 | 2336 | 100 | 100 | 100 | 100 | 100 | 100
21 | final delivery | 2011-07-15 08:00 | 2011-07-15 17:00 | 1d | project leader | 800 | 0 | 0 | 0 | 800 | 2011-07-29 08:00 | 1d | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 100% | Finished | 800 | 800 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
24/05, 2011 | 2011-05-18 08:00 | 2011-05-24 17:00 | 13526.6396 | 13526.6396 | 13526.6396 | 2011-05-24 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
20/06, 2011 | 2011-05-24 17:00 | 2011-06-20 17:00 | 115357.8897 | 115357.89 | 115357.8897 | 2011-06-20 17:00 | 0.00027637 | 100% | 0.00027637 | 100% | 0 | 100% | 100% | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 180485.2698 | 180485.2696 | 180485.2696 | 180485.2698 | 180485.2695 | 180485.2696 | 180485.2696 | 180485.2697 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
27/06, 2011 | 2011-06-20 17:00 | 2011-06-27 17:00 | 143433.17 | 129405.8898 | 129405.8897 | 2011-06-22 11:00 | -14027.2802 | 90.22% | 7.8964e-05 | 100% | -3d 5h | 87.5% | 92.23% | 2011-07-21 11:00 | 2011-07-22 14:00 | 2011-07-22 14:00 | 2011-07-20 16:00 | 2011-07-22 14:00 | 2011-07-22 14:00 | 2011-07-21 14:00 | 2011-07-26 09:00 | 2011-07-26 09:00 | 180485.27 | 180485.2699 | 186022.1492 | 187782.3243 | 186022.1491 | 187782.3243 | 181504.2793 | 181794.9976 | 0.875 | 1 | 0.9022 | 0.9223 | -3.625 | 1 | 1 | 0.875 | 1
12/07, 2011 | 2011-06-27 17:00 | 2011-07-12 17:00 | 176069.2701 | 166619.97 | 166619.97 | 2011-07-06 17:00 | -9449.3 | 94.63% | 9.5367e-06 | 100% | -4d | 90% | 98.46% | 2011-07-20 10:00 | 2011-07-20 12:00 | 2011-07-20 12:00 | 2011-07-20 09:00 | 2011-07-20 12:00 | 2011-07-20 12:00 | 2011-07-21 17:00 | 2011-07-22 15:00 | 2011-07-22 15:00 | 180485.27 | 180485.27 | 181271.5946 | 182025.8589 | 181271.5946 | 182025.8589 | 180635.7096 | 180768.2354 | 0.9 | 1 | 0.94633 | 0.98463 | -4 | 1 | 1 | 0.9 | 1
Actual Schedule | 2011-07-12 17:00 | 2011-07-29 17:00 | 180485.2701 | 180485.2701 | 180485.2701 | 2011-07-15 17:00 | 0 | 100% | 0 | 100% | -10d | 81.13% | 100% | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-15 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 2011-07-29 17:00 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 180485.2701 | 0.81132 | 1 | 1 | 1 | -10 | 1 | 1 | 0.81132 | 1