## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Gabala Resort Outdoor Pool | 1 |  |  | 2013-03-18 08:00 | 2013-05-30 17:00 | 54d |  |  | 21053 |  |  | 47413 | 73.375
1 | Preparation work | 1.1 |  | FS2 | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d | Standard operator[3.00 #3] | 1800 | 0 | 0 | 0 | 1800 | 4.375
2 | Earthworks and digging | 1.2 | 1FS | FS3;FS9 | 2013-03-25 08:00 | 2013-04-02 17:00 | 7d | Bricklayers[3.00 #3] | 3360 | 3652 | 0 | 0 | 7012 | 8.375
3 | Mount shuttering | 1.3 | 2FS | FS4 | 2013-04-03 08:00 | 2013-04-08 17:00 | 4d | Standard operator[2.00 #3] | 960 | 735 | 0 | 0 | 1695 | 5.375
4 | Formwork and steel placement | 1.4 | 3FS | FS5 | 2013-04-09 08:00 | 2013-04-12 17:00 | 4d | Standard operator[3.00 #3] | 1440 | 634 | 0 | 0 | 2074 | 3.375
5 | Concrete shell pour | 1.5 | 4FS | FS6 | 2013-04-15 08:00 | 2013-04-22 17:00 | 6d | Concrete finisher[3.00 #3] | 3312 | 3782 | 0 | 0 | 7094 | 7.375
6 | Mount water inlets/outlets | 1.6 | 5FS | FS7;FS11 | 2013-04-23 08:00 | 2013-04-24 17:00 | 2d | Standard operator[2.00 #3] | 480 | 300 | 0 | 0 | 780 | 1.375
7 | Lay tiles | 1.7 | 6FS | FS8 | 2013-04-25 08:00 | 2013-05-01 17:00 | 5d | Tilers[2.00 #2] | 1600 | 600 | 0 | 0 | 2200 | 6.375
8 | Lay pipes | 1.8 | 7FS | FS10 | 2013-05-02 08:00 | 2013-05-08 17:00 | 5d | Plumber[3.00 #3] | 3360 | 450 | 0 | 0 | 3810 | 6.375
9 | Connect pipes | 1.9 | 2FS | FS10 | 2013-04-03 08:00 | 2013-04-05 17:00 | 3d | Plumber[2.00 #3] | 1344 | 250 | 0 | 0 | 1594 | 2.375
10 | Mount filter unit | 1.10 | 8FS;9FS | FS12 | 2013-05-09 08:00 | 2013-05-09 17:00 | 1d | Standard operator[2.00 #3] | 240 | 1200 | 0 | 0 | 1440 | 0.375
11 | Connect filtering system | 1.11 | 6FS | FS12;FS13 | 2013-04-25 08:00 | 2013-04-25 17:00 | 1d | Standard operator | 120 | 250 | 0 | 0 | 370 | 0.375
12 | Mount pumps | 1.12 | 10FS;11FS | FS14 | 2013-05-10 08:00 | 2013-05-10 17:00 | 1d | Heating and cooling specialist[2.00 #2] | 432 | 800 | 0 | 0 | 1232 | 0.375
13 | Connect pumps | 1.13 | 11FS | FS14 | 2013-04-26 08:00 | 2013-04-26 17:00 | 1d |  | 0 | 150 | 0 | 0 | 150 | 0.375
14 | Internal finishing works of construction | 1.14 | 12FS;13FS | FS15 | 2013-05-13 08:00 | 2013-05-14 17:00 | 2d | Standard operator[2.00 #3];Heating and cooling specialist;Electrician | 1552 | 400 | 0 | 0 | 1952 | 1.375
15 | Final cleaning | 1.15 | 14FS | FS16 | 2013-05-15 08:00 | 2013-05-20 17:00 | 4d | Standard operator[2.00 #3] | 960 | 600 | 0 | 0 | 1560 | 5.375
16 | Surrounding design works | 1.16 | 15FS | FS17 | 2013-05-21 08:00 | 2013-05-27 17:00 | 5d | Designer;Standard operator[2.00 #3];Electrician | 4800 | 6000 | 0 | 0 | 10800 | 6.375
17 | Fill with water | 1.17 | 16FS | FS18 | 2013-05-28 08:00 | 2013-05-28 17:00 | 1d | Standard operator | 120 | 250 | 0 | 0 | 370 | 0.375
18 | Chemical treatment | 1.18 | 17FS |  | 2013-05-29 08:00 | 2013-05-30 17:00 | 2d | Chemical cleaning specialist | 480 | 1000 | 0 | 0 | 1480 | 1.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Standard operator | Renewable | 3 | 0 | 15 | 1[3.00 Standard operator];3[2.00 Standard operator];4[3.00 Standard operator];6[2.00 Standard operator];10[2.00 Standard operator];11;14[2.00 Standard operator];15[2.00 Standard operator];16[2.00 Standard operator];17; | 7800
2 | Bricklayers | Renewable | 3 | 0 | 20 | 2[3.00 Bricklayers]; | 3360
3 | Concrete finisher | Renewable | 3 | 0 | 23 | 5[3.00 Concrete finisher]; | 3312
4 | Tilers | Renewable | 2 | 0 | 20 | 7[2.00 Tilers]; | 1600
5 | Plumber | Renewable | 3 | 0 | 28 | 8[3.00 Plumber];9[2.00 Plumber]; | 4704
6 | Heating and cooling specialist | Renewable | 2 | 0 | 27 | 12[2.00 Heating and cooling specialist];14; | 864
7 | Designer | Renewable | 1 | 0 | 50 | 16; | 2000
8 | Chemical cleaning specialist | Renewable | 1 | 0 | 30 | 18; | 480
9 | Electrician | Renewable | 1 | 0 | 40 | 14;16; | 2240

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Gabala Resort Outdoor Pool | 432h |  |  |  |  | 99 | 100 | 101
1 | Preparation work | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Earthworks and digging | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Mount shuttering | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Formwork and steel placement | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Concrete shell pour | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Mount water inlets/outlets | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Lay tiles | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Lay pipes | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Connect pipes | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Mount filter unit | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Connect filtering system | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Mount pumps | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Connect pumps | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Internal finishing works of construction | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Final cleaning | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Surrounding design works | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Fill with water | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Chemical treatment | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold