## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Station Ghent | 1 |  |  | 2010-10-04 08:00 | 2012-08-17 17:00 | 440d |  |  | 0 |  |  | 0 | 683.375
5 | Voorbereiding uitvoering | 1.1 |  | FS22-8w;FS12-2w;FS6-9w;FS18+20w 3d | 2010-10-04 08:00 | 2011-02-15 17:00 | 92d |  | 0 | 0 | 0 | 0 | 0 | 134.375
6 | Werfinstallatie | 1.2 | 5FS-9w | SS7;FS23+1w;FS27+2w;FS31+3w | 2010-12-09 08:00 | 2011-01-05 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 27.375
7 | Bronbemaling | 1.3 | 6SS |  | 2011-03-23 08:00 | 2011-06-01 17:00 | 46d |  | 0 | 0 | 0 | 0 | 0 | 70.375
14 | Grondwerken en infrastructuur | 1.4 |  |  | 2010-12-20 08:00 | 2011-10-17 17:00 | 191d |  |  | 0 |  |  | 0 | 301.375
22 | Voorbereiding & verwijdering ballast | 1.4.1 | 5FS-8w | FS23-35w | 2010-12-20 08:00 | 2011-10-04 17:00 | 182d |  | 0 | 0 | 0 | 0 | 0 | 288.375
26 | Zone 2: As 84-88 | 1.4.2 |  |  | 2011-01-13 08:00 | 2011-08-03 17:00 | 125d |  |  | 0 |  |  | 0 | 202.375
23 | Afbraakwerken | 1.4.2.1 | 6FS+1w;22FS-35w | FS24-5w | 2011-01-13 08:00 | 2011-02-23 17:00 | 30d |  | 0 | 0 | 0 | 0 | 0 | 41.375
24 | Grondwerken | 1.4.2.2 | 23FS-5w | FS25-3d;FS28-3w | 2011-01-25 08:00 | 2011-03-28 17:00 | 45d |  | 0 | 0 | 0 | 0 | 0 | 62.375
25 | Infrastructuur | 1.4.2.3 | 24FS-3d | FS21+2w;FS13-9w | 2011-03-24 08:00 | 2011-08-03 17:00 | 75d |  | 0 | 0 | 0 | 0 | 0 | 132.375
30 | Zone 3: As 84-79 | 1.4.3 |  |  | 2011-01-21 08:00 | 2011-10-17 17:00 | 172d |  |  | 0 |  |  | 0 | 269.375
27 | Afbraakwerken | 1.4.3.1 | 6FS+2w | FS28-8w | 2011-01-21 08:00 | 2011-05-12 17:00 | 75d |  | 0 | 0 | 0 | 0 | 0 | 111.375
28 | Grondwerken | 1.4.3.2 | 24FS-3w;27FS-8w | FS29-3w;FS32-3w | 2011-03-11 08:00 | 2011-05-26 17:00 | 50d |  | 0 | 0 | 0 | 0 | 0 | 76.375
29 | Infrastructuur | 1.4.3.3 | 28FS-3w | FS21-9w;FS15-20w | 2011-05-10 08:00 | 2011-10-17 17:00 | 100d |  | 0 | 0 | 0 | 0 | 0 | 160.375
34 | Zone 4: As 79-74 | 1.5 |  |  | 2011-02-01 08:00 | 2011-10-17 17:00 | 165d |  |  | 0 |  |  | 0 | 258.375
31 | Afbraakwerken | 1.5.1 | 6FS+3w | FS33-6w | 2011-02-01 08:00 | 2011-06-06 17:00 | 85d |  | 0 | 0 | 0 | 0 | 0 | 125.375
32 | Grondwerken | 1.5.2 | 28FS-3w | FS33-1w 2d | 2011-05-11 08:00 | 2011-06-14 17:00 | 25d |  | 0 | 0 | 0 | 0 | 0 | 34.375
33 | Infrastructuur | 1.5.3 | 32FS-1w 2d;31FS-6w | FS21-9w | 2011-06-07 08:00 | 2011-10-17 17:00 | 80d |  | 0 | 0 | 0 | 0 | 0 | 132.375
17 | Superstructuur station | 1.6 |  |  | 2011-02-02 08:00 | 2012-03-01 17:00 | 257d |  |  | 0 |  |  | 0 | 393.375
12 | Zone 1: As 88-97 | 1.6.1 | 5FS-2w |  | 2011-02-02 08:00 | 2012-03-01 17:00 | 257d |  | 0 | 0 | 0 | 0 | 0 | 393.375
13 | Zone 2: As 84-88 | 1.6.2 | 25FS-9w | FS15-4w;FS16-3w;FS18-3w 3d | 2011-05-16 08:00 | 2011-09-21 17:00 | 78d |  | 0 | 0 | 0 | 0 | 0 | 128.375
15 | Zone 3: As 84-79 | 1.6.3 | 29FS-20w;13FS-4w | FS21-20w;FS18-19w | 2011-08-25 08:00 | 2012-01-10 17:00 | 94d |  | 0 | 0 | 0 | 0 | 0 | 138.375
16 | Zone 4: As 79-74 | 1.6.4 | 13FS-3w | FS21-24w;FS18-23w | 2011-09-02 08:00 | 2012-02-06 17:00 | 107d |  | 0 | 0 | 0 | 0 | 0 | 157.375
18 | Perron en overkappingen | 1.7 | 5FS+20w 3d;13FS-3w 3d;15FS-19w;16FS-23w |  | 2011-08-29 08:00 | 2012-08-17 17:00 | 230d |  | 0 | 0 | 0 | 0 | 0 | 354.375
21 | Grote overkapping | 1.8 | 25FS+2w;29FS-9w;33FS-9w;15FS-20w;16FS-24w |  | 2011-08-18 08:00 | 2012-08-08 17:00 | 230d |  | 0 | 0 | 0 | 0 | 0 | 356.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Station Ghent | 3520h |  |  |  |  | 99 | 100 | 101
5 | Voorbereiding uitvoering | 736h | manual - absolute | 667 | 736 | 982 | 90 | 100 | 133
6 | Werfinstallatie | 120h | manual - absolute | 105 | 120 | 125 | 87 | 100 | 104
7 | Bronbemaling | 368h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Grondwerken en infrastructuur | 1528h |  |  |  |  | 99 | 100 | 101
22 | Voorbereiding & verwijdering ballast | 1456h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Zone 2: As 84-88 | 1000h |  |  |  |  | 99 | 100 | 101
23 | Afbraakwerken | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Grondwerken | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Infrastructuur | 600h | manual - absolute | 563 | 600 | 720 | 93 | 100 | 120
30 | Zone 3: As 84-79 | 1376h |  |  |  |  | 99 | 100 | 101
27 | Afbraakwerken | 600h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Grondwerken | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Infrastructuur | 800h | manual - absolute | 748 | 800 | 961 | 93 | 100 | 120
34 | Zone 4: As 79-74 | 1320h |  |  |  |  | 99 | 100 | 101
31 | Afbraakwerken | 680h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Grondwerken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Infrastructuur | 640h | manual - absolute | 588 | 640 | 768 | 91 | 100 | 120
17 | Superstructuur station | 2056h |  |  |  |  | 99 | 100 | 101
12 | Zone 1: As 88-97 | 2056h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Zone 2: As 84-88 | 624h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Zone 3: As 84-79 | 752h | manual - absolute | 651 | 752 | 782 | 86 | 100 | 103
16 | Zone 4: As 79-74 | 856h | manual - absolute | 731 | 856 | 903 | 85 | 100 | 105
18 | Perron en overkappingen | 1840h | manual - absolute | 1725 | 1840 | 2208 | 93 | 100 | 120
21 | Grote overkapping | 1840h | manual - absolute | 1726 | 1840 | 2208 | 93 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2010-12-27
1:00 - 2:00 | No | Tuesday | Yes | 2010-12-28
2:00 - 3:00 | No | Wednesday | Yes | 2010-12-29
3:00 - 4:00 | No | Thursday | Yes | 2010-12-30
4:00 - 5:00 | No | Friday | Yes | 2010-12-31
5:00 - 6:00 | No | Saturday | No | 2011-07-04
6:00 - 7:00 | No | Sunday | No | 2011-07-05
7:00 - 8:00 | No |  |  | 2011-07-06
8:00 - 9:00 | Yes |  |  | 2011-07-07
9:00 - 10:00 | Yes |  |  | 2011-07-08
10:00 - 11:00 | Yes |  |  | 2011-07-11
11:00 - 12:00 | Yes |  |  | 2011-07-12
12:00 - 13:00 | No |  |  | 2011-07-13
13:00 - 14:00 | Yes |  |  | 2011-07-14
14:00 - 15:00 | Yes |  |  | 2011-07-15
15:00 - 16:00 | Yes |  |  | 2011-07-18
16:00 - 17:00 | Yes |  |  | 2011-07-19
17:00 - 18:00 | No |  |  | 2011-07-20
18:00 - 19:00 | No |  |  | 2011-07-21
19:00 - 20:00 | No |  |  | 2011-07-22
20:00 - 21:00 | No |  |  | 2011-12-26
21:00 - 22:00 | No |  |  | 2011-12-27
22:00 - 23:00 | No |  |  | 2011-12-28
23:00 - 0:00 | No |  |  | 2011-12-29
2011-12-30
2012-07-02
Generated by PMConverter v1.1.3 |  |  |  | 2012-07-03
2012-07-04
2012-07-05
2012-07-06
2012-07-09
2012-07-10
2012-07-11
2012-07-12
2012-07-13
2012-07-16
2012-07-17
2012-07-18
2012-07-19
2012-07-20
2012-12-24
2012-12-25
2012-12-26
2012-12-27
2012-12-28
2013-07-01
2013-07-02
2013-07-03
2013-07-04
2013-07-05
2013-07-08
2013-07-09
2013-07-10
2013-07-11
2013-07-12
2013-07-15
2013-07-16
2013-07-17
2013-07-18
2013-07-19
2011-04-11
2011-04-12
2011-04-13
2011-04-14
2011-04-15
2012-04-09
2012-04-10
2012-04-11
2012-04-12
2012-04-13
2013-04-15
2013-04-16
2013-04-17
2013-04-18
2013-04-19

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold