## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Brussels Finance Tower | 1 |  |  | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 | 594.375
1 | Koningstraat | 1.1 |  |  | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 | 594.375
2 | Werfinstallatie | 1.1.1 |  |  | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 594.375
9 | Beton | 1.1.2 |  |  | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 | 254.375
10 | Verdiep +3 | 1.1.2.1 |  |  | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 18.375
11 | Verdiep +4 | 1.1.2.2 |  |  | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 16.375
12 | Verdiep +5 | 1.1.2.3 |  | FS13+2w 1d | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 18.375
13 | Verdiep +6 | 1.1.2.4 | 12FS+2w 1d |  | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 18.375
14 | Verdiep +7 | 1.1.2.5 |  |  | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 18.375
15 | Verdiep +8 | 1.1.2.6 |  |  | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 18.375
16 | Verdiep +9 | 1.1.2.7 |  |  | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 18.375
17 | Verdiep +10 | 1.1.2.8 |  |  | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 18.375
18 | Verdiep +2 | 1.1.2.9 |  |  | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 16.375
19 | Verdiep +1 | 1.1.2.10 |  |  | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 16.375
20 | Verdiep glk | 1.1.2.11 |  |  | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 39.375
21 | Buitentrappen (2 fazen) | 1.1.2.12 |  |  | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 33.375
765 | Gevels inbegrepen natuursteen (start = landmeter) | 1.1.3 |  |  | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 214.375
764 | Gevels Wind & waterdicht +3 t/m +10 | 1.1.4 |  |  | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 26.375
45 | Technisch lokaal +10 | 1.1.5 |  |  | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 | 23.375
46 | Metselwerk | 1.1.5.1 |  |  | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 11.375
48 | HVAC Groepen | 1.1.5.2 |  |  | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2.375
49 | Dakdichting | 1.1.6 |  |  | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 | 161.375
50 | Balkons : wachtslabben | 1.1.6.1 |  |  | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 8.375
51 | Balkons: horizontaal definitief | 1.1.6.2 |  | SS55+2d | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 4.375
52 | Boven Schachten | 1.1.6.3 |  |  | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 4.375
53 | Metselwerk, helling, dampscherm, slabben | 1.1.6.4 |  |  | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 23.375
54 | Helling, dampscherm, definitief | 1.1.6.5 |  | FS56 | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 18.375
55 | Definitief | 1.1.6.6 | 51SS+2d |  | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 29.375
56 | Piste renigingsmachine op dak | 1.1.7 | 54FS |  | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 25.375
57 | Renigingsmachine | 1.1.8 |  |  | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 6.375
58 | Metselwerk (behalve gaslokaal) | 1.1.9 |  |  | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 53.375
59 | Sluiten technische schachten | 1.1.10 |  | SS61+1w | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 29.375
61 | Pleisterwerken | 1.1.11 | 59SS+1w |  | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 44.375
62 | Chapes | 1.1.12 |  |  | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 52.375
63 | Vloeren & faience | 1.1.13 |  |  | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 48.375
64 | Binnenschrijnwerk | 1.1.14 |  |  | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 67.375
65 | Tapijt | 1.1.15 |  |  | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 | 49.375
66 | Smeedwerk | 1.1.16 |  |  | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 34.375
67 | Schilderwerken | 1.1.17 |  | FS68 | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 55.375
68 | Einde opkuisen | 1.1.18 | 67FS | FS69 | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 13.375
69 | Voorlopige receptie | 1.1.19 | 68FS |  | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 13.375
752 | Verdiep +3 | 1.1.20 |  |  | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 357.375
753 | Verdiep +4 | 1.1.21 |  |  | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 352.375
754 | Verdiep +5 | 1.1.22 |  |  | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 347.375
755 | Verdiep +6 | 1.1.23 |  |  | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 344.375
756 | Verdiep +7 | 1.1.24 |  |  | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 339.375
757 | Verdiep +8 | 1.1.25 |  |  | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 336.375
758 | Verdiep +9 | 1.1.26 |  |  | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 328.375
759 | Verdiep +10 | 1.1.27 |  |  | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 323.375
760 | Technische lokaal +10 | 1.1.28 |  |  | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 120.375
761 | Verdiep +2 | 1.1.29 |  |  | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 301.375
762 | Verdiep +1 | 1.1.30 |  |  | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 | 300.375
763 | Verdiep glk | 1.1.31 |  |  | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 | 299.375
742 | Liften | 1.1.32 |  |  | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 | 298.375
743 | Goederenlift KGL1 | 1.1.32.1 |  |  | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 | 298.375
744 | KGL1 - werflift montage | 1.1.32.1.1 |  | FS745 | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 73.375
745 | KGL1 werflift | 1.1.32.1.2 | 744FS | FS746 | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 | 161.375
746 | KGL1 opkuisen | 1.1.32.1.3 | 745FS |  | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 | 13.375
747 | Personenliften KPL1-4 | 1.1.32.2 |  |  | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 | 56.375
748 | KPL 1 | 1.1.32.2.1 |  |  | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 56.375
749 | KPL 2 | 1.1.32.2.2 |  |  | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 56.375
750 | KPL 3 | 1.1.32.2.3 |  |  | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 56.375
751 | KPL 4 | 1.1.32.2.4 |  |  | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 56.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Brussels Finance Tower | 3400h |  |  |  |  | 99 | 100 | 101
1 | Koningstraat | 3400h |  |  |  |  | 99 | 100 | 101
2 | Werfinstallatie | 3400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Beton | 1464h |  |  |  |  | 99 | 100 | 101
10 | Verdiep +3 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Verdiep +4 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Verdiep +5 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Verdiep +6 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Verdiep +7 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Verdiep +8 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Verdiep +9 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Verdiep +10 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Verdiep +2 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Verdiep +1 | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Verdiep glk | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Buitentrappen (2 fazen) | 192h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
765 | Gevels inbegrepen natuursteen (start = landmeter) | 1240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
764 | Gevels Wind & waterdicht +3 t/m +10 | 152h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Technisch lokaal +10 | 144h |  |  |  |  | 99 | 100 | 101
46 | Metselwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | HVAC Groepen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Dakdichting | 928h |  |  |  |  | 99 | 100 | 101
50 | Balkons : wachtslabben | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Balkons: horizontaal definitief | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Boven Schachten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Metselwerk, helling, dampscherm, slabben | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Helling, dampscherm, definitief | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Definitief | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Piste renigingsmachine op dak | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Renigingsmachine | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Metselwerk (behalve gaslokaal) | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Sluiten technische schachten | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Pleisterwerken | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Chapes | 312h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Vloeren & faience | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Binnenschrijnwerk | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Tapijt | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Smeedwerk | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Schilderwerken | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Einde opkuisen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Voorlopige receptie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
752 | Verdiep +3 | 2048h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
753 | Verdiep +4 | 2024h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
754 | Verdiep +5 | 2000h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
755 | Verdiep +6 | 1976h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
756 | Verdiep +7 | 1952h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
757 | Verdiep +8 | 1928h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
758 | Verdiep +9 | 1880h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
759 | Verdiep +10 | 1856h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
760 | Technische lokaal +10 | 696h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
761 | Verdiep +2 | 1728h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
762 | Verdiep +1 | 1720h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
763 | Verdiep glk | 1712h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
742 | Liften | 1704h |  |  |  |  | 99 | 100 | 101
743 | Goederenlift KGL1 | 1704h |  |  |  |  | 99 | 100 | 101
744 | KGL1 - werflift montage | 416h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
745 | KGL1 werflift | 928h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
746 | KGL1 opkuisen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
747 | Personenliften KPL1-4 | 328h |  |  |  |  | 99 | 100 | 101
748 | KPL 1 | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
749 | KPL 2 | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
750 | KPL 3 | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
751 | KPL 4 | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-04-30 17:00 |  | TP Name | 30/04, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 33d | [5 empty] | 515899.6421 |  | 3.378% |  | 521532.0423 | 335591.0405
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 33d | [5 empty] | 515899.6421 |  | 3.378% |  | 521532.0423 | 335591.0405
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 33d | 143671.4458 | 1428007.0977 | 328d | 277584.7188 | 0 | 421256.1646 | 1428007.0977 | 23% | Started | 425572.2449 | 143671.4458 | 100 | 7.7647 | 23 | 100 | 22.7667 | 23
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 7d | [5 empty] | 94643.4775 |  | 3.341% |  | 95959.7974 | 191919.5947
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 7d | 89562.4775 | 294276.7119 | 23d | 5081 | -5080.9399 | 94643.4775 | 289195.772 | 25% | Started | 95959.7974 | 191919.5947 | 100 | 23.3333 | 25 | 100 | 24.6571 | 25
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 |  | 0 | 0 | 57256.3184 | 24d | 0 | 0 | 0 | 57256.3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 |  | 0 | 0 | 134150.4004 | 40d | 0 | 0 | 0 | 134150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 |  | 0 | 0 | 439132.1562 | 256d | 0 | 0 | 0 | 439132.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2006-05-31 17:00 |  | TP Name | 31/05, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 56d | [5 empty] | 1019680.8472 |  | 6.628% |  | 1023378.1408 | 785117.9199
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 56d | [5 empty] | 1019680.8472 |  | 6.628% |  | 1023378.1408 | 785117.9199
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 56d | 243806.0898 | 1293043.0122 | 297d | 312409.6875 | 0 | 556215.7773 | 1293043.0122 | 30% | Started | 555094.2445 | 243806.0898 | 100 | 13.1765 | 30 | 100 | 30.0606 | 30
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 30d | [5 empty] | 463465.0698 |  | 16.3% |  | 468283.8963 | 541311.8301
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 4d | 78736.3203 | 177156.7207 | 9d | 5435.0898 | -5435.0898 | 84171.4102 | 171721.6309 | 33% | Started | 84444.7069 | 157472.6406 | 100 | 30.7692 | 33 | 100 | 32.8932 | 33
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 |  | 0 | 0 | 57256.3184 | 24d | 0 | 0 | 0 | 57256.3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 |  | 0 | 0 | 134150.4004 | 40d | 0 | 0 | 0 | 134150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 |  | 0 | 0 | 439132.1562 | 256d | 0 | 0 | 0 | 439132.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2006-06-30 17:00 |  | TP Name | 30/06, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 78d | [5 empty] | 1695132.3878 |  | 11.07% |  | 1708582.5041 | 1550157.6064
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 78d | [5 empty] | 1695132.3878 |  | 11.07% |  | 1708582.5041 | 1550157.6064
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 78d | 339587.0537 | 1023114.8413 | 235d | 486548.0625 | 0 | 826135.1162 | 1023114.8413 | 45% | Started | 832641.3116 | 339587.0537 | 100 | 18.3529 | 45 | 100 | 44.6484 | 45
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 52d | [5 empty] | 868997.2715 |  | 30.5% |  | 875941.1926 | 1210570.5527
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 236208.9609 | 100 |  | 0 | 100 |  | 0
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 78736.3203 | 100 |  | 0 | 100 |  | 0
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 |  | 0 | 0 | 255893.041 | 13d | 0 | 0 | 0 | 255893.041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 12d | 236208.9609 | 19684.0801 | 1d | 631.96 | 0 | 236840.921 | 19684.0801 | 92.31% | Started | 236208.9621 | 255893.041 | 100 | 92.3077 | 92.3077 | 100 | 92.5547 | 92.3077
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 |  | 0 | 0 | 57256.3184 | 24d | 0 | 0 | 0 | 57256.3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 |  | 0 | 0 | 134150.4004 | 40d | 0 | 0 | 0 | 134150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 |  | 0 | 0 | 439132.1562 | 256d | 0 | 0 | 0 | 439132.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2006-08-31 17:00 |  | TP Name | 31/08, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 122d | [5 empty] | 2384409.6914 |  | 15.5% |  | 2392801.591 | 2194453.376
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 122d | [5 empty] | 2384409.6914 |  | 15.5% |  | 2392801.591 | 2194453.376
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 101d | 439721.6978 | 936041.2378 | 215d | 475507.25 | 0 | 915228.9478 | 936041.2378 | 49% | Started | 906653.9143 | 531148.9814 | 100 | 23.7647 | 49 | 100 | 49.4634 | 49
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 96d | [5 empty] | 1469180.7437 |  | 51.74% |  | 1486147.6768 | 1663304.3945
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 4d | 78736.3203 | 177156.7207 | 9d | -300 | 0 | 78436.3203 | 177156.7207 | 30.77% | Started | 78736.3232 | 255893.041 | 100 | 30.7692 | 30.7692 | 100 | 30.652 | 30.7692
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 |  | 0 | 0 | 57256.3184 | 24d | 0 | 0 | 0 | 57256.3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 |  | 0 | 0 | 134150.4004 | 40d | 0 | 0 | 0 | 134150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 |  | 0 | 0 | 439132.1562 | 256d | 0 | 0 | 0 | 439132.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2006-09-30 17:00 |  | TP Name | 30/09, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 143d | [5 empty] | 3022387.8755 |  | 19.7% |  | 3042114.2785 | 2652903.4502
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 143d | [5 empty] | 3022387.8755 |  | 19.7% |  | 3042114.2785 | 2652903.4502
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 122d | 531148.9814 | 796723.4722 | 183d | 521590.4688 | 0 | 1052739.4502 | 796723.4722 | 57% | Started | 1054679.0093 | 622576.2651 | 100 | 28.7059 | 57 | 100 | 56.8952 | 57
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 117d | [5 empty] | 1969648.4253 |  | 69.2% |  | 1987435.2692 | 2004494.7852
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 4d | 68238.0781 | 187654.7148 | 11d | 4940.79 | 0 | 73178.8682 | 187654.7148 | 26.67% | Started | 68238.0817 | 85297.5977 | 100 | 26.6667 | 26.6667 | 100 | 28.5975 | 26.6667
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 |  | 0 | 0 | 255892.793 | 15d | 0 | 0 | 0 | 255892.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 |  | 0 | 0 | 57256.3184 | 24d | 0 | 0 | 0 | 57256.3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 |  | 0 | 0 | 134150.4004 | 40d | 0 | 0 | 0 | 134150.4004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 |  | 0 | 0 | 439132.1562 | 256d | 0 | 0 | 0 | 439132.1562 | 0% | Not Started | 0 | 17153.5999 | 100 |  | 0 | 100 |  | 0
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 8678.8 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2006-10-31 17:00 |  | TP Name | 31/10, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 165d | [5 empty] | 3738623.499 |  | 24.02% |  | 3709426.3956 | 3908923.7744
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 165d | [5 empty] | 3738623.499 |  | 24.02% |  | 3709426.3956 | 3908923.7744
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 144d | 626929.9453 | 657405.7065 | 151d | 622592 | 39228 | 1249521.9453 | 696633.7065 | 65% | Started | 1202704.1044 | 718357.229 | 100 | 33.8824 | 65 | 100 | 67.5303 | 65
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 139d | [5 empty] | 2400508.6831 |  | 84.42% |  | 2424741.4918 | 2520545.251
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d | 255892.793 | 6397.3198 | 3h | -4716.1099 | 0 | 251176.6831 | 6397.3198 | 97.56% | Started | 249651.5113 | 255892.793 | 100 | 100 | 97.561 | 100 | 98.157 | 97.561
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 89562.4775 | 100 |  | 0 | 100 |  | 0
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 |  | 0 | 0 | 191919.5947 | 15d | 0 | 0 | 0 | 191919.5947 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 |  | 0 | 0 | 57256.3184 | 24d | 0 | 0 | 0 | 57256.3184 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 391260.332 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 22d | 73782.7202 | 46952.6401 | 14d | 14810.1504 | 0 | 88592.8706 | 46952.6401 | 61.11% | Started | 81980.7994 | 73782.7202 | 100 | 55 | 61.1111 | 100 | 66.04 | 61.1111
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 |  | 0 | 0 | 439132.1562 | 256d | 0 | 0 | 0 | 439132.1562 | 0% | Not Started | 0 | 54891.5195 | 100 |  | 0 | 100 |  | 0
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 46865.5203 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 38644.3213 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 30224.6407 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 21597.1201 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 12755.1202 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2006-11-30 17:00 |  | TP Name | 30/11, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 187d | [5 empty] | 4212580.3928 |  | 27.05% |  | 4177440.679 | 5133728.7441
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 187d | [5 empty] | 4212580.3928 |  | 27.05% |  | 4177440.679 | 5133728.7441
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 166d | 722710.9092 | 548563.7021 | 126d | 634700 | 39228 | 1357410.9092 | 587791.7021 | 70% | Started | 1295219.8302 | 814138.1929 | 100 | 39.0588 | 70 | 100 | 73.3611 | 70
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 161d | [5 empty] | 2742061.5732 |  | 96.66% |  | 2776225.0096 | 2838678.7622
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 9d | 115151.7568 | 76767.8379 | 6d | -2500 | 2500 | 112651.7568 | 79267.8379 | 60% | Started | 115151.7614 | 191919.5947 | 100 | 60 | 60 | 100 | 58.6974 | 60
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.88 | 23856.7993 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 |  | 0 | 0 | 2756606.8848 | 155d | 0 | 0 | 0 | 2756606.8848 | 0% | Not Started | 0 | 782520.6641 | 100 |  | 0 | 100 |  | 0
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 19697.4395
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 |  | 0 | 0 | 19697.4395 | 7d | 0 | 0 | 0 | 19697.4395 | 0% | Not Started | 0 | 19697.4395 | 100 |  | 0 | 100 |  | 0
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 22d | 73782.7202 | 46952.6401 | 14d | 14810.1504 | 0 | 88592.8706 | 46952.6401 | 61.11% | Started | 81980.7994 | 134150.4004 | 100 | 55 | 61.1111 | 100 | 66.04 | 61.1111
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 14d | 24015.0398 | 415117.1165 | 242d | 500 | 0 | 24515.0398 | 415117.1165 | 5.469% | Started | 24015.0398 | 92629.4392 | 100 | 5.4688 | 5.4688 | 100 | 5.5826 | 5.4688
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 |  | 0 | 0 | 439147.2825 | 253d | 0 | 0 | 0 | 439147.2825 | 0% | Not Started | 0 | 85052.2405 | 100 |  | 0 | 100 |  | 0
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 |  | 0 | 0 | 439140.0146 | 250d | 0 | 0 | 0 | 439140.0146 | 0% | Not Started | 0 | 77288.6426 | 100 |  | 0 | 100 |  | 0
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 69338.8817 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 61191.8403 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 52842.641 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 39243.1194 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 30286.0801 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 22363.4404 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 12254.8799 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 2052.0801 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2006-12-31 17:00 |  | TP Name | 31/12, 2006
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 208d | [5 empty] | 5643738.2872 |  | 36.15% |  | 5582046.8938 | 6086409.8833
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 208d | [5 empty] | 5643738.2872 |  | 36.15% |  | 5582046.8938 | 6086409.8833
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 187d | 814138.1929 | 474551.1392 | 109d | 632262 | 70000 | 1446400.1929 | 544551.1392 | 74% | Started | 1369232.4329 | 905565.4766 | 100 | 44 | 74 | 100 | 78.1705 | 74
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 182d | [5 empty] | 2773850.8525 |  | 97.66% |  | 2805012.9443 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 11d | 140741.0361 | 51178.5586 | 4d | 3700 | -3700 | 144441.0361 | 47478.5586 | 75% | Started | 143939.696 | 191919.5947 | 100 | 73.3333 | 75 | 100 | 75.2612 | 75
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.88 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 21d | 373475.7715 | 1814025.1758 | 102d | 570000 | 0 | 943475.7715 | 1814025.1758 | 34% | Started | 937246.3507 | 1155996.4355 | 100 | 13.5484 | 34 | 100 | 34.226 | 34
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 21d | [5 empty] | 19464.4395 |  | 15.14% |  | 19697.4395 | 19697.4395
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 |  | 0 | 0 | 39193.9189 | 18d | 0 | 0 | 0 | 39193.9189 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 22d | 73782.7202 | 46952.6401 | 14d | 14810.1504 | 0 | 88592.8706 | 46952.6401 | 61.11% | Started | 81980.7994 | 134150.4004 | 100 | 55 | 61.1111 | 100 | 66.04 | 61.1111
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 35d | 60037.5995 | 248727.1979 | 145d | 130900 | 0 | 190937.5995 | 248727.1979 | 43% | Started | 188826.8303 | 128651.9989 | 100 | 13.6719 | 43 | 100 | 43.4807 | 43
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 21d | 36450.9602 | 402696.3223 | 232d | 127000 | -127000 | 163450.9602 | 275696.3223 | 37% | Started | 162484.4966 | 121503.2007 | 100 | 8.3004 | 37 | 100 | 37.2201 | 37
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 10d | 17565.6006 | 421574.4141 | 240d | 0 | 0 | 17565.6006 | 421574.4141 | 4% | Started | 17565.6002 | 114176.4038 | 100 | 4 | 4 | 100 | 4 | 4
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 |  | 0 | 0 | 439146.2509 | 247d | 0 | 0 | 0 | 439146.2509 | 0% | Not Started | 0 | 106675.2026 | 100 |  | 0 | 100 |  | 0
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 98986.8005 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 91108.0017 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 78486.2388 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 70036.5602 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 65057.2813 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 55146.9595 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 45145.7617 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 23947.4404
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 23947.4404
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 |  | 0 | 0 | 113206.082 | 52d | 0 | 0 | 0 | 113206.082 | 0% | Not Started | 0 | 23947.4404 | 100 |  | 0 | 100 |  | 0
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2007-01-31 17:00 |  | TP Name | 31/01, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 231d | [5 empty] | 6894675.7789 |  | 44.26% |  | 6834440.1218 | 7304968.786
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 231d | [5 empty] | 6894675.7789 |  | 44.26% |  | 6834440.1218 | 7304968.786
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 210d | 914272.8369 | 404892.2563 | 93d | 601000 | 70000 | 1515272.8369 | 474892.2563 | 78% | Started | 1443244.9253 | 1005700.1206 | 100 | 49.4118 | 78 | 100 | 81.8927 | 78
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 205d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.8429 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.88 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 44d | 782520.6641 | 1191565.5566 | 67d | 784000 | 0 | 1566520.6641 | 1191565.5566 | 57% | Started | 1571265.9046 | 1565041.3281 | 100 | 28.3871 | 57 | 100 | 56.8279 | 57
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 134151.2012
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 |  | 0 | 0 | 134151.2012 | 10d | 0 | 0 | 0 | 134151.2012 | 0% | Not Started | 0 | 134151.2012 | 100 |  | 0 | 100 |  | 0
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 44d | [5 empty] | 41718.8389 |  | 31.87% |  | 41471.8399 | 73429.1185
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 |  | 0 | 0 | 16671.2 | 5d | 0 | 0 | 0 | 16671.2 | 0% | Not Started | 0 | 10002.72 | 100 |  | 0 | 100 |  | 0
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 10d | 21774.3994 | 17419.5195 | 8d | 480 | -480 | 22254.3994 | 16939.5195 | 55.56% | Started | 21774.4005 | 39193.9189 | 100 | 55.5556 | 55.5556 | 100 | 56.7802 | 55.5556
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 |  | 0 | 0 | 22675.2008 | 15d | 0 | 0 | 0 | 22675.2008 | 0% | Not Started | 0 | 4535.0402 | 100 |  | 0 | 100 |  | 0
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 |  | 0 | 0 | 13667.1997 | 20d | 0 | 0 | 0 | 13667.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 |  | 0 | 0 | 75157.2021 | 5d | 0 | 0 | 0 | 75157.2021 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 45d | 150919.2004 | 23476.3201 | 7d | -39000 | -1000 | 111919.2004 | 22476.3201 | 83% | Started | 111344.8301 | 134150.4004 | 100 | 112.5 | 83 | 100 | 83.4282 | 83
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 58d | 99490.8792 | 198981.7583 | 116d | 140500 | 0 | 239990.8792 | 198981.7583 | 55% | Started | 241522.6912 | 168105.2786 | 100 | 22.6562 | 55 | 100 | 54.6512 | 55
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 21d | 36450.9602 | 402696.3223 | 232d | 127000 | -127000 | 163450.9602 | 275696.3223 | 37% | Started | 162484.4966 | 161425.6809 | 100 | 8.3004 | 37 | 100 | 37.2201 | 37
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 33d | 57966.4819 | 270510.249 | 154d | 105000 | 0 | 162966.4819 | 270510.249 | 37% | Started | 162481.8075 | 154577.2852 | 100 | 13.2 | 37 | 100 | 37.1104 | 37
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 23d | 40892.161 | 398254.0898 | 224d | 17000 | -17000 | 57892.161 | 381254.0898 | 13% | Started | 57089.0105 | 147567.3636 | 100 | 9.3117 | 13 | 100 | 13.1829 | 13
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 |  | 0 | 0 | 439141.4424 | 244d | 0 | 0 | 0 | 439141.4424 | 0% | Not Started | 0 | 140381.2808 | 100 |  | 0 | 100 |  | 0
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 133017.6825 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 121466.7981 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 113572.8003 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 111817.2021 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 102123.999 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 92343.6035 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 23d | [5 empty] | 215887.1152 |  | 18.17% |  | 190541.7731 | 74019.3613
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 16d | [5 empty] | 34832.6406 |  | 9.771% |  | 34832.6419 | 74019.3613
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 16d | 34832.6406 | 78373.4414 | 36d | 0 | 0 | 34832.6406 | 78373.4414 | 30.77% | Started | 34832.6419 | 74019.3613 | 100 | 30.7692 | 30.7692 | 100 | 30.7692 | 30.7692
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 23d | [5 empty] | 181054.4746 |  | 22.5% |  | 155709.1312 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 0 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2007-02-28 17:00 |  | TP Name | 28/02, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 251d | [5 empty] | 7665293.11 |  | 49.05% |  | 7574280.9098 | 8327449.0433
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 251d | [5 empty] | 7665293.11 |  | 49.05% |  | 7574280.9098 | 8327449.0433
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 230d | 1001346.4404 | 239452.4097 | 55d | 700000 | 60000 | 1701346.4404 | 299452.4097 | 87% | Started | 1609773.2538 | 1092773.7241 | 100 | 54.1176 | 87 | 100 | 91.9491 | 87
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 225d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.8429 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.88 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 44d | 782520.6641 | 1191565.5566 | 67d | 784000 | 0 | 1566520.6641 | 1191565.5566 | 57% | Started | 1571265.9046 | 1920732.5391 | 100 | 28.3871 | 57 | 100 | 56.8279 | 57
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 2d | [5 empty] | 21830.2402 |  | 15.17% |  | 21464.1917 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 2d | 26830.2402 | 107320.9609 | 8d | -5000 | 10000 | 21830.2402 | 117320.9609 | 16% | Started | 21464.1917 | 134151.2012 | 100 | 20 | 16 | 100 | 16.2729 | 16
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 |  | 0 | 0 | 7366.8003 | 3d | 0 | 0 | 0 | 7366.8003 | 0% | Not Started | 0 | 7366.8003 | 100 |  | 0 | 100 |  | 0
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 64d | [5 empty] | 91296.8889 |  | 70.85% |  | 92191.0393 | 98237.7592
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 |  | 0 | 0 | 7951.5997 | 5d | 0 | 0 | 0 | 7951.5997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 11d | 16628.4806 | 6046.7202 | 4d | 0 | 0 | 16628.4806 | 6046.7202 | 73.33% | Started | 16628.481 | 22675.2008 | 100 | 73.3333 | 73.3333 | 100 | 73.3333 | 73.3333
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 6d | 4100.1599 | 9567.0398 | 14d | -300 | 300 | 3800.1599 | 9867.0398 | 30% | Started | 4100.1601 | 5466.8799 | 100 | 30 | 30 | 100 | 27.805 | 30
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 1d | 15031.4404 | 60125.7617 | 4d | 5000 | -5000 | 20031.4404 | 55125.7617 | 28% | Started | 21044.0167 | 0 | 100 | 20 | 28 | 100 | 26.6527 | 28
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 45d | 150919.2004 | 23476.3201 | 7d | -39000 | -1000 | 111919.2004 | 22476.3201 | 83% | Started | 111344.8301 | 134150.4004 | 100 | 112.5 | 83 | 100 | 83.4282 | 83
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 |  | 0 | 0 | 122781.1191 | 22d | 0 | 0 | 0 | 122781.1191 | 0% | Not Started | 0 | 16742.8799 | 100 |  | 0 | 100 |  | 0
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 |  | 0 | 0 | 127818.241 | 33d | 0 | 0 | 0 | 127818.241 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 78d | 133798.0789 | 178397.4385 | 104d | 128000 | 0 | 261798.0789 | 178397.4385 | 59% | Started | 259087.9607 | 202412.4783 | 100 | 30.4688 | 59 | 100 | 59.6172 | 59
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 41d | 71166.1604 | 244742.1614 | 141d | 123000 | 0 | 194166.1604 | 244742.1614 | 44% | Started | 193224.8032 | 196140.8811 | 100 | 16.2055 | 44 | 100 | 44.2144 | 44
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 33d | 57966.4819 | 270510.249 | 154d | 105000 | 0 | 162966.4819 | 270510.249 | 37% | Started | 162481.8075 | 189708.4863 | 100 | 13.2 | 37 | 100 | 37.1104 | 37
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 43d | 76450.5619 | 275577.6068 | 155d | 69000 | 0 | 145450.5619 | 275577.6068 | 37% | Started | 162484.1149 | 183125.7645 | 100 | 17.4089 | 37 | 100 | 33.1212 | 37
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 20d | 35995.2002 | 403146.2422 | 224d | 96000 | -96000 | 131995.2002 | 307146.2422 | 30% | Started | 131742.4379 | 176376.481 | 100 | 8.1967 | 30 | 100 | 30.0576 | 30
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 |  | 0 | 0 | 439140.5682 | 241d | 0 | 0 | 0 | 439140.5682 | 0% | Not Started | 0 | 169460.8832 | 100 |  | 0 | 100 |  | 0
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 |  | 0 | 0 | 439149.1931 | 235d | 0 | 0 | 0 | 439149.1931 | 0% | Not Started | 0 | 158841.1975 | 100 |  | 0 | 100 |  | 0
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 151430.4004 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 |  | 0 | 0 | 368344.0664 | 87d | 0 | 0 | 0 | 368344.0664 | 0% | Not Started | 0 | 76209.1172 | 100 |  | 0 | 100 |  | 0
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 152478.0029 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 142973.5986 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 133385.2051 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 43d | [5 empty] | 433114.9512 |  | 36.34% |  | 381083.5463 | 113206.082
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 36d | [5 empty] | 69665.2813 |  | 19.54% |  | 69665.2838 | 113206.082
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 32d | 69665.2813 | 43540.8008 | 20d | 0 | 0 | 69665.2813 | 43540.8008 | 61.54% | Started | 69665.2838 | 113206.082 | 100 | 61.5385 | 61.5385 | 100 | 61.5385 | 61.5385
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 43d | [5 empty] | 363449.6699 |  | 45% |  | 311418.2625 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 0 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 20d | 84395.1953 | 88614.9551 | 21d | 98000 | -65000 | 182395.1953 | 23614.9551 | 90% | Started | 155709.1312 | 0 | 100 | 48.7805 | 90 | 100 | 105.4246 | 90
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2007-03-31 17:00 |  | TP Name | 31/03, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 273d | [5 empty] | 8788952.1463 |  | 59.74% |  | 9225140.7521 | 10071796.819
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 273d | [5 empty] | 8788952.1463 |  | 59.74% |  | 9225140.7521 | 10071796.819
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 252d | 1097127.4043 | 204622.9683 | 47d | 640000 | 43000 | 1737127.4043 | 247622.9683 | 89% | Started | 1646779.5 | 1188554.688 | 100 | 59.2941 | 89 | 100 | 93.8828 | 89
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 247d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 66d | 1173780.9961 | 426829.4531 | 24d | 560000 | 0 | 1733780.9961 | 426829.4531 | 85% | Started | 2343115.9178 | 2311992.8711 | 100 | 42.5806 | 85 | 100 | 62.8955 | 85
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 |  | 0 | 0 | 376803.4355 | 19d | 0 | 0 | 0 | 376803.4355 | 0% | Not Started | 0 | 376803.4355 | 100 |  | 0 | 100 |  | 0
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 24d | [5 empty] | 59257.6831 |  | 40.28% |  | 57002.7454 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 24d | 321962.8828 | 80490.7207 | 6d | -270000 | 4000 | 51962.8828 | 84490.7207 | 37% | Started | 49635.9451 | 134151.2012 | 100 | 240 | 37 | 100 | 38.7346 | 37
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 86d | [5 empty] | 103436.8889 |  | 80.08% |  | 104201.459 | 120327.1191
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 4d | 6361.2798 | 3180.6399 | 2d | 0 | 0 | 6361.2798 | 3180.6399 | 75% | Started | 5963.6998 | 7951.5997 | 100 | 80 | 75 | 100 | 80 | 75
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 |  | 0 | 0 | 23925.4404 | 22d | 0 | 0 | 0 | 23925.4404 | 0% | Not Started | 0 | 14137.7603 | 100 |  | 0 | 100 |  | 0
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 2d | 11161.9199 | 111619.1992 | 20d | -2000 | 2000 | 9161.9199 | 113619.1992 | 9.091% | Started | 11161.9084 | 122781.1191 | 100 | 9.0909 | 9.0909 | 100 | 7.462 | 9.0909
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 21d 1h | 81823.0406 | 45995.2003 | 11d 7h | 7000 | -7000 | 88823.0406 | 38995.2003 | 69% | Started | 88194.586 | 77465.6006 | 100 | 64.0152 | 69 | 100 | 69.4917 | 69
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 |  | 0 | 0 | 17397.1195 | 39d | 0 | 0 | 0 | 17397.1195 | 0% | Not Started | 0 | 4014.7199 | 100 |  | 0 | 100 |  | 0
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 14602.8799 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 100d | 171535.9985 | 73760.4794 | 43d | 194000 | 0 | 365535.9985 | 73760.4794 | 83% | Started | 364479.6824 | 240150.3979 | 100 | 39.0625 | 83 | 100 | 83.2405 | 83
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 63d | 109352.8806 | 220441.5212 | 127d | 110000 | 0 | 219352.8806 | 220441.5212 | 50% | Started | 219573.6412 | 234327.6013 | 100 | 24.9012 | 50 | 100 | 49.9497 | 50
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 55d | 96610.8032 | 244161.8481 | 139d | 100000 | 0 | 196610.8032 | 244161.8481 | 44% | Started | 193221.6054 | 228352.8076 | 100 | 22 | 44 | 100 | 44.7718 | 44
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 65d | 115564.8029 | 270243.8467 | 152d | 53000 | 0 | 168564.8029 | 270243.8467 | 38% | Started | 166875.5732 | 222240.0055 | 100 | 26.3158 | 38 | 100 | 38.3847 | 38
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 42d | 75589.9204 | 275363.2815 | 153d | 87000 | 0 | 162589.9204 | 275363.2815 | 37% | Started | 162482.3358 | 215971.2012 | 100 | 17.2131 | 37 | 100 | 37.0245 | 37
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 21d 1h | 38493.1307 | 400647.4375 | 219d 7h | 124000 | -124000 | 162493.1307 | 276647.4375 | 37% | Started | 162482.0123 | 209548.4039 | 100 | 8.7656 | 37 | 100 | 37.0025 | 37
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 14d 1h | 26395.6696 | 412753.5235 | 220d 7h | 0 | 0 | 26395.6696 | 412753.5235 | 6.011% | Started | 26395.5022 | 199953.0369 | 100 | 6.0106 | 6.0106 | 100 | 6.0106 | 6.0106
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 193073.7605 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 21d 1h | 89439.8667 | 278904.1997 | 65d 7h | 1400 | -1400 | 90839.8667 | 277504.1997 | 24.28% | Started | 89439.8333 | 169353.5938 | 100 | 24.2816 | 24.2816 | 100 | 24.6617 | 24.2816
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 197204.8838 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 187908.1582 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 178530.9668 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 65d | [5 empty] | 649398.177 |  | 49% |  | 513766.7876 | 142068.4834
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 58d | [5 empty] | 103806.082 |  | 31.75% |  | 113206.082 | 142068.4834
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 28862.4014 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 65d | [5 empty] | 545592.095 |  | 57.88% |  | 400560.7056 | 0
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 0 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 20d | 84395.1953 | 88614.9551 | 21d | 98000 | -78000 | 182395.1953 | 10614.9551 | 90% | Started | 155709.1312 | 0 | 100 | 48.7805 | 90 | 100 | 105.4246 | 90
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 21d 1h | 89142.425 | 83867.7253 | 19d 7h | 93000 | -73000 | 182142.425 | 10867.7253 | 51.52% | Started | 89142.4432 | 0 | 100 | 51.5244 | 51.5244 | 100 | 105.2785 | 51.5244
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2007-04-30 17:00 |  | TP Name | 30/04, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 294d | [5 empty] | 9715403.245 |  | 64.5% |  | 9959349.0364 | 11422569.3878
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 294d | [5 empty] | 9715403.245 |  | 64.5% |  | 9959349.0364 | 11422569.3878
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 273d | 1188554.688 | 178500.8872 | 41d | 602000 | 129000 | 1790554.688 | 307500.8872 | 90% | Started | 1665282.6231 | 1279981.9717 | 100 | 64.2353 | 90 | 100 | 96.7703 | 90
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 268d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 66d | 1173780.9961 | 426829.4531 | 24d | 560000 | 0 | 1733780.9961 | 426829.4531 | 85% | Started | 2343115.9178 | 2685468.6426 | 100 | 42.5806 | 85 | 100 | 62.8955 | 85
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 14d | 277644.6367 | 99158.7988 | 5d | 11000 | -9000 | 288644.6367 | 90158.7988 | 73.68% | Started | 277644.6332 | 376803.4355 | 100 | 73.6842 | 73.6842 | 100 | 76.6035 | 73.6842
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 45d | [5 empty] | 59257.6831 |  | 40.28% |  | 57002.7454 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 24d | 321962.8828 | 80490.7207 | 6d | -270000 | 4000 | 51962.8828 | 84490.7207 | 37% | Started | 49635.9451 | 134151.2012 | 100 | 240 | 37 | 100 | 38.7346 | 37
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 107d | [5 empty] | 107102.2489 |  | 83.28% |  | 108364.399 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 2d | 2175.04 | 21750.4004 | 20d | 0 | 0 | 2175.04 | 21750.4004 | 9.091% | Started | 2175.0401 | 23925.4404 | 100 | 9.0909 | 9.0909 | 100 | 9.0909 | 9.0909
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 42d | 162677.7612 | 15493.1201 | 4d | -52000 | 2000 | 110677.7612 | 17493.1201 | 86% | Started | 109923.6891 | 127818.241 | 100 | 127.2727 | 86 | 100 | 86.59 | 86
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 12d | 5352.9598 | 12044.1596 | 27d | 0 | 0 | 5352.9598 | 12044.1596 | 30.77% | Started | 5352.96 | 13382.3996 | 100 | 30.7692 | 30.7692 | 100 | 30.7692 | 30.7692
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 |  | 0 | 0 | 259179.2041 | 35d | 0 | 0 | 0 | 259179.2041 | 0% | Not Started | 0 | 37025.6006 | 100 |  | 0 | 100 |  | 0
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 45633.9996 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 |  | 0 | 0 | 132057.5977 | 40d | 0 | 0 | 0 | 132057.5977 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 276172.9576 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 84d | 145803.8408 | 65958.8804 | 38d | 227000 | 0 | 372803.8408 | 65958.8804 | 68.85% | Started | 302363.7087 | 270778.5615 | 100 | 33.2016 | 68.8525 | 100 | 84.8927 | 68.8525
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 79d | 138768.2446 | 161603.5254 | 92d | 140000 | 0 | 278768.2446 | 161603.5254 | 46.2% | Started | 202877.5489 | 265240.5688 | 100 | 31.6 | 46.1988 | 100 | 63.4805 | 46.1988
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 89d | 158234.8839 | 213350.4053 | 120d | 10000 | 0 | 168234.8839 | 213350.4053 | 42.58% | Started | 187004.8574 | 259576.3264 | 100 | 36.0324 | 42.5837 | 100 | 38.3095 | 42.5837
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 63d | 113384.8806 | 271763.7615 | 151d | 87000 | 0 | 200384.8806 | 271763.7615 | 37% | Started | 162482.3358 | 253766.1614 | 100 | 25.8197 | 37 | 100 | 45.6311 | 37
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 21d 1h | 38493.1307 | 400647.4375 | 219d 7h | 124000 | -124000 | 162493.1307 | 276647.4375 | 37% | Started | 162482.0123 | 247813.7646 | 100 | 8.7656 | 37 | 100 | 37.0025 | 37
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 35d | 65405.199 | 392431.1938 | 210d | -20000 | 0 | 45405.199 | 392431.1938 | 10% | Started | 43914.92 | 239196.1562 | 100 | 14.8936 | 10 | 100 | 10.3394 | 10
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 |  | 0 | 0 | 439148.1611 | 232d | 0 | 0 | 0 | 439148.1611 | 0% | Not Started | 0 | 232824.2406 | 100 |  | 0 | 100 |  | 0
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 42d | 177821.2734 | 186288.9531 | 44d | 4000 | -4000 | 181821.2734 | 182288.9531 | 48.84% | Started | 179888.9606 | 258264.2305 | 100 | 48.2759 | 48.8372 | 100 | 49.3618 | 48.8372
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 239898.7246 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 230800.2378 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 221624.6484 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 86d | [5 empty] | 649398.177 |  | 49% |  | 513766.7876 | 371031.5151
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 79d | [5 empty] | 103806.082 |  | 31.75% |  | 113206.082 | 185362.0854
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 72156.0034 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 86d | [5 empty] | 545592.095 |  | 57.88% |  | 400560.7056 | 185669.4297
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 46417.3574 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 20d | 84395.1953 | 88614.9551 | 21d | 98000 | -78000 | 182395.1953 | 10614.9551 | 90% | Started | 155709.1312 | 46417.3574 | 100 | 48.7805 | 90 | 100 | 105.4246 | 90
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 21d 1h | 89142.425 | 83867.7253 | 19d 7h | 93000 | -73000 | 182142.425 | 10867.7253 | 51.52% | Started | 89142.4432 | 46417.3574 | 100 | 51.5244 | 51.5244 | 100 | 105.2785 | 51.5244
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 46417.3574 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2007-05-31 17:00 |  | TP Name | 31/05, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 317d | [5 empty] | 11552951.9301 |  | 72.94% |  | 11262579.3247 | 12782984.1784
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 317d | [5 empty] | 11552951.9301 |  | 72.94% |  | 11262579.3247 | 12782984.1784
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 296d | 1288689.332 | 156732.4863 | 36d | 548000 | 119000 | 1836689.332 | 275732.4863 | 90% | Started | 1665282.6231 | 1380116.6157 | 100 | 69.6471 | 90 | 100 | 99.2637 | 90
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 291d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 89d | 1582825.8887 | 231199.2871 | 13d | 940000 | 0 | 2522825.8887 | 231199.2871 | 92% | Started | 2536078.38 | 2756606.8848 | 100 | 57.4194 | 92 | 100 | 91.5192 | 92
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 100% | Finished | 376803.4355 | 376803.4355 | 100 | 100 | 100 | 100 | 111.1756 | 100
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 68d | [5 empty] | 59257.6831 |  | 40.28% |  | 57002.7454 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 24d | 321962.8828 | 80490.7207 | 6d | -270000 | 4000 | 51962.8828 | 84490.7207 | 37% | Started | 49635.9451 | 134151.2012 | 100 | 240 | 37 | 100 | 38.7346 | 37
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 130d | [5 empty] | 107940.1693 |  | 85.11% |  | 110735.1925 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 23d | 25012.9604 | 20662.8804 | 19d | -22000 | 0 | 3012.9604 | 20662.8804 | 19% | Started | 4545.8336 | 23925.4404 | 100 | 104.5455 | 19 | 100 | 12.5931 | 19
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 100% | Finished | 127818.241 | 127818.241 | 100 | 139.3939 | 100 | 100 | 98.8129 | 100
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 35d | 15612.7995 | 5352.9598 | 12d | -3600 | 0 | 12012.7995 | 5352.9598 | 69% | Started | 12004.0124 | 17397.1195 | 100 | 89.7436 | 69 | 100 | 69.0505 | 69
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 2h | 1851.28 | 251774.084 | 34d | 0 | 0 | 1851.28 | 251774.084 | 0.7299% | Started | 1891.819 | 207343.3633 | 100 | 0.71429 | 0.72993 | 100 | 0.71429 | 0.72993
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 |  | 0 | 0 | 129647.998 | 50d | 0 | 0 | 0 | 129647.998 | 0% | Not Started | 0 | 10371.8398 | 100 |  | 0 | 100 |  | 0
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 |  | 0 | 0 | 45633.9996 | 25d | 0 | 0 | 0 | 45633.9996 | 0% | Not Started | 0 | 45633.9996 | 100 |  | 0 | 100 |  | 0
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 1h | 412.68 | 128756.1577 | 39d | 0 | 0 | 412.68 | 128756.1577 | 1% | Started | 1320.5759 | 0 | 100 | 0.3125 | 1 | 100 | 0.3125 | 1
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 315626.2373 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 105d | 182254.801 | 39922.4802 | 23d | 217000 | 0 | 399254.801 | 39922.4802 | 91% | Started | 399624.0386 | 310701.0417 | 100 | 41.502 | 91 | 100 | 90.9159 | 91
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 102d | 179169.126 | 38644.3213 | 22d | 221000 | 0 | 400169.126 | 38644.3213 | 91% | Started | 399617.4248 | 305641.4502 | 100 | 40.8 | 91 | 100 | 91.1256 | 91
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 112d | 199127.0449 | 122676.483 | 69d | 118000 | 0 | 317127.0449 | 122676.483 | 72% | Started | 316185.3132 | 300468.4874 | 100 | 45.3441 | 72 | 100 | 72.2144 | 72
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 86d | 154779.3608 | 75589.9204 | 42d | 208000 | 0 | 362779.3608 | 75589.9204 | 83% | Started | 364487.3898 | 295160.6416 | 100 | 35.2459 | 83 | 100 | 82.6111 | 83
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 44d | 80175.0415 | 176749.5233 | 97d | 180000 | 0 | 260175.0415 | 176749.5233 | 60% | Started | 263484.3514 | 289723.4454 | 100 | 18.2573 | 60 | 100 | 59.2464 | 60
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 58d | 108385.7583 | 276570.5557 | 148d | 54000 | 0 | 162385.7583 | 276570.5557 | 37% | Started | 162485.2035 | 282176.7156 | 100 | 24.6809 | 37 | 100 | 36.9774 | 37
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 23d | 43536.2401 | 395611.921 | 209d | 36000 | -36000 | 79536.2401 | 359611.921 | 9.914% | Started | 43536.2406 | 276360.4807 | 100 | 9.9138 | 9.9138 | 100 | 18.1115 | 9.9138
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 65d | 275199.5898 | 88910.6367 | 21d | 0 | 7000 | 275199.5898 | 95910.6367 | 74% | Started | 272574.6127 | 355642.5469 | 100 | 74.7126 | 74 | 100 | 74.7126 | 74
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 |  | 0 | 0 | 439136.6484 | 216d | 0 | 0 | 0 | 439136.6484 | 0% | Not Started | 0 | 286658.6455 | 100 |  | 0 | 100 |  | 0
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 277777.2773 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 268822.4902 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 109d | [5 empty] | 649398.177 |  | 49% |  | 513766.7876 | 806666.2158
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 102d | [5 empty] | 103806.082 |  | 31.75% |  | 113206.082 | 232778.8877
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 119572.8057 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 109d | [5 empty] | 545592.095 |  | 57.88% |  | 400560.7056 | 573887.3281
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 143471.832 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 20d | 84395.1953 | 88614.9551 | 21d | 98000 | -78000 | 182395.1953 | 10614.9551 | 90% | Started | 155709.1312 | 143471.832 | 100 | 48.7805 | 90 | 100 | 105.4246 | 90
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 21d 1h | 89142.425 | 83867.7253 | 19d 7h | 93000 | -73000 | 182142.425 | 10867.7253 | 51.52% | Started | 89142.4432 | 143471.832 | 100 | 51.5244 | 51.5244 | 100 | 105.2785 | 51.5244
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 143471.832 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2007-06-30 17:00 |  | TP Name | 30/06, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 338d | [5 empty] | 12407618.201 |  | 78.18% |  | 12072241.3211 | 13585278.9817
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 338d | [5 empty] | 12407618.201 |  | 78.18% |  | 12072241.3211 | 13585278.9817
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 297d 6h | 1296308.2723 | 130610.4053 | 30d | 565000 | 119000 | 1861308.2723 | 249610.4053 | 93% | Started | 1720792.1027 | 1471543.8994 | 100 | 70.0588 | 93 | 100 | 100.5942 | 93
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 312d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 111d | 1974086.2207 | 355691.2109 | 20d | 800000 | 0 | 2774086.2207 | 355691.2109 | 92% | Started | 2536078.38 | 2756606.8848 | 100 | 71.6129 | 92 | 100 | 100.6341 | 92
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 100% | Finished | 376803.4355 | 376803.4355 | 100 | 100 | 100 | 100 | 111.1756 | 100
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 89d | [5 empty] | 59257.6831 |  | 40.28% |  | 57002.7454 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 24d | 321962.8828 | 80490.7207 | 6d | -270000 | 4000 | 51962.8828 | 84490.7207 | 37% | Started | 49635.9451 | 134151.2012 | 100 | 240 | 37 | 100 | 38.7346 | 37
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 151d | [5 empty] | 107940.1693 |  | 85.11% |  | 110735.1925 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 23d | 25012.9604 | 20662.8804 | 19d | -22000 | 0 | 3012.9604 | 20662.8804 | 19% | Started | 4545.8336 | 23925.4404 | 100 | 104.5455 | 19 | 100 | 12.5931 | 19
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 100% | Finished | 127818.241 | 127818.241 | 100 | 139.3939 | 100 | 100 | 98.8129 | 100
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 49d | 21857.9193 | 0 | 0 | -3780 | 0 | 18077.9193 | 0 | 100% | Finished | 17397.1195 | 17397.1195 | 100 | 125.641 | 100 | 100 | 103.9133 | 100
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 22d | 162912.6426 | 229558.7236 | 31d | -135000 | 0 | 27912.6426 | 229558.7236 | 41.51% | Started | 107583.8222 | 259179.2041 | 100 | 62.8571 | 41.5094 | 100 | 10.7696 | 41.5094
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 2007-06-12 08:00 | 14d | 36301.4395 | 93346.5586 | 36d | 0 | 0 | 36301.4395 | 93346.5586 | 28% | Started | 36301.4396 | 64823.999 | 100 | 28 | 28 | 100 | 28 | 28
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 2007-06-29 08:00 | 1d | 1825.36 | 43808.6396 | 24d | 0 | 0 | 1825.36 | 43808.6396 | 4% | Started | 1825.3599 | 45633.9996 | 100 | 4 | 4 | 100 | 4 | 4
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 22d | 72631.6787 | 128756.1577 | 39d | -70000 | 0 | 2631.6787 | 128756.1577 | 36.07% | Started | 47627.3286 | 0 | 100 | 55 | 36.0656 | 100 | 1.9928 | 36.0656
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 351648.797 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 105d | 182254.801 | 39922.4802 | 23d | 217000 | 0 | 399254.801 | 39922.4802 | 91% | Started | 399624.0386 | 347152.002 | 100 | 41.502 | 91 | 100 | 90.9159 | 91
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 102d | 179169.126 | 38644.3213 | 22d | 221000 | 0 | 400169.126 | 38644.3213 | 91% | Started | 399617.4248 | 342529.2114 | 100 | 40.8 | 91 | 100 | 91.1256 | 91
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 134d | 238241.2859 | 80006.402 | 45d | 111000 | 0 | 349241.2859 | 80006.402 | 82% | Started | 360099.9226 | 337804.8083 | 100 | 54.251 | 82 | 100 | 79.5273 | 82
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 108d | 194374.0811 | 37794.9602 | 21d | 207000 | 0 | 401374.0811 | 37794.9602 | 91% | Started | 399618.7241 | 332955.6018 | 100 | 44.2623 | 91 | 100 | 91.3997 | 91
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 66d | 120262.5623 | 89285.8417 | 49d | 230000 | 0 | 350262.5623 | 89285.8417 | 80% | Started | 351312.4598 | 327988.8062 | 100 | 27.3859 | 80 | 100 | 79.7609 | 80
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 90d | 168184.7974 | 164447.3574 | 88d | 107000 | 0 | 275184.7974 | 164447.3574 | 63% | Started | 276663.9896 | 321419.835 | 100 | 38.2979 | 63 | 100 | 62.6632 | 63
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 45d | 85179.6002 | 225252.7206 | 119d | 128000 | 0 | 213179.6002 | 225252.7206 | 49% | Started | 215182.6031 | 316110.9608 | 100 | 19.3966 | 49 | 100 | 48.5439 | 49
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 86d | 364110.2266 | 0 | 0 | 0 | 0 | 364110.2266 | 0 | 100% | Finished | 368344.0664 | 368344.0664 | 100 | 98.8506 | 100 | 100 | 98.8506 | 100
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 2007-06-25 08:00 | 5d | 10165.2002 | 428971.4482 | 211d | 0 | 0 | 10165.2002 | 428971.4482 | 2.315% | Started | 10165.1999 | 329352.4863 | 100 | 2.3148 | 2.3148 | 100 | 2.3148 | 2.3148
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 320669.3569 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 311916.1719 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 130d | [5 empty] | 649398.177 |  | 49% |  | 513766.7876 | 968113.0913
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 123d | [5 empty] | 103806.082 |  | 31.75% |  | 113206.082 | 276072.4897
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 162866.4077 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 130d | [5 empty] | 545592.095 |  | 57.88% |  | 400560.7056 | 692040.6016
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 173010.1504 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 20d | 84395.1953 | 88614.9551 | 21d | 98000 | -78000 | 182395.1953 | 10614.9551 | 90% | Started | 155709.1312 | 173010.1504 | 100 | 48.7805 | 90 | 100 | 105.4246 | 90
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 21d 1h | 89142.425 | 83867.7253 | 19d 7h | 93000 | -73000 | 182142.425 | 10867.7253 | 51.52% | Started | 89142.4432 | 173010.1504 | 100 | 51.5244 | 51.5244 | 100 | 105.2785 | 51.5244
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 173010.1504 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2007-07-31 17:00 |  | TP Name | 31/07, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 360d | [5 empty] | 12724860.799 |  | 79.89% |  | 12335087.5595 | 14234388.1115
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 360d | [5 empty] | 12724860.799 |  | 79.89% |  | 12335087.5595 | 14234388.1115
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 319d | 1388823.9761 | 104488.3242 | 24d | 497000 | 119000 | 1885823.9761 | 223488.3242 | 94% | Started | 1739295.2258 | 1567324.8633 | 100 | 75.0588 | 94 | 100 | 101.9191 | 94
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 334d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 133d | 2365346.5527 | 266768.4082 | 15d | 433000 | 0 | 2798346.5527 | 266768.4082 | 92% | Started | 2536078.38 | 2756606.8848 | 100 | 85.8065 | 92 | 100 | 101.5142 | 92
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 100% | Finished | 376803.4355 | 376803.4355 | 100 | 100 | 100 | 100 | 111.1756 | 100
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 111d | [5 empty] | 59257.6831 |  | 40.28% |  | 57002.7454 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 24d | 321962.8828 | 80490.7207 | 6d | -270000 | 4000 | 51962.8828 | 84490.7207 | 37% | Started | 49635.9451 | 134151.2012 | 100 | 240 | 37 | 100 | 38.7346 | 37
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 139d | [5 empty] | 128602.8896 |  | 100% |  | 130114.7993 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 34d | 36975.6807 | 0 | 0 | -13300 | 0 | 23675.6807 | 0 | 100% | Finished | 23925.4404 | 23925.4404 | 100 | 154.5455 | 100 | 100 | 98.9561 | 100
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 100% | Finished | 127818.241 | 127818.241 | 100 | 139.3939 | 100 | 100 | 98.8129 | 100
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 49d | 21857.9193 | 0 | 0 | -3780 | 0 | 18077.9193 | 0 | 100% | Finished | 17397.1195 | 17397.1195 | 100 | 125.641 | 100 | 100 | 103.9133 | 100
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 22d | 162912.6426 | 229558.7236 | 31d | -135000 | 0 | 27912.6426 | 229558.7236 | 41.51% | Started | 107583.8222 | 259179.2041 | 100 | 62.8571 | 41.5094 | 100 | 10.7696 | 41.5094
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 2007-06-12 08:00 | 36d | 93346.5586 | 77788.7988 | 30d | -41000 | 0 | 52346.5586 | 77788.7988 | 40% | Started | 51859.2 | 121869.1182 | 100 | 72 | 40 | 100 | 40.3759 | 40
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 2007-06-29 08:00 | 1d | 1825.36 | 43808.6396 | 24d | 0 | 0 | 1825.36 | 43808.6396 | 4% | Started | 1825.3599 | 45633.9996 | 100 | 4 | 4 | 100 | 4 | 4
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 22d | 72631.6787 | 128756.1577 | 39d | -70000 | 0 | 2631.6787 | 128756.1577 | 36.07% | Started | 47627.3286 | 0 | 100 | 55 | 36.0656 | 100 | 1.9928 | 36.0656
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 389386.7167 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 127d | 220441.5212 | 20829.1201 | 12d | 198000 | 0 | 418441.5212 | 20829.1201 | 95% | Started | 417189.9131 | 385338.7222 | 100 | 50.1976 | 95 | 100 | 95.285 | 95
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 102d | 179169.126 | 38644.3213 | 22d | 221000 | 0 | 400169.126 | 38644.3213 | 91% | Started | 399617.4248 | 381173.5327 | 100 | 40.8 | 91 | 100 | 91.1256 | 91
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 156d | 277355.5269 | 37336.3209 | 21d | 123000 | 0 | 400355.5269 | 37336.3209 | 91% | Started | 399623.0998 | 376919.0493 | 100 | 63.1579 | 91 | 100 | 91.1668 | 91
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 108d | 194374.0811 | 37794.9602 | 21d | 207000 | 0 | 401374.0811 | 37794.9602 | 91% | Started | 399618.7241 | 372550.322 | 100 | 44.2623 | 91 | 100 | 91.3997 | 91
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 88d | 160350.083 | 63775.6012 | 35d | 214000 | 0 | 374350.083 | 63775.6012 | 85% | Started | 373269.4935 | 368076.3269 | 100 | 36.5145 | 85 | 100 | 85.2461 | 85
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 90d | 168184.7974 | 164447.3574 | 88d | 107000 | 0 | 275184.7974 | 164447.3574 | 63% | Started | 276663.9896 | 362531.6743 | 100 | 38.2979 | 63 | 100 | 62.6632 | 63
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 67d | 126822.9603 | 181716.4805 | 96d | 130000 | 0 | 256822.9603 | 181716.4805 | 59% | Started | 259097.4036 | 357754.3209 | 100 | 28.8793 | 59 | 100 | 58.4821 | 59
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 86d | 364110.2266 | 0 | 0 | 0 | 0 | 364110.2266 | 0 | 100% | Finished | 368344.0664 | 368344.0664 | 100 | 98.8506 | 100 | 100 | 98.8506 | 100
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 2007-06-25 08:00 | 27d | 54892.0811 | 335451.6064 | 165d | 49000 | 0 | 103892.0811 | 335451.6064 | 22% | Started | 96610.0621 | 374079.3672 | 100 | 12.5 | 22 | 100 | 23.6583 | 22
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 |  | 0 | 0 | 439133.1958 | 215d | 0 | 0 | 0 | 439133.1958 | 0% | Not Started | 0 | 365603.9165 | 100 |  | 0 | 100 |  | 0
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 |  | 0 | 0 | 439145.1367 | 214d | 0 | 0 | 0 | 439145.1367 | 0% | Not Started | 0 | 357061.9336 | 100 |  | 0 | 100 |  | 0
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 152d | [5 empty] | 649398.177 |  | 49% |  | 513766.7876 | 1013468.2935
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 145d | [5 empty] | 103806.082 |  | 31.75% |  | 113206.082 | 321427.6919
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 |  | 0 | 0 | 239145.6113 | 116d | 0 | 0 | 0 | 239145.6113 | 0% | Not Started | 0 | 208221.6099 | 100 |  | 0 | 100 |  | 0
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 152d | [5 empty] | 545592.095 |  | 57.88% |  | 400560.7056 | 692040.6016
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 23d | 97054.4746 | 75955.6758 | 18d | 84000 | -65000 | 181054.4746 | 10955.6758 | 90% | Started | 155709.1312 | 173010.1504 | 100 | 56.0976 | 90 | 100 | 104.6496 | 90
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 20d | 84395.1953 | 88614.9551 | 21d | 98000 | -78000 | 182395.1953 | 10614.9551 | 90% | Started | 155709.1312 | 173010.1504 | 100 | 48.7805 | 90 | 100 | 105.4246 | 90
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 21d 1h | 89142.425 | 83867.7253 | 19d 7h | 93000 | -73000 | 182142.425 | 10867.7253 | 51.52% | Started | 89142.4432 | 173010.1504 | 100 | 51.5244 | 51.5244 | 100 | 105.2785 | 51.5244
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 |  | 0 | 0 | 173010.1504 | 41d | 0 | 0 | 0 | 173010.1504 | 0% | Not Started | 0 | 173010.1504 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2007-08-31 17:00 |  | TP Name | 31/08, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 383d | [5 empty] | 14001456.0536 |  | 86.85% |  | 13409942.2383 | 14907850.8408
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 383d | [5 empty] | 14001456.0536 |  | 86.85% |  | 13409942.2383 | 14907850.8408
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 342d | 1488958.6201 | 82719.9233 | 19d | 572000 | 75000 | 2060958.6201 | 157719.9233 | 96% | Started | 1776301.472 | 1667459.5073 | 100 | 80.4706 | 96 | 100 | 111.3843 | 96
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 357d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 156d | 2774391.4453 | 213414.7266 | 12d | 78000 | 0 | 2852391.4453 | 213414.7266 | 92.86% | Started | 2559706.3226 | 2756606.8848 | 100 | 100.6452 | 92.8571 | 100 | 103.4747 | 92.8571
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 100% | Finished | 376803.4355 | 376803.4355 | 100 | 100 | 100 | 100 | 111.1756 | 100
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 34d | [5 empty] | 139908.8843 |  | 100% |  | 141518.0015 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 34d | 456114.084 | 0 | 0 | -323500 | 0 | 132614.084 | 0 | 100% | Finished | 134151.2012 | 134151.2012 | 100 | 340 | 100 | 100 | 98.8542 | 100
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 139d | [5 empty] | 128602.8896 |  | 100% |  | 130114.7993 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 34d | 36975.6807 | 0 | 0 | -13300 | 0 | 23675.6807 | 0 | 100% | Finished | 23925.4404 | 23925.4404 | 100 | 154.5455 | 100 | 100 | 98.9561 | 100
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 100% | Finished | 127818.241 | 127818.241 | 100 | 139.3939 | 100 | 100 | 98.8129 | 100
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 49d | 21857.9193 | 0 | 0 | -3780 | 0 | 18077.9193 | 0 | 100% | Finished | 17397.1195 | 17397.1195 | 100 | 125.641 | 100 | 100 | 103.9133 | 100
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 45d | 333230.4053 | 177722.8828 | 24d | -255000 | 0 | 78230.4053 | 177722.8828 | 42% | Started | 108855.2623 | 259179.2041 | 100 | 128.5714 | 42 | 100 | 30.1839 | 42
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 2007-06-12 08:00 | 36d | 93346.5586 | 77788.7988 | 30d | -41000 | 0 | 52346.5586 | 77788.7988 | 40% | Started | 51859.2 | 129647.998 | 100 | 72 | 40 | 100 | 40.3759 | 40
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 |  | 0 | 0 | 8493.1199 | 36d | 0 | 0 | 0 | 8493.1199 | 0% | Not Started | 0 | 3774.72 | 100 |  | 0 | 100 |  | 0
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 2007-06-29 08:00 | 24d | 43808.6396 | 36507.1997 | 20d | 0 | 0 | 43808.6396 | 36507.1997 | 19% | Started | 8670.4598 | 45633.9996 | 100 | 96 | 19 | 100 | 96 | 19
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 45d | 148564.7974 | 92440.3184 | 28d | -109000 | 0 | 39564.7974 | 92440.3184 | 37% | Started | 48861.3118 | 59425.9189 | 100 | 112.5 | 37 | 100 | 29.9603 | 37
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 428839.9963 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 130d | 225648.8013 | 0 | 0 | 198000 | 0 | 423648.8013 | 0 | 100% | Finished | 439147.2825 | 425261.2024 | 100 | 51.3834 | 100 | 100 | 96.4708 | 100
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 125d | 219570.0073 | 0 | 0 | 204000 | 0 | 423570.0073 | 0 | 100% | Finished | 439140.0146 | 421574.4141 | 100 | 50 | 100 | 100 | 96.4544 | 100
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 169d | 300468.4874 | 0 | 0 | 123000 | 0 | 423468.4874 | 0 | 100% | Finished | 439146.2509 | 417811.2103 | 100 | 68.4211 | 100 | 100 | 96.4299 | 100
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 108d | 194374.0811 | 37794.9602 | 21d | 207000 | 0 | 401374.0811 | 37794.9602 | 91% | Started | 399618.7241 | 413944.8022 | 100 | 44.2623 | 91 | 100 | 91.3997 | 91
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 111d | 202259.7638 | 38265.3607 | 21d | 199000 | 0 | 401259.7638 | 38265.3607 | 91% | Started | 399617.9286 | 409986.0077 | 100 | 46.0581 | 91 | 100 | 91.3739 | 91
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 113d | 211165.3567 | 44849.2793 | 24d | 183000 | 0 | 394165.3567 | 44849.2793 | 90% | Started | 395234.2633 | 405512.2336 | 100 | 48.0851 | 90 | 100 | 89.7566 | 90
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 90d | 170359.2004 | 107894.1603 | 57d | 161000 | 0 | 331359.2004 | 107894.1603 | 75% | Started | 329361.1208 | 401290.561 | 100 | 38.7931 | 75 | 100 | 75.455 | 75
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 86d | 364110.2266 | 0 | 0 | 0 | 0 | 364110.2266 | 0 | 100% | Finished | 368344.0664 | 368344.0664 | 100 | 98.8506 | 100 | 100 | 98.8506 | 100
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 2007-06-25 08:00 | 50d | 101652.002 | 193138.8037 | 95d | 144000 | 0 | 245652.002 | 193138.8037 | 56% | Started | 245916.5242 | 420839.2881 | 100 | 23.1481 | 56 | 100 | 55.9398 | 56
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 | 2007-08-01 08:00 | 23d | 46977.0396 | 394198.6362 | 193d | 0 | 0 | 46977.0396 | 394198.6362 | 10.65% | Started | 46759.5548 | 412580.9561 | 100 | 10.6977 | 10.6481 | 100 | 10.6977 | 10.6481
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 | 2007-08-01 08:00 | 23d | 47197.8418 | 385791.0547 | 188d | 5000 | -5000 | 52197.8418 | 380791.0547 | 10.9% | Started | 47868.8997 | 404259.7754 | 100 | 10.7477 | 10.9005 | 100 | 11.8862 | 10.9005
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 175d | [5 empty] | 973846.1284 |  | 83.35% |  | 874001.0454 | 1044392.2949
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 168d | [5 empty] | 228222.8843 |  | 51.04% |  | 181960.4439 | 352351.6934
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 | 2007-08-01 08:00 | 23d | 47416.8022 | 117511.2056 | 57d | 77000 | 0 | 124416.8022 | 117511.2056 | 28.75% | Started | 68754.3618 | 239145.6113 | 100 | 19.8276 | 28.75 | 100 | 52.0255 | 28.75
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 175d | [5 empty] | 745623.2441 |  | 100% |  | 692040.6016 | 692040.6016
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 45d | 189889.1895 | 0 | 0 | -3000 | 0 | 186889.1895 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 109.7561 | 100 | 100 | 108.0221 | 100
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 42d | 177229.9102 | 0 | 0 | 9000 | 0 | 186229.9102 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 102.439 | 100 | 100 | 107.641 | 100
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 43d | 181449.6699 | 0 | 0 | 5000 | 0 | 186449.6699 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 104.878 | 100 | 100 | 107.7681 | 100
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-08-01 08:00 | 23d | 97054.4746 | 0 | 0 | 89000 | 0 | 186054.4746 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 56.0976 | 100 | 100 | 107.5396 | 100

## TP17
| TP Status Date | 2007-09-30 17:00 |  | TP Name | 30/09, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 404d | [5 empty] | 14936088.7014 |  | 93.24% |  | 14397407.2272 | 15335575.8859
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 404d | [5 empty] | 14936088.7014 |  | 93.24% |  | 14397407.2272 | 15335575.8859
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 362d | 1576032.2236 | 69658.8828 | 16d | 494000 | 75000 | 2070032.2236 | 144658.8828 | 96% | Started | 1776301.472 | 1754533.1108 | 100 | 85.1765 | 96 | 100 | 111.8746 | 96
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 377d | [5 empty] | 2819056.6411 |  | 99.34% |  | 2852992.86 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 16d | 38170.8789 | 19085.4395 | 8d | -630 | 0 | 37540.8789 | 19085.4395 | 66.67% | Started | 38170.8971 | 57256.3184 | 100 | 66.6667 | 66.6667 | 100 | 65.5664 | 66.6667
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 156d | 2774391.4453 | 213414.7266 | 12d | 78000 | 0 | 2852391.4453 | 213414.7266 | 92.86% | Started | 2559706.3226 | 2756606.8848 | 100 | 100.6452 | 92.8571 | 100 | 103.4747 | 92.8571
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 100% | Finished | 376803.4355 | 376803.4355 | 100 | 100 | 100 | 100 | 111.1756 | 100
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 34d | [5 empty] | 139908.8843 |  | 100% |  | 141518.0015 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 34d | 456114.084 | 0 | 0 | -323500 | 0 | 132614.084 | 0 | 100% | Finished | 134151.2012 | 134151.2012 | 100 | 340 | 100 | 100 | 98.8542 | 100
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 139d | [5 empty] | 128602.8896 |  | 100% |  | 130114.7993 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 34d | 36975.6807 | 0 | 0 | -13300 | 0 | 23675.6807 | 0 | 100% | Finished | 23925.4404 | 23925.4404 | 100 | 154.5455 | 100 | 100 | 98.9561 | 100
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 100% | Finished | 127818.241 | 127818.241 | 100 | 139.3939 | 100 | 100 | 98.8129 | 100
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 49d | 21857.9193 | 0 | 0 | -3780 | 0 | 18077.9193 | 0 | 100% | Finished | 17397.1195 | 17397.1195 | 100 | 125.641 | 100 | 100 | 103.9133 | 100
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 65d | 481332.8076 | 59240.9609 | 8d | -281000 | 0 | 200332.8076 | 59240.9609 | 77% | Started | 199567.9822 | 259179.2041 | 100 | 185.7143 | 77 | 100 | 77.2951 | 77
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 2007-06-12 08:00 | 56d | 145205.7578 | 25929.5996 | 10d | 30000 | 0 | 175205.7578 | 25929.5996 | 84.85% | Started | 110004.3653 | 129647.998 | 100 | 112 | 84.8485 | 100 | 135.1396 | 84.8485
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 | 2007-09-17 08:00 | 10d | 2359.2 | 6133.92 | 26d | 0 | 0 | 2359.2 | 6133.92 | 27.78% | Started | 2359.2001 | 8493.1199 | 100 | 27.7778 | 27.7778 | 100 | 27.7778 | 27.7778
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 2007-06-29 08:00 | 44d | 80315.8394 | 5476.08 | 3d | -39700 | 0 | 40615.8394 | 5476.08 | 89% | Started | 40614.259 | 45633.9996 | 100 | 176 | 89 | 100 | 89.0035 | 89
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 65d | 214593.5962 | 33014.3994 | 10d | -116000 | 0 | 98593.5962 | 33014.3994 | 75% | Started | 99043.1982 | 125454.7178 | 100 | 162.5 | 75 | 100 | 74.6595 | 75
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 439132.1562 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 130d | 225648.8013 | 0 | 0 | 198000 | 0 | 423648.8013 | 0 | 100% | Finished | 439147.2825 | 439147.2825 | 100 | 51.3834 | 100 | 100 | 96.4708 | 100
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 125d | 219570.0073 | 0 | 0 | 204000 | 0 | 423570.0073 | 0 | 100% | Finished | 439140.0146 | 439140.0146 | 100 | 50 | 100 | 100 | 96.4544 | 100
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 169d | 300468.4874 | 0 | 0 | 123000 | 0 | 423468.4874 | 0 | 100% | Finished | 439146.2509 | 439146.2509 | 100 | 68.4211 | 100 | 100 | 96.4299 | 100
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 128d | 230369.2812 | 0 | 0 | 193000 | 0 | 423369.2812 | 0 | 100% | Finished | 439141.4424 | 439141.4424 | 100 | 52.459 | 100 | 100 | 96.4084 | 100
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 123d | 224125.6842 | 0 | 0 | 199000 | 0 | 423125.6842 | 0 | 100% | Finished | 439140.5682 | 439140.5682 | 100 | 51.0373 | 100 | 100 | 96.3531 | 100
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 129d | 241064.8762 | 0 | 0 | 182000 | 0 | 423064.8762 | 0 | 100% | Finished | 439149.1931 | 439149.1931 | 100 | 54.8936 | 100 | 100 | 96.3374 | 100
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 110d | 208216.8005 | 0 | 0 | 215000 | 0 | 423216.8005 | 0 | 100% | Finished | 439148.1611 | 439148.1611 | 100 | 47.4138 | 100 | 100 | 96.3722 | 100
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 86d | 364110.2266 | 0 | 0 | 0 | 0 | 364110.2266 | 0 | 100% | Finished | 368344.0664 | 368344.0664 | 100 | 98.8506 | 100 | 100 | 98.8506 | 100
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 2007-06-25 08:00 | 70d | 142312.8027 | 50826.001 | 25d | 246000 | 0 | 388312.8027 | 50826.001 | 89% | Started | 390831.6108 | 439136.6484 | 100 | 32.4074 | 89 | 100 | 88.4264 | 89
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 | 2007-08-01 08:00 | 43d | 87826.6392 | 179738.2383 | 88d | 172000 | 0 | 259826.6392 | 179738.2383 | 59% | Started | 259088.574 | 439133.1958 | 100 | 20 | 59 | 100 | 59.1681 | 59
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 | 2007-08-01 08:00 | 43d | 88239.4434 | 342697.373 | 167d | 8000 | -5000 | 96239.4434 | 337697.373 | 22% | Started | 96611.9296 | 439145.1367 | 100 | 20.0935 | 22 | 100 | 21.9152 | 22
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 195d | [5 empty] | 1032078.1304 |  | 94.36% |  | 989388.7998 | 1045636.9349
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 188d | [5 empty] | 286454.8862 |  | 83.41% |  | 297348.1982 | 353596.3334
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 52d | 113206.082 | 0 | 0 | -9400 | 0 | 103806.082 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 100 | 100 | 100 | 91.6966 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 | 2007-08-01 08:00 | 43d | 88648.8042 | 55663.2026 | 27d | 94000 | 0 | 182648.8042 | 55663.2026 | 77% | Started | 184142.1162 | 239145.6113 | 100 | 37.069 | 77 | 100 | 76.3756 | 77
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 |  | 0 | 0 | 4148.8 | 10d | 0 | 0 | 0 | 4148.8 | 0% | Not Started | 0 | 1244.64 | 100 |  | 0 | 100 |  | 0
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 175d | [5 empty] | 745623.2441 |  | 100% |  | 692040.6016 | 692040.6016
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 45d | 189889.1895 | 0 | 0 | -3000 | 0 | 186889.1895 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 109.7561 | 100 | 100 | 108.0221 | 100
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 42d | 177229.9102 | 0 | 0 | 9000 | 0 | 186229.9102 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 102.439 | 100 | 100 | 107.641 | 100
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 43d | 181449.6699 | 0 | 0 | 5000 | 0 | 186449.6699 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 104.878 | 100 | 100 | 107.7681 | 100
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-08-01 08:00 | 23d | 97054.4746 | 0 | 0 | 89000 | 0 | 186054.4746 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 56.0976 | 100 | 100 | 107.5396 | 100

## TP18
| TP Status Date | 2007-10-31 17:00 |  | TP Name | 31/10, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Brussels Finance Tower | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 426d | [5 empty] | 16338027.1975 |  | 100% |  | 15440865.8897 | 15440865.8897
1 | Koningstraat | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  |  | 2 |  |  | 15440865.8897 |  | 426d | [5 empty] | 16338027.1975 |  | 100% |  | 15440865.8897 | 15440865.8897
2 | Werfinstallatie | 2006-03-15 08:00 | 2007-10-30 17:00 | 425d |  | 0 | 0 | 544.21 | 1850314.0747 | 1850314.0747 | 2006-03-15 08:00 | 385d | 1676166.8677 | 0 | 0 | 569033.3125 | 0 | 2245200.1802 | 0 | 100% | Finished | 1850314.0747 | 1850314.0747 | 100 | 90.5882 | 100 | 100 | 121.3416 | 100
9 | Beton | 2006-04-10 08:00 | 2006-12-20 17:00 | 183d |  |  | 0 |  |  | 2872078.2812 |  | 184d | [5 empty] | 2838094.8889 |  | 100% |  | 2872078.2812 | 2872078.2812
10 | Verdiep +3 | 2006-06-15 08:00 | 2006-07-03 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-01 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
11 | Verdiep +4 | 2006-06-27 08:00 | 2006-07-13 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-08 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
12 | Verdiep +5 | 2006-08-04 08:00 | 2006-08-22 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-08-28 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
13 | Verdiep +6 | 2006-09-11 08:00 | 2006-09-29 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-11 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
14 | Verdiep +7 | 2006-09-25 08:00 | 2006-10-13 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-09-26 08:00 | 15d | 255892.793 | 0 | 0 | -3030.3501 | 0 | 252862.4429 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 100 | 100 | 100 | 98.8158 | 100
15 | Verdiep +8 | 2006-10-09 08:00 | 2006-10-27 17:00 | 15d |  | 0 | 0 | 2132.4399 | 255892.793 | 255892.793 | 2006-10-11 08:00 | 15d 3h | 262290.1128 | 0 | 0 | -9400 | 0 | 252890.1128 | 0 | 100% | Finished | 255892.793 | 255892.793 | 100 | 102.5 | 100 | 100 | 98.8266 | 100
16 | Verdiep +9 | 2006-10-23 08:00 | 2006-11-10 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-01 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
17 | Verdiep +10 | 2006-11-06 08:00 | 2006-11-24 17:00 | 15d |  | 0 | 0 | 1599.33 | 191919.5947 | 191919.5947 | 2006-11-20 08:00 | 15d | 191919.5947 | 0 | 0 | -2272.77 | 0 | 189646.8247 | 0 | 100% | Finished | 191919.5947 | 191919.5947 | 100 | 100 | 100 | 100 | 98.8158 | 100
18 | Verdiep +2 | 2006-06-05 08:00 | 2006-06-21 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-06-15 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
19 | Verdiep +1 | 2006-05-22 08:00 | 2006-06-07 17:00 | 13d |  | 0 | 0 | 2460.51 | 255893.041 | 255893.041 | 2006-05-26 08:00 | 13d | 255893.041 | 0 | 0 | -3030.3501 | 0 | 252862.6909 | 0 | 100% | Finished | 255893.041 | 255893.041 | 100 | 100 | 100 | 100 | 98.8158 | 100
20 | Verdiep glk | 2006-04-10 08:00 | 2006-05-19 17:00 | 30d |  | 0 | 0 | 1599.33 | 383839.1895 | 383839.1895 | 2006-04-20 08:00 | 30d | 383839.1895 | 0 | 0 | -4545.5298 | 0 | 379293.6597 | 0 | 100% | Finished | 383839.1895 | 383839.1895 | 100 | 100 | 100 | 100 | 98.8158 | 100
21 | Buitentrappen (2 fazen) | 2006-11-17 08:00 | 2006-12-20 17:00 | 24d |  | 0 | 0 | 298.21 | 57256.3184 | 57256.3184 | 2006-11-09 08:00 | 39d | 93041.5173 | 0 | 0 | -36462.3906 | 0 | 56579.1267 | 0 | 100% | Finished | 57256.3184 | 57256.3184 | 100 | 162.5 | 100 | 100 | 98.8173 | 100
765 | Gevels inbegrepen natuursteen (start = landmeter) | 2006-10-02 08:00 | 2007-05-04 17:00 | 155d |  | 0 | 0 | 2223.0701 | 2756606.8848 | 2756606.8848 | 2006-12-01 08:00 | 179d | 3183436.3379 | 0 | 0 | -118755.7109 | 0 | 3064680.627 | 0 | 100% | Finished | 2756606.8848 | 2756606.8848 | 100 | 115.4839 | 100 | 100 | 111.1758 | 100
764 | Gevels Wind & waterdicht +3 t/m +10 | 2007-03-02 08:00 | 2007-03-28 17:00 | 19d |  | 0 | 0 | 2478.97 | 376803.4355 | 376803.4355 | 2007-04-11 08:00 | 19d | 376803.4355 | 0 | 0 | 42110 | 0 | 418913.4355 | 0 | 100% | Finished | 376803.4355 | 376803.4355 | 100 | 100 | 100 | 100 | 111.1756 | 100
45 | Technisch lokaal +10 | 2007-01-15 08:00 | 2007-02-07 17:00 | 18d |  |  | 0 |  |  | 141518.0015 |  | 34d | [5 empty] | 139908.8843 |  | 100% |  | 141518.0015 | 141518.0015
46 | Metselwerk | 2007-01-15 08:00 | 2007-01-26 17:00 | 10d |  | 0 | 0 | 1676.89 | 134151.2012 | 134151.2012 | 2007-02-27 08:00 | 34d | 456114.084 | 0 | 0 | -323500 | 0 | 132614.084 | 0 | 100% | Finished | 134151.2012 | 134151.2012 | 100 | 340 | 100 | 100 | 98.8542 | 100
48 | HVAC Groepen | 2007-02-05 08:00 | 2007-02-07 17:00 | 3d |  | 0 | 0 | 306.95 | 7366.8003 | 7366.8003 | 2007-03-01 08:00 | 3d | 7366.8003 | 0 | 0 | -72 | 0 | 7294.8003 | 0 | 100% | Finished | 7366.8003 | 7366.8003 | 100 | 100 | 100 | 100 | 99.0226 | 100
49 | Dakdichting | 2006-11-02 08:00 | 2007-04-12 17:00 | 116d |  |  | 0 |  |  | 130114.7993 |  | 139d | [5 empty] | 128602.8896 |  | 100% |  | 130114.7993 | 130114.7993
50 | Balkons : wachtslabben | 2006-11-02 08:00 | 2006-11-10 17:00 | 7d |  | 0 | 0 | 351.74 | 19697.4395 | 19697.4395 | 2006-12-01 08:00 | 7d | 19697.4395 | 0 | 0 | -233 | 0 | 19464.4395 | 0 | 100% | Finished | 19697.4395 | 19697.4395 | 100 | 100 | 100 | 100 | 98.8171 | 100
51 | Balkons: horizontaal definitief | 2007-03-12 08:00 | 2007-03-16 17:00 | 5d |  | 0 | 0 | 198.79 | 7951.5997 | 7951.5997 | 2007-03-27 08:00 | 5d | 7951.5997 | 0 | 0 | -100 | 0 | 7851.5997 | 0 | 100% | Finished | 7951.5997 | 7951.5997 | 100 | 100 | 100 | 100 | 98.7424 | 100
52 | Boven Schachten | 2007-01-29 08:00 | 2007-02-02 17:00 | 5d |  | 0 | 0 | 416.78 | 16671.2 | 16671.2 | 2007-02-22 08:00 | 5d | 16671.2 | 0 | 0 | -197 | 0 | 16474.2 | 0 | 100% | Finished | 16671.2 | 16671.2 | 100 | 100 | 100 | 100 | 98.8183 | 100
53 | Metselwerk, helling, dampscherm, slabben | 2007-01-08 08:00 | 2007-01-31 17:00 | 18d |  | 0 | 0 | 272.18 | 39193.9189 | 39193.9189 | 2007-01-18 08:00 | 18d | 39193.9189 | 0 | 0 | -464.15 | 0 | 38729.769 | 0 | 100% | Finished | 39193.9189 | 39193.9189 | 100 | 100 | 100 | 100 | 98.8158 | 100
54 | Helling, dampscherm, definitief | 2007-01-29 08:00 | 2007-02-16 17:00 | 15d |  | 0 | 0 | 188.96 | 22675.2008 | 22675.2008 | 2007-02-14 08:00 | 15d | 22675.2008 | 0 | 0 | -268 | 0 | 22407.2008 | 0 | 100% | Finished | 22675.2008 | 22675.2008 | 100 | 100 | 100 | 100 | 98.8181 | 100
55 | Definitief | 2007-03-14 08:00 | 2007-04-12 17:00 | 22d |  | 0 | 0 | 135.94 | 23925.4404 | 23925.4404 | 2007-04-27 08:00 | 34d | 36975.6807 | 0 | 0 | -13300 | 0 | 23675.6807 | 0 | 100% | Finished | 23925.4404 | 23925.4404 | 100 | 154.5455 | 100 | 100 | 98.9561 | 100
56 | Piste renigingsmachine op dak | 2007-02-19 08:00 | 2007-03-16 17:00 | 20d |  | 0 | 0 | 85.42 | 13667.1997 | 13667.1997 | 2007-02-21 08:00 | 20d | 13667.1997 | 0 | 0 | -4000 | 0 | 9667.1997 | 0 | 100% | Finished | 13667.1997 | 13667.1997 | 100 | 100 | 100 | 100 | 70.7328 | 100
57 | Renigingsmachine | 2007-03-13 08:00 | 2007-03-19 17:00 | 5d |  | 0 | 0 | 1878.9301 | 75157.2021 | 75157.2021 | 2007-02-28 08:00 | 5d | 75157.2021 | 0 | 0 | -24000 | 0 | 51157.2021 | 0 | 100% | Finished | 75157.2021 | 75157.2021 | 100 | 100 | 100 | 100 | 68.0669 | 100
58 | Metselwerk (behalve gaslokaal) | 2006-10-02 08:00 | 2006-11-24 17:00 | 40d |  | 0 | 0 | 419.22 | 134150.4004 | 134150.4004 | 2006-10-02 08:00 | 67d | 224701.9207 | 0 | 0 | -89000 | 0 | 135701.9207 | 0 | 100% | Finished | 134150.4004 | 134150.4004 | 100 | 167.5 | 100 | 100 | 101.1566 | 100
59 | Sluiten technische schachten | 2007-02-26 08:00 | 2007-03-27 17:00 | 22d |  | 0 | 0 | 697.62 | 122781.1191 | 122781.1191 | 2007-03-29 08:00 | 22d | 122781.1191 | 0 | 0 | -1200 | 0 | 121581.1191 | 0 | 100% | Finished | 122781.1191 | 122781.1191 | 100 | 100 | 100 | 100 | 99.0227 | 100
61 | Pleisterwerken | 2007-03-05 08:00 | 2007-04-18 17:00 | 33d |  | 0 | 0 | 484.16 | 127818.241 | 127818.241 | 2007-03-01 08:00 | 46d | 178170.8813 | 0 | 0 | -51870 | 0 | 126300.8813 | 0 | 100% | Finished | 127818.241 | 127818.241 | 100 | 139.3939 | 100 | 100 | 98.8129 | 100
62 | Chapes | 2007-03-20 08:00 | 2007-05-11 17:00 | 39d |  | 0 | 0 | 55.76 | 17397.1195 | 17397.1195 | 2007-04-13 08:00 | 49d | 21857.9193 | 0 | 0 | -3780 | 0 | 18077.9193 | 0 | 100% | Finished | 17397.1195 | 17397.1195 | 100 | 125.641 | 100 | 100 | 103.9133 | 100
63 | Vloeren & faience | 2007-04-24 08:00 | 2007-06-11 17:00 | 35d |  | 0 | 0 | 925.64 | 259179.2041 | 259179.2041 | 2007-05-31 15:00 | 88d | 651650.5703 | 0 | 0 | -418485.1562 | 0 | 233165.4141 | 0 | 100% | Finished | 259179.2041 | 259179.2041 | 100 | 251.4286 | 100 | 100 | 89.963 | 100
64 | Binnenschrijnwerk | 2007-05-28 08:00 | 2007-08-03 17:00 | 50d |  | 0 | 0 | 324.12 | 129647.998 | 129647.998 | 2007-06-12 08:00 | 79d | 204843.8369 | 0 | 0 | -3406.26 | 0 | 201437.5769 | 0 | 100% | Finished | 129647.998 | 129647.998 | 100 | 158 | 100 | 100 | 155.3727 | 100
65 | Tapijt | 2007-08-10 08:00 | 2007-09-28 17:00 | 36d |  | 0 | 0 | 29.49 | 8493.1199 | 8493.1199 | 2007-09-17 08:00 | 33d | 7785.3599 | 0 | 0 | 942.17 | 0 | 8727.5299 | 0 | 100% | Finished | 8493.1199 | 8493.1199 | 100 | 91.6667 | 100 | 100 | 102.76 | 100
66 | Smeedwerk | 2007-03-21 08:00 | 2007-04-24 17:00 | 25d |  | 0 | 0 | 228.17 | 45633.9996 | 45633.9996 | 2007-06-29 08:00 | 47d | 85791.9193 | 0 | 0 | -40700 | 0 | 45091.9193 | 0 | 100% | Finished | 45633.9996 | 45633.9996 | 100 | 188 | 100 | 100 | 98.8121 | 100
67 | Schilderwerken | 2007-08-08 08:00 | 2007-10-02 17:00 | 40d |  | 0 | 0 | 412.68 | 132057.5977 | 132057.5977 | 2007-05-31 16:00 | 88d | 290526.7148 | 0 | 0 | -160033.9844 | 0 | 130492.7305 | 0 | 100% | Finished | 132057.5977 | 132057.5977 | 100 | 220 | 100 | 100 | 98.815 | 100
68 | Einde opkuisen | 2007-10-03 08:00 | 2007-10-16 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2007-10-03 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
69 | Voorlopige receptie | 2007-10-17 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2007-10-18 08:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
752 | Verdiep +3 | 2006-09-18 08:00 | 2007-09-10 17:00 | 256d |  | 0 | 0 | 214.42 | 439132.1562 | 439132.1562 | 2006-11-13 08:00 | 121d | 207558.5582 | 0 | 0 | 216000 | 0 | 423558.5582 | 0 | 100% | Finished | 439132.1562 | 439132.1562 | 100 | 47.2656 | 100 | 100 | 96.4536 | 100
753 | Verdiep +4 | 2006-09-25 08:00 | 2007-09-12 17:00 | 253d |  | 0 | 0 | 216.97 | 439147.2825 | 439147.2825 | 2006-12-01 08:00 | 130d | 225648.8013 | 0 | 0 | 198000 | 0 | 423648.8013 | 0 | 100% | Finished | 439147.2825 | 439147.2825 | 100 | 51.3834 | 100 | 100 | 96.4708 | 100
754 | Verdiep +5 | 2006-10-02 08:00 | 2007-09-14 17:00 | 250d |  | 0 | 0 | 219.57 | 439140.0146 | 439140.0146 | 2006-12-18 08:00 | 125d | 219570.0073 | 0 | 0 | 204000 | 0 | 423570.0073 | 0 | 100% | Finished | 439140.0146 | 439140.0146 | 100 | 50 | 100 | 100 | 96.4544 | 100
755 | Verdiep +6 | 2006-10-09 08:00 | 2007-09-18 17:00 | 247d |  | 0 | 0 | 222.24 | 439146.2509 | 439146.2509 | 2007-01-01 08:00 | 169d | 300468.4874 | 0 | 0 | 123000 | 0 | 423468.4874 | 0 | 100% | Finished | 439146.2509 | 439146.2509 | 100 | 68.4211 | 100 | 100 | 96.4299 | 100
756 | Verdiep +7 | 2006-10-16 08:00 | 2007-09-20 17:00 | 244d |  | 0 | 0 | 224.97 | 439141.4424 | 439141.4424 | 2007-02-01 08:00 | 128d | 230369.2812 | 0 | 0 | 193000 | 0 | 423369.2812 | 0 | 100% | Finished | 439141.4424 | 439141.4424 | 100 | 52.459 | 100 | 100 | 96.4084 | 100
757 | Verdiep +8 | 2006-10-23 08:00 | 2007-09-24 17:00 | 241d |  | 0 | 0 | 227.77 | 439140.5682 | 439140.5682 | 2007-03-01 08:00 | 123d | 224125.6842 | 0 | 0 | 199000 | 0 | 423125.6842 | 0 | 100% | Finished | 439140.5682 | 439140.5682 | 100 | 51.0373 | 100 | 100 | 96.3531 | 100
758 | Verdiep +9 | 2006-11-02 08:00 | 2007-09-26 17:00 | 235d |  | 0 | 0 | 233.59 | 439149.1931 | 439149.1931 | 2007-03-12 08:00 | 129d | 241064.8762 | 0 | 0 | 182000 | 0 | 423064.8762 | 0 | 100% | Finished | 439149.1931 | 439149.1931 | 100 | 54.8936 | 100 | 100 | 96.3374 | 100
759 | Verdiep +10 | 2006-11-09 08:00 | 2007-09-28 17:00 | 232d |  | 0 | 0 | 236.61 | 439148.1611 | 439148.1611 | 2007-05-01 08:00 | 110d | 208216.8005 | 0 | 0 | 215000 | 0 | 423216.8005 | 0 | 100% | Finished | 439148.1611 | 439148.1611 | 100 | 47.4138 | 100 | 100 | 96.3722 | 100
760 | Technische lokaal +10 | 2007-02-05 08:00 | 2007-06-05 17:00 | 87d |  | 0 | 0 | 529.23 | 368344.0664 | 368344.0664 | 2007-03-01 08:00 | 86d | 364110.2266 | 0 | 0 | 0 | 0 | 364110.2266 | 0 | 100% | Finished | 368344.0664 | 368344.0664 | 100 | 98.8506 | 100 | 100 | 98.8506 | 100
761 | Verdiep +2 | 2006-11-16 08:00 | 2007-09-13 17:00 | 216d |  | 0 | 0 | 254.13 | 439136.6484 | 439136.6484 | 2007-06-25 08:00 | 93d | 189072.7236 | 0 | 0 | 234566.6875 | 0 | 423639.4111 | 0 | 100% | Finished | 439136.6484 | 439136.6484 | 100 | 43.0556 | 100 | 100 | 96.471 | 100
762 | Verdiep +1 | 2006-11-23 08:00 | 2007-09-19 17:00 | 215d |  | 0 | 0 | 255.31 | 439133.1958 | 439133.1958 | 2007-08-01 08:00 | 66d | 134803.6787 | 0 | 0 | 288835.7188 | 0 | 423639.3975 | 0 | 100% | Finished | 439133.1958 | 439133.1958 | 100 | 30.6977 | 100 | 100 | 96.4717 | 100
763 | Verdiep glk | 2006-11-30 08:00 | 2007-09-25 17:00 | 214d |  | 0 | 0 | 256.51 | 439145.1367 | 439145.1367 | 2007-08-01 08:00 | 66d | 135437.2852 | 0 | 0 | 288202.125 | 0 | 423639.4102 | 0 | 100% | Finished | 439145.1367 | 439145.1367 | 100 | 30.8411 | 100 | 100 | 96.4691 | 100
742 | Liften | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 1048541.095 |  | 218d | [5 empty] | 1399171.9373 |  | 100% |  | 1048541.095 | 1048541.095
743 | Goederenlift KGL1 | 2006-12-15 08:00 | 2007-10-09 17:00 | 213d |  |  | 0 |  |  | 356500.4934 |  | 211d | [5 empty] | 653548.6931 |  | 100% |  | 356500.4934 | 356500.4934
744 | KGL1 - werflift montage | 2006-12-15 08:00 | 2007-02-26 17:00 | 52d |  | 0 | 0 | 272.13 | 113206.082 | 113206.082 | 2007-01-10 08:00 | 75d | 163278.0029 | 0 | 0 | 44255.6211 | 0 | 207533.624 | 0 | 100% | Finished | 113206.082 | 113206.082 | 100 | 144.2308 | 100 | 100 | 183.3237 | 100
745 | KGL1 werflift | 2007-03-13 08:00 | 2007-08-21 17:00 | 116d |  | 0 | 0 | 257.7 | 239145.6113 | 239145.6113 | 2007-08-01 08:00 | 66d | 136065.6064 | 0 | 0 | 302343.5625 | 0 | 438409.1689 | 0 | 100% | Finished | 239145.6113 | 239145.6113 | 100 | 56.8966 | 100 | 100 | 183.3231 | 100
746 | KGL1 opkuisen | 2007-09-26 08:00 | 2007-10-09 17:00 | 10d |  | 0 | 0 | 51.86 | 4148.8 | 4148.8 | 2007-10-01 08:00 | 10d | 4148.8 | 0 | 0 | 3457.1001 | 0 | 7605.9001 | 0 | 100% | Finished | 4148.8 | 4148.8 | 100 | 100 | 100 | 100 | 183.3277 | 100
747 | Personenliften KPL1-4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  |  | 0 |  |  | 692040.6016 |  | 175d | [5 empty] | 745623.2441 |  | 100% |  | 692040.6016 | 692040.6016
748 | KPL 1 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-01-01 08:00 | 45d | 189889.1895 | 0 | 0 | -3000 | 0 | 186889.1895 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 109.7561 | 100 | 100 | 108.0221 | 100
749 | KPL 2 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-02-01 08:00 | 42d | 177229.9102 | 0 | 0 | 9000 | 0 | 186229.9102 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 102.439 | 100 | 100 | 107.641 | 100
750 | KPL 3 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-03-01 08:00 | 43d | 181449.6699 | 0 | 0 | 5000 | 0 | 186449.6699 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 104.878 | 100 | 100 | 107.7681 | 100
751 | KPL 4 | 2007-04-16 08:00 | 2007-06-11 17:00 | 41d |  | 0 | 0 | 527.47 | 173010.1504 | 173010.1504 | 2007-08-01 08:00 | 23d | 97054.4746 | 0 | 0 | 89000 | 0 | 186054.4746 | 0 | 100% | Finished | 173010.1504 | 173010.1504 | 100 | 56.0976 | 100 | 100 | 107.5396 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/04, 2006 | 2006-03-15 08:00 | 2006-04-30 17:00 | 335591.0405 | 521532.0423 | 515899.6421 | 2006-05-15 16:00 | 185941.0017 | 155.4% | 5632.4002 | 101.1% | 10d 7h | 133% | 54.97% | 2007-10-23 16:00 | 2007-04-02 12:00 | 2007-03-28 12:00 | 2007-10-04 15:00 | 2007-04-02 12:00 | 2007-03-28 16:00 | 2007-10-16 09:00 | 2007-06-05 14:00 | 2007-05-31 12:00 | 15435233.4895 | 15274108.8571 | 10116066.7729 | 11737278.9461 | 10012387.6532 | 11616091.1884 | 13842109.7733 | 14398957.707 | 1.3295 | 1.0109 | 1.5541 | 0.54968 | 10.875 | 1.0109 | 1 | 1.3295 | 1
31/05, 2006 | 2006-04-30 17:00 | 2006-05-31 17:00 | 785117.9199 | 1023378.1408 | 1019680.8472 | 2006-06-12 12:00 | 238260.2209 | 130.3% | 3697.2936 | 100.4% | 7d 4h | 113.4% | 72.7% | 2007-10-22 12:00 | 2007-06-13 17:00 | 2007-06-12 16:00 | 2007-10-05 17:00 | 2007-06-13 17:00 | 2007-06-13 09:00 | 2007-10-19 12:00 | 2007-08-21 15:00 | 2007-08-20 14:00 | 15437168.596 | 15385080.63 | 12080526.8243 | 13734315.7123 | 12040565.8422 | 13688379.8682 | 14575112.6775 | 15021504.0312 | 1.1339 | 1.0036 | 1.3035 | 0.72697 | 7.5 | 1.0036 | 1 | 1.1339 | 1
30/06, 2006 | 2006-05-31 17:00 | 2006-06-30 17:00 | 1550157.6064 | 1708582.5041 | 1695132.3878 | 2006-07-10 16:00 | 158424.8977 | 110.2% | 13450.1164 | 100.8% | 5d 7h | 107.5% | 72.53% | 2007-10-24 14:00 | 2007-09-05 14:00 | 2007-08-31 12:00 | 2007-10-18 17:00 | 2007-09-05 14:00 | 2007-09-03 09:00 | 2007-10-23 09:00 | 2007-09-19 10:00 | 2007-09-14 15:00 | 15427415.7733 | 15319313.9934 | 14154117.2435 | 14465541.9743 | 14056038.9852 | 14365012.1522 | 15069159.2211 | 15139547.3967 | 1.0753 | 1.0079 | 1.1022 | 0.72534 | 5.875 | 1.0079 | 1 | 1.0753 | 1
31/08, 2006 | 2006-06-30 17:00 | 2006-08-31 17:00 | 2194453.376 | 2392801.591 | 2384409.6914 | 2006-09-20 16:00 | 198348.215 | 109% | 8391.8996 | 100.4% | 13d 7h | 111.4% | 86.78% | 2007-10-23 12:00 | 2007-09-11 15:00 | 2007-09-10 11:00 | 2007-10-15 17:00 | 2007-09-11 15:00 | 2007-09-10 16:00 | 2007-10-11 09:00 | 2007-08-30 14:00 | 2007-08-29 15:00 | 15432473.9901 | 15386712.5504 | 14350871.4564 | 14100058.9605 | 14308903.3525 | 14058970.4921 | 15165442.1547 | 15107258.9863 | 1.1137 | 1.0035 | 1.0904 | 0.86783 | 13.875 | 1.0035 | 1 | 1.1137 | 1
30/09, 2006 | 2006-08-31 17:00 | 2006-09-30 17:00 | 2652903.4502 | 3042114.2785 | 3022387.8755 | 2006-10-11 11:00 | 389210.8283 | 114.7% | 19726.403 | 100.7% | 7d 3h | 105.2% | 86.63% | 2007-10-16 10:00 | 2007-08-15 14:00 | 2007-08-13 10:00 | 2007-10-01 17:00 | 2007-08-15 14:00 | 2007-08-14 09:00 | 2007-10-19 14:00 | 2007-10-02 09:00 | 2007-09-28 12:00 | 15421139.4866 | 15340740.5439 | 13834832.0889 | 14813054.4118 | 13764719.459 | 14736598.5594 | 15006910.4943 | 15231458.2216 | 1.0516 | 1.0065 | 1.1467 | 0.86631 | 7.375 | 1.0065 | 1 | 1.0516 | 1
31/10, 2006 | 2006-09-30 17:00 | 2006-10-31 17:00 | 3908923.7744 | 3709426.3956 | 3738623.499 | 2006-10-26 11:00 | -199497.3789 | 94.9% | -29197.1035 | 99.22% | -3d 5h | 97.8% | 85.52% | 2007-11-07 12:00 | 2007-11-30 16:00 | 2007-12-06 11:00 | 2007-11-12 11:00 | 2007-11-30 16:00 | 2007-12-05 09:00 | 2007-11-05 14:00 | 2007-11-13 12:00 | 2007-11-15 14:00 | 15470062.9932 | 15562401.8122 | 16100993.811 | 15733588.7448 | 16198298.7219 | 15828001.7898 | 15666332.8327 | 15596247.1829 | 0.97803 | 0.99219 | 0.94896 | 0.85516 | -3.625 | 0.99219 | 1 | 0.97803 | 1
30/11, 2006 | 2006-10-31 17:00 | 2006-11-30 17:00 | 5133728.7441 | 4177440.679 | 4212580.3928 | 2006-11-07 14:00 | -956288.0651 | 81.37% | -35139.7138 | 99.17% | -17d 3h | 90.71% | 82.56% | 2007-12-06 11:00 | 2008-03-14 10:00 | 2008-03-20 14:00 | 2007-12-18 16:00 | 2008-03-14 10:00 | 2008-03-19 09:00 | 2007-11-23 11:00 | 2007-12-31 12:00 | 2008-01-02 16:00 | 15476005.6035 | 15570751.0634 | 18054397.4777 | 16629738.9154 | 18170831.804 | 16734189.3267 | 15993523.5514 | 15767847.4837 | 0.90709 | 0.99166 | 0.81372 | 0.82558 | -17.375 | 0.99166 | 1 | 0.90709 | 1
31/12, 2006 | 2006-11-30 17:00 | 2006-12-31 17:00 | 6086409.8833 | 5582046.8938 | 5643738.2872 | 2006-12-14 16:00 | -504362.9895 | 91.71% | -61691.3934 | 98.91% | -11d 1h | 94.65% | 88.39% | 2007-11-19 16:00 | 2007-12-24 11:00 | 2007-12-31 12:00 | 2007-11-23 10:00 | 2007-12-24 11:00 | 2007-12-27 10:00 | 2007-11-15 09:00 | 2007-12-03 17:00 | 2007-12-06 14:00 | 15502557.2831 | 15611514.4978 | 16393345.8265 | 16059658.801 | 16512147.8145 | 16174772.963 | 15758648.3073 | 15698031.5607 | 0.94651 | 0.98907 | 0.91713 | 0.88385 | -11.125 | 0.98907 | 1 | 0.94651 | 1
31/01, 2007 | 2006-12-31 17:00 | 2007-01-31 17:00 | 7304968.786 | 6834440.1218 | 6894675.7789 | 2007-01-19 15:00 | -470528.6642 | 93.56% | -60235.6571 | 99.13% | -8d 2h | 96.43% | 86.74% | 2007-11-16 17:00 | 2007-12-11 10:00 | 2007-12-17 10:00 | 2007-11-20 16:00 | 2007-12-11 10:00 | 2007-12-13 10:00 | 2007-11-12 10:00 | 2007-11-21 15:00 | 2007-11-23 14:00 | 15501101.5468 | 15576954.6821 | 16093625.5792 | 15819858.0567 | 16174700.9527 | 15898520.5674 | 15675592.9935 | 15624471.85 | 0.96429 | 0.99126 | 0.93559 | 0.86741 | -8.25 | 0.99126 | 1 | 0.96429 | 1
28/02, 2007 | 2007-01-31 17:00 | 2007-02-28 17:00 | 8327449.0433 | 7574280.9098 | 7665293.11 | 2007-02-08 09:00 | -753168.1335 | 90.96% | -91012.2002 | 98.81% | -14d 7h | 94.07% | 86.41% | 2007-11-28 15:00 | 2007-12-28 10:00 | 2008-01-04 16:00 | 2007-11-30 15:00 | 2007-12-28 10:00 | 2008-01-01 16:00 | 2007-11-20 16:00 | 2007-12-06 15:00 | 2007-12-11 09:00 | 15531878.0899 | 15626402.602 | 16314112.2316 | 16027443.7927 | 16418036.032 | 16127922.9988 | 15755053.8381 | 15703503.6649 | 0.94074 | 0.98813 | 0.90956 | 0.86407 | -14.875 | 0.98813 | 1 | 0.94074 | 1
31/03, 2007 | 2007-02-28 17:00 | 2007-03-31 17:00 | 10071796.819 | 9225140.7521 | 8788952.1463 | 2007-03-16 09:00 | -846656.0669 | 91.59% | 436188.6059 | 105% | -10d 7h | 96.02% | 85.34% | 2007-12-03 10:00 | 2007-12-24 17:00 | 2007-11-23 09:00 | 2007-11-30 17:00 | 2007-12-24 17:00 | 2007-12-11 17:00 | 2007-11-14 16:00 | 2007-11-23 14:00 | 2007-11-13 14:00 | 15004677.2838 | 14710781.6615 | 15575138.1081 | 15262554.2924 | 15254269.617 | 14956465.5756 | 14865577.6079 | 14813480.9008 | 0.96016 | 1.0496 | 0.91594 | 0.8534 | -10.875 | 1.0496 | 1 | 0.96016 | 1
30/04, 2007 | 2007-03-31 17:00 | 2007-04-30 17:00 | 11422569.3878 | 9959349.0364 | 9715403.245 | 2007-03-28 16:00 | -1463220.3513 | 87.19% | 243945.7914 | 102.5% | -23d 1h | 92.13% | 87.11% | 2007-12-26 10:00 | 2008-01-25 12:00 | 2008-01-09 12:00 | 2007-12-21 14:00 | 2008-01-25 12:00 | 2008-01-18 15:00 | 2007-12-03 09:00 | 2007-12-20 10:00 | 2007-12-14 09:00 | 15196920.0983 | 15062655.001 | 16002260.5865 | 15664885.3119 | 15848269.3584 | 15519157.8044 | 15227415.1307 | 15173145.8981 | 0.92134 | 1.0251 | 0.8719 | 0.87106 | -23.125 | 1.0251 | 1 | 0.92134 | 1
31/05, 2007 | 2007-04-30 17:00 | 2007-05-31 17:00 | 12782984.1784 | 11262579.3247 | 11552951.9301 | 2007-04-26 15:00 | -1520404.8537 | 88.11% | -290372.6054 | 97.49% | -25d 2h | 92.03% | 88.12% | 2007-12-27 16:00 | 2008-01-18 11:00 | 2008-02-05 15:00 | 2007-12-21 15:00 | 2008-01-18 11:00 | 2008-01-24 14:00 | 2007-12-05 10:00 | 2007-12-20 15:00 | 2007-12-26 12:00 | 15731238.4951 | 15838963.3706 | 16295291.0971 | 16092855.4128 | 16417558.4161 | 16209903.521 | 15923065.4948 | 15887444.2741 | 0.92035 | 0.97487 | 0.88106 | 0.8812 | -25.25 | 0.97487 | 1 | 0.92035 | 1
30/06, 2007 | 2007-05-31 17:00 | 2007-06-30 17:00 | 13585278.9817 | 12072241.3211 | 12407618.201 | 2007-05-15 10:00 | -1513037.6606 | 88.86% | -335376.8799 | 97.3% | -33d 6h | 90.01% | 88.74% | 2007-12-27 14:00 | 2008-01-14 10:00 | 2008-01-31 12:00 | 2007-12-21 14:00 | 2008-01-14 10:00 | 2008-01-18 09:00 | 2007-12-17 15:00 | 2008-01-04 09:00 | 2008-01-09 16:00 | 15776242.7696 | 15869825.955 | 16198439.0877 | 16149919.283 | 16303751.2371 | 16253883.5119 | 15930910.3537 | 15922439.4654 | 0.90015 | 0.97297 | 0.88863 | 0.88744 | -33.75 | 0.97297 | 1 | 0.90015 | 1
31/07, 2007 | 2007-06-30 17:00 | 2007-07-31 17:00 | 14234388.1115 | 12335087.5595 | 12724860.799 | 2007-05-21 17:00 | -1899300.5521 | 86.66% | -389773.2396 | 96.94% | -51d | 85.83% | 89.2% | 2008-01-11 10:00 | 2008-01-30 12:00 | 2008-02-20 16:00 | 2008-01-04 17:00 | 2008-01-30 12:00 | 2008-02-05 12:00 | 2008-01-09 17:00 | 2008-02-06 09:00 | 2008-02-12 11:00 | 15830639.1292 | 15928777.8149 | 16308852.7186 | 16343243.3197 | 16422102.3518 | 16457579.6525 | 15998204.0667 | 16003896.8678 | 0.85833 | 0.96937 | 0.86657 | 0.892 | -51 | 0.96937 | 1 | 0.85833 | 1
31/08, 2007 | 2007-07-31 17:00 | 2007-08-31 17:00 | 14907850.8408 | 13409942.2383 | 14001456.0536 | 2007-06-21 17:00 | -1497908.6025 | 89.95% | -591513.8154 | 95.78% | -51d | 86.68% | 92.02% | 2007-12-27 10:00 | 2008-01-04 12:00 | 2008-02-04 11:00 | 2007-12-24 12:00 | 2008-01-04 12:00 | 2008-01-10 11:00 | 2008-01-09 17:00 | 2008-01-30 10:00 | 2008-02-05 17:00 | 16032379.7051 | 16121963.9387 | 16259236.6113 | 16344358.9407 | 16358827.5244 | 16447704.6077 | 16148066.6502 | 16162999.9162 | 0.86684 | 0.95775 | 0.89952 | 0.92022 | -51 | 0.95775 | 1 | 0.86684 | 1
30/09, 2007 | 2007-08-31 17:00 | 2007-09-30 17:00 | 15335575.8859 | 14397407.2272 | 14936088.7014 | 2007-08-08 14:00 | -938168.6587 | 93.88% | -538681.4742 | 96.39% | -37d 3h | 90.73% | 94.96% | 2007-12-05 16:00 | 2007-12-07 15:00 | 2008-01-01 14:00 | 2007-12-04 14:00 | 2007-12-07 15:00 | 2007-12-11 12:00 | 2007-12-21 11:00 | 2007-12-31 12:00 | 2008-01-02 16:00 | 15979547.3638 | 16018588.5496 | 16047541.5657 | 16086212.0271 | 16089126.7663 | 16129244.0897 | 16024257.8461 | 16031469.509 | 0.90726 | 0.96393 | 0.93882 | 0.94957 | -37.375 | 0.96393 | 1 | 0.90726 | 1
31/10, 2007 | 2007-09-30 17:00 | 2007-10-31 17:00 | 15440865.8897 | 15440865.8897 | 16338027.1975 | 2007-10-30 17:00 | 0 | 100% | -897161.3078 | 94.51% | -1d | 99.77% | 100% | 2007-10-30 17:00 | 2007-10-30 17:00 | 2007-12-04 15:00 | 2007-10-31 17:00 | 2007-10-31 17:00 | 2007-10-31 17:00 | 2007-10-31 17:00 | 2007-10-31 17:00 | 2007-10-31 17:00 | 16338027.1975 | 16338027.1975 | 16338027.1975 | 16338027.1975 | 16338027.1975 | 16338027.1975 | 16338027.1975 | 16338027.1975 | 0.99765 | 0.94509 | 1 | 1 | -1 | 0.94509 | 1 | 0.99765 | 1