## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PET Packaging | 1 |  |  | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 | 728.375
6 | WP1 | 1.1 |  |  | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 | 304.375
1 | 1.1 | 1.1.1 |  | FS2 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 59.375
2 | 1.2 | 1.1.2 | 1FS | FS3 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 59.375
3 | 1.3 | 1.1.3 | 2FS | FS4 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 61.375
4 | 1.4 | 1.1.4 | 3FS | FS5 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 60.375
5 | 1.5 | 1.1.5 | 4FS |  | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 59.375
11 | WP2 | 1.2 |  |  | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 | 576.3333
7 | 2.1 | 1.2.1 |  | FS9 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 301.375
8 | 2.2 | 1.2.2 |  | FS9 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 182.375
9 | 2.3 | 1.2.3 | 7FS;8FS | FS10 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 62
10 | 2.4 | 1.2.4 | 9FS |  | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 | 92
16 | WP3 | 1.3 |  |  | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 | 178.375
12 | 3.1 | 1.3.1 |  | FS13;FS14;FS15 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 56.375
13 | 3.2 | 1.3.2 | 12FS |  | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 121.375
14 | 3.3 | 1.3.3 | 12FS |  | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 90.375
15 | 3.4 | 1.3.4 | 12FS |  | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 90.375
20 | WP4 | 1.4 |  |  | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 | 395.375
17 | 4.1 | 1.4.1 |  | FS18;FS19 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 119.375
18 | 4.2 | 1.4.2 | 17FS |  | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 89.375
19 | 4.3 | 1.4.3 | 17FS |  | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 89.375
24 | WP5 | 1.5 |  |  | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 | 518.375
21 | 5.1 | 1.5.1 |  | FS22;FS23 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 243.375
22 | 5.2 | 1.5.2 | 21FS |  | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 88.375
23 | 5.3 | 1.5.3 | 21FS |  | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 88.375
31 | WP6 | 1.6 |  |  | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 | 305.375
25 | 6.1 | 1.6.1 |  |  | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 305.375
26 | 6.2 | 1.6.2 |  |  | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 213.375
27 | 6.3 | 1.6.3 |  |  | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 244.375
28 | 6.4 | 1.6.4 |  |  | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 244.375
29 | 6.5A | 1.6.5 |  |  | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 91.375
35 | 6.5B | 1.6.6 |  |  | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 | 28.375
30 | 6.6 | 1.6.7 |  |  | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 122.375
34 | WP7 | 1.7 |  |  | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 | 671.375
32 | 7.1 | 1.7.1 |  |  | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 671.375
33 | 7.2 | 1.7.2 |  |  | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 671.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | PET Packaging | 4168h |  |  |  |  | 99 | 100 | 101
6 | WP1 | 1752h |  |  |  |  | 99 | 100 | 101
1 | 1.1 | 352h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | 1.2 | 352h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | 1.3 | 352h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | 1.4 | 344h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | 1.5 | 352h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | WP2 | 3303h |  |  |  |  | 99 | 100 | 101
7 | 2.1 | 1728h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | 2.2 | 1048h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | 2.3 | 352h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | 2.4 | 528h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | WP3 | 1032h |  |  |  |  | 99 | 100 | 101
12 | 3.1 | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | 3.2 | 704h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | 3.3 | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | 3.4 | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | WP4 | 2256h |  |  |  |  | 99 | 100 | 101
17 | 4.1 | 688h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | 4.2 | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | 4.3 | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | WP5 | 2968h |  |  |  |  | 99 | 100 | 101
21 | 5.1 | 1392h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | 5.2 | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | 5.3 | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | WP6 | 1744h |  |  |  |  | 99 | 100 | 101
25 | 6.1 | 1744h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | 6.2 | 1216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | 6.3 | 1400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | 6.4 | 1400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | 6.5A | 528h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | 6.5B | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | 6.6 | 712h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | WP7 | 3840h |  |  |  |  | 99 | 100 | 101
32 | 7.1 | 3840h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | 7.2 | 3840h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-01-31 17:00 |  | TP Name | 31/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 98025.9473
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 76711.5
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 |  | 0 | 0 | 76711.5 | 216d | 0 | 0 | 0 | 76711.5 | 0% | Not Started | 0 | 76711.5 | 100 |  | 0 | 100 |  | 0
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 21314.4473
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 |  | 0 | 0 | 21314.4473 | 41d | 0 | 0 | 0 | 21314.4473 | 0% | Not Started | 0 | 21314.4473 | 100 |  | 0 | 100 |  | 0
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 |  | 0 | 0 | 22200.1543 | 480d | 0 | 0 | 0 | 22200.1543 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 |  | 0 | 0 | 22200.1543 | 480d | 0 | 0 | 0 | 22200.1543 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-02-28 17:00 |  | TP Name | 28/02, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 98025.9473
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 76711.5
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 |  | 0 | 0 | 76711.5 | 216d | 0 | 0 | 0 | 76711.5 | 0% | Not Started | 0 | 76711.5 | 100 |  | 0 | 100 |  | 0
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 21314.4473
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 |  | 0 | 0 | 21314.4473 | 41d | 0 | 0 | 0 | 21314.4473 | 0% | Not Started | 0 | 21314.4473 | 100 |  | 0 | 100 |  | 0
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 |  | 0 | 0 | 22200.1543 | 480d | 0 | 0 | 0 | 22200.1543 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 |  | 0 | 0 | 22200.1543 | 480d | 0 | 0 | 0 | 22200.1543 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-03-31 17:00 |  | TP Name | 31/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 23d | [5 empty] | 126782.5952 |  | 14.5% |  | 126782.5952 | 190725.937
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 23d | [5 empty] | 5670.7866 |  | 20% |  | 5670.7866 | 5670.7866
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 23d | 5670.7866 | 0 | 21d | 0 | 0 | 5670.7866 | 0 | 52.27% | Started | 5670.7866 | 5670.7866 | 100 | 52.2727 | 52.2727 | 100 | 100 | 52.2727
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 23d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 76711.5
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 23d | 76711.5 | 0 | 239d | 0 | 0 | 76711.5 | 0 | 8.779% | Started | 76711.5 | 76711.5 | 100 | 10.6481 | 8.7786 | 100 | 100 | 8.7786
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 63943.3418
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 |  | 0 | 0 | 21314.4473 | 41d | 0 | 0 | 0 | 21314.4473 | 0% | Not Started | 0 | 21314.4473 | 100 |  | 0 | 100 |  | 0
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 42628.8945 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 23d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 23d | 22200.1543 | 0 | 500d | 0 | 0 | 22200.1543 | 0 | 4.398% | Started | 22200.1543 | 22200.1543 | 100 | 4.7917 | 4.3977 | 100 | 100 | 4.3977
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 23d | 22200.1543 | 0 | 500d | 0 | 0 | 22200.1543 | 0 | 4.398% | Started | 22200.1543 | 22200.1543 | 100 | 4.7917 | 4.3977 | 100 | 100 | 4.3977

## TP4
| TP Status Date | 2011-04-30 17:00 |  | TP Name | 30/04, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 44d | [5 empty] | 148097.0425 |  | 16.93% |  | 148097.0425 | 306548.4917
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 44d | [5 empty] | 5670.7866 |  | 20% |  | 5670.7866 | 5670.7866
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 44d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 76711.5
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 44d | 76711.5 | 0 | 218d | 0 | 0 | 76711.5 | 0 | 16.79% | Started | 76711.5 | 76711.5 | 100 | 20.3704 | 16.7939 | 100 | 100 | 16.7939
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 21d | [5 empty] | 21314.4473 |  | 16.67% |  | 21314.4473 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 21d | 21314.4473 | 0 | 22d | 0 | 0 | 21314.4473 | 0 | 48.84% | Started | 21314.4473 | 21314.4473 | 100 | 51.2195 | 48.8372 | 100 | 100 | 48.8372
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 42628.8945 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 51879.2148 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 44d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 44d | 22200.1543 | 0 | 479d | 0 | 0 | 22200.1543 | 0 | 8.413% | Started | 22200.1543 | 22200.1543 | 100 | 9.1667 | 8.413 | 100 | 100 | 8.413
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 44d | 22200.1543 | 0 | 479d | 0 | 0 | 22200.1543 | 0 | 8.413% | Started | 22200.1543 | 22200.1543 | 100 | 9.1667 | 8.413 | 100 | 100 | 8.413

## TP5
| TP Status Date | 2011-05-31 17:00 |  | TP Name | 31/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 66d | [5 empty] | 153767.8291 |  | 17.58% |  | 153767.8291 | 358246.1807
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 66d | [5 empty] | 11341.5732 |  | 40% |  | 11341.5732 | 11341.5732
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 22d | 5670.7866 | 0 | 22d | 0 | 0 | 5670.7866 | 0 | 50% | Started | 5670.7866 | 5670.7866 | 100 | 50 | 50 | 100 | 100 | 50
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 66d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 122738.4023
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 66d | 76711.5 | 0 | 196d | 0 | 0 | 76711.5 | 0 | 25.19% | Started | 76711.5 | 76711.5 | 100 | 30.5556 | 25.1908 | 100 | 100 | 25.1908
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 43d | [5 empty] | 21314.4473 |  | 16.67% |  | 21314.4473 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 42628.8945 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 51879.2148 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 66d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 66d | 22200.1543 | 0 | 457d | 0 | 0 | 22200.1543 | 0 | 12.62% | Started | 22200.1543 | 22200.1543 | 100 | 13.75 | 12.6195 | 100 | 100 | 12.6195
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 66d | 22200.1543 | 0 | 457d | 0 | 0 | 22200.1543 | 0 | 12.62% | Started | 22200.1543 | 22200.1543 | 100 | 13.75 | 12.6195 | 100 | 100 | 12.6195

## TP6
| TP Status Date | 2011-06-30 17:00 |  | TP Name | 30/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 88d | [5 empty] | 153767.8291 |  | 17.58% |  | 153767.8291 | 358246.1807
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 88d | [5 empty] | 11341.5732 |  | 40% |  | 11341.5732 | 11341.5732
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 88d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 122738.4023
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 88d | 76711.5 | 0 | 174d | 0 | 0 | 76711.5 | 0 | 33.59% | Started | 76711.5 | 76711.5 | 100 | 40.7407 | 33.5878 | 100 | 100 | 33.5878
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 65d | [5 empty] | 21314.4473 |  | 16.67% |  | 21314.4473 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 42628.8945 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 51879.2148 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 88d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 88d | 22200.1543 | 0 | 435d | 0 | 0 | 22200.1543 | 0 | 16.83% | Started | 22200.1543 | 22200.1543 | 100 | 18.3333 | 16.826 | 100 | 100 | 16.826
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 88d | 22200.1543 | 0 | 435d | 0 | 0 | 22200.1543 | 0 | 16.83% | Started | 22200.1543 | 22200.1543 | 100 | 18.3333 | 16.826 | 100 | 100 | 16.826

## TP7
| TP Status Date | 2011-07-31 17:00 |  | TP Name | 31/07, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 109d | [5 empty] | 159438.6157 |  | 18.23% |  | 159438.6157 | 488485.6938
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 109d | [5 empty] | 17012.3599 |  | 60% |  | 17012.3599 | 17012.3599
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 21d | 5670.7866 | 0 | 23d | 0 | 0 | 5670.7866 | 0 | 47.73% | Started | 5670.7866 | 5670.7866 | 100 | 47.7273 | 47.7273 | 100 | 100 | 47.7273
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 109d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 122738.4023
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 109d | 76711.5 | 0 | 153d | 0 | 0 | 76711.5 | 0 | 41.6% | Started | 76711.5 | 76711.5 | 100 | 50.463 | 41.6031 | 100 | 100 | 41.6031
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 86d | [5 empty] | 21314.4473 |  | 16.67% |  | 21314.4473 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 42628.8945 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 51879.2148 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 124568.7266 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 109d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 109d | 22200.1543 | 0 | 414d | 0 | 0 | 22200.1543 | 0 | 20.84% | Started | 22200.1543 | 22200.1543 | 100 | 22.7083 | 20.8413 | 100 | 100 | 20.8413
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 109d | 22200.1543 | 0 | 414d | 0 | 0 | 22200.1543 | 0 | 20.84% | Started | 22200.1543 | 22200.1543 | 100 | 22.7083 | 20.8413 | 100 | 100 | 20.8413

## TP8
| TP Status Date | 2011-08-31 17:00 |  | TP Name | 31/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 132d | [5 empty] | 159438.6157 |  | 18.23% |  | 159438.6157 | 488485.6938
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 132d | [5 empty] | 17012.3599 |  | 60% |  | 17012.3599 | 17012.3599
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 43d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 132d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 122738.4023
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 132d | 76711.5 | 0 | 130d | 0 | 0 | 76711.5 | 0 | 50.38% | Started | 76711.5 | 76711.5 | 100 | 61.1111 | 50.3817 | 100 | 100 | 50.3817
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 109d | [5 empty] | 21314.4473 |  | 16.67% |  | 21314.4473 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 |  | 0 | 0 | 42628.8945 | 88d | 0 | 0 | 0 | 42628.8945 | 0% | Not Started | 0 | 42628.8945 | 100 |  | 0 | 100 |  | 0
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 |  | 0 | 0 | 51879.2148 | 86d | 0 | 0 | 0 | 51879.2148 | 0% | Not Started | 0 | 51879.2148 | 100 |  | 0 | 100 |  | 0
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 124568.7266 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 132d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 132d | 22200.1543 | 0 | 391d | 0 | 0 | 22200.1543 | 0 | 25.24% | Started | 22200.1543 | 22200.1543 | 100 | 27.5 | 25.239 | 100 | 100 | 25.239
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 132d | 22200.1543 | 0 | 391d | 0 | 0 | 22200.1543 | 0 | 25.24% | Started | 22200.1543 | 22200.1543 | 100 | 27.5 | 25.239 | 100 | 100 | 25.239

## TP9
| TP Status Date | 2011-09-30 17:00 |  | TP Name | 30/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 154d | [5 empty] | 259617.5117 |  | 29.69% |  | 259617.5117 | 494156.4805
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 154d | [5 empty] | 22683.1465 |  | 80% |  | 22683.1465 | 22683.1465
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 22d | 5670.7866 | 0 | 21d | 0 | 0 | 5670.7866 | 0 | 51.16% | Started | 5670.7866 | 5670.7866 | 100 | 51.1628 | 51.1628 | 100 | 100 | 51.1628
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 154d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 122738.4023
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 154d | 76711.5 | 0 | 108d | 0 | 0 | 76711.5 | 0 | 58.78% | Started | 76711.5 | 76711.5 | 100 | 71.2963 | 58.7786 | 100 | 100 | 58.7786
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 131d | [5 empty] | 63943.3418 |  | 50% |  | 63943.3418 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 22d | 42628.8945 | 0 | 65d | 0 | 0 | 42628.8945 | 0 | 25.29% | Started | 42628.8945 | 42628.8945 | 100 | 25 | 25.2874 | 100 | 100 | 25.2874
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 22d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 22d | 51879.2148 | 0 | 65d | 0 | 0 | 51879.2148 | 0 | 25.29% | Started | 51879.2148 | 51879.2148 | 100 | 25.5814 | 25.2874 | 100 | 100 | 25.2874
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 |  | 0 | 0 | 124568.7266 | 174d | 0 | 0 | 0 | 124568.7266 | 0% | Not Started | 0 | 124568.7266 | 100 |  | 0 | 100 |  | 0
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 154d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 154d | 22200.1543 | 0 | 369d | 0 | 0 | 22200.1543 | 0 | 29.45% | Started | 22200.1543 | 22200.1543 | 100 | 32.0833 | 29.4455 | 100 | 100 | 29.4455
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 154d | 22200.1543 | 0 | 369d | 0 | 0 | 22200.1543 | 0 | 29.45% | Started | 22200.1543 | 22200.1543 | 100 | 32.0833 | 29.4455 | 100 | 100 | 29.4455

## TP10
| TP Status Date | 2011-10-31 17:00 |  | TP Name | 31/10, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 175d | [5 empty] | 384186.2383 |  | 43.93% |  | 384186.2383 | 494156.4805
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 175d | [5 empty] | 22683.1465 |  | 80% |  | 22683.1465 | 22683.1465
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 |  | 0 | 0 | 5670.7866 | 44d | 0 | 0 | 0 | 5670.7866 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 175d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 122738.4023
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 175d | 76711.5 | 0 | 87d | 0 | 0 | 76711.5 | 0 | 66.79% | Started | 76711.5 | 76711.5 | 100 | 81.0185 | 66.7939 | 100 | 100 | 66.7939
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 152d | [5 empty] | 63943.3418 |  | 50% |  | 63943.3418 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 43d | 42628.8945 | 0 | 44d | 0 | 0 | 42628.8945 | 0 | 49.43% | Started | 42628.8945 | 42628.8945 | 100 | 48.8636 | 49.4253 | 100 | 100 | 49.4253
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 43d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 43d | 51879.2148 | 0 | 44d | 0 | 0 | 51879.2148 | 0 | 49.43% | Started | 51879.2148 | 51879.2148 | 100 | 50 | 49.4253 | 100 | 100 | 49.4253
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 21d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 21d | 124568.7266 | 0 | 262d | 0 | 0 | 124568.7266 | 0 | 7.42% | Started | 124568.7266 | 124568.7266 | 100 | 12.069 | 7.4205 | 100 | 100 | 7.4205
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 175d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 175d | 22200.1543 | 0 | 348d | 0 | 0 | 22200.1543 | 0 | 33.46% | Started | 22200.1543 | 22200.1543 | 100 | 36.4583 | 33.4608 | 100 | 100 | 33.4608
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 175d | 22200.1543 | 0 | 348d | 0 | 0 | 22200.1543 | 0 | 33.46% | Started | 22200.1543 | 22200.1543 | 100 | 36.4583 | 33.4608 | 100 | 100 | 33.4608

## TP11
| TP Status Date | 2011-11-30 17:00 |  | TP Name | 30/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 197d | [5 empty] | 421828.6948 |  | 48.23% |  | 421828.6948 | 515169.5669
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 197d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 22d | 5670.7866 | 0 | 22d | 0 | 0 | 5670.7866 | 0 | 50% | Started | 5670.7866 | 5670.7866 | 100 | 50 | 50 | 100 | 100 | 50
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 197d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 138080.7021
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 197d | 76711.5 | 0 | 65d | 0 | 0 | 76711.5 | 0 | 75.19% | Started | 76711.5 | 76711.5 | 100 | 91.2037 | 75.1908 | 100 | 100 | 75.1908
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 174d | [5 empty] | 95915.0117 |  | 75% |  | 95915.0117 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 65d | 42628.8945 | 0 | 22d | 0 | 0 | 42628.8945 | 0 | 74.71% | Started | 42628.8945 | 42628.8945 | 100 | 73.8636 | 74.7126 | 100 | 100 | 74.7126
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 22d | 31971.6699 | 0 | 65d | 0 | 0 | 31971.6699 | 0 | 25.29% | Started | 31971.6699 | 31971.6699 | 100 | 33.8462 | 25.2874 | 100 | 100 | 25.2874
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 65d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 65d | 51879.2148 | 0 | 22d | 0 | 0 | 51879.2148 | 0 | 74.71% | Started | 51879.2148 | 51879.2148 | 100 | 75.5814 | 74.7126 | 100 | 100 | 74.7126
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 43d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 43d | 124568.7266 | 0 | 240d | 0 | 0 | 124568.7266 | 0 | 15.19% | Started | 124568.7266 | 124568.7266 | 100 | 24.7126 | 15.1943 | 100 | 100 | 15.1943
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 197d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 197d | 22200.1543 | 0 | 326d | 0 | 0 | 22200.1543 | 0 | 37.67% | Started | 22200.1543 | 22200.1543 | 100 | 41.0417 | 37.6673 | 100 | 100 | 37.6673
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 197d | 22200.1543 | 0 | 326d | 0 | 0 | 22200.1543 | 0 | 37.67% | Started | 22200.1543 | 22200.1543 | 100 | 41.0417 | 37.6673 | 100 | 100 | 37.6673

## TP12
| TP Status Date | 2011-12-31 17:00 |  | TP Name | 31/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 219d | [5 empty] | 421828.6948 |  | 48.23% |  | 421828.6948 | 515169.5669
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 219d | [5 empty] | 76711.5 |  | 47.62% |  | 76711.5 | 138080.7021
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 219d | 76711.5 | 0 | 43d | 0 | 0 | 76711.5 | 0 | 83.59% | Started | 76711.5 | 76711.5 | 100 | 101.3889 | 83.5878 | 100 | 100 | 83.5878
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 |  | 0 | 0 | 46026.9023 | 131d | 0 | 0 | 0 | 46026.9023 | 0% | Not Started | 0 | 46026.9023 | 100 |  | 0 | 100 |  | 0
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 196d | [5 empty] | 95915.0117 |  | 75% |  | 95915.0117 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 44d | 31971.6699 | 0 | 43d | 0 | 0 | 31971.6699 | 0 | 50.57% | Started | 31971.6699 | 31971.6699 | 100 | 67.6923 | 50.5747 | 100 | 100 | 50.5747
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 87d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 65d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 65d | 124568.7266 | 0 | 218d | 0 | 0 | 124568.7266 | 0 | 22.97% | Started | 124568.7266 | 124568.7266 | 100 | 37.3563 | 22.9682 | 100 | 100 | 22.9682
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 219d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 219d | 22200.1543 | 0 | 304d | 0 | 0 | 22200.1543 | 0 | 41.87% | Started | 22200.1543 | 22200.1543 | 100 | 45.625 | 41.8738 | 100 | 100 | 41.8738
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 219d | 22200.1543 | 0 | 304d | 0 | 0 | 22200.1543 | 0 | 41.87% | Started | 22200.1543 | 22200.1543 | 100 | 45.625 | 41.8738 | 100 | 100 | 41.8738

## TP13
| TP Status Date | 2012-01-31 17:00 |  | TP Name | 31/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 241d | [5 empty] | 467855.5972 |  | 53.5% |  | 467855.5972 | 515169.5669
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 241d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 138080.7021
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 241d | 76711.5 | 0 | 21d | 0 | 0 | 76711.5 | 0 | 91.98% | Started | 76711.5 | 76711.5 | 100 | 111.5741 | 91.9847 | 100 | 100 | 91.9847
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 22d | 46026.9023 | 0 | 196d | 0 | 0 | 46026.9023 | 0 | 10.09% | Started | 46026.9023 | 46026.9023 | 100 | 16.7939 | 10.0917 | 100 | 100 | 10.0917
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 218d | [5 empty] | 95915.0117 |  | 75% |  | 95915.0117 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 66d | 31971.6699 | 0 | 21d | 0 | 0 | 31971.6699 | 0 | 75.86% | Started | 31971.6699 | 31971.6699 | 100 | 101.5385 | 75.8621 | 100 | 100 | 75.8621
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 109d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 51879.2148
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 87d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 87d | 124568.7266 | 0 | 196d | 0 | 0 | 124568.7266 | 0 | 30.74% | Started | 124568.7266 | 124568.7266 | 100 | 50 | 30.742 | 100 | 100 | 30.742
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 241d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 241d | 22200.1543 | 0 | 282d | 0 | 0 | 22200.1543 | 0 | 46.08% | Started | 22200.1543 | 22200.1543 | 100 | 50.2083 | 46.0803 | 100 | 100 | 46.0803
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 241d | 22200.1543 | 0 | 282d | 0 | 0 | 22200.1543 | 0 | 46.08% | Started | 22200.1543 | 22200.1543 | 100 | 50.2083 | 46.0803 | 100 | 100 | 46.0803

## TP14
| TP Status Date | 2012-02-29 17:00 |  | TP Name | 29/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 262d | [5 empty] | 467855.5972 |  | 53.5% |  | 467855.5972 | 592988.3872
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 262d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 138080.7021
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 43d | 46026.9023 | 0 | 175d | 0 | 0 | 46026.9023 | 0 | 19.72% | Started | 46026.9023 | 46026.9023 | 100 | 32.8244 | 19.7248 | 100 | 100 | 19.7248
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 239d | [5 empty] | 95915.0117 |  | 75% |  | 95915.0117 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 |  | 0 | 0 | 31971.6699 | 65d | 0 | 0 | 0 | 31971.6699 | 0% | Not Started | 0 | 31971.6699 | 100 |  | 0 | 100 |  | 0
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 130d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 108d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 108d | 124568.7266 | 0 | 175d | 0 | 0 | 124568.7266 | 0 | 38.16% | Started | 124568.7266 | 124568.7266 | 100 | 62.069 | 38.1625 | 100 | 100 | 38.1625
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 262d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 262d | 22200.1543 | 0 | 261d | 0 | 0 | 22200.1543 | 0 | 50.1% | Started | 22200.1543 | 22200.1543 | 100 | 54.5833 | 50.0956 | 100 | 100 | 50.0956
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 262d | 22200.1543 | 0 | 261d | 0 | 0 | 22200.1543 | 0 | 50.1% | Started | 22200.1543 | 22200.1543 | 100 | 54.5833 | 50.0956 | 100 | 100 | 50.0956

## TP15
| TP Status Date | 2012-03-31 17:00 |  | TP Name | 31/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 284d | [5 empty] | 499827.2671 |  | 57.15% |  | 499827.2671 | 633262.9966
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 284d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 138080.7021
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 65d | 46026.9023 | 0 | 153d | 0 | 0 | 46026.9023 | 0 | 29.82% | Started | 46026.9023 | 46026.9023 | 100 | 49.6183 | 29.8165 | 100 | 100 | 29.8165
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 261d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 22d | 31971.6699 | 0 | 21d | 0 | 0 | 31971.6699 | 0 | 51.16% | Started | 31971.6699 | 31971.6699 | 100 | 33.8462 | 51.1628 | 100 | 100 | 51.1628
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 152d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 130d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 130d | 124568.7266 | 0 | 153d | 0 | 0 | 124568.7266 | 0 | 45.94% | Started | 124568.7266 | 124568.7266 | 100 | 74.7126 | 45.9364 | 100 | 100 | 45.9364
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 40274.6094
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 284d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 284d | 22200.1543 | 0 | 239d | 0 | 0 | 22200.1543 | 0 | 54.3% | Started | 22200.1543 | 22200.1543 | 100 | 59.1667 | 54.3021 | 100 | 100 | 54.3021
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 284d | 22200.1543 | 0 | 239d | 0 | 0 | 22200.1543 | 0 | 54.3% | Started | 22200.1543 | 22200.1543 | 100 | 59.1667 | 54.3021 | 100 | 100 | 54.3021

## TP16
| TP Status Date | 2012-04-30 17:00 |  | TP Name | 30/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 305d | [5 empty] | 499827.2671 |  | 57.15% |  | 499827.2671 | 633262.9966
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 305d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 138080.7021
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 86d | 46026.9023 | 0 | 132d | 0 | 0 | 46026.9023 | 0 | 39.45% | Started | 46026.9023 | 46026.9023 | 100 | 65.6489 | 39.4495 | 100 | 100 | 39.4495
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 173d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 151d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 151d | 124568.7266 | 0 | 132d | 0 | 0 | 124568.7266 | 0 | 53.36% | Started | 124568.7266 | 124568.7266 | 100 | 86.7816 | 53.3569 | 100 | 100 | 53.3569
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 40274.6094
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 305d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 305d | 22200.1543 | 0 | 218d | 0 | 0 | 22200.1543 | 0 | 58.32% | Started | 22200.1543 | 22200.1543 | 100 | 63.5417 | 58.3174 | 100 | 100 | 58.3174
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 305d | 22200.1543 | 0 | 218d | 0 | 0 | 22200.1543 | 0 | 58.32% | Started | 22200.1543 | 22200.1543 | 100 | 63.5417 | 58.3174 | 100 | 100 | 58.3174

## TP17
| TP Status Date | 2012-05-31 17:00 |  | TP Name | 31/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 328d | [5 empty] | 499827.2671 |  | 57.15% |  | 499827.2671 | 748908.0493
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 328d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 109d | 46026.9023 | 0 | 109d | 0 | 0 | 46026.9023 | 0 | 50% | Started | 46026.9023 | 46026.9023 | 100 | 83.2061 | 50 | 100 | 100 | 50
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 196d | [5 empty] | 51879.2148 |  | 40% |  | 51879.2148 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 |  | 0 | 0 | 38909.4102 | 64d | 0 | 0 | 0 | 38909.4102 | 0% | Not Started | 0 | 38909.4102 | 100 |  | 0 | 100 |  | 0
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 174d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 174d | 124568.7266 | 0 | 109d | 0 | 0 | 124568.7266 | 0 | 61.48% | Started | 124568.7266 | 124568.7266 | 100 | 100 | 61.4841 | 100 | 100 | 61.4841
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 132906.2109
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 328d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 328d | 22200.1543 | 0 | 195d | 0 | 0 | 22200.1543 | 0 | 62.72% | Started | 22200.1543 | 22200.1543 | 100 | 68.3333 | 62.7151 | 100 | 100 | 62.7151
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 328d | 22200.1543 | 0 | 195d | 0 | 0 | 22200.1543 | 0 | 62.72% | Started | 22200.1543 | 22200.1543 | 100 | 68.3333 | 62.7151 | 100 | 100 | 62.7151

## TP18
| TP Status Date | 2012-06-30 17:00 |  | TP Name | 30/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 349d | [5 empty] | 577646.0874 |  | 66.05% |  | 577646.0874 | 777100.2759
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 349d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 130d | 46026.9023 | 0 | 88d | 0 | 0 | 46026.9023 | 0 | 59.63% | Started | 46026.9023 | 46026.9023 | 100 | 99.2366 | 59.633 | 100 | 100 | 59.633
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 217d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 21d | 38909.4102 | 0 | 45d | 0 | 0 | 38909.4102 | 0 | 31.82% | Started | 38909.4102 | 38909.4102 | 100 | 32.8125 | 31.8182 | 100 | 100 | 31.8182
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 21d | 38909.4102 | 0 | 45d | 0 | 0 | 38909.4102 | 0 | 31.82% | Started | 38909.4102 | 38909.4102 | 100 | 32.8125 | 31.8182 | 100 | 100 | 31.8182
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 195d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 195d | 124568.7266 | 0 | 88d | 0 | 0 | 124568.7266 | 0 | 68.9% | Started | 124568.7266 | 124568.7266 | 100 | 112.069 | 68.9046 | 100 | 100 | 68.9046
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 161098.4375
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 349d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 349d | 22200.1543 | 0 | 174d | 0 | 0 | 22200.1543 | 0 | 66.73% | Started | 22200.1543 | 22200.1543 | 100 | 72.7083 | 66.7304 | 100 | 100 | 66.7304
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 349d | 22200.1543 | 0 | 174d | 0 | 0 | 22200.1543 | 0 | 66.73% | Started | 22200.1543 | 22200.1543 | 100 | 72.7083 | 66.7304 | 100 | 100 | 66.7304

## TP19
| TP Status Date | 2012-07-31 17:00 |  | TP Name | 31/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 371d | [5 empty] | 577646.0874 |  | 66.05% |  | 577646.0874 | 777100.2759
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 371d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 152d | 46026.9023 | 0 | 66d | 0 | 0 | 46026.9023 | 0 | 69.72% | Started | 46026.9023 | 46026.9023 | 100 | 116.0305 | 69.7248 | 100 | 100 | 69.7248
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 239d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 43d | 38909.4102 | 0 | 23d | 0 | 0 | 38909.4102 | 0 | 65.15% | Started | 38909.4102 | 38909.4102 | 100 | 67.1875 | 65.1515 | 100 | 100 | 65.1515
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 43d | 38909.4102 | 0 | 23d | 0 | 0 | 38909.4102 | 0 | 65.15% | Started | 38909.4102 | 38909.4102 | 100 | 67.1875 | 65.1515 | 100 | 100 | 65.1515
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 217d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 217d | 124568.7266 | 0 | 66d | 0 | 0 | 124568.7266 | 0 | 76.68% | Started | 124568.7266 | 124568.7266 | 100 | 124.7126 | 76.6784 | 100 | 100 | 76.6784
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 161098.4375
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 371d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 371d | 22200.1543 | 0 | 152d | 0 | 0 | 22200.1543 | 0 | 70.94% | Started | 22200.1543 | 22200.1543 | 100 | 77.2917 | 70.9369 | 100 | 100 | 70.9369
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 371d | 22200.1543 | 0 | 152d | 0 | 0 | 22200.1543 | 0 | 70.94% | Started | 22200.1543 | 22200.1543 | 100 | 77.2917 | 70.9369 | 100 | 100 | 70.9369

## TP20
| TP Status Date | 2012-08-31 17:00 |  | TP Name | 31/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 394d | [5 empty] | 577646.0874 |  | 66.05% |  | 577646.0874 | 777100.2759
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 394d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 175d | 46026.9023 | 0 | 43d | 0 | 0 | 46026.9023 | 0 | 80.28% | Started | 46026.9023 | 46026.9023 | 100 | 133.5878 | 80.2752 | 100 | 100 | 80.2752
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 240d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 124568.7266
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 240d | 124568.7266 | 0 | 43d | 0 | 0 | 124568.7266 | 0 | 84.81% | Started | 124568.7266 | 124568.7266 | 100 | 137.931 | 84.8057 | 100 | 100 | 84.8057
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 161098.4375
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 394d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 394d | 22200.1543 | 0 | 129d | 0 | 0 | 22200.1543 | 0 | 75.33% | Started | 22200.1543 | 22200.1543 | 100 | 82.0833 | 75.3346 | 100 | 100 | 75.3346
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 394d | 22200.1543 | 0 | 129d | 0 | 0 | 22200.1543 | 0 | 75.33% | Started | 22200.1543 | 22200.1543 | 100 | 82.0833 | 75.3346 | 100 | 100 | 75.3346

## TP21
| TP Status Date | 2012-09-30 17:00 |  | TP Name | 30/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 414d | [5 empty] | 577646.0874 |  | 66.05% |  | 577646.0874 | 870526.8228
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 414d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 195d | 46026.9023 | 0 | 23d | 0 | 0 | 46026.9023 | 0 | 89.45% | Started | 46026.9023 | 46026.9023 | 100 | 148.855 | 89.4495 | 100 | 100 | 89.4495
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 260d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 260d | 124568.7266 | 0 | 23d | 0 | 0 | 124568.7266 | 0 | 91.87% | Started | 124568.7266 | 124568.7266 | 100 | 149.4253 | 91.8728 | 100 | 100 | 91.8728
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 161098.4375
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 |  | 0 | 0 | 40274.6094 | 218d | 0 | 0 | 0 | 40274.6094 | 0% | Not Started | 0 | 40274.6094 | 100 |  | 0 | 100 |  | 0
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 414d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 414d | 22200.1543 | 0 | 109d | 0 | 0 | 22200.1543 | 0 | 79.16% | Started | 22200.1543 | 22200.1543 | 100 | 86.25 | 79.1587 | 100 | 100 | 79.1587
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 414d | 22200.1543 | 0 | 109d | 0 | 0 | 22200.1543 | 0 | 79.16% | Started | 22200.1543 | 22200.1543 | 100 | 86.25 | 79.1587 | 100 | 100 | 79.1587

## TP22
| TP Status Date | 2012-10-31 17:00 |  | TP Name | 31/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 437d | [5 empty] | 617920.6968 |  | 70.66% |  | 617920.6968 | 870526.8228
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 437d | [5 empty] | 122738.4023 |  | 76.19% |  | 122738.4023 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 |  | 0 | 0 | 15342.2998 | 44d | 0 | 0 | 0 | 15342.2998 | 0% | Not Started | 0 | 15342.2998 | 100 |  | 0 | 100 |  | 0
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 283d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 23d | [5 empty] | 40274.6094 |  | 24.39% |  | 40274.6094 | 161098.4375
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 23d | 40274.6094 | 0 | 195d | 0 | 0 | 40274.6094 | 0 | 10.55% | Started | 40274.6094 | 40274.6094 | 100 | 10.5505 | 10.5505 | 100 | 100 | 10.5505
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 437d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 437d | 22200.1543 | 0 | 86d | 0 | 0 | 22200.1543 | 0 | 83.56% | Started | 22200.1543 | 22200.1543 | 100 | 91.0417 | 83.5564 | 100 | 100 | 83.5564
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 437d | 22200.1543 | 0 | 86d | 0 | 0 | 22200.1543 | 0 | 83.56% | Started | 22200.1543 | 22200.1543 | 100 | 91.0417 | 83.5564 | 100 | 100 | 83.5564

## TP23
| TP Status Date | 2012-11-30 17:00 |  | TP Name | 30/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 459d | [5 empty] | 633262.9966 |  | 72.41% |  | 633262.9966 | 870526.8228
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 459d | [5 empty] | 138080.7021 |  | 85.71% |  | 138080.7021 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 22d | 15342.2998 | 0 | 21d | 0 | 0 | 15342.2998 | 0 | 51.16% | Started | 15342.2998 | 15342.2998 | 100 | 50 | 51.1628 | 100 | 100 | 51.1628
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 305d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 45d | [5 empty] | 40274.6094 |  | 24.39% |  | 40274.6094 | 161098.4375
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 45d | 40274.6094 | 0 | 173d | 0 | 0 | 40274.6094 | 0 | 20.64% | Started | 40274.6094 | 40274.6094 | 100 | 20.6422 | 20.6422 | 100 | 100 | 20.6422
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 |  | 0 | 0 | 32219.6875 | 175d | 0 | 0 | 0 | 32219.6875 | 0% | Not Started | 0 | 32219.6875 | 100 |  | 0 | 100 |  | 0
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 |  | 0 | 0 | 12082.3828 | 66d | 0 | 0 | 0 | 12082.3828 | 0% | Not Started | 0 | 12082.3828 | 100 |  | 0 | 100 |  | 0
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 |  | 0 | 0 | 16109.8438 | 89d | 0 | 0 | 0 | 16109.8438 | 0% | Not Started | 0 | 16109.8438 | 100 |  | 0 | 100 |  | 0
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 459d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 459d | 22200.1543 | 0 | 64d | 0 | 0 | 22200.1543 | 0 | 87.76% | Started | 22200.1543 | 22200.1543 | 100 | 95.625 | 87.7629 | 100 | 100 | 87.7629
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 459d | 22200.1543 | 0 | 64d | 0 | 0 | 22200.1543 | 0 | 87.76% | Started | 22200.1543 | 22200.1543 | 100 | 95.625 | 87.7629 | 100 | 100 | 87.7629

## TP24
| TP Status Date | 2012-12-31 17:00 |  | TP Name | 31/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 480d | [5 empty] | 725894.5981 |  | 83% |  | 725894.5981 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 480d | [5 empty] | 138080.7021 |  | 85.71% |  | 138080.7021 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 326d | [5 empty] | 124568.7266 |  | 57.14% |  | 124568.7266 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 |  | 0 | 0 | 46713.2734 | 65d | 0 | 0 | 0 | 46713.2734 | 0% | Not Started | 0 | 46713.2734 | 100 |  | 0 | 100 |  | 0
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 66d | [5 empty] | 132906.2109 |  | 80.49% |  | 132906.2109 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 66d | 40274.6094 | 0 | 152d | 0 | 0 | 40274.6094 | 0 | 30.28% | Started | 40274.6094 | 40274.6094 | 100 | 30.2752 | 30.2752 | 100 | 100 | 30.2752
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 |  | 0 | 0 | 28192.2266 | 152d | 0 | 0 | 0 | 28192.2266 | 0% | Not Started | 0 | 28192.2266 | 100 |  | 0 | 100 |  | 0
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 21d | 32219.6875 | 0 | 152d | 0 | 0 | 32219.6875 | 0 | 12.14% | Started | 32219.6875 | 32219.6875 | 100 | 12 | 12.1387 | 100 | 100 | 12.1387
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 21d | 32219.6875 | 0 | 152d | 0 | 0 | 32219.6875 | 0 | 12.14% | Started | 32219.6875 | 32219.6875 | 100 | 12 | 12.1387 | 100 | 100 | 12.1387
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 21d | 12082.3828 | 0 | 43d | 0 | 0 | 12082.3828 | 0 | 32.81% | Started | 12082.3828 | 12082.3828 | 100 | 31.8182 | 32.8125 | 100 | 100 | 32.8125
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 21d | 16109.8438 | 0 | 64d | 0 | 0 | 16109.8438 | 0 | 24.71% | Started | 16109.8438 | 16109.8438 | 100 | 23.5955 | 24.7059 | 100 | 100 | 24.7059
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 480d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 480d | 22200.1543 | 0 | 43d | 0 | 0 | 22200.1543 | 0 | 91.78% | Started | 22200.1543 | 22200.1543 | 100 | 100 | 91.7782 | 100 | 100 | 91.7782
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 480d | 22200.1543 | 0 | 43d | 0 | 0 | 22200.1543 | 0 | 91.78% | Started | 22200.1543 | 22200.1543 | 100 | 100 | 91.7782 | 100 | 100 | 91.7782

## TP25
| TP Status Date | 2013-01-31 17:00 |  | TP Name | 31/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 503d | [5 empty] | 847513.3716 |  | 96.91% |  | 847513.3716 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 503d | [5 empty] | 138080.7021 |  | 85.71% |  | 138080.7021 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 349d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 23d | 46713.2734 | 0 | 41d | 0 | 0 | 46713.2734 | 0 | 35.94% | Started | 46713.2734 | 46713.2734 | 100 | 35.3846 | 35.9375 | 100 | 100 | 35.9375
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 23d | 46713.2734 | 0 | 41d | 0 | 0 | 46713.2734 | 0 | 35.94% | Started | 46713.2734 | 46713.2734 | 100 | 35.3846 | 35.9375 | 100 | 100 | 35.9375
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 89d | [5 empty] | 161098.4375 |  | 97.56% |  | 161098.4375 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 89d | 40274.6094 | 0 | 129d | 0 | 0 | 40274.6094 | 0 | 40.83% | Started | 40274.6094 | 40274.6094 | 100 | 40.8257 | 40.8257 | 100 | 100 | 40.8257
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 23d | 28192.2266 | 0 | 129d | 0 | 0 | 28192.2266 | 0 | 15.13% | Started | 28192.2266 | 28192.2266 | 100 | 15.1316 | 15.1316 | 100 | 100 | 15.1316
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 44d | 32219.6875 | 0 | 129d | 0 | 0 | 32219.6875 | 0 | 25.43% | Started | 32219.6875 | 32219.6875 | 100 | 25.1429 | 25.4335 | 100 | 100 | 25.4335
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 44d | 32219.6875 | 0 | 129d | 0 | 0 | 32219.6875 | 0 | 25.43% | Started | 32219.6875 | 32219.6875 | 100 | 25.1429 | 25.4335 | 100 | 100 | 25.4335
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 44d | 12082.3828 | 0 | 20d | 0 | 0 | 12082.3828 | 0 | 68.75% | Started | 12082.3828 | 12082.3828 | 100 | 66.6667 | 68.75 | 100 | 100 | 68.75
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 44d | 16109.8438 | 0 | 41d | 0 | 0 | 16109.8438 | 0 | 51.76% | Started | 16109.8438 | 16109.8438 | 100 | 49.4382 | 51.7647 | 100 | 100 | 51.7647
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 503d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 503d | 22200.1543 | 0 | 20d | 0 | 0 | 22200.1543 | 0 | 96.18% | Started | 22200.1543 | 22200.1543 | 100 | 104.7917 | 96.1759 | 100 | 100 | 96.1759
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 503d | 22200.1543 | 0 | 20d | 0 | 0 | 22200.1543 | 0 | 96.18% | Started | 22200.1543 | 22200.1543 | 100 | 104.7917 | 96.1759 | 100 | 100 | 96.1759

## TP26
| TP Status Date | 2013-02-28 17:00 |  | TP Name | 28/02, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 523d | [5 empty] | 847513.3716 |  | 96.91% |  | 847513.3716 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 523d | [5 empty] | 138080.7021 |  | 85.71% |  | 138080.7021 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 369d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 43d | 46713.2734 | 0 | 21d | 0 | 0 | 46713.2734 | 0 | 67.19% | Started | 46713.2734 | 46713.2734 | 100 | 66.1538 | 67.1875 | 100 | 100 | 67.1875
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 43d | 46713.2734 | 0 | 21d | 0 | 0 | 46713.2734 | 0 | 67.19% | Started | 46713.2734 | 46713.2734 | 100 | 66.1538 | 67.1875 | 100 | 100 | 67.1875
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 109d | [5 empty] | 161098.4375 |  | 97.56% |  | 161098.4375 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 109d | 40274.6094 | 0 | 109d | 0 | 0 | 40274.6094 | 0 | 50% | Started | 40274.6094 | 40274.6094 | 100 | 50 | 50 | 100 | 100 | 50
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 43d | 28192.2266 | 0 | 109d | 0 | 0 | 28192.2266 | 0 | 28.29% | Started | 28192.2266 | 28192.2266 | 100 | 28.2895 | 28.2895 | 100 | 100 | 28.2895
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 64d | 32219.6875 | 0 | 109d | 0 | 0 | 32219.6875 | 0 | 36.99% | Started | 32219.6875 | 32219.6875 | 100 | 36.5714 | 36.9942 | 100 | 100 | 36.9942
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 64d | 32219.6875 | 0 | 109d | 0 | 0 | 32219.6875 | 0 | 36.99% | Started | 32219.6875 | 32219.6875 | 100 | 36.5714 | 36.9942 | 100 | 100 | 36.9942
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 100% | Finished | 12082.3828 | 12082.3828 | 100 | 96.9697 | 100 | 100 | 100 | 100
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 64d | 16109.8438 | 0 | 21d | 0 | 0 | 16109.8438 | 0 | 75.29% | Started | 16109.8438 | 16109.8438 | 100 | 71.9101 | 75.2941 | 100 | 100 | 75.2941
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100

## TP27
| TP Status Date | 2013-03-31 17:00 |  | TP Name | 31/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 544d | [5 empty] | 847513.3716 |  | 96.91% |  | 847513.3716 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 544d | [5 empty] | 138080.7021 |  | 85.71% |  | 138080.7021 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 |  | 0 | 0 | 23013.4512 | 66d | 0 | 0 | 0 | 23013.4512 | 0% | Not Started | 0 | 23013.4512 | 100 |  | 0 | 100 |  | 0
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 390d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 130d | [5 empty] | 161098.4375 |  | 97.56% |  | 161098.4375 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 130d | 40274.6094 | 0 | 88d | 0 | 0 | 40274.6094 | 0 | 59.63% | Started | 40274.6094 | 40274.6094 | 100 | 59.633 | 59.633 | 100 | 100 | 59.633
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 64d | 28192.2266 | 0 | 88d | 0 | 0 | 28192.2266 | 0 | 42.11% | Started | 28192.2266 | 28192.2266 | 100 | 42.1053 | 42.1053 | 100 | 100 | 42.1053
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 85d | 32219.6875 | 0 | 88d | 0 | 0 | 32219.6875 | 0 | 49.13% | Started | 32219.6875 | 32219.6875 | 100 | 48.5714 | 49.1329 | 100 | 100 | 49.1329
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 85d | 32219.6875 | 0 | 88d | 0 | 0 | 32219.6875 | 0 | 49.13% | Started | 32219.6875 | 32219.6875 | 100 | 48.5714 | 49.1329 | 100 | 100 | 49.1329
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 100% | Finished | 12082.3828 | 12082.3828 | 100 | 96.9697 | 100 | 100 | 100 | 100
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 85d | 16109.8438 | 0 | 0 | 0 | 0 | 16109.8438 | 0 | 100% | Finished | 16109.8438 | 16109.8438 | 100 | 95.5056 | 100 | 100 | 100 | 100
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100

## TP28
| TP Status Date | 2013-04-30 17:00 |  | TP Name | 30/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 566d | [5 empty] | 870526.8228 |  | 99.54% |  | 870526.8228 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 566d | [5 empty] | 161094.1533 |  | 100% |  | 161094.1533 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 | 2013-04-01 08:00 | 22d | 23013.4512 | 0 | 43d | 0 | 0 | 23013.4512 | 0 | 33.85% | Started | 23013.4512 | 23013.4512 | 100 | 33.3333 | 33.8462 | 100 | 100 | 33.8462
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 390d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 152d | [5 empty] | 161098.4375 |  | 97.56% |  | 161098.4375 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 152d | 40274.6094 | 0 | 66d | 0 | 0 | 40274.6094 | 0 | 69.72% | Started | 40274.6094 | 40274.6094 | 100 | 69.7248 | 69.7248 | 100 | 100 | 69.7248
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 86d | 28192.2266 | 0 | 66d | 0 | 0 | 28192.2266 | 0 | 56.58% | Started | 28192.2266 | 28192.2266 | 100 | 56.5789 | 56.5789 | 100 | 100 | 56.5789
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 107d | 32219.6875 | 0 | 66d | 0 | 0 | 32219.6875 | 0 | 61.85% | Started | 32219.6875 | 32219.6875 | 100 | 61.1429 | 61.8497 | 100 | 100 | 61.8497
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 107d | 32219.6875 | 0 | 66d | 0 | 0 | 32219.6875 | 0 | 61.85% | Started | 32219.6875 | 32219.6875 | 100 | 61.1429 | 61.8497 | 100 | 100 | 61.8497
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 100% | Finished | 12082.3828 | 12082.3828 | 100 | 96.9697 | 100 | 100 | 100 | 100
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 85d | 16109.8438 | 0 | 0 | 0 | 0 | 16109.8438 | 0 | 100% | Finished | 16109.8438 | 16109.8438 | 100 | 95.5056 | 100 | 100 | 100 | 100
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100

## TP29
| TP Status Date | 2013-05-31 17:00 |  | TP Name | 31/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 589d | [5 empty] | 870526.8228 |  | 99.54% |  | 870526.8228 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 589d | [5 empty] | 161094.1533 |  | 100% |  | 161094.1533 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 | 2013-04-01 08:00 | 45d | 23013.4512 | 0 | 20d | 0 | 0 | 23013.4512 | 0 | 69.23% | Started | 23013.4512 | 23013.4512 | 100 | 68.1818 | 69.2308 | 100 | 100 | 69.2308
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 390d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 175d | [5 empty] | 161098.4375 |  | 97.56% |  | 161098.4375 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 175d | 40274.6094 | 0 | 43d | 0 | 0 | 40274.6094 | 0 | 80.28% | Started | 40274.6094 | 40274.6094 | 100 | 80.2752 | 80.2752 | 100 | 100 | 80.2752
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 109d | 28192.2266 | 0 | 43d | 0 | 0 | 28192.2266 | 0 | 71.71% | Started | 28192.2266 | 28192.2266 | 100 | 71.7105 | 71.7105 | 100 | 100 | 71.7105
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 130d | 32219.6875 | 0 | 43d | 0 | 0 | 32219.6875 | 0 | 75.14% | Started | 32219.6875 | 32219.6875 | 100 | 74.2857 | 75.1445 | 100 | 100 | 75.1445
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 130d | 32219.6875 | 0 | 43d | 0 | 0 | 32219.6875 | 0 | 75.14% | Started | 32219.6875 | 32219.6875 | 100 | 74.2857 | 75.1445 | 100 | 100 | 75.1445
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 100% | Finished | 12082.3828 | 12082.3828 | 100 | 96.9697 | 100 | 100 | 100 | 100
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 85d | 16109.8438 | 0 | 0 | 0 | 0 | 16109.8438 | 0 | 100% | Finished | 16109.8438 | 16109.8438 | 100 | 95.5056 | 100 | 100 | 100 | 100
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100

## TP30
| TP Status Date | 2013-06-30 17:00 |  | TP Name | 30/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 609d | [5 empty] | 870526.8228 |  | 99.54% |  | 870526.8228 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 609d | [5 empty] | 161094.1533 |  | 100% |  | 161094.1533 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 | 2013-04-01 08:00 | 65d | 23013.4512 | 0 | 0 | 0 | 0 | 23013.4512 | 0 | 100% | Finished | 23013.4512 | 23013.4512 | 100 | 98.4848 | 100 | 100 | 100 | 100
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 390d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 195d | [5 empty] | 161098.4375 |  | 97.56% |  | 161098.4375 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 195d | 40274.6094 | 0 | 23d | 0 | 0 | 40274.6094 | 0 | 89.45% | Started | 40274.6094 | 40274.6094 | 100 | 89.4495 | 89.4495 | 100 | 100 | 89.4495
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 129d | 28192.2266 | 0 | 23d | 0 | 0 | 28192.2266 | 0 | 84.87% | Started | 28192.2266 | 28192.2266 | 100 | 84.8684 | 84.8684 | 100 | 100 | 84.8684
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 150d | 32219.6875 | 0 | 23d | 0 | 0 | 32219.6875 | 0 | 86.71% | Started | 32219.6875 | 32219.6875 | 100 | 85.7143 | 86.7052 | 100 | 100 | 86.7052
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 150d | 32219.6875 | 0 | 23d | 0 | 0 | 32219.6875 | 0 | 86.71% | Started | 32219.6875 | 32219.6875 | 100 | 85.7143 | 86.7052 | 100 | 100 | 86.7052
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 100% | Finished | 12082.3828 | 12082.3828 | 100 | 96.9697 | 100 | 100 | 100 | 100
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 |  | 0 | 0 | 4027.4609 | 21d | 0 | 0 | 0 | 4027.4609 | 0% | Not Started | 0 | 4027.4609 | 100 |  | 0 | 100 |  | 0
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 85d | 16109.8438 | 0 | 0 | 0 | 0 | 16109.8438 | 0 | 100% | Finished | 16109.8438 | 16109.8438 | 100 | 95.5056 | 100 | 100 | 100 | 100
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100

## TP31
| TP Status Date | 2013-07-31 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | PET Packaging | 2011-01-03 08:00 | 2012-12-31 17:00 | 521d |  |  | 874554.2837 |  |  | 874554.2837 |  | 632d | [5 empty] | 874554.2837 |  | 100% |  | 874554.2837 | 874554.2837
6 | WP1 | 2011-03-01 08:00 | 2011-12-30 17:00 | 219d |  |  | 28353.9331 |  |  | 28353.9331 |  | 219d | [5 empty] | 28353.9331 |  | 100% |  | 28353.9331 | 28353.9331
1 | 1.1 | 2011-03-01 08:00 | 2011-04-29 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-03-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
2 | 1.2 | 2011-05-02 08:00 | 2011-06-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-05-02 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
3 | 1.3 | 2011-07-01 08:00 | 2011-08-31 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-07-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
4 | 1.4 | 2011-09-01 08:00 | 2011-10-31 17:00 | 43d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-09-01 08:00 | 43d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
5 | 1.5 | 2011-11-01 08:00 | 2011-12-30 17:00 | 44d |  | 0 | 5670.7866 | 0 | 0 | 5670.7866 | 2011-11-01 08:00 | 44d | 5670.7866 | 0 | 0 | 0 | 0 | 5670.7866 | 0 | 100% | Finished | 5670.7866 | 5670.7866 | 100 | 100 | 100 | 100 | 100 | 100
11 | WP2 | 2011-01-03 08:00 | 2012-08-01 16:00 | 412d 7h |  |  | 161094.1533 |  |  | 161094.1533 |  | 609d | [5 empty] | 161094.1533 |  | 100% |  | 161094.1533 | 161094.1533
7 | 2.1 | 2011-01-03 08:00 | 2011-10-31 17:00 | 216d |  | 0 | 76711.5 | 0 | 0 | 76711.5 | 2011-03-01 08:00 | 262d | 76711.5 | 0 | 0 | 0 | 0 | 76711.5 | 0 | 100% | Finished | 76711.5 | 76711.5 | 100 | 121.2963 | 100 | 100 | 100 | 100
8 | 2.2 | 2011-05-02 08:00 | 2011-10-31 17:00 | 131d |  | 0 | 46026.9023 | 0 | 0 | 46026.9023 | 2012-01-02 08:00 | 218d | 46026.9023 | 0 | 0 | 0 | 0 | 46026.9023 | 0 | 100% | Finished | 46026.9023 | 46026.9023 | 100 | 166.4122 | 100 | 100 | 100 | 100
9 | 2.3 | 2011-11-01 09:00 | 2012-01-02 09:00 | 44d |  | 0 | 15342.2998 | 0 | 0 | 15342.2998 | 2012-11-01 08:00 | 43d | 15342.2998 | 0 | 0 | 0 | 0 | 15342.2998 | 0 | 100% | Finished | 15342.2998 | 15342.2998 | 100 | 97.7273 | 100 | 100 | 100 | 100
10 | 2.4 | 2012-05-01 16:00 | 2012-08-01 16:00 | 66d |  | 0 | 23013.4512 | 0 | 0 | 23013.4512 | 2013-04-01 08:00 | 65d | 23013.4512 | 0 | 0 | 0 | 0 | 23013.4512 | 0 | 100% | Finished | 23013.4512 | 23013.4512 | 100 | 98.4848 | 100 | 100 | 100 | 100
16 | WP3 | 2011-01-03 08:00 | 2011-06-30 17:00 | 129d |  |  | 127886.6816 |  |  | 127886.6816 |  | 282d | [5 empty] | 127886.6816 |  | 100% |  | 127886.6816 | 127886.6816
12 | 3.1 | 2011-01-03 08:00 | 2011-02-28 17:00 | 41d |  | 0 | 21314.4473 | 0 | 0 | 21314.4473 | 2011-04-01 08:00 | 43d | 21314.4473 | 0 | 0 | 0 | 0 | 21314.4473 | 0 | 100% | Finished | 21314.4473 | 21314.4473 | 100 | 104.878 | 100 | 100 | 100 | 100
13 | 3.2 | 2011-03-01 08:00 | 2011-06-30 17:00 | 88d |  | 0 | 42628.8945 | 0 | 0 | 42628.8945 | 2011-09-01 08:00 | 87d | 42628.8945 | 0 | 0 | 0 | 0 | 42628.8945 | 0 | 100% | Finished | 42628.8945 | 42628.8945 | 100 | 98.8636 | 100 | 100 | 100 | 100
14 | 3.3 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2011-11-01 08:00 | 87d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 133.8462 | 100 | 100 | 100 | 100
15 | 3.4 | 2011-04-01 08:00 | 2011-06-30 17:00 | 65d |  | 0 | 31971.6699 | 0 | 0 | 31971.6699 | 2012-03-01 08:00 | 43d | 31971.6699 | 0 | 0 | 0 | 0 | 31971.6699 | 0 | 100% | Finished | 31971.6699 | 31971.6699 | 100 | 66.1538 | 100 | 100 | 100 | 100
20 | WP4 | 2011-04-01 08:00 | 2012-04-30 17:00 | 282d |  |  | 129698.0352 |  |  | 129698.0352 |  | 262d | [5 empty] | 129698.0352 |  | 100% |  | 129698.0352 | 129698.0352
17 | 4.1 | 2011-04-01 08:00 | 2011-07-29 17:00 | 86d |  | 0 | 51879.2148 | 0 | 0 | 51879.2148 | 2011-09-01 08:00 | 87d | 51879.2148 | 0 | 0 | 0 | 0 | 51879.2148 | 0 | 100% | Finished | 51879.2148 | 51879.2148 | 100 | 101.1628 | 100 | 100 | 100 | 100
18 | 4.2 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
19 | 4.3 | 2012-02-01 08:00 | 2012-04-30 17:00 | 64d |  | 0 | 38909.4102 | 0 | 0 | 38909.4102 | 2012-06-01 08:00 | 66d | 38909.4102 | 0 | 0 | 0 | 0 | 38909.4102 | 0 | 100% | Finished | 38909.4102 | 38909.4102 | 100 | 103.125 | 100 | 100 | 100 | 100
24 | WP5 | 2011-07-01 08:00 | 2012-11-30 17:00 | 371d |  |  | 217995.2734 |  |  | 217995.2734 |  | 390d | [5 empty] | 217995.2734 |  | 100% |  | 217995.2734 | 217995.2734
21 | 5.1 | 2011-07-01 08:00 | 2012-02-29 17:00 | 174d |  | 0 | 124568.7266 | 0 | 0 | 124568.7266 | 2011-10-03 08:00 | 283d | 124568.7266 | 0 | 0 | 0 | 0 | 124568.7266 | 0 | 100% | Finished | 124568.7266 | 124568.7266 | 100 | 162.6437 | 100 | 100 | 100 | 100
22 | 5.2 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
23 | 5.3 | 2012-09-03 08:00 | 2012-11-30 17:00 | 65d |  | 0 | 46713.2734 | 0 | 0 | 46713.2734 | 2013-01-01 08:00 | 64d | 46713.2734 | 0 | 0 | 0 | 0 | 46713.2734 | 0 | 100% | Finished | 46713.2734 | 46713.2734 | 100 | 98.4615 | 100 | 100 | 100 | 100
31 | WP6 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  |  | 165125.8984 |  |  | 165125.8984 |  | 218d | [5 empty] | 165125.8984 |  | 100% |  | 165125.8984 | 165125.8984
25 | 6.1 | 2012-03-01 08:00 | 2012-12-31 17:00 | 218d |  | 0 | 40274.6094 | 0 | 0 | 40274.6094 | 2012-10-01 08:00 | 218d | 40274.6094 | 0 | 0 | 0 | 0 | 40274.6094 | 0 | 100% | Finished | 40274.6094 | 40274.6094 | 100 | 100 | 100 | 100 | 100 | 100
26 | 6.2 | 2012-06-01 08:00 | 2012-12-31 17:00 | 152d |  | 0 | 28192.2266 | 0 | 0 | 28192.2266 | 2013-01-01 08:00 | 152d | 28192.2266 | 0 | 0 | 0 | 0 | 28192.2266 | 0 | 100% | Finished | 28192.2266 | 28192.2266 | 100 | 100 | 100 | 100 | 100 | 100
27 | 6.3 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 173d | 32219.6875 | 0 | 0 | 0 | 0 | 32219.6875 | 0 | 100% | Finished | 32219.6875 | 32219.6875 | 100 | 98.8571 | 100 | 100 | 100 | 100
28 | 6.4 | 2012-05-01 08:00 | 2012-12-31 17:00 | 175d |  | 0 | 32219.6875 | 0 | 0 | 32219.6875 | 2012-12-03 08:00 | 173d | 32219.6875 | 0 | 0 | 0 | 0 | 32219.6875 | 0 | 100% | Finished | 32219.6875 | 32219.6875 | 100 | 98.8571 | 100 | 100 | 100 | 100
29 | 6.5A | 2012-05-01 08:00 | 2012-07-31 17:00 | 66d |  | 0 | 12082.3828 | 0 | 0 | 12082.3828 | 2012-12-03 08:00 | 64d | 12082.3828 | 0 | 0 | 0 | 0 | 12082.3828 | 0 | 100% | Finished | 12082.3828 | 12082.3828 | 100 | 96.9697 | 100 | 100 | 100 | 100
35 | 6.5B | 2012-12-03 08:00 | 2012-12-31 17:00 | 21d |  | 0 | 4027.4609 | 0 | 0 | 4027.4609 | 2013-07-01 08:00 | 23d | 4027.4609 | 0 | 0 | 0 | 0 | 4027.4609 | 0 | 100% | Finished | 4027.4609 | 4027.4609 | 100 | 109.5238 | 100 | 100 | 100 | 100
30 | 6.6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 16109.8438 | 0 | 0 | 16109.8438 | 2012-12-03 08:00 | 85d | 16109.8438 | 0 | 0 | 0 | 0 | 16109.8438 | 0 | 100% | Finished | 16109.8438 | 16109.8438 | 100 | 95.5056 | 100 | 100 | 100 | 100
34 | WP7 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  |  | 44400.3086 |  |  | 44400.3086 |  | 523d | [5 empty] | 44400.3086 |  | 100% |  | 44400.3086 | 44400.3086
32 | 7.1 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100
33 | 7.2 | 2011-03-01 08:00 | 2012-12-31 17:00 | 480d |  | 0 | 22200.1543 | 0 | 0 | 22200.1543 | 2011-03-01 08:00 | 523d | 22200.1543 | 0 | 0 | 0 | 0 | 22200.1543 | 0 | 100% | Finished | 22200.1543 | 22200.1543 | 100 | 108.9583 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
31/01, 2011 | 2011-01-03 08:00 | 2011-01-31 17:00 | 98025.9473 | 0 | 0 | 2011-01-03 08:00 | -98025.9473 | 0% | 0 | 0% | -21d | 0% | 100% | 2013-03-22 11:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 2013-01-29 17:00 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 0 | 0 | 0 | 1 | -21 | 0 | 1 | 0 | 1
28/02, 2011 | 2011-01-31 17:00 | 2011-02-28 17:00 | 98025.9473 | 0 | 0 | 2011-01-03 08:00 | -98025.9473 | 0% | 0 | 0% | -41d | 0% | 100% | 2013-03-22 11:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 2013-02-26 17:00 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 0 | 0 | 0 | 1 | -41 | 0 | 1 | 0 | 1
31/03, 2011 | 2011-02-28 17:00 | 2011-03-31 17:00 | 190725.937 | 126782.5952 | 126782.5952 | 2011-02-28 17:00 | -63943.3418 | 66.47% | 0 | 100% | -23d | 64.06% | 78.26% | 2013-02-22 09:00 | 2014-01-02 15:00 | 2014-01-02 15:00 | 2013-01-30 12:00 | 2014-01-02 15:00 | 2014-01-02 15:00 | 2013-01-31 17:00 | 2014-02-13 10:00 | 2014-02-13 10:00 | 874554.2837 | 874554.2837 | 1251696.1191 | 1294035.9626 | 1251696.1191 | 1294035.9626 | 928297.9665 | 932462.5289 | 0.64062 | 1 | 0.66474 | 0.78256 | -23 | 1 | 1 | 0.64062 | 1
30/04, 2011 | 2011-03-31 17:00 | 2011-04-30 17:00 | 306548.4917 | 148097.0425 | 148097.0425 | 2011-02-28 17:00 | -158451.4492 | 48.31% | 0 | 100% | -44d | 48.24% | 100% | 2013-05-13 11:00 | 2015-02-19 11:00 | 2015-02-19 11:00 | 2013-03-01 16:00 | 2015-02-19 11:00 | 2015-02-19 11:00 | 2013-03-01 17:00 | 2015-02-23 09:00 | 2015-02-23 09:00 | 874554.2837 | 874554.2837 | 1651802.7739 | 1654166.9328 | 1651802.7739 | 1654166.9328 | 958312.5284 | 958449.6081 | 0.48235 | 1 | 0.48311 | 1 | -44 | 1 | 1 | 0.48235 | 1
31/05, 2011 | 2011-04-30 17:00 | 2011-05-31 17:00 | 358246.1807 | 153767.8291 | 153767.8291 | 2011-02-28 17:00 | -204478.3516 | 42.92% | 0 | 100% | -66d | 38.32% | 100% | 2013-06-19 16:00 | 2015-08-27 16:00 | 2015-08-27 16:00 | 2013-03-27 09:00 | 2015-08-27 16:00 | 2015-08-27 16:00 | 2013-04-02 17:00 | 2016-03-18 14:00 | 2016-03-18 14:00 | 874554.2837 | 874554.2837 | 1833046.2317 | 2034844.674 | 1833046.2317 | 2034844.674 | 967439.1043 | 975986.9191 | 0.38318 | 1 | 0.42922 | 1 | -66 | 1 | 1 | 0.38318 | 1
30/06, 2011 | 2011-05-31 17:00 | 2011-06-30 17:00 | 358246.1807 | 153767.8291 | 153767.8291 | 2011-02-28 17:00 | -204478.3516 | 42.92% | 0 | 100% | -88d | 31.78% | 100% | 2013-06-19 16:00 | 2015-08-27 16:00 | 2015-08-27 16:00 | 2013-04-12 14:00 | 2015-08-27 16:00 | 2015-08-27 16:00 | 2013-05-02 17:00 | 2017-04-14 10:00 | 2017-04-14 10:00 | 874554.2837 | 874554.2837 | 1833046.2317 | 2421608.1374 | 1833046.2317 | 2421608.1374 | 967439.1043 | 988430.7792 | 0.31783 | 1 | 0.42922 | 1 | -88 | 1 | 1 | 0.31783 | 1
31/07, 2011 | 2011-06-30 17:00 | 2011-07-31 17:00 | 488485.6938 | 159438.6157 | 159438.6157 | 2011-02-28 17:00 | -329047.0781 | 32.64% | 0 | 100% | -109d | 27.33% | 100% | 2013-10-01 17:00 | 2017-02-14 10:00 | 2017-02-14 10:00 | 2013-05-21 17:00 | 2017-02-14 10:00 | 2017-02-14 10:00 | 2013-05-31 17:00 | 2018-04-24 09:00 | 2018-04-24 09:00 | 874554.2837 | 874554.2837 | 2350399.5173 | 2775715.4498 | 2350399.5173 | 2775715.4498 | 985895.6261 | 996157.416 | 0.27333 | 1 | 0.32639 | 1 | -109 | 1 | 1 | 0.27333 | 1
31/08, 2011 | 2011-07-31 17:00 | 2011-08-31 17:00 | 488485.6938 | 159438.6157 | 159438.6157 | 2011-02-28 17:00 | -329047.0781 | 32.64% | 0 | 100% | -132d | 23.7% | 100% | 2013-10-01 17:00 | 2017-02-14 10:00 | 2017-02-14 10:00 | 2013-06-12 12:00 | 2017-02-14 10:00 | 2017-02-14 10:00 | 2013-07-03 17:00 | 2019-06-06 11:00 | 2019-06-06 11:00 | 874554.2837 | 874554.2837 | 2350399.5173 | 3176877.8976 | 2350399.5173 | 3176877.8976 | 985895.6261 | 1003333.64 | 0.23699 | 1 | 0.32639 | 1 | -132 | 1 | 1 | 0.23699 | 1
30/09, 2011 | 2011-08-31 17:00 | 2011-09-30 17:00 | 494156.4805 | 259617.5117 | 259617.5117 | 2011-03-31 17:00 | -234538.9688 | 52.54% | 0 | 100% | -131d | 32.82% | 100% | 2013-07-15 15:00 | 2014-10-21 14:00 | 2014-10-21 14:00 | 2013-05-09 12:00 | 2014-10-21 14:00 | 2014-10-21 14:00 | 2013-07-02 17:00 | 2017-02-01 11:00 | 2017-02-01 11:00 | 874554.2837 | 874554.2837 | 1430089.3683 | 2133252.9888 | 1430089.3683 | 2133252.9888 | 939049.3356 | 970000.631 | 0.32821 | 1 | 0.52538 | 1 | -131 | 1 | 1 | 0.32821 | 1
31/10, 2011 | 2011-09-30 17:00 | 2011-10-31 17:00 | 494156.4805 | 384186.2383 | 384186.2383 | 2011-06-30 17:00 | -109970.2422 | 77.75% | 0 | 100% | -87d | 59.72% | 69.3% | 2013-04-02 12:00 | 2013-07-29 09:00 | 2013-07-29 09:00 | 2013-03-08 09:00 | 2013-07-29 09:00 | 2013-07-29 09:00 | 2013-05-01 17:00 | 2014-05-07 11:00 | 2014-05-07 11:00 | 874554.2837 | 874554.2837 | 1014918.2201 | 1205267.6166 | 1014918.2201 | 1205267.6166 | 897396.3775 | 917517.043 | 0.59722 | 1 | 0.77746 | 0.69303 | -87 | 1 | 1 | 0.59722 | 1
30/11, 2011 | 2011-10-31 17:00 | 2011-11-30 17:00 | 515169.5669 | 421828.6948 | 421828.6948 | 2011-06-30 17:00 | -93340.8721 | 81.88% | 0 | 100% | -109d | 54.2% | 78.23% | 2013-03-19 14:00 | 2013-06-11 10:00 | 2013-06-11 10:00 | 2013-03-01 09:00 | 2013-06-11 10:00 | 2013-06-11 10:00 | 2013-05-31 17:00 | 2014-09-09 10:00 | 2014-09-09 10:00 | 874554.2837 | 874554.2837 | 974731.9193 | 1257089.8588 | 974731.9193 | 1257089.8588 | 891576.5124 | 920203.7649 | 0.54202 | 1 | 0.81882 | 0.78228 | -109 | 1 | 1 | 0.54202 | 1
31/12, 2011 | 2011-11-30 17:00 | 2011-12-31 17:00 | 515169.5669 | 421828.6948 | 421828.6948 | 2011-06-30 17:00 | -93340.8721 | 81.88% | 0 | 100% | -131d | 49.62% | 78.23% | 2013-03-19 14:00 | 2013-06-11 10:00 | 2013-06-11 10:00 | 2013-03-07 09:00 | 2013-06-11 10:00 | 2013-06-11 10:00 | 2013-07-02 17:00 | 2015-01-12 09:00 | 2015-01-12 09:00 | 874554.2837 | 874554.2837 | 974731.9193 | 1334298.8739 | 974731.9193 | 1334298.8739 | 891576.5124 | 925287.4335 | 0.49615 | 1 | 0.81882 | 0.78228 | -131 | 1 | 1 | 0.49615 | 1
31/01, 2012 | 2011-12-31 17:00 | 2012-01-31 17:00 | 515169.5669 | 467855.5972 | 467855.5972 | 2011-06-30 17:00 | -47313.9697 | 90.82% | 0 | 100% | -153d | 45.74% | 91.08% | 2013-02-08 09:00 | 2013-03-14 15:00 | 2013-03-14 15:00 | 2013-02-05 16:00 | 2013-03-14 15:00 | 2013-03-14 15:00 | 2013-08-01 17:00 | 2015-05-14 16:00 | 2015-05-14 16:00 | 874554.2837 | 874554.2837 | 915683.4899 | 1356917.8421 | 915683.4899 | 1356917.8421 | 882164.4366 | 924056.9878 | 0.45745 | 1 | 0.90816 | 0.91076 | -153 | 1 | 1 | 0.45745 | 1
29/02, 2012 | 2012-01-31 17:00 | 2012-02-29 17:00 | 592988.3872 | 467855.5972 | 467855.5972 | 2011-06-30 17:00 | -125132.79 | 78.9% | 0 | 100% | -174d | 42.57% | 91.08% | 2013-04-15 12:00 | 2013-07-15 11:00 | 2013-07-15 11:00 | 2013-03-29 17:00 | 2013-07-15 11:00 | 2013-07-15 11:00 | 2013-08-30 17:00 | 2015-09-10 15:00 | 2015-09-10 15:00 | 874554.2837 | 874554.2837 | 983330.0292 | 1423124.605 | 983330.0292 | 1423124.605 | 892474.9744 | 927325.0305 | 0.42574 | 1 | 0.78898 | 0.91076 | -174 | 1 | 1 | 0.42574 | 1
31/03, 2012 | 2012-02-29 17:00 | 2012-03-31 17:00 | 633262.9966 | 499827.2671 | 499827.2671 | 2011-11-01 09:00 | -133435.7295 | 78.93% | 0 | 100% | -108d 7h | 66.5% | 100% | 2013-04-22 12:00 | 2013-07-15 09:00 | 2013-07-15 09:00 | 2013-04-05 12:00 | 2013-07-15 09:00 | 2013-07-15 09:00 | 2013-05-31 16:00 | 2014-01-02 12:00 | 2014-01-02 12:00 | 874554.2837 | 874554.2837 | 974592.7892 | 1063326.5402 | 974592.7892 | 1063326.5402 | 891040.9185 | 901463.9408 | 0.665 | 1 | 0.78929 | 1 | -108.875 | 1 | 1 | 0.665 | 1
30/04, 2012 | 2012-03-31 17:00 | 2012-04-30 17:00 | 633262.9966 | 499827.2671 | 499827.2671 | 2011-11-01 09:00 | -133435.7295 | 78.93% | 0 | 100% | -129d 7h | 62.46% | 100% | 2013-04-22 12:00 | 2013-07-15 09:00 | 2013-07-15 09:00 | 2013-04-11 16:00 | 2013-07-15 09:00 | 2013-07-15 09:00 | 2013-07-01 16:00 | 2014-03-14 09:00 | 2014-03-14 09:00 | 874554.2837 | 874554.2837 | 974592.7892 | 1099737.2624 | 974592.7892 | 1099737.2624 | 891040.9185 | 904969.2021 | 0.62464 | 1 | 0.78929 | 1 | -129.875 | 1 | 1 | 0.62464 | 1
31/05, 2012 | 2012-04-30 17:00 | 2012-05-31 17:00 | 748908.0493 | 499827.2671 | 499827.2671 | 2011-11-01 09:00 | -249080.7822 | 66.74% | 0 | 100% | -152d 7h | 58.57% | 100% | 2013-07-26 11:00 | 2013-12-30 14:00 | 2013-12-30 14:00 | 2013-06-20 15:00 | 2013-12-30 14:00 | 2013-12-30 14:00 | 2013-08-01 16:00 | 2014-05-30 12:00 | 2014-05-30 12:00 | 874554.2837 | 874554.2837 | 1061293.3925 | 1139615.6725 | 1061293.3925 | 1139615.6725 | 901256.7242 | 908408.9887 | 0.5857 | 1 | 0.66741 | 1 | -152.875 | 1 | 1 | 0.5857 | 1
30/06, 2012 | 2012-05-31 17:00 | 2012-06-30 17:00 | 777100.2759 | 577646.0874 | 577646.0874 | 2012-01-31 17:00 | -199454.1885 | 74.33% | 0 | 100% | -108d | 72.31% | 97.02% | 2013-06-14 16:00 | 2013-09-09 16:00 | 2013-09-09 16:00 | 2013-05-21 09:00 | 2013-09-09 16:00 | 2013-09-09 16:00 | 2013-05-30 17:00 | 2013-10-07 12:00 | 2013-10-07 12:00 | 874554.2837 | 874554.2837 | 977073.0831 | 988263.8057 | 977073.0831 | 988263.8057 | 890620.1614 | 891962.5818 | 0.72308 | 1 | 0.74334 | 0.97022 | -108 | 1 | 1 | 0.72308 | 1
31/07, 2012 | 2012-06-30 17:00 | 2012-07-31 17:00 | 777100.2759 | 577646.0874 | 577646.0874 | 2012-01-31 17:00 | -199454.1885 | 74.33% | 0 | 100% | -130d | 68.45% | 97.02% | 2013-06-14 16:00 | 2013-09-09 16:00 | 2013-09-09 16:00 | 2013-05-28 15:00 | 2013-09-09 16:00 | 2013-09-09 16:00 | 2013-07-01 17:00 | 2013-12-03 09:00 | 2013-12-03 09:00 | 874554.2837 | 874554.2837 | 977073.0831 | 1011426.8564 | 977073.0831 | 1011426.8564 | 890620.1614 | 894553.2814 | 0.68447 | 1 | 0.74334 | 0.97022 | -130 | 1 | 1 | 0.68447 | 1
31/08, 2012 | 2012-07-31 17:00 | 2012-08-31 17:00 | 777100.2759 | 577646.0874 | 577646.0874 | 2012-01-31 17:00 | -199454.1885 | 74.33% | 0 | 100% | -153d | 64.83% | 97.02% | 2013-06-14 16:00 | 2013-09-09 16:00 | 2013-09-09 16:00 | 2013-06-05 14:00 | 2013-09-09 16:00 | 2013-09-09 16:00 | 2013-08-01 17:00 | 2014-01-30 14:00 | 2014-01-30 14:00 | 874554.2837 | 874554.2837 | 977073.0831 | 1035642.7732 | 977073.0831 | 1035642.7732 | 890620.1614 | 897020.6309 | 0.64828 | 1 | 0.74334 | 0.97022 | -153 | 1 | 1 | 0.64828 | 1
30/09, 2012 | 2012-08-31 17:00 | 2012-09-30 17:00 | 870526.8228 | 577646.0874 | 577646.0874 | 2012-01-31 17:00 | -292880.7354 | 66.36% | 0 | 100% | -173d | 61.98% | 97.02% | 2013-09-02 12:00 | 2014-01-06 09:00 | 2014-01-06 09:00 | 2013-08-02 09:00 | 2014-01-06 09:00 | 2014-01-06 09:00 | 2013-08-29 17:00 | 2014-03-24 14:00 | 2014-03-24 14:00 | 874554.2837 | 874554.2837 | 1025094.022 | 1056700.0921 | 1025094.022 | 1056700.0921 | 895973.9816 | 898990.591 | 0.61978 | 1 | 0.66356 | 0.97022 | -173 | 1 | 1 | 0.61978 | 1
31/10, 2012 | 2012-09-30 17:00 | 2012-10-31 17:00 | 870526.8228 | 617920.6968 | 617920.6968 | 2012-02-29 17:00 | -252606.126 | 70.98% | 0 | 100% | -175d | 63.39% | 97.41% | 2013-07-30 12:00 | 2013-10-24 17:00 | 2013-10-24 17:00 | 2013-07-12 15:00 | 2013-10-24 17:00 | 2013-10-24 17:00 | 2013-09-02 17:00 | 2014-02-25 16:00 | 2014-02-25 16:00 | 874554.2837 | 874554.2837 | 979466.1543 | 1022775.0022 | 979466.1543 | 1022775.0022 | 890365.6919 | 894830.075 | 0.63389 | 1 | 0.70982 | 0.97413 | -175 | 1 | 1 | 0.63389 | 1
30/11, 2012 | 2012-10-31 17:00 | 2012-11-30 17:00 | 870526.8228 | 633262.9966 | 633262.9966 | 2012-04-30 17:00 | -237263.8262 | 72.74% | 0 | 100% | -154d | 69.2% | 100% | 2013-07-17 11:00 | 2013-10-01 10:00 | 2013-10-01 10:00 | 2013-07-10 10:00 | 2013-10-01 10:00 | 2013-10-01 10:00 | 2013-08-02 17:00 | 2013-11-20 16:00 | 2013-11-20 16:00 | 874554.2837 | 874554.2837 | 964958.5775 | 981949.8277 | 964958.5775 | 981949.8277 | 888465.4727 | 890393.5242 | 0.692 | 1 | 0.72745 | 1 | -154 | 1 | 1 | 0.692 | 1
31/12, 2012 | 2012-11-30 17:00 | 2012-12-31 17:00 | 874554.2837 | 725894.5981 | 725894.5981 | 2012-05-01 16:00 | -148659.6855 | 83% | 0 | 100% | -174d 1h | 66.58% | 100% | 2013-05-03 12:00 | 2013-05-29 15:00 | 2013-05-29 15:00 | 2013-05-03 12:00 | 2013-05-29 15:00 | 2013-05-29 15:00 | 2013-09-02 09:00 | 2014-01-01 12:00 | 2014-01-01 12:00 | 874554.2837 | 874554.2837 | 904999.0647 | 949178.7673 | 904999.0647 | 949178.7673 | 879786.0824 | 885202.864 | 0.66579 | 1 | 0.83002 | 1 | -174.125 | 1 | 1 | 0.66579 | 1
31/01, 2013 | 2012-12-31 17:00 | 2013-01-31 17:00 | 874554.2837 | 847513.3716 | 847513.3716 | 2012-08-31 17:00 | -27040.9121 | 96.91% | 0 | 100% | -109d | 79.96% | 97.04% | 2013-01-23 09:00 | 2013-01-23 14:00 | 2013-01-23 14:00 | 2013-02-25 16:00 | 2013-02-26 11:00 | 2013-02-26 11:00 | 2013-05-31 17:00 | 2013-07-02 12:00 | 2013-07-02 12:00 | 874554.2837 | 874554.2837 | 875417.0558 | 881330.0525 | 875417.0558 | 881330.0525 | 874722.5433 | 875683.146 | 0.79963 | 1 | 0.96908 | 0.97039 | -109 | 1 | 1 | 0.79963 | 1
28/02, 2013 | 2013-01-31 17:00 | 2013-02-28 17:00 | 874554.2837 | 847513.3716 | 847513.3716 | 2012-08-31 17:00 | -27040.9121 | 96.91% | 0 | 100% | -129d | 77.13% | 97.04% | 2013-01-23 09:00 | 2013-01-23 14:00 | 2013-01-23 14:00 | 2013-03-26 12:00 | 2013-03-26 17:00 | 2013-03-26 17:00 | 2013-06-28 17:00 | 2013-08-05 12:00 | 2013-08-05 12:00 | 874554.2837 | 874554.2837 | 875417.0558 | 882573.3128 | 875417.0558 | 882573.3128 | 874722.5433 | 875850.5593 | 0.77128 | 1 | 0.96908 | 0.97039 | -129 | 1 | 1 | 0.77128 | 1
31/03, 2013 | 2013-02-28 17:00 | 2013-03-31 17:00 | 874554.2837 | 847513.3716 | 847513.3716 | 2012-08-31 17:00 | -27040.9121 | 96.91% | 0 | 100% | -150d | 74.36% | 97.04% | 2013-01-23 09:00 | 2013-01-23 14:00 | 2013-01-23 14:00 | 2013-04-25 09:00 | 2013-04-25 14:00 | 2013-04-25 14:00 | 2013-07-29 17:00 | 2013-09-09 14:00 | 2013-09-09 14:00 | 874554.2837 | 874554.2837 | 875417.0558 | 883878.7361 | 875417.0558 | 883878.7361 | 874722.5433 | 876015.9546 | 0.74359 | 1 | 0.96908 | 0.97039 | -150 | 1 | 1 | 0.74359 | 1
30/04, 2013 | 2013-03-31 17:00 | 2013-04-30 17:00 | 874554.2837 | 870526.8228 | 870526.8228 | 2012-11-30 17:00 | -4027.4609 | 99.54% | 0 | 100% | -107d | 82.37% | 100% | 2013-01-03 11:00 | 2013-01-03 11:00 | 2013-01-03 11:00 | 2013-05-03 15:00 | 2013-05-03 15:00 | 2013-05-03 15:00 | 2013-05-29 17:00 | 2013-06-05 12:00 | 2013-06-05 12:00 | 874554.2837 | 874554.2837 | 874572.9166 | 875416.1603 | 874572.9166 | 875416.1603 | 874557.9965 | 874701.4621 | 0.82372 | 1 | 0.99539 | 1 | -107 | 1 | 1 | 0.82372 | 1
31/05, 2013 | 2013-04-30 17:00 | 2013-05-31 17:00 | 874554.2837 | 870526.8228 | 870526.8228 | 2012-11-30 17:00 | -4027.4609 | 99.54% | 0 | 100% | -130d | 79.37% | 100% | 2013-01-03 11:00 | 2013-01-03 11:00 | 2013-01-03 11:00 | 2013-06-05 16:00 | 2013-06-05 16:00 | 2013-06-05 16:00 | 2013-07-01 17:00 | 2013-07-09 12:00 | 2013-07-09 12:00 | 874554.2837 | 874554.2837 | 874572.9166 | 875601.4235 | 874572.9166 | 875601.4235 | 874557.9965 | 874727.6512 | 0.79365 | 1 | 0.99539 | 1 | -130 | 1 | 1 | 0.79365 | 1
30/06, 2013 | 2013-05-31 17:00 | 2013-06-30 17:00 | 874554.2837 | 870526.8228 | 870526.8228 | 2012-11-30 17:00 | -4027.4609 | 99.54% | 0 | 100% | -150d | 76.92% | 100% | 2013-01-03 11:00 | 2013-01-03 11:00 | 2013-01-03 11:00 | 2013-07-03 17:00 | 2013-07-03 17:00 | 2013-07-03 17:00 | 2013-07-29 17:00 | 2013-08-07 10:00 | 2013-08-07 10:00 | 874554.2837 | 874554.2837 | 874572.9166 | 875762.522 | 874572.9166 | 875762.522 | 874557.9965 | 874749.1608 | 0.76923 | 1 | 0.99539 | 1 | -150 | 1 | 1 | 0.76923 | 1
Actual Schedule | 2013-06-30 17:00 | 2013-07-31 17:00 | 874554.2837 | 874554.2837 | 874554.2837 | 2012-12-31 17:00 | 0 | 100% | 0 | 100% | -152d | 77.41% | 100% | 2012-12-31 17:00 | 2012-12-31 17:00 | 2012-12-31 17:00 | 2013-07-31 17:00 | 2013-07-31 17:00 | 2013-07-31 17:00 | 2013-07-31 17:00 | 2013-07-31 17:00 | 2013-07-31 17:00 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 874554.2837 | 0.77415 | 1 | 1 | 1 | -152 | 1 | 1 | 0.77415 | 1