## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Government Office Building | 1 |  |  | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 | 553.375
456 | werfinrichting | 1.1 |  | FS459 | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 11.375
468 | grondwerken en fundering ondergrondse werken | 1.2 |  |  | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 | 260.375
458 | installatie bronbemaling | 1.2.1 |  | FS459;FS460;FS461 | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 4.375
459 | bronbemaling | 1.2.2 | 458FS;456FS |  | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 253.375
460 | grondwerken toren | 1.2.3 | 458FS | FS465;SS1 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 25.375
461 | voorbereiding secanspalen parking | 1.2.4 | 458FS | FS462 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 25.375
462 | secanspalen parking | 1.2.5 | 461FS | FS463 | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 11.375
463 | grondwerken parking | 1.2.6 | 462FS | SS464;SS457;FS466 | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 30.375
464 | ankers secanspalen eerste rij | 1.2.7 | 463SS |  | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 6.375
457 | ankers secanspalen tweede rij | 1.2.8 | 463SS |  | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 6.375
465 | funderingsplaat gebouw | 1.2.9 | 460FS | FS475 | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 18.375
466 | trekankers funderingsplaat parking | 1.2.10 | 463FS | FS467 | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 11.375
467 | funderingsplaat parking | 1.2.11 | 466FS | FS476 | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 20.375
436 | 100 ruwbouw | 1.3 |  |  | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 | 346.375
416 | 18 radier | 1.3.1 |  |  | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 | 107.375
1 | radier torengebouw | 1.3.1.1 | 460SS | FF2-2d;FS475 | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 42.375
2 | opstellen torenkraan TK2 | 1.3.1.2 | 1FF-2d |  | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 1.375
3 | berlinerwand parking + einde grondwerken | 1.3.1.3 |  | FS4 | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 18.375
4 | trekankers parking | 1.3.1.4 | 3FS | FS5 | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 11.375
5 | radier parking | 1.3.1.5 | 4FS | FF6+2d;FS476 | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 20.375
6 | opstellen torenkraan TK1 in parking | 1.3.1.6 | 5FF+2d |  | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 6.375
475 | 40 ruwbouw boven -2 toren | 1.3.2 | 1FS;465FS | FS477 | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 18.375
476 | 45 ruwbouw boven -2 parking | 1.3.3 | 467FS;5FS | FS478 | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 29.375
477 | 50 ruwbouw boven -1 toren | 1.3.4 | 475FS | FS479 | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 18.375
478 | 55 ruwbouw boven -1 parking | 1.3.5 | 476FS | FS186 | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 33.375
479 | 60 ruwbouw boven gelijkvloers | 1.3.6 | 477FS | FS480 | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 11.375
480 | 70 ruwbouw boven +1 | 1.3.7 | 479FS | FS481 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
481 | 80 ruwbouw boven +2 | 1.3.8 | 480FS | FS482 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 14.375
482 | 90 ruwbouw boven +3 | 1.3.9 | 481FS | FS483 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 15.375
483 | 100 ruwbouw boven +4 | 1.3.10 | 482FS | FS484 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
484 | 110 ruwbouw boven +5 | 1.3.11 | 483FS | FS485;FS189 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
485 | 120 ruwbouw boven +6 | 1.3.12 | 484FS | FS486;FS195 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 34.375
486 | 130 ruwbouw boven +7 | 1.3.13 | 485FS | FS487 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 14.375
487 | 140 ruwbouw boven +8 | 1.3.14 | 486FS | FS488;FS227 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
488 | 150 ruwbouw boven +9 | 1.3.15 | 487FS | FS489 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
489 | 160 ruwbouw boven +10 | 1.3.16 | 488FS | FS490;FF294;FS310-1d | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
490 | 170 ruwbouw boven +11 | 1.3.17 | 489FS | FS491;FS183;FS326-1d | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
491 | 180 ruwbouw boven +12 | 1.3.18 | 490FS | FS492;FS226;FS342-1d | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
492 | 190 ruwbouw boven +13 | 1.3.19 | 491FS | FS493;FS358-1d | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 15.375
493 | 200 ruwbouw boven +14 | 1.3.20 | 492FS | FS182;FS411;FS192;FS374-1d | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 13.375
438 | 150 dak | 1.4 |  |  | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 | 225.375
437 | 301 dakwerken | 1.4.1 |  |  | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 | 225.375
182 | hellingsbeton | 1.4.1.1 | 493FS | FS185 | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 6.375
183 | dakwerken niveau +2 | 1.4.1.2 | 490FS | FS194;FS414 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 6.375
184 | dakwerken gebouw | 1.4.1.3 | 185FS |  | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 34.375
185 | installatie gevelreiniging | 1.4.1.4 | 182FS | FS184;FS287 | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 6.375
186 | dakwerken parkingdak | 1.4.1.5 | 478FS | FS187 | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 34.375
187 | beschermbeton dak | 1.4.1.6 | 186FS | FS390 | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 34.375
440 | 180 gevel | 1.5 |  |  | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 | 282.375
439 | 311 gordijngevel | 1.5.1 |  |  | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 | 282.375
188 | montage hefsteigers | 1.5.1.1 |  | FS190 | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 13.375
189 | gevel 0 - 2 | 1.5.1.2 | 484FS | FS261 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 105.375
190 | gevel 3-5 | 1.5.1.3 | 188FS | FS191;FS197-2w;FS203;SS210+4w;FS219;FS236 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 37.1667
191 | gevel 6-9 | 1.5.1.4 | 190FS | FS192;FS213-2w;FS229-1w 2d;FS251;FS303;FS318 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 41.1667
192 | gevel 9-boven | 1.5.1.5 | 493FS;191FS | FS193;FS357-4w;FS389-2w;FS469-3w;FS399 | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 111.375
193 | afbouw steigers | 1.5.1.6 | 192FS |  | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 20.375
441 | 205 gelijkvloers | 1.6 |  |  | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 | 157.375
274 | pleisterwerken | 1.6.1 | 226FS;275FS | FS293;SS258 | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 7.375
275 | traceren plafond + boren ophangpunten | 1.6.2 | 227FS | FS274;FS276;SS259 | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
276 | technieken in vals plafond | 1.6.3 | 275FS;228FS-1w | FS295-1w;FS296 | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 18.375
277 | gk strook gevel structuur | 1.6.4 | 229FS | FS278;FS360 | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
278 | structuur vp | 1.6.5 | 260FS;261FS;277FS | FS279 | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
279 | technieken in vloer | 1.6.6 | 278FS | FS280 | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 | 6.375
280 | chape | 1.6.7 | 279FS | FS281 | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 | 27.375
281 | plaatsen convectoren | 1.6.8 | 280FS | FS282 | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
282 | afwerking vloeren | 1.6.9 | 281FS |  | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 | 13.375
283 | uitplamuren kolommen | 1.6.10 | 233FS | FS300 | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
284 | metselwerken | 1.6.11 | 259SS | FS291 | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 11.375
285 | binnenwanden | 1.6.12 | 288FS | FS290-4d;FS271-4d | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
286 | sanitaire wanden | 1.6.13 | 398FS | FS268 | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
287 | binnenschrijnwerk | 1.6.14 | 266FS;185FS;267FS-2w 2d;263FS | FS290 | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
288 | dichtleggen vp + gkstrook | 1.6.15 |  | FS285;FS289;FS369 | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
289 | natuursteen inkomhal | 1.6.16 | 288FS | FF290 | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 | 13.375
290 | schilderwerken | 1.6.17 | 287FS;285FS-4d;289FF |  | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
291 | auditorium - verder te detailleren | 1.6.18 | 284FS | FS292 | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 127.375
292 | opkuis | 1.6.19 | 291FS |  | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
442 | 210 eerste verdieping | 1.7 |  |  | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 | 169.375
258 | pleisterwerken | 1.7.1 | 274SS |  | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 7.375
259 | traceren plafond + boren ophangpunten | 1.7.2 | 275SS | FS260;SS265;SS266;SS284 | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
260 | technieken in vals plafond | 1.7.3 | 259FS | FS262;FS278 | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 18.375
261 | gk strook gevel structuur | 1.7.4 | 189FS | FS262;FS278;FS376 | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
262 | structuur vp | 1.7.5 | 260FS;261FS;230FS | SS264;FS263 | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
263 | vloergoten + verhoogde vloer + bekabeling | 1.7.6 | 262FS | FS287;FS269;FS378 | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
264 | plaatsen convectoren | 1.7.7 | 262SS |  | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 11.375
265 | uitplamuren kolommen | 1.7.8 | 259SS |  | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
266 | metselwerken | 1.7.9 | 259SS | FS287;FS269 | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 11.375
267 | binnenwanden | 1.7.10 | 270FS | FS287-2w 2d;FS269-2w 2d;FS271-4d | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
268 | sanitaire wanden | 1.7.11 | 286FS | FS269 | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 4.375
269 | binnenschrijnwerk | 1.7.12 | 266FS;268FS;267FS-2w 2d;263FS | FS271 | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
270 | dichtleggen vp + gkstrook | 1.7.13 |  | FS267;FS271;FS385 | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
271 | schilderwerken | 1.7.14 | 269FS;285FS-4d;270FS;267FS-4d | FS272;FS273 | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
272 | tapijt | 1.7.15 | 271FS | FS273 | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
273 | opkuis | 1.7.16 | 271FS;272FS |  | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
443 | 220 tweede verdieping | 1.8 |  |  | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 | 43.375
414 | tegels | 1.8.1 | 183FS | FS415 | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 14.375
415 | bekleding kernen | 1.8.2 | 414FS |  | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 28.375
444 | 230 derde verdieping | 1.9 |  |  | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 | 226.375
194 | pleisterwerken | 1.9.1 | 195FS;183FS | FS226 | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
195 | traceren plafond + boren ophangpunten | 1.9.2 | 485FS | FS194;FS196;SS201;SS202;FS212;SS218;FS210;SS211;SS217 | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
196 | technieken in vals plafond | 1.9.3 | 195FS | FS198;FS214;FS228-1w | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 18.375
197 | gk strook gevel structuur | 1.9.4 | 190FS-2w | FS198;FS214;FS229 | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 4.375
198 | structuur vp | 1.9.5 | 196FS;197FS | FS230;FS199;SS200;FS215 | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 5.375
199 | vloergoten + verhoogde vloer + bekabeling | 1.9.6 | 198FS | FS205;FS206;FS222;FS231 | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
200 | plaatsen convectoren | 1.9.7 | 198SS |  | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
201 | uitplamuren kolommen | 1.9.8 | 195SS |  | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 3.375
202 | metselwerken | 1.9.9 | 195SS | FS205 | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
203 | binnenwanden | 1.9.10 | 190FS;206FS |  | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 19.375
204 | sanitaire wanden | 1.9.11 |  |  | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
205 | binnenschrijnwerk | 1.9.12 | 202FS;199FS | FS207 | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
206 | dichtleggen vp + gkstrook | 1.9.13 | 199FS | FS203;FS207;FS223;FS238 | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
207 | schilderwerken | 1.9.14 | 205FS;206FS | FS208;FS224 | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 27.375
208 | tapijt | 1.9.15 | 207FS | FS209 | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
209 | opkuis | 1.9.16 | 208FS |  | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
445 | 240 vierde verdieping | 1.10 |  |  | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 | 139.375
210 | pleisterwerken | 1.10.1 | 195FS;190SS+4w | FS242 | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
211 | traceren plafond + boren ophangpunten | 1.10.2 | 195SS | FS212 | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
212 | technieken in vals plafond | 1.10.3 | 195FS;211FS | FS214 | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 18.375
213 | gk strook gevel structuur | 1.10.4 | 191FS-2w | FS245 | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 4.375
214 | structuur vp | 1.10.5 | 196FS;197FS;212FS | SS216 | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 5.375
215 | vloergoten + verhoogde vloer + bekabeling | 1.10.6 | 198FS | FS247;FS221 | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
216 | plaatsen convectoren | 1.10.7 | 214SS |  | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
217 | uitplamuren kolommen | 1.10.8 | 195SS |  | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 3.375
218 | metselwerken | 1.10.9 | 195SS | FS221 | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
219 | binnenwanden | 1.10.10 | 190FS;222FS |  | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 19.375
220 | sanitaire wanden | 1.10.11 |  | FS235 | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
221 | binnenschrijnwerk | 1.10.12 | 215FS;218FS | FS223 | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
222 | dichtleggen vp + gkstrook | 1.10.13 | 199FS | FS219;FS254 | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
223 | schilderwerken | 1.10.14 | 206FS;221FS | FS224 | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 27.375
224 | tapijt | 1.10.15 | 223FS;207FS | FS225 | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
225 | opkuis | 1.10.16 | 224FS |  | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
446 | 250 vijfde verdieping | 1.11 |  |  | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 | 160.375
226 | pleisterwerken | 1.11.1 | 194FS;491FS;227FS | FS293;FS274 | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 7.375
227 | traceren plafond + boren ophangpunten | 1.11.2 | 487FS | FS275;FS226;FS228;SS233;SS234;SS243;SS249;SS250 | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
228 | technieken in vals plafond | 1.11.3 | 227FS;196FS-1w | FS230;FS276-1w;FS246 | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 18.375
229 | gk strook gevel structuur | 1.11.4 | 191FS-1w 2d;197FS | FS277;FS246 | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
230 | structuur vp | 1.11.5 | 228FS;198FS | FS262;FS231;SS232 | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
231 | vloergoten + verhoogde vloer + bekabeling | 1.11.6 | 230FS;199FS | FS237;FS298 | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 27.375
232 | plaatsen convectoren | 1.11.7 | 230SS |  | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
233 | uitplamuren kolommen | 1.11.8 | 227SS | FS283 | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
234 | metselwerken | 1.11.9 | 227SS | FS237 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
235 | sanitaire wanden | 1.11.10 | 220FS | FS252 | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 4.375
236 | binnenwanden | 1.11.11 | 190FS;238FS |  | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
237 | binnenschrijnwerk | 1.11.12 | 234FS;231FS | FS239 | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
238 | dichtleggen vp + gkstrook | 1.11.13 | 206FS | FS236;FS239;FS255;FS305 | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
239 | schilderwerken | 1.11.14 | 237FS;238FS | FS240;FS256 | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
240 | tapijt | 1.11.15 | 239FS | FS241 | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
241 | opkuis | 1.11.16 | 240FS |  | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
447 | 260 zesde verdieping | 1.12 |  |  | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 | 160.375
242 | pleisterwerken | 1.12.1 | 210FS | FS309 | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 7.375
243 | traceren plafond + boren ophangpunten | 1.12.2 | 227SS | FS244;FS294;FS310 | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
244 | technieken in vals plafond | 1.12.3 | 243FS |  | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 18.375
245 | gk strook gevel structuur | 1.12.4 | 213FS | FS312;FS246 | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
246 | structuur vp | 1.12.5 | 228FS;245FS;229FS | FS247;SS248 | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
247 | vloergoten + verhoogde vloer + bekabeling | 1.12.6 | 246FS;215FS | FS314;FS253 | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 27.375
248 | plaatsen convectoren | 1.12.7 | 246SS |  | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
249 | uitplamuren kolommen | 1.12.8 | 227SS |  | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
250 | metselwerken | 1.12.9 | 227SS | FS253 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
251 | binnenwanden | 1.12.10 | 191FS;254FS |  | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
252 | sanitaire wanden | 1.12.11 | 235FS | FS302 | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
253 | binnenschrijnwerk | 1.12.12 | 250FS;247FS | FS255 | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
254 | dichtleggen vp + gkstrook | 1.12.13 | 222FS | FS251;FS321 | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
255 | schilderwerken | 1.12.14 | 253FS;238FS | FS256 | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
256 | tapijt | 1.12.15 | 239FS;255FS | FS257 | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
257 | opkuis | 1.12.16 | 256FS |  | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
448 | 270 zevende verdieping | 1.13 |  |  | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 | 160.375
293 | pleisterwerken | 1.13.1 | 226FS;274FS | FS325 | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
294 | traceren plafond + boren ophangpunten | 1.13.2 | 243FS;489FF | FS295;SS300;SS301;SS316;SS317 | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
295 | technieken in vals plafond | 1.13.3 | 294FS;276FS-1w | FS297;FS313 | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 22.375
296 | gk strook gevel structuur | 1.13.4 | 276FS | FS313;FS328 | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 4.375
297 | structuur vp | 1.13.5 | 295FS | SS299;FS298 | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 5.375
298 | vloergoten + verhoogde vloer + bekabeling | 1.13.6 | 231FS;297FS | FS304;FS330 | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
299 | plaatsen convectoren | 1.13.7 | 297SS |  | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
300 | uitplamuren kolommen | 1.13.8 | 294SS;283FS |  | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
301 | metselwerken | 1.13.9 | 294SS | FS304 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
302 | sanitaire wanden | 1.13.10 | 252FS | FS319 | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 4.375
303 | binnenwanden | 1.13.11 | 305FS;191FS |  | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
304 | binnenschrijnwerk | 1.13.12 | 301FS;298FS | FS306 | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
305 | dichtleggen vp + gkstrook | 1.13.13 | 238FS | FS306;FS322;FS303;FS337 | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
306 | schilderwerken | 1.13.14 | 304FS;305FS | FS307;FS323 | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
307 | tapijt | 1.13.15 | 306FS | FS308 | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
308 | opkuis | 1.13.16 | 307FS |  | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
449 | 280 achtste verdieping | 1.14 |  |  | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 | 160.375
309 | pleisterwerken | 1.14.1 | 242FS | FS341 | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
310 | traceren plafond + boren ophangpunten | 1.14.2 | 243FS;489FS-1d | FS311;FS326 | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
311 | technieken in vals plafond | 1.14.3 | 310FS |  | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 22.375
312 | gk strook gevel structuur | 1.14.4 | 245FS | FS344;FS313 | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 4.375
313 | structuur vp | 1.14.5 | 295FS;312FS;296FS | FS314;SS315 | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 5.375
314 | vloergoten + verhoogde vloer + bekabeling | 1.14.6 | 313FS;247FS | FS346;FS320 | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
315 | plaatsen convectoren | 1.14.7 | 313SS |  | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
316 | uitplamuren kolommen | 1.14.8 | 294SS |  | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
317 | metselwerken | 1.14.9 | 294SS | FS320 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
318 | binnenwanden | 1.14.10 | 321FS;191FS |  | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
319 | sanitaire wanden | 1.14.11 | 302FS | FS334 | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
320 | binnenschrijnwerk | 1.14.12 | 317FS;314FS | FS322 | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
321 | dichtleggen vp + gkstrook | 1.14.13 | 254FS | FS318;FS353 | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
322 | schilderwerken | 1.14.14 | 320FS;305FS | FS323 | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
323 | tapijt | 1.14.15 | 306FS;322FS | FS324 | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
324 | opkuis | 1.14.16 | 323FS |  | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
450 | 290 negende verdieping | 1.15 |  |  | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 | 146.375
325 | pleisterwerken | 1.15.1 | 293FS | FS357 | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
326 | traceren plafond + boren ophangpunten | 1.15.2 | 310FS;490FS-1d | FS327;SS332;SS333;SS348;SS349;SS342 | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
327 | technieken in vals plafond | 1.15.3 | 326FS | FS329;FS345 | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 21.375
328 | gk strook gevel structuur | 1.15.4 | 296FS | FS329;FS345 | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
329 | structuur vp | 1.15.5 | 327FS;328FS | SS331;FS346;FS330 | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 5.375
330 | vloergoten + verhoogde vloer + bekabeling | 1.15.6 | 329FS;298FS | FS336 | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
331 | plaatsen convectoren | 1.15.7 | 329SS |  | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
332 | uitplamuren kolommen | 1.15.8 | 326SS |  | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 17.375
333 | metselwerken | 1.15.9 | 326SS | FS336 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 15.375
334 | sanitaire wanden | 1.15.10 | 319FS | FS351 | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
335 | binnenwanden | 1.15.11 | 337FS |  | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
336 | binnenschrijnwerk | 1.15.12 | 330FS;333FS | FS338 | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
337 | dichtleggen vp + gkstrook | 1.15.13 | 305FS | FS335;FS338;FS354 | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
338 | schilderwerken | 1.15.14 | 336FS;337FS | FS339;FS340;FS355 | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
339 | tapijt | 1.15.15 | 338FS |  | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
340 | opkuis | 1.15.16 | 338FS |  | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
451 | 300 tiende verdieping | 1.16 |  |  | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 | 146.375
341 | pleisterwerken | 1.16.1 | 309FS | FS373 | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
342 | traceren plafond + boren ophangpunten | 1.16.2 | 326SS;491FS-1d | FS343;FS358 | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
343 | technieken in vals plafond | 1.16.3 | 342FS |  | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 21.375
344 | gk strook gevel structuur | 1.16.4 | 312FS | FS345 | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
345 | structuur vp | 1.16.5 | 327FS;344FS;328FS | SS347 | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 5.375
346 | vloergoten + verhoogde vloer + bekabeling | 1.16.6 | 329FS;314FS | FS352 | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
347 | plaatsen convectoren | 1.16.7 | 345SS |  | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
348 | uitplamuren kolommen | 1.16.8 | 326SS |  | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 17.375
349 | metselwerken | 1.16.9 | 326SS | FS352 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 15.375
350 | binnenwanden | 1.16.10 | 353FS |  | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
351 | sanitaire wanden | 1.16.11 | 334FS | FS366 | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 4.375
352 | binnenschrijnwerk | 1.16.12 | 349FS;346FS | FS354 | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 3.375
353 | dichtleggen vp + gkstrook | 1.16.13 | 321FS | FS350 | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
354 | schilderwerken | 1.16.14 | 352FS;337FS | FS355 | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
355 | tapijt | 1.16.15 | 338FS;354FS | FS356 | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
356 | opkuis | 1.16.16 | 355FS |  | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
452 | 310 elfde verdieping | 1.17 |  |  | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 | 130.375
357 | pleisterwerken | 1.17.1 | 325FS;192FS-4w | FS389 | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
358 | traceren plafond + boren ophangpunten | 1.17.2 | 342FS;492FS-1d | FS359;SS364;SS365;SS380;SS381;SS374 | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 4.375
359 | technieken in vals plafond | 1.17.3 | 358FS | FS361;FS377 | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 34.375
360 | gk strook gevel structuur | 1.17.4 | 277FS | FS361;FS377;FS392 | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
361 | structuur vp | 1.17.5 | 359FS;360FS | SS363;FS362 | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
362 | vloergoten + verhoogde vloer + bekabeling | 1.17.6 | 361FS | FS394;FS368 | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
363 | plaatsen convectoren | 1.17.7 | 361SS |  | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 11.375
364 | uitplamuren kolommen | 1.17.8 | 358SS |  | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
365 | metselwerken | 1.17.9 | 358SS | FS368 | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
366 | sanitaire wanden | 1.17.10 | 351FS | FS383 | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
367 | binnenwanden | 1.17.11 | 369FS |  | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
368 | binnenschrijnwerk | 1.17.12 | 362FS;365FS | FS370 | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 5.375
369 | dichtleggen vp + gkstrook | 1.17.13 | 288FS | FS367;FS401;FS370;FS386 | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 11.375
370 | schilderwerken | 1.17.14 | 369FS;368FS | FS371;FS387 | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
371 | tapijt | 1.17.15 | 370FS | FS372 | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
372 | opkuis | 1.17.16 | 371FS |  | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
453 | 320 twaalfde verdieping | 1.18 |  |  | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 | 130.375
373 | pleisterwerken | 1.18.1 | 341FS |  | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
374 | traceren plafond + boren ophangpunten | 1.18.2 | 358SS;493FS-1d | FS375 | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 4.375
375 | technieken in vals plafond | 1.18.3 | 374FS |  | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 34.375
376 | gk strook gevel structuur | 1.18.4 | 261FS | FS377 | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2.375
377 | structuur vp | 1.18.5 | 359FS;360FS;376FS | SS379;FS378 | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
378 | vloergoten + verhoogde vloer + bekabeling | 1.18.6 | 377FS;263FS | FS384 | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 13.375
379 | plaatsen convectoren | 1.18.7 | 377SS |  | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 11.375
380 | uitplamuren kolommen | 1.18.8 | 358SS |  | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
381 | metselwerken | 1.18.9 | 358SS | FS384 | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
382 | binnenwanden | 1.18.10 | 385FS |  | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 5.375
383 | sanitaire wanden | 1.18.11 | 366FS | FS398 | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 18.375
384 | binnenschrijnwerk | 1.18.12 | 381FS;378FS | FS386 | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 5.375
385 | dichtleggen vp + gkstrook | 1.18.13 | 270FS | FS382 | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 11.375
386 | schilderwerken | 1.18.14 | 369FS;384FS | FS387;FS413 | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
387 | tapijt | 1.18.15 | 370FS;386FS | FS388 | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 4.375
388 | opkuis | 1.18.16 | 387FS |  | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
454 | 330 dertiende verdieping | 1.19 |  |  | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 | 187.375
389 | pleisterwerken | 1.19.1 | 192FS-2w;357FS |  | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 6.375
390 | traceren plafond + boren ophangpunten | 1.19.2 | 187FS | FS391;SS396;SS397 | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2.375
391 | technieken in vals plafond | 1.19.3 | 390FS | FS393 | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 34.375
392 | gk strook gevel structuur | 1.19.4 | 360FS | FS393 | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 4.375
393 | structuur vp | 1.19.5 | 391FS;392FS | FS394;SS395 | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 3.375
394 | vloergoten + verhoogde vloer + bekabeling | 1.19.6 | 393FS;362FS | FS400 | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 11.375
395 | plaatsen convectoren | 1.19.7 | 393SS |  | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 13.375
396 | uitplamuren kolommen | 1.19.8 | 390SS |  | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 1.375
397 | metselwerken | 1.19.9 | 390SS | FS400 | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
398 | sanitaire wanden | 1.19.10 | 383FS | FS286 | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2.375
399 | binnenwanden | 1.19.11 | 401FS;192FS | FS402-4d | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 3.375
400 | binnenschrijnwerk | 1.19.12 | 394FS;397FS | FS402 | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 5.375
401 | dichtleggen vp + gkstrook | 1.19.13 | 369FS | FS402;FS399 | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 9.375
402 | schilderwerken | 1.19.14 | 401FS;400FS;399FS-4d | FS403 | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 11.375
403 | tapijt | 1.19.15 | 402FS | FS404 | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2.375
404 | verhoorkamer | 1.19.16 | 403FS | FS405 | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 | 18.375
405 | opkuis | 1.19.17 | 404FS |  | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 6.375
455 | 340 veertiende verdieping | 1.20 |  |  | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 | 148
406 | vlottende vloeren | 1.20.1 |  | FS407 | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 20.375
407 | polybetons | 1.20.2 | 406FS | FS408 | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 6.375
408 | machines techn. Ruimtes | 1.20.3 | 407FS | FS410;FS411 | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 13.375
409 | cv operationeel | 1.20.4 |  |  | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
410 | metselwerken | 1.20.5 | 408FS |  | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 13.375
411 | technieken aansluiten | 1.20.6 | 408FS;493FS | FS412 | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 62.375
412 | binnenschrijnwerk | 1.20.7 | 411FS | FS413 | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 5.375
413 | schilderwerken | 1.20.8 | 412FS;386FS |  | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 13.375
469 | buitenaanleg | 1.21 | 192FS-3w |  | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 | 69.375
474 | testen en opleveringen | 1.22 |  |  | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 | 98.375
470 | afregelen niveaus faze 1 tem +6 | 1.22.1 |  | FS471-2w | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 27.375
471 | opleveringen faze 1 | 1.22.2 | 470FS-2w |  | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 27.375
472 | afregelen niveaus faze +2 | 1.22.3 |  |  | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 27.375
473 | opleveringen faze 2 | 1.22.4 |  |  | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 | 34.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Government Office Building | 2816h |  |  |  |  | 99 | 100 | 101
456 | werfinrichting | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
468 | grondwerken en fundering ondergrondse werken | 1240h |  |  |  |  | 99 | 100 | 101
458 | installatie bronbemaling | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
459 | bronbemaling | 1200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
460 | grondwerken toren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
461 | voorbereiding secanspalen parking | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
462 | secanspalen parking | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
463 | grondwerken parking | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
464 | ankers secanspalen eerste rij | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
457 | ankers secanspalen tweede rij | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
465 | funderingsplaat gebouw | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
466 | trekankers funderingsplaat parking | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
467 | funderingsplaat parking | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
436 | 100 ruwbouw | 1720h |  |  |  |  | 99 | 100 | 101
416 | 18 radier | 544h |  |  |  |  | 99 | 100 | 101
1 | radier torengebouw | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | opstellen torenkraan TK2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | berlinerwand parking + einde grondwerken | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | trekankers parking | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | radier parking | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | opstellen torenkraan TK1 in parking | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
475 | 40 ruwbouw boven -2 toren | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
476 | 45 ruwbouw boven -2 parking | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
477 | 50 ruwbouw boven -1 toren | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
478 | 55 ruwbouw boven -1 parking | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
479 | 60 ruwbouw boven gelijkvloers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
480 | 70 ruwbouw boven +1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
481 | 80 ruwbouw boven +2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
482 | 90 ruwbouw boven +3 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
483 | 100 ruwbouw boven +4 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
484 | 110 ruwbouw boven +5 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
485 | 120 ruwbouw boven +6 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
486 | 130 ruwbouw boven +7 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
487 | 140 ruwbouw boven +8 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
488 | 150 ruwbouw boven +9 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
489 | 160 ruwbouw boven +10 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
490 | 170 ruwbouw boven +11 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
491 | 180 ruwbouw boven +12 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
492 | 190 ruwbouw boven +13 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
493 | 200 ruwbouw boven +14 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
438 | 150 dak | 1072h |  |  |  |  | 99 | 100 | 101
437 | 301 dakwerken | 1072h |  |  |  |  | 99 | 100 | 101
182 | hellingsbeton | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | dakwerken niveau +2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | dakwerken gebouw | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
185 | installatie gevelreiniging | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
186 | dakwerken parkingdak | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
187 | beschermbeton dak | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
440 | 180 gevel | 1400h |  |  |  |  | 99 | 100 | 101
439 | 311 gordijngevel | 1400h |  |  |  |  | 99 | 100 | 101
188 | montage hefsteigers | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | gevel 0 - 2 | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | gevel 3-5 | 220h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
191 | gevel 6-9 | 220h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | gevel 9-boven | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | afbouw steigers | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
441 | 205 gelijkvloers | 816h |  |  |  |  | 99 | 100 | 101
274 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
275 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
276 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
277 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
278 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
279 | technieken in vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
280 | chape | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
281 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
282 | afwerking vloeren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
283 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
284 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
285 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
286 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
287 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
288 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
289 | natuursteen inkomhal | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
290 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
291 | auditorium - verder te detailleren | 640h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
292 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
442 | 210 eerste verdieping | 880h |  |  |  |  | 99 | 100 | 101
258 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
259 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
260 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
261 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
262 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
263 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
264 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
265 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
266 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
267 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
268 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
269 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
270 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
271 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
272 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
273 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
443 | 220 tweede verdieping | 240h |  |  |  |  | 99 | 100 | 101
414 | tegels | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
415 | bekleding kernen | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
444 | 230 derde verdieping | 1208h |  |  |  |  | 99 | 100 | 101
194 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
197 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
199 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
200 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
201 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
204 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
205 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
206 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
445 | 240 vierde verdieping | 704h |  |  |  |  | 99 | 100 | 101
210 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
211 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
214 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
216 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
220 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
221 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
222 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
225 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
446 | 250 vijfde verdieping | 824h |  |  |  |  | 99 | 100 | 101
226 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
227 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
228 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
232 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
233 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
234 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
235 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
236 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
237 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
239 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
240 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
241 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
447 | 260 zesde verdieping | 824h |  |  |  |  | 99 | 100 | 101
242 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
243 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
244 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
245 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
246 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
247 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
248 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
249 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
250 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
251 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
252 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
253 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
254 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
255 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
256 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
257 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
448 | 270 zevende verdieping | 824h |  |  |  |  | 99 | 100 | 101
293 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
294 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
295 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
296 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
297 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
298 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
299 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
300 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
301 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
302 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
303 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
304 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
305 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
306 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
307 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
308 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
449 | 280 achtste verdieping | 824h |  |  |  |  | 99 | 100 | 101
309 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
310 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
311 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
312 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
313 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
314 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
315 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
316 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
317 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
318 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
319 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
320 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
321 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
322 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
323 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
324 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
450 | 290 negende verdieping | 744h |  |  |  |  | 99 | 100 | 101
325 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
326 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
327 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
328 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
329 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
330 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
331 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
332 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
333 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
334 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
335 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
336 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
337 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
338 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
339 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
340 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
451 | 300 tiende verdieping | 744h |  |  |  |  | 99 | 100 | 101
341 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
342 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
343 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
344 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
345 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
346 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
347 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
348 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
349 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
350 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
351 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
352 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
353 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
354 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
355 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
356 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
452 | 310 elfde verdieping | 664h |  |  |  |  | 99 | 100 | 101
357 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
358 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
359 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
360 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
361 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
362 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
363 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
364 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
365 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
366 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
367 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
368 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
369 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
370 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
371 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
372 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
453 | 320 twaalfde verdieping | 664h |  |  |  |  | 99 | 100 | 101
373 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
374 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
375 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
376 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
377 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
378 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
379 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
380 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
381 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
382 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
383 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
384 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
385 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
386 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
387 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
388 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
454 | 330 dertiende verdieping | 992h |  |  |  |  | 99 | 100 | 101
389 | pleisterwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
390 | traceren plafond + boren ophangpunten | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
391 | technieken in vals plafond | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
392 | gk strook gevel structuur | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
393 | structuur vp | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
394 | vloergoten + verhoogde vloer + bekabeling | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
395 | plaatsen convectoren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
396 | uitplamuren kolommen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
397 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
398 | sanitaire wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
399 | binnenwanden | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
400 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
401 | dichtleggen vp + gkstrook | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
402 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
403 | tapijt | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
404 | verhoorkamer | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
405 | opkuis | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
455 | 340 veertiende verdieping | 768h |  |  |  |  | 99 | 100 | 101
406 | vlottende vloeren | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
407 | polybetons | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
408 | machines techn. Ruimtes | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
409 | cv operationeel | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
410 | metselwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
411 | technieken aansluiten | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
412 | binnenschrijnwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
413 | schilderwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
469 | buitenaanleg | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
474 | testen en opleveringen | 568h |  |  |  |  | 99 | 100 | 101
470 | afregelen niveaus faze 1 tem +6 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
471 | opleveringen faze 1 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
472 | afregelen niveaus faze +2 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
473 | opleveringen faze 2 | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2008-12-31 17:00 |  | TP Name | 31/12, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 15d | [5 empty] | 1111851.0845 |  | 5.195% |  | 1009398.6581 | 1018793.3984
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 10d | [5 empty] | 149342.8579 |  | 26.67% |  | 142296.6581 | 142296.6581
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 5d | 27227.4199 | 0 | 145d | 5824.0298 | 0 | 33051.4497 | 0 | 3.333% | Started | 27227.4199 | 27227.4199 | 100 | 3.3333 | 3.3333 | 100 | 121.3903 | 3.3333
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 5d | 104828.3281 | 0 | 5d | 243.32 | 0 | 105071.6481 | 0 | 50% | Started | 104828.3281 | 104828.3281 | 100 | 50 | 50 | 100 | 100.2321 | 50
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 5d | 9333.3301 | 0 | 5d | 784.72 | 0 | 10118.05 | 0 | 50% | Started | 9333.3301 | 9333.3301 | 100 | 50 | 50 | 100 | 108.4077 | 50
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 |  | 0 | 0 | 9333.3301 | 10d | 0 | 0 | 0 | 9333.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 |  | 0 | 0 | 241105.1562 | 23d | 0 | 0 | 0 | 241105.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 |  | 0 | 0 | 4666.6699 | 5d | 0 | 0 | 0 | 4666.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 |  | 0 | 0 | 4666.5698 | 5d | 0 | 0 | 0 | 4666.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 |  | 0 | 0 | 20710.5293 | 15d | 0 | 0 | 0 | 20710.5293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 |  | 0 | 0 | 90000 | 8d | 0 | 0 | 0 | 90000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 |  | 0 | 0 | 20710.5293 | 15d | 0 | 0 | 0 | 20710.5293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9394.7402
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 9394.7402
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 |  | 0 | 0 | 9394.7402 | 21d | 0 | 0 | 0 | 9394.7402 | 0% | Not Started | 0 | 9394.7402 | 100 |  | 0 | 100 |  | 0
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 |  | 0 | 0 | 26178.6699 | 2d | 0 | 0 | 0 | 26178.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 |  | 0 | 0 | 152015.2188 | 15d | 0 | 0 | 0 | 152015.2188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 |  | 0 | 0 | 90000 | 8d | 0 | 0 | 0 | 90000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 |  | 0 | 0 | 6710.5298 | 15d | 0 | 0 | 0 | 6710.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 |  | 0 | 0 | 45272.3281 | 5d | 0 | 0 | 0 | 45272.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 |  | 0 | 0 | 378979.8125 | 15d | 0 | 0 | 0 | 378979.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 |  | 0 | 0 | 378979.8125 | 15d | 0 | 0 | 0 | 378979.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 |  | 0 | 0 | 232877.5781 | 25d | 0 | 0 | 0 | 232877.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 |  | 0 | 0 | 2053.97 | 10d | 0 | 0 | 0 | 2053.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2009-01-31 17:00 |  | TP Name | 31/01, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 35d | [5 empty] | 1395731.6302 |  | 6.639% |  | 1289942.414 | 1316121.0839
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 30d | [5 empty] | 423013.3035 |  | 77.5% |  | 413445.6738 | 413445.6738
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 25d | 27227.4199 | 0 | 125d | 5824.0298 | 0 | 33051.4497 | 0 | 16.67% | Started | 27227.4199 | 27227.4199 | 100 | 16.6667 | 16.6667 | 100 | 121.3903 | 16.6667
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 5d | 241105.1562 | 0 | 18d | 559.63 | 0 | 241664.7863 | 0 | 21.74% | Started | 241105.1562 | 241105.1562 | 100 | 21.7391 | 21.7391 | 100 | 100.2321 | 21.7391
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 |  | 0 | 0 | 4666.6699 | 5d | 0 | 0 | 0 | 4666.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 |  | 0 | 0 | 4666.5698 | 5d | 0 | 0 | 0 | 4666.5698 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 |  | 0 | 0 | 90000 | 8d | 0 | 0 | 0 | 90000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 |  | 0 | 0 | 20710.5293 | 15d | 0 | 0 | 0 | 20710.5293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 12d | [5 empty] | 10210.1002 |  | 0.1596% |  | 9394.7402 | 35573.4102
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 12d | [5 empty] | 10210.1002 |  | 2.851% |  | 9394.7402 | 35573.4102
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 12d | 9394.7402 | 0 | 9d | 815.36 | 0 | 10210.1002 | 0 | 57.14% | Started | 9394.7402 | 9394.7402 | 100 | 57.1429 | 57.1429 | 100 | 108.6789 | 57.1429
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 |  | 0 | 0 | 26178.6699 | 2d | 0 | 0 | 0 | 26178.6699 | 0% | Not Started | 0 | 26178.6699 | 100 |  | 0 | 100 |  | 0
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 |  | 0 | 0 | 152015.2188 | 15d | 0 | 0 | 0 | 152015.2188 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 |  | 0 | 0 | 90000 | 8d | 0 | 0 | 0 | 90000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 |  | 0 | 0 | 6710.5298 | 15d | 0 | 0 | 0 | 6710.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 |  | 0 | 0 | 45272.3281 | 5d | 0 | 0 | 0 | 45272.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 |  | 0 | 0 | 378979.8125 | 15d | 0 | 0 | 0 | 378979.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 |  | 0 | 0 | 378979.8125 | 15d | 0 | 0 | 0 | 378979.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 |  | 0 | 0 | 232877.5781 | 25d | 0 | 0 | 0 | 232877.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 |  | 0 | 0 | 2053.97 | 10d | 0 | 0 | 0 | 2053.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2009-02-28 17:00 |  | TP Name | 28/02, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 55d | [5 empty] | 2475149.1619 |  | 11.97% |  | 2325429.1674 | 2036449.3549
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 50d | [5 empty] | 523441.8732 |  | 96.12% |  | 512778.9135 | 512778.9135
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 45d | 27227.4199 | 0 | 105d | 5824.0298 | 0 | 33051.4497 | 0 | 30% | Started | 27227.4199 | 27227.4199 | 100 | 30 | 30 | 100 | 121.3903 | 30
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 2d | 90000 | 0 | 6d | 310.61 | 0 | 90310.61 | 0 | 25% | Started | 90000 | 90000 | 100 | 25 | 25 | 100 | 100.3451 | 25
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 |  | 0 | 0 | 20710.5293 | 15d | 0 | 0 | 0 | 20710.5293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 32d | [5 empty] | 989199.0621 |  | 16.06% |  | 945548.2539 | 656568.4414
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 32d | [5 empty] | 189061.6989 |  | 56.92% |  | 187588.6289 | 277588.6289
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 10d | 152015.2188 | 0 | 5d | 959.66 | 0 | 152974.8787 | 0 | 66.67% | Started | 152015.2188 | 152015.2188 | 100 | 66.6667 | 66.6667 | 100 | 100.6313 | 66.6667
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 |  | 0 | 0 | 90000 | 8d | 0 | 0 | 0 | 90000 | 0% | Not Started | 0 | 90000 | 100 |  | 0 | 100 |  | 0
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 |  | 0 | 0 | 6710.5298 | 15d | 0 | 0 | 0 | 6710.5298 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 |  | 0 | 0 | 45272.3281 | 5d | 0 | 0 | 0 | 45272.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 10d | 378979.8125 | 0 | 43d | 21088.8691 | 0 | 400068.6816 | 0 | 18.87% | Started | 378979.8125 | 378979.8125 | 100 | 66.6667 | 18.8679 | 100 | 105.5646 | 18.8679
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 10d | 378979.8125 | 0 | 46d | 21088.8691 | 0 | 400068.6816 | 0 | 17.86% | Started | 378979.8125 | 0 | 100 | 66.6667 | 17.8571 | 100 | 105.5646 | 17.8571
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 |  | 0 | 0 | 232877.5781 | 25d | 0 | 0 | 0 | 232877.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 |  | 0 | 0 | 2053.97 | 10d | 0 | 0 | 0 | 2053.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2009-03-31 17:00 |  | TP Name | 31/03, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 77d | [5 empty] | 2594640.3109 |  | 12.57% |  | 2442850.2265 | 3246082.164
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 72d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 67d | 27227.4199 | 0 | 83d | 5824.0298 | 0 | 33051.4497 | 0 | 44.67% | Started | 27227.4199 | 27227.4199 | 100 | 44.6667 | 44.6667 | 100 | 121.3903 | 44.6667
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 54d | [5 empty] | 1086802.6019 |  | 17.7% |  | 1042258.7837 | 1845490.7212
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 54d | [5 empty] | 286665.2386 |  | 86.26% |  | 284299.1587 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 9d | 6710.5298 | 0 | 6d | 582.4 | 0 | 7292.9298 | 0 | 60% | Started | 6710.5298 | 6710.5298 | 100 | 60 | 60 | 100 | 108.6789 | 60
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 |  | 0 | 0 | 45272.3281 | 5d | 0 | 0 | 0 | 45272.3281 | 0% | Not Started | 0 | 45272.3281 | 100 |  | 0 | 100 |  | 0
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 32d | 378979.8125 | 0 | 21d | 21088.8691 | 0 | 400068.6816 | 0 | 60.38% | Started | 378979.8125 | 378979.8125 | 100 | 213.3333 | 60.3774 | 100 | 105.5646 | 60.3774
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 505306.4062 | 100 |  | 0 | 100 |  | 0
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 32d | 378979.8125 | 0 | 24d | 21088.8691 | 0 | 400068.6816 | 0 | 57.14% | Started | 378979.8125 | 378979.8125 | 100 | 213.3333 | 57.1429 | 100 | 105.5646 | 57.1429
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 |  | 0 | 0 | 505306.4062 | 20d | 0 | 0 | 0 | 505306.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 252653.2031 | 100 |  | 0 | 100 |  | 0
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 |  | 0 | 0 | 232877.5781 | 25d | 0 | 0 | 0 | 232877.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 |  | 0 | 0 | 2053.97 | 10d | 0 | 0 | 0 | 2053.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2009-04-30 17:00 |  | TP Name | 30/04, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 97d | [5 empty] | 3973669.0151 |  | 19.31% |  | 3751388.5703 | 4256694.9765
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 92d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 87d | 27227.4199 | 0 | 63d | 5824.0298 | 0 | 33051.4497 | 0 | 58% | Started | 27227.4199 | 27227.4199 | 100 | 58 | 58 | 100 | 121.3903 | 58
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 74d | [5 empty] | 2465831.3062 |  | 39.93% |  | 2350797.1274 | 2856103.5337
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 52d | 378979.8125 | 0 | 1d | 21088.8691 | 0 | 400068.6816 | 0 | 98.11% | Started | 378979.8125 | 378979.8125 | 100 | 346.6667 | 98.1132 | 100 | 105.5646 | 98.1132
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 14d | 505306.4062 | 0 | 14d | 28118.4902 | 0 | 533424.8965 | 0 | 50% | Started | 505306.4062 | 505306.4062 | 100 | 70 | 50 | 100 | 105.5646 | 50
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 52d | 378979.8125 | 0 | 4d | 21088.8691 | 0 | 400068.6816 | 0 | 92.86% | Started | 378979.8125 | 378979.8125 | 100 | 346.6667 | 92.8571 | 100 | 105.5646 | 92.8571
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 14d | 505306.4062 | 0 | 28d | 28118.4902 | 0 | 533424.8965 | 0 | 33.33% | Started | 505306.4062 | 505306.4062 | 100 | 70 | 33.3333 | 100 | 105.5646 | 33.3333
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 15d | 252653.2031 | 0 | 6d | 14059.25 | 0 | 266712.4531 | 0 | 71.43% | Started | 252653.2031 | 252653.2031 | 100 | 150 | 71.4286 | 100 | 105.5646 | 71.4286
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 252653.2031 | 100 |  | 0 | 100 |  | 0
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 252653.2031 | 100 |  | 0 | 100 |  | 0
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 |  | 0 | 0 | 232877.5781 | 25d | 0 | 0 | 0 | 232877.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 |  | 0 | 0 | 2053.97 | 10d | 0 | 0 | 0 | 2053.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2009-05-31 17:00 |  | TP Name | 31/05, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 115d | [5 empty] | 4507093.9214 |  | 21.91% |  | 4256694.9765 | 4509348.1796
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 110d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 105d | 27227.4199 | 0 | 45d | 5824.0298 | 0 | 33051.4497 | 0 | 70% | Started | 27227.4199 | 27227.4199 | 100 | 70 | 70 | 100 | 121.3903 | 70
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 92d | [5 empty] | 2999256.2124 |  | 48.51% |  | 2856103.5337 | 3108756.7368
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 32d | 505306.4062 | 0 | 10d | 28118.4902 | 0 | 533424.8965 | 0 | 76.19% | Started | 505306.4062 | 505306.4062 | 100 | 160 | 76.1905 | 100 | 105.5646 | 76.1905
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 7d | 252653.2031 | 0 | 3d | 14059.25 | 0 | 266712.4531 | 0 | 70% | Started | 252653.2031 | 252653.2031 | 100 | 70 | 70 | 100 | 105.5646 | 70
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 252653.2031 | 100 |  | 0 | 100 |  | 0
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 |  | 0 | 0 | 232877.5781 | 25d | 0 | 0 | 0 | 232877.5781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 |  | 0 | 0 | 2053.97 | 10d | 0 | 0 | 0 | 2053.97 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2009-06-30 17:00 |  | TP Name | 30/06, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 136d | [5 empty] | 5539355.0388 |  | 27.02% |  | 5249586.134 | 6572151.3671
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 131d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 126d | 27227.4199 | 0 | 24d | 5824.0298 | 0 | 33051.4497 | 0 | 84% | Started | 27227.4199 | 27227.4199 | 100 | 84 | 84 | 100 | 121.3903 | 84
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 113d | [5 empty] | 3799393.5718 |  | 61.38% |  | 3614063.1431 | 3866716.3462
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 2d | 252653.2031 | 0 | 6d | 14059.25 | 0 | 266712.4531 | 0 | 25% | Started | 252653.2031 | 252653.2031 | 100 | 20 | 25 | 100 | 105.5646 | 25
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 252653.2031 | 100 |  | 0 | 100 |  | 0
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 11d | [5 empty] | 229681.5181 |  | 38.95% |  | 232877.5781 | 232877.5781
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 11d | [5 empty] | 229681.5181 |  | 38.95% |  | 232877.5781 | 232877.5781
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 11d | 232877.5781 | 0 | 9d | -3196.0601 | 0 | 229681.5181 | 0 | 55% | Started | 232877.5781 | 232877.5781 | 100 | 44 | 55 | 100 | 98.6276 | 55
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 2d | [5 empty] | 2442.24 |  | 0.06205% |  | 2053.97 | 1071966
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 2d | [5 empty] | 2442.24 |  | 0.06205% |  | 2053.97 | 1071966
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 2d | 2053.97 | 0 | 8d | 388.27 | 0 | 2442.24 | 0 | 20% | Started | 2053.97 | 0 | 100 | 20 | 20 | 100 | 118.9034 | 20
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2009-08-03 09:00 |  | TP Name | 31/07, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 151d | [5 empty] | 6339492.3982 |  | 30.92% |  | 6007545.7433 | 6592631.7968
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 139d 1h | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 134d | 27227.4199 | 0 | 16d | 5824.0298 | 0 | 33051.4497 | 0 | 89.33% | Started | 27227.4199 | 27227.4199 | 100 | 89.3333 | 89.3333 | 100 | 121.3903 | 89.3333
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 128d | [5 empty] | 4599530.9312 |  | 74.25% |  | 4372022.7524 | 3866716.3462
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 0 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 1d | 252653.2031 | 0 | 7d | 14059.25 | 0 | 266712.4531 | 0 | 12.5% | Started | 252653.2031 | 0 | 100 | 10 | 12.5 | 100 | 105.5646 | 12.5
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 19d 1h | [5 empty] | 229681.5181 |  | 38.95% |  | 232877.5781 | 253358.0078
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 19d 1h | [5 empty] | 229681.5181 |  | 38.95% |  | 232877.5781 | 253358.0078
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 19d | 232877.5781 | 0 | 1d | -3196.0601 | 0 | 229681.5181 | 0 | 95% | Started | 232877.5781 | 232877.5781 | 100 | 76 | 95 | 100 | 98.6276 | 95
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 |  | 0 | 0 | 20480.4297 | 10d | 0 | 0 | 0 | 20480.4297 | 0% | Not Started | 0 | 20480.4297 | 100 |  | 0 | 100 |  | 0
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 10d 1h | [5 empty] | 2442.24 |  | 0.06205% |  | 2053.97 | 1071966
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 10d 1h | [5 empty] | 2442.24 |  | 0.06205% |  | 2053.97 | 1071966
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 0 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2009-08-31 17:00 |  | TP Name | 31/08, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 164d | [5 empty] | 8029808.3377 |  | 39.91% |  | 7753530.1916 | 7099992.173
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 141d | [5 empty] | 5132955.8374 |  | 82.84% |  | 4877329.1587 | 4372022.7524
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 0 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 5d | 252653.2031 | 0 | 3d | 14059.25 | 0 | 266712.4531 | 0 | 62.5% | Started | 252653.2031 | 0 | 100 | 50 | 62.5 | 100 | 105.5646 | 62.5
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 39d | [5 empty] | 250550.2177 |  | 42.38% |  | 253358.0078 | 253358.0078
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 39d | [5 empty] | 250550.2177 |  | 42.38% |  | 253358.0078 | 253358.0078
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 30d | [5 empty] | 485203.6902 |  | 14.9% |  | 493371.72 | 1074019.97
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 30d | [5 empty] | 485203.6902 |  | 14.9% |  | 493371.72 | 1074019.97
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 20d | 491317.75 | 0 | 22d | -8556.2998 | 0 | 482761.4502 | 0 | 47.62% | Started | 491317.75 | 0 | 100 | 72.7273 | 47.619 | 100 | 98.2585 | 47.619
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 14d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 11d | 88472.6172 | 0 | 14d | 7360.98 | 0 | 95833.5972 | 0 | 44% | Started | 88472.6172 | 0 | 100 | 73.3333 | 44 | 100 | 108.3201 | 44
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 14d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 8d | 88472.6172 | 0 | 7d | 7360.98 | 0 | 95833.5972 | 0 | 53.33% | Started | 88472.6172 | 0 | 100 | 53.3333 | 53.3333 | 100 | 108.3201 | 53.3333
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 8d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 5d | 88472.6172 | 0 | 10d | 7360.98 | 0 | 95833.5972 | 0 | 33.33% | Started | 88472.6172 | 0 | 100 | 33.3333 | 33.3333 | 100 | 108.3201 | 33.3333
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 8d | 24999.8008 | 0 | 2d | -3252.5 | 0 | 21747.3008 | 0 | 80% | Started | 24999.8008 | 0 | 100 | 80 | 80 | 100 | 86.9899 | 80
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 8d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 2d | 88472.6172 | 0 | 13d | 7360.98 | 0 | 95833.5972 | 0 | 13.33% | Started | 88472.6172 | 0 | 100 | 13.3333 | 13.3333 | 100 | 108.3201 | 13.3333
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 8d | 24999.8008 | 0 | 2d | -3252.5 | 0 | 21747.3008 | 0 | 80% | Started | 24999.8008 | 0 | 100 | 80 | 80 | 100 | 86.9899 | 80
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 2d | [5 empty] | 48683.7228 |  | 12.33% |  | 69061.3325 | 0
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 2d | 39378.6016 | 0 | 1d | -17202.7598 | 0 | 22175.8418 | 0 | 66.67% | Started | 39378.6016 | 0 | 100 | 66.6667 | 66.6667 | 100 | 56.3144 | 66.6667
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 2d | 24999.8008 | 0 | 8d | -3252.5 | 0 | 21747.3008 | 0 | 20% | Started | 24999.8008 | 0 | 100 | 20 | 20 | 100 | 86.9899 | 20
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 2d | [5 empty] | 26507.881 |  | 5.301% |  | 29682.731 | 0
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 2d | 24999.8008 | 0 | 8d | -3252.5 | 0 | 21747.3008 | 0 | 20% | Started | 24999.8008 | 0 | 100 | 20 | 20 | 100 | 86.9899 | 20
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2009-09-30 17:00 |  | TP Name | 30/09, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 186d 1h | [5 empty] | 9332823.373 |  | 46.54% |  | 9042881.5363 | 9218188.2199
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 163d | [5 empty] | 5933093.1968 |  | 95.71% |  | 5635288.7681 | 5129982.3618
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 0 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 3d | 252653.2031 | 0 | 5d | 14059.25 | 0 | 266712.4531 | 0 | 37.5% | Started | 252653.2031 | 0 | 100 | 30 | 37.5 | 100 | 105.5646 | 37.5
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 |  | 0 | 0 | 252653.2031 | 10d | 0 | 0 | 0 | 252653.2031 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 61d | [5 empty] | 250550.2177 |  | 42.38% |  | 253358.0078 | 253358.0078
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 61d | [5 empty] | 250550.2177 |  | 42.38% |  | 253358.0078 | 253358.0078
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 |  | 0 | 0 | 66991.6562 | 5d | 0 | 0 | 0 | 66991.6562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 |  | 0 | 0 | 46575.5195 | 5d | 0 | 0 | 0 | 46575.5195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 |  | 0 | 0 | 139726.5469 | 15d | 0 | 0 | 0 | 139726.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 52d 1h | [5 empty] | 485203.6902 |  | 14.9% |  | 493371.72 | 1565337.72
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 52d 1h | [5 empty] | 485203.6902 |  | 14.9% |  | 493371.72 | 1565337.72
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 |  | 0 | 0 | 491317.75 | 27d 4h | 0 | 0 | 0 | 491317.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 64379.4023
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 39378.6016 | 100 |  | 0 | 100 |  | 0
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 24999.8008 | 100 |  | 0 | 100 |  | 0
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 64378.4023
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 39378.6016 | 100 |  | 0 | 100 |  | 0
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 24999.8008 | 100 |  | 0 | 100 |  | 0
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 |  | 0 | 0 | 14638.2695 | 10d | 0 | 0 | 0 | 14638.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 36d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 36d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 30d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 30d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 24d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 64378.4023
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 24d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 64378.4023
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 12d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 9d | 88472.6172 | 0 | 6d | 7360.98 | 0 | 95833.5972 | 0 | 60% | Started | 88472.6172 | 0 | 100 | 60 | 60 | 100 | 108.3201 | 60
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 12d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 1d | 88472.6172 | 0 | 14d | 7360.98 | 0 | 95833.5972 | 0 | 6.667% | Started | 88472.6172 | 0 | 100 | 6.6667 | 6.6667 | 100 | 108.3201 | 6.6667
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 |  | 0 | 0 | 39378.6016 | 3d | 0 | 0 | 0 | 39378.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 |  | 0 | 0 | 4682.9302 | 2d | 0 | 0 | 0 | 4682.9302 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 |  | 0 | 0 | 68850 | 15d | 0 | 0 | 0 | 68850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2009-10-31 17:00 |  | TP Name | 31/10, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 208d | [5 empty] | 11044440.211 |  | 55.7% |  | 10822831.613 | 10793119.9191
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5635288.7681
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 0 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 83d | [5 empty] | 501481.2304 |  | 84.75% |  | 506651.7305 | 299933.5273
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 83d | [5 empty] | 501481.2304 |  | 84.75% |  | 506651.7305 | 299933.5273
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 0 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 4d | 139726.5469 | 0 | 11d | -1917.63 | 0 | 137808.9169 | 0 | 26.67% | Started | 139726.5469 | 0 | 100 | 26.6667 | 26.6667 | 100 | 98.6276 | 26.6667
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 |  | 0 | 0 | 91163.3906 | 5d | 0 | 0 | 0 | 91163.3906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 74d | [5 empty] | 967965.1404 |  | 29.75% |  | 984689.47 | 2056655.47
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 74d | [5 empty] | 967965.1404 |  | 29.75% |  | 984689.47 | 2056655.47
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 |  | 0 | 0 | 1250627 | 70d | 0 | 0 | 0 | 1250627 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 4d | [5 empty] | 48683.7228 |  | 13.26% |  | 69061.3325 | 152852.0195
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 1d | 39378.6016 | 0 | 2d | -17202.7598 | 0 | 22175.8418 | 0 | 33.33% | Started | 39378.6016 | 39378.6016 | 100 | 33.3333 | 33.3333 | 100 | 56.3144 | 33.3333
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 |  | 0 | 0 | 88472.6172 | 15d | 0 | 0 | 0 | 88472.6172 | 0% | Not Started | 0 | 88472.6172 | 100 |  | 0 | 100 |  | 0
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 4d | 24999.8008 | 0 | 6d | -3252.5 | 0 | 21747.3008 | 0 | 40% | Started | 24999.8008 | 24999.8008 | 100 | 40 | 40 | 100 | 86.9899 | 40
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 80d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 4d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 1d | 88472.6172 | 0 | 14d | 7360.98 | 0 | 95833.5972 | 0 | 6.667% | Started | 88472.6172 | 88472.6172 | 100 | 6.6667 | 6.6667 | 100 | 108.3201 | 6.6667
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 4d | 24999.8008 | 0 | 6d | -3252.5 | 0 | 21747.3008 | 0 | 40% | Started | 24999.8008 | 24999.8008 | 100 | 40 | 40 | 100 | 86.9899 | 40
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 8d | [5 empty] | 15026.5395 |  | 27.73% |  | 14638.2695 | 14638.2695
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 8d | 14638.2695 | 0 | 2d | 388.27 | 0 | 15026.5395 | 0 | 80% | Started | 14638.2695 | 14638.2695 | 100 | 80 | 80 | 100 | 102.6524 | 80
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 |  | 0 | 0 | 38146.8906 | 20d | 0 | 0 | 0 | 38146.8906 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 58d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 161462.6396
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 58d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 161462.6396
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 52d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 161462.6396
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 52d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 161462.6396
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 46d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 46d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 34d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 64378.4023
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 34d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 64378.4023
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 18d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 18d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 7d | 88472.6172 | 0 | 8d | 7360.98 | 0 | 95833.5972 | 0 | 46.67% | Started | 88472.6172 | 0 | 100 | 46.6667 | 46.6667 | 100 | 108.3201 | 46.6667
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 7d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 4d | 88472.6172 | 0 | 11d | 7360.98 | 0 | 95833.5972 | 0 | 26.67% | Started | 88472.6172 | 0 | 100 | 26.6667 | 26.6667 | 100 | 108.3201 | 26.6667
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 7d | 24999.8008 | 0 | 3d | -3252.5 | 0 | 21747.3008 | 0 | 70% | Started | 24999.8008 | 0 | 100 | 70 | 70 | 100 | 86.9899 | 70
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 9d | [5 empty] | 69432.38 |  | 21.33% |  | 68850 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 9d | 68850 | 0 | 6d | 582.38 | 0 | 69432.38 | 0 | 60% | Started | 68850 | 0 | 100 | 60 | 60 | 100 | 100.8459 | 60
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 |  | 0 | 0 | 64694.3984 | 5d | 0 | 0 | 0 | 64694.3984 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 |  | 0 | 0 | 52474.0508 | 10d | 0 | 0 | 0 | 52474.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2009-11-30 17:00 |  | TP Name | 30/11, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 227d | [5 empty] | 15184272.3171 |  | 73.69% |  | 14317301.6808 | 14017136.3426
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 102d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 366925.1836
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 102d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 366925.1836
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 0 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 8d | 91163.3906 | 0 | 2d | 6225.1099 | 0 | 97388.5005 | 0 | 80% | Started | 91163.3906 | 0 | 100 | 160 | 80 | 100 | 106.8285 | 80
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 93d | [5 empty] | 2196812.4704 |  | 67.52% |  | 2235316.47 | 3307282.47
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 93d | [5 empty] | 2196812.4704 |  | 67.52% |  | 2235316.47 | 3307282.47
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 19d | 1250627 | 0 | 14d | -21779.6699 | 0 | 1228847.3301 | 0 | 57.58% | Started | 1250627 | 1250627 | 100 | 27.1429 | 57.5758 | 100 | 98.2585 | 57.5758
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 23d | [5 empty] | 674792.4449 |  | 30.25% |  | 157534.9497 | 162965.6796
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 544.23 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 957.81 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 13d | 1 | 0 | 67d | 530274.125 | 0 | 530275.125 | 0 | 16.25% | Started | 1 | 1 | 100 | 16.25 | 16.25 | 100 | 53027512.5 | 16.25
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 23d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 350596.3671
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 544.23 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 957.81 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 187631.6875 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 27d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 17d | 38146.8906 | 0 | 3d | 2165.3799 | 0 | 40312.2705 | 0 | 85% | Started | 38146.8906 | 38146.8906 | 100 | 85 | 85 | 100 | 105.6764 | 85
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 77d | [5 empty] | 473414.1261 |  | 80.62% |  | 451457.0073 | 439788.7973
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 2d | 11668.21 | 0 | 6d | 866.15 | 0 | 12534.36 | 0 | 25% | Started | 11668.21 | 0 | 100 | 25 | 25 | 100 | 107.4232 | 25
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 77d | [5 empty] | 473414.1261 |  | 80.62% |  | 451457.0073 | 476990.0864
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 2d | 11668.21 | 0 | 6d | 866.15 | 0 | 12534.36 | 0 | 25% | Started | 11668.21 | 0 | 100 | 25 | 25 | 100 | 107.4232 | 25
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 71d | [5 empty] | 460879.7661 |  | 78.54% |  | 439788.7973 | 387797.6562
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 3d | 8611.6201 | 0 | 2d | 194.13 | 0 | 8805.7501 | 0 | 60% | Started | 8611.6201 | 8611.6201 | 100 | 60 | 60 | 100 | 102.2543 | 60
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 2d | 84509.5 | 0 | 8d | 38412.4688 | 0 | 122921.9688 | 0 | 20% | Started | 84509.5 | 0 | 100 | 20 | 20 | 100 | 145.4534 | 20
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 71d | [5 empty] | 460879.7661 |  | 78.54% |  | 439788.7973 | 387797.6562
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 3d | 8611.6201 | 0 | 2d | 194.13 | 0 | 8805.7501 | 0 | 60% | Started | 8611.6201 | 8611.6201 | 100 | 60 | 60 | 100 | 102.2543 | 60
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 2d | 84509.5 | 0 | 8d | 38412.4688 | 0 | 122921.9688 | 0 | 20% | Started | 84509.5 | 0 | 100 | 20 | 20 | 100 | 145.4534 | 20
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 65d | [5 empty] | 329152.0372 |  | 61.91% |  | 346667.6772 | 199208.1587
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 0 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 65d | [5 empty] | 329152.0472 |  | 61.91% |  | 346667.6772 | 162006.8696
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 0 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 53d | [5 empty] | 329152.0472 |  | 61.91% |  | 346667.6772 | 152851.0195
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 0 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 7d | 187631.6875 | 0 | 3d | -4288.9502 | 0 | 183342.7373 | 0 | 70% | Started | 187631.6875 | 0 | 100 | 70 | 70 | 100 | 97.7142 | 70
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 53d | [5 empty] | 329152.0472 |  | 61.91% |  | 346667.6772 | 152851.0195
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 0 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 7d | 187631.6875 | 0 | 3d | -4288.9502 | 0 | 183342.7373 | 0 | 70% | Started | 187631.6875 | 0 | 100 | 70 | 70 | 100 | 97.7142 | 70
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 37d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 64378.4023
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 37d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 64378.4023
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 26d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 0
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 0 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 0 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 28d | [5 empty] | 187550.2592 |  | 57.64% |  | 186018.4492 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 0 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 0 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 8d | 52474.0508 | 0 | 2d | 755.3 | 0 | 53229.3508 | 0 | 80% | Started | 52474.0508 | 0 | 100 | 80 | 80 | 100 | 101.4394 | 80
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 |  | 0 | 0 | 24999.8008 | 10d | 0 | 0 | 0 | 24999.8008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 |  | 0 | 0 | 75251.5078 | 45d | 0 | 0 | 0 | 75251.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2009-12-31 17:00 |  | TP Name | 31/12, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 243d | [5 empty] | 15851825.6108 |  | 76.26% |  | 14816939.0976 | 15474629.0461
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 139726.5469 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 100% | Finished | 91163.3906 | 91163.3906 | 100 | 200 | 100 | 100 | 106.8285 | 100
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 107d | [5 empty] | 2196812.4704 |  | 67.52% |  | 2235316.47 | 3307282.47
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 107d | [5 empty] | 2196812.4704 |  | 67.52% |  | 2235316.47 | 3307282.47
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 |  | 0 | 0 | 1071966 | 60d | 0 | 0 | 0 | 1071966 | 0% | Not Started | 0 | 1071966 | 100 |  | 0 | 100 |  | 0
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 100% | Finished | 1250627 | 1250627 | 100 | 47.1429 | 100 | 100 | 98.2585 | 100
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 |  | 0 | 0 | 3080.96 | 15d | 0 | 0 | 0 | 3080.96 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 37d | [5 empty] | 674792.4449 |  | 30.25% |  | 157534.9497 | 196440.4992
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 544.23 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 957.81 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 26237.0293 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 2554.8601 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 27d | 1 | 0 | 53d | 530274.125 | 0 | 530275.125 | 0 | 33.75% | Started | 1 | 1 | 100 | 33.75 | 33.75 | 100 | 53027512.5 | 33.75
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 37d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 355279.2973
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 8611.6201 | 100 |  | 0 | 100 |  | 0
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 544.23 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 957.81 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 187631.6875 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 100% | Finished | 38146.8906 | 38146.8906 | 100 | 100 | 100 | 100 | 105.6764 | 100
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 91d | [5 empty] | 571274.895 |  | 91.17% |  | 510536.8465 | 488962.1678
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 100 | 100 | 100 | 1881.0273 | 100
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 0 | 100 | 100 | 100 | 100 | 102.9952 | 100
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 100 | 100 | 100 | 192.0797 | 100
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 15626.6104 | 100 |  | 0 | 100 |  | 0
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 93d | [5 empty] | 571274.895 |  | 91.17% |  | 510536.8465 | 526163.4568
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 15626.6104 | 100 |  | 0 | 100 |  | 0
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 85d | [5 empty] | 511729.6651 |  | 87.26% |  | 488658.2963 | 476990.0864
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 2d | 37201.2891 | 0 | 1d | 1114.25 | 0 | 38315.5391 | 0 | 66.67% | Started | 37201.2891 | 37201.2891 | 100 | 66.6667 | 66.6667 | 100 | 102.9952 | 66.6667
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 85d | [5 empty] | 473414.1261 |  | 80.62% |  | 451457.0073 | 476990.0864
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 79d | [5 empty] | 460879.7561 |  | 78.54% |  | 439788.7973 | 392480.5864
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 6d | 84509.5 | 0 | 4d | 38412.4688 | 0 | 122921.9688 | 0 | 60% | Started | 84509.5 | 0 | 100 | 60 | 60 | 100 | 145.4534 | 60
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 79d | [5 empty] | 460879.7661 |  | 78.54% |  | 439788.7973 | 392480.5864
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 6d | 84509.5 | 0 | 4d | 38412.4688 | 0 | 122921.9688 | 0 | 60% | Started | 84509.5 | 0 | 100 | 60 | 60 | 100 | 145.4534 | 60
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 67d | [5 empty] | 337957.7973 |  | 63.45% |  | 355279.2973 | 194735.2388
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 0 | 100 | 100 | 100 | 100 | 102.2543 | 100
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 0 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 0 | 100 | 100 | 100 | 100 | 97.7142 | 100
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 67d | [5 empty] | 337957.7973 |  | 63.45% |  | 355279.2973 | 194735.2388
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 0 | 100 | 100 | 100 | 100 | 102.2543 | 100
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 0 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 0 | 100 | 100 | 100 | 100 | 97.7142 | 100
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 51d | [5 empty] | 153323.07 |  | 29.67% |  | 166145.5698 | 190052.3086
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 2d | 8611.6201 | 0 | 3d | 194.13 | 0 | 8805.7501 | 0 | 40% | Started | 8611.6201 | 0 | 100 | 40 | 40 | 100 | 102.2543 | 40
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 51d | [5 empty] | 153323.07 |  | 29.67% |  | 166145.5698 | 190052.3086
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 2d | 8611.6201 | 0 | 3d | 194.13 | 0 | 8805.7501 | 0 | 40% | Started | 8611.6201 | 0 | 100 | 40 | 40 | 100 | 102.2543 | 40
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 40d | [5 empty] | 144517.3199 |  | 28.13% |  | 157533.9497 | 152851.0195
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 |  | 0 | 0 | 8611.6201 | 5d | 0 | 0 | 0 | 8611.6201 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 0 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 42d | [5 empty] | 297319.3178 |  | 88.7% |  | 286269.7578 | 0
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 0 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 0 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 100% | Finished | 52474.0508 | 0 | 100 | 100 | 100 | 100 | 101.4394 | 100
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 12d | 24999.8008 | 0 | 3d | -3252.5 | 0 | 21747.3008 | 0 | 80% | Started | 24999.8008 | 0 | 100 | 120 | 80 | 100 | 86.9899 | 80
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 12d | 75251.5078 | 0 | 33d | 12770.25 | 0 | 88021.7578 | 0 | 26.67% | Started | 75251.5078 | 0 | 100 | 26.6667 | 26.6667 | 100 | 116.9701 | 26.6667
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2010-01-31 17:00 |  | TP Name | 31/01, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 261d | [5 empty] | 17911569.3714 |  | 85.51% |  | 16614471.1623 | 16907759.0059
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 139726.5469 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 100% | Finished | 91163.3906 | 91163.3906 | 100 | 200 | 100 | 100 | 106.8285 | 100
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3307282.47
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3307282.47
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 2010-01-04 08:00 | 20d | 1071966 | 0 | 0 | -18668.2891 | 0 | 1053297.7109 | 0 | 100% | Finished | 1071966 | 1071966 | 100 | 33.3333 | 100 | 100 | 98.2585 | 100
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 100% | Finished | 1250627 | 1250627 | 100 | 47.1429 | 100 | 100 | 98.2585 | 100
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 2010-01-04 10:00 | 15d | 3080.96 | 0 | 0 | 582.4 | 0 | 3663.36 | 0 | 100% | Finished | 3080.96 | 0 | 100 | 100 | 100 | 100 | 118.9032 | 100
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 57d | [5 empty] | 696132.555 |  | 34.14% |  | 177814.7798 | 520800.3072
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 544.23 | 100 |  | 0 | 100 |  | 0
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 957.81 | 100 |  | 0 | 100 |  | 0
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 |  | 0 | 0 | 26237.0293 | 5d | 0 | 0 | 0 | 26237.0293 | 0% | Not Started | 0 | 26237.0293 | 100 |  | 0 | 100 |  | 0
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 |  | 0 | 0 | 2554.8601 | 10d | 0 | 0 | 0 | 2554.8601 | 0% | Not Started | 0 | 2554.8601 | 100 |  | 0 | 100 |  | 0
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 187631.6875 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 9851.1602 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 1037.39 | 100 |  | 0 | 100 |  | 0
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 20841.1602 | 100 |  | 0 | 100 |  | 0
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 4d | 11668.21 | 0 | 4d | 866.15 | 0 | 12534.36 | 0 | 50% | Started | 11668.21 | 11668.21 | 100 | 50 | 50 | 100 | 107.4232 | 50
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 |  | 0 | 0 | 18002.3008 | 10d | 0 | 0 | 0 | 18002.3008 | 0% | Not Started | 0 | 18002.3008 | 100 |  | 0 | 100 |  | 0
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 15626.6104 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 47d | 1 | 0 | 33d | 530274.125 | 0 | 530275.125 | 0 | 58.75% | Started | 1 | 1 | 100 | 58.75 | 58.75 | 100 | 53027512.5 | 58.75
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 22500 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 57d | [5 empty] | 165857.43 |  | 31.75% |  | 177813.7798 | 526163.4568
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-14 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 544.23 | 100 |  | 0 | 100 |  | 0
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 957.81 | 100 |  | 0 | 100 |  | 0
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 84509.5 | 100 |  | 0 | 100 |  | 0
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 187631.6875 | 100 |  | 0 | 100 |  | 0
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 1037.39 | 100 |  | 0 | 100 |  | 0
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 20841.1602 | 100 |  | 0 | 100 |  | 0
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 4d | 11668.21 | 0 | 4d | 866.15 | 0 | 12534.36 | 0 | 50% | Started | 11668.21 | 11668.21 | 100 | 50 | 50 | 100 | 107.4232 | 50
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 15626.6104 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 100% | Finished | 38146.8906 | 38146.8906 | 100 | 100 | 100 | 100 | 105.6764 | 100
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 109d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 522770.9373
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 100 | 100 | 100 | 1881.0273 | 100
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 0 | 100 | 100 | 100 | 100 | 102.9952 | 100
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 100 | 100 | 100 | 192.0797 | 100
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-04 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-18 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-01-21 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 111d | [5 empty] | 598788.6049 |  | 95.98% |  | 537472.2264 | 559972.2264
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-06 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-27 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 22500 | 100 |  | 0 | 100 |  | 0
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 105d | [5 empty] | 587363.3553 |  | 93.96% |  | 526163.4568 | 537472.2264
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 8d | 15626.6104 | 0 | 7d | 461.85 | 0 | 16088.4604 | 0 | 53.33% | Started | 15626.6104 | 15626.6104 | 100 | 80 | 53.3333 | 100 | 102.9555 | 53.3333
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 11308.7695 | 100 |  | 0 | 100 |  | 0
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 105d | [5 empty] | 587363.3553 |  | 93.96% |  | 526163.4568 | 537472.2264
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-05 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 8d | 15626.6104 | 0 | 7d | 461.85 | 0 | 16088.4604 | 0 | 53.33% | Started | 15626.6104 | 15626.6104 | 100 | 80 | 53.3333 | 100 | 102.9555 | 53.3333
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 11308.7695 | 100 |  | 0 | 100 |  | 0
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 99d | [5 empty] | 571274.885 |  | 91.17% |  | 510536.8465 | 476990.0864
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-08 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 0 | 100 | 175 | 100 | 100 | 1881.0273 | 100
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 5d | 20841.1602 | 0 | 1d | 19190.4805 | 0 | 40031.6406 | 0 | 83.33% | Started | 20841.1602 | 0 | 100 | 125 | 83.3333 | 100 | 192.0797 | 83.3333
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 99d | [5 empty] | 571274.895 |  | 91.17% |  | 510536.8465 | 476990.0864
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 0 | 100 | 175 | 100 | 100 | 1881.0273 | 100
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-13 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 5d | 20841.1602 | 0 | 1d | 19190.4805 | 0 | 40031.6406 | 0 | 83.33% | Started | 20841.1602 | 0 | 100 | 125 | 83.3333 | 100 | 192.0797 | 83.3333
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 87d | [5 empty] | 531243.2544 |  | 87.45% |  | 489695.6863 | 392480.5864
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 0 | 100 | 100 | 100 | 100 | 145.4534 | 100
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-18 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 4d | 1037.39 | 0 | 3d | 18476.1992 | 0 | 19513.5892 | 0 | 57.14% | Started | 1037.39 | 0 | 100 | 100 | 57.1429 | 100 | 1881.0273 | 57.1429
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 87d | [5 empty] | 531243.2544 |  | 87.45% |  | 489695.6863 | 392480.5864
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 0 | 100 | 100 | 100 | 100 | 145.4534 | 100
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 4d | 1037.39 | 0 | 3d | 18476.1992 | 0 | 19513.5892 | 0 | 57.14% | Started | 1037.39 | 0 | 100 | 100 | 57.1429 | 100 | 1881.0273 | 57.1429
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-21 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 71d | [5 empty] | 191638.6091 |  | 36.31% |  | 203346.8589 | 194735.2388
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 0 | 100 | 100 | 100 | 100 | 102.2543 | 100
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-26 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 71d | [5 empty] | 191638.6091 |  | 36.31% |  | 203346.8589 | 194735.2388
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 0 | 100 | 100 | 100 | 100 | 102.2543 | 100
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-29 08:00 | 1d | 37201.2891 | 0 | 2d | 1114.25 | 0 | 38315.5391 | 0 | 33.33% | Started | 37201.2891 | 37201.2891 | 100 | 33.3333 | 33.3333 | 100 | 102.9952 | 33.3333
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 60d | [5 empty] | 153323.07 |  | 29.67% |  | 166145.5698 | 194735.2388
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 0 | 100 | 100 | 100 | 100 | 102.2543 | 100
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 |  | 0 | 0 | 544.23 | 3d | 0 | 0 | 0 | 544.23 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 |  | 0 | 0 | 957.81 | 4d | 0 | 0 | 0 | 957.81 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 |  | 0 | 0 | 37201.2891 | 3d | 0 | 0 | 0 | 37201.2891 | 0% | Not Started | 0 | 37201.2891 | 100 |  | 0 | 100 |  | 0
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 |  | 0 | 0 | 11668.21 | 8d | 0 | 0 | 0 | 11668.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 62d | [5 empty] | 297319.3178 |  | 88.7% |  | 286269.7578 | 133544.3984
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 68850 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 64694.3984 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 100% | Finished | 52474.0508 | 0 | 100 | 100 | 100 | 100 | 101.4394 | 100
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 15d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 0 | 100 | 150 | 100 | 100 | 86.9899 | 100
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 32d | 75251.5078 | 0 | 13d | 12770.25 | 0 | 88021.7578 | 0 | 71.11% | Started | 75251.5078 | 0 | 100 | 71.1111 | 71.1111 | 100 | 116.9701 | 71.1111
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 |  | 0 | 0 | 194720.8281 | 50d | 0 | 0 | 0 | 194720.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2010-02-28 17:00 |  | TP Name | 28/02, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 281d | [5 empty] | 20222835.0155 |  | 94.92% |  | 18442142.1876 | 18451257.5991
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 139726.5469 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 100% | Finished | 91163.3906 | 91163.3906 | 100 | 200 | 100 | 100 | 106.8285 | 100
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3307282.47
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3307282.47
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 2010-01-04 08:00 | 20d | 1071966 | 0 | 0 | -18668.2891 | 0 | 1053297.7109 | 0 | 100% | Finished | 1071966 | 1071966 | 100 | 33.3333 | 100 | 100 | 98.2585 | 100
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 100% | Finished | 1250627 | 1250627 | 100 | 47.1429 | 100 | 100 | 98.2585 | 100
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 2010-01-04 10:00 | 15d | 3080.96 | 0 | 0 | 582.4 | 0 | 3663.36 | 0 | 100% | Finished | 3080.96 | 0 | 100 | 100 | 100 | 100 | 118.9032 | 100
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 77d | [5 empty] | 859324.7145 |  | 54.76% |  | 285190.8492 | 520800.3072
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 | 2010-02-10 08:00 | 5d | 26237.0293 | 0 | 0 | 589.25 | 0 | 26826.2793 | 0 | 100% | Finished | 26237.0293 | 26237.0293 | 100 | 100 | 100 | 100 | 102.2459 | 100
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 | 2010-02-17 08:00 | 8d | 2554.8601 | 0 | 2d | 388.27 | 0 | 2943.1301 | 0 | 80% | Started | 2554.8601 | 2554.8601 | 100 | 80 | 80 | 100 | 115.1973 | 80
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 |  | 0 | 0 | 187631.6875 | 10d | 0 | 0 | 0 | 187631.6875 | 0% | Not Started | 0 | 187631.6875 | 100 |  | 0 | 100 |  | 0
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 |  | 0 | 0 | 9851.1602 | 10d | 0 | 0 | 0 | 9851.1602 | 0% | Not Started | 0 | 9851.1602 | 100 |  | 0 | 100 |  | 0
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-08 08:00 | 4d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 133.3333 | 100 | 100 | 102.9952 | 100
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 3d | 20841.1602 | 0 | 3d | 19190.4805 | 0 | 40031.6406 | 0 | 50% | Started | 20841.1602 | 20841.1602 | 100 | 75 | 50 | 100 | 192.0797 | 50
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 | 2010-02-05 08:00 | 10d | 18002.3008 | 0 | 0 | 16267.6904 | 0 | 34269.9912 | 0 | 100% | Finished | 18002.3008 | 18002.3008 | 100 | 100 | 100 | 100 | 190.3645 | 100
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 15626.6104 | 100 |  | 0 | 100 |  | 0
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 67d | 1 | 0 | 13d | 530274.125 | 0 | 530275.125 | 0 | 83.75% | Started | 1 | 1 | 100 | 83.75 | 83.75 | 100 | 53027512.5 | 83.75
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 22500 | 100 |  | 0 | 100 |  | 0
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 77d | [5 empty] | 571274.895 |  | 91.17% |  | 510536.8465 | 559972.2264
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-14 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-10 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-04 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-12 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 3d | 20841.1602 | 0 | 3d | 19190.4805 | 0 | 40031.6406 | 0 | 50% | Started | 20841.1602 | 20841.1602 | 100 | 75 | 50 | 100 | 192.0797 | 50
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 15626.6104 | 100 |  | 0 | 100 |  | 0
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 11308.7695 | 100 |  | 0 | 100 |  | 0
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 22500 | 100 |  | 0 | 100 |  | 0
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 100% | Finished | 38146.8906 | 38146.8906 | 100 | 100 | 100 | 100 | 105.6764 | 100
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 109d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 522770.9373
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 100 | 100 | 100 | 1881.0273 | 100
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 0 | 100 | 100 | 100 | 100 | 102.9952 | 100
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 100 | 100 | 100 | 192.0797 | 100
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-04 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-18 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-01-21 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-06 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-27 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-01 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-05 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 119d | [5 empty] | 621482.7249 |  | 100% |  | 559972.2264 | 537472.2264
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-08 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 1d | 22500 | 0 | 4d | 194.13 | 0 | 22694.13 | 0 | 20% | Started | 22500 | 0 | 100 | 20 | 20 | 100 | 100.8628 | 20
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 119d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 537472.2264
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-13 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 1d | 22500 | 0 | 4d | 194.13 | 0 | 22694.13 | 0 | 20% | Started | 22500 | 0 | 100 | 20 | 20 | 100 | 100.8628 | 20
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 107d | [5 empty] | 587363.3553 |  | 93.96% |  | 526163.4568 | 526163.4568
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-18 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 11d | 15626.6104 | 0 | 4d | 461.85 | 0 | 16088.4604 | 0 | 73.33% | Started | 15626.6104 | 15626.6104 | 100 | 110 | 73.3333 | 100 | 102.9555 | 73.3333
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 107d | [5 empty] | 587363.3553 |  | 93.96% |  | 526163.4568 | 526163.4568
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-21 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 11d | 15626.6104 | 0 | 4d | 461.85 | 0 | 16088.4604 | 0 | 73.33% | Started | 15626.6104 | 15626.6104 | 100 | 110 | 73.3333 | 100 | 102.9555 | 73.3333
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 91d | [5 empty] | 531243.2544 |  | 87.45% |  | 489695.6863 | 509499.4565
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-15 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-26 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 8d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 0 | 100 | 200 | 100 | 100 | 1881.0273 | 100
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 20841.1602 | 100 |  | 0 | 100 |  | 0
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 91d | [5 empty] | 531243.2544 |  | 87.45% |  | 489695.6863 | 509499.4565
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-24 08:00 | 3d | 84509.5 | 0 | 7d | 38412.4688 | 0 | 122921.9688 | 0 | 30% | Started | 84509.5 | 84509.5 | 100 | 30 | 30 | 100 | 145.4534 | 30
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 0 | 100 | 175 | 100 | 100 | 1881.0273 | 100
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-29 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 20841.1602 | 100 |  | 0 | 100 |  | 0
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 80d | [5 empty] | 388807.6964 |  | 72.17% |  | 404148.7963 | 194735.2388
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 0 | 100 | 100 | 100 | 100 | 102.2543 | 100
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-09 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 0 | 100 | 100 | 100 | 100 | 32.8685 | 100
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 0 | 100 | 100 | 100 | 100 | 116.2141 | 100
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 |  | 0 | 0 | 84509.5 | 10d | 0 | 0 | 0 | 84509.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 0 | 100 | 100 | 100 | 100 | 97.7142 | 100
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-03 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 |  | 0 | 0 | 1037.39 | 4d | 0 | 0 | 0 | 1037.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 |  | 0 | 0 | 20841.1602 | 4d | 0 | 0 | 0 | 20841.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-17 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 82d | [5 empty] | 337350.9584 |  | 95.16% |  | 307110.918 | 286269.7578
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 68850 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 64694.3984 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 100% | Finished | 52474.0508 | 52474.0508 | 100 | 100 | 100 | 100 | 101.4394 | 100
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 15d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 150 | 100 | 100 | 86.9899 | 100
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 45d | 75251.5078 | 0 | 0 | 12770.25 | 0 | 88021.7578 | 0 | 100% | Finished | 75251.5078 | 75251.5078 | 100 | 100 | 100 | 100 | 116.9701 | 100
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-18 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 0 | 100 | 150 | 100 | 100 | 192.0797 | 100
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 | 2010-02-26 08:00 | 1d | 194720.8281 | 0 | 49d | 133669.8125 | 0 | 328390.6406 | 0 | 2% | Started | 194720.8281 | 194720.8281 | 100 | 2 | 2 | 100 | 168.6469 | 2
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 8d | [5 empty] | 155951.0508 |  | 23.53% |  | 99385.1797 | 99385.1797
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-02-17 08:00 | 8d | 99385.1797 | 0 | 12d | 56565.8711 | 0 | 155951.0508 | 0 | 40% | Started | 99385.1797 | 99385.1797 | 100 | 40 | 40 | 100 | 156.9158 | 40
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2010-03-31 17:00 |  | TP Name | 31/03, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 304d | [5 empty] | 21060797.0238 |  | 98.3% |  | 19100448.7153 | 19049541.6652
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 139726.5469 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 100% | Finished | 91163.3906 | 91163.3906 | 100 | 200 | 100 | 100 | 106.8285 | 100
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3310363.4299
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3310363.4299
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 2010-01-04 08:00 | 20d | 1071966 | 0 | 0 | -18668.2891 | 0 | 1053297.7109 | 0 | 100% | Finished | 1071966 | 1071966 | 100 | 33.3333 | 100 | 100 | 98.2585 | 100
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 100% | Finished | 1250627 | 1250627 | 100 | 47.1429 | 100 | 100 | 98.2585 | 100
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 2010-01-04 10:00 | 15d | 3080.96 | 0 | 0 | 582.4 | 0 | 3663.36 | 0 | 100% | Finished | 3080.96 | 3080.96 | 100 | 100 | 100 | 100 | 118.9032 | 100
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 99d | [5 empty] | 1092383.8923 |  | 100% |  | 520800.3072 | 520800.3072
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 | 2010-02-10 08:00 | 5d | 26237.0293 | 0 | 0 | 589.25 | 0 | 26826.2793 | 0 | 100% | Finished | 26237.0293 | 26237.0293 | 100 | 100 | 100 | 100 | 102.2459 | 100
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 | 2010-02-17 08:00 | 10d | 2554.8601 | 0 | 0 | 388.27 | 0 | 2943.1301 | 0 | 100% | Finished | 2554.8601 | 2554.8601 | 100 | 100 | 100 | 100 | 115.1973 | 100
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-03-03 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 | 2010-03-17 08:00 | 10d | 9851.1602 | 0 | 0 | 1082.6899 | 0 | 10933.8501 | 0 | 100% | Finished | 9851.1602 | 9851.1602 | 100 | 100 | 100 | 100 | 110.9905 | 100
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-08 08:00 | 4d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 133.3333 | 100 | 100 | 102.9952 | 100
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 | 2010-02-05 08:00 | 10d | 18002.3008 | 0 | 0 | 16267.6904 | 0 | 34269.9912 | 0 | 100% | Finished | 18002.3008 | 18002.3008 | 100 | 100 | 100 | 100 | 190.3645 | 100
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 80d | 1 | 0 | 0 | 530274.125 | 0 | 530275.125 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 53027512.5 | 100
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-18 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 99d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-14 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-10 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-04 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-12 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 13d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 130 | 100 | 100 | 102.9555 | 100
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-26 08:00 | 3d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 60 | 100 | 100 | 100.8628 | 100
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 100% | Finished | 38146.8906 | 38146.8906 | 100 | 100 | 100 | 100 | 105.6764 | 100
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 109d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 522770.9373
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 100 | 100 | 100 | 1881.0273 | 100
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 0 | 100 | 100 | 100 | 100 | 102.9952 | 100
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 100 | 100 | 100 | 192.0797 | 100
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-04 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-18 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-01-21 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-06 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-27 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-01 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-05 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7249 |  | 100% |  | 559972.2264 | 559972.2264
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-08 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-13 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-18 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-05 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 119d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-21 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-10 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 114d | [5 empty] | 598788.6049 |  | 95.98% |  | 537472.2264 | 559972.2264
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-15 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-26 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 8d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 200 | 100 | 100 | 1881.0273 | 100
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-01 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-09 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-30 08:00 | 2d | 11308.7695 | 0 | 1d | 116.48 | 0 | 11425.2495 | 0 | 66.67% | Started | 11308.7695 | 11308.7695 | 100 | 66.6667 | 66.6667 | 100 | 101.03 | 66.6667
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 22500 | 100 |  | 0 | 100 |  | 0
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 114d | [5 empty] | 587363.3553 |  | 93.96% |  | 526163.4568 | 559972.2264
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-24 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-29 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-10 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-18 08:00 | 8d | 15626.6104 | 0 | 7d | 461.85 | 0 | 16088.4604 | 0 | 53.33% | Started | 15626.6104 | 15626.6104 | 100 | 80 | 53.3333 | 100 | 102.9555 | 53.3333
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 11308.7695 | 100 |  | 0 | 100 |  | 0
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 22500 | 100 |  | 0 | 100 |  | 0
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 103d | [5 empty] | 587363.3553 |  | 93.96% |  | 526163.4568 | 476990.0864
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-09 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-03-01 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-03 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-03-01 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 0 | 100 | 175 | 100 | 100 | 1881.0273 | 100
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 0 | 100 | 150 | 100 | 100 | 192.0797 | 100
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-17 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 0 | 100 | 100 | 100 | 100 | 107.4232 | 100
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-23 08:00 | 7d | 15626.6104 | 0 | 8d | 461.85 | 0 | 16088.4604 | 0 | 46.67% | Started | 15626.6104 | 0 | 100 | 70 | 46.6667 | 100 | 102.9555 | 46.6667
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 |  | 0 | 0 | 11308.7695 | 3d | 0 | 0 | 0 | 11308.7695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 13d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 105d | [5 empty] | 337350.9584 |  | 95.16% |  | 307110.918 | 286269.7578
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 68850 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 64694.3984 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 100% | Finished | 52474.0508 | 52474.0508 | 100 | 100 | 100 | 100 | 101.4394 | 100
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 15d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 150 | 100 | 100 | 86.9899 | 100
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 45d | 75251.5078 | 0 | 0 | 12770.25 | 0 | 88021.7578 | 0 | 100% | Finished | 75251.5078 | 75251.5078 | 100 | 100 | 100 | 100 | 116.9701 | 100
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-18 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 0 | 100 | 150 | 100 | 100 | 192.0797 | 100
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 |  | 0 | 0 | 15626.6104 | 10d | 0 | 0 | 0 | 15626.6104 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 | 2010-02-26 08:00 | 24d | 194720.8281 | 0 | 26d | 133669.8125 | 0 | 328390.6406 | 0 | 48% | Started | 194720.8281 | 194720.8281 | 100 | 48 | 48 | 100 | 168.6469 | 48
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 31d | [5 empty] | 320186.1719 |  | 47.06% |  | 198770.3594 | 198770.3594
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-02-17 08:00 | 20d | 99385.1797 | 0 | 0 | 56565.8711 | 0 | 155951.0508 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 156.9158 | 100
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-03-03 08:00 | 20d | 99385.1797 | 0 | 0 | 64849.9414 | 0 | 164235.1211 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 165.2511 | 100
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 |  | 0 | 0 | 99385.1797 | 20d | 0 | 0 | 0 | 99385.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 |  | 0 | 0 | 124231.4688 | 25d | 0 | 0 | 0 | 124231.4688 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2010-04-30 17:00 |  | TP Name | 30/04, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 326d | [5 empty] | 21524152.0519 |  | 99.88% |  | 19407310.5132 | 19396000.7437
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 139726.5469 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 100% | Finished | 91163.3906 | 91163.3906 | 100 | 200 | 100 | 100 | 106.8285 | 100
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3310363.4299
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3310363.4299
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 2010-01-04 08:00 | 20d | 1071966 | 0 | 0 | -18668.2891 | 0 | 1053297.7109 | 0 | 100% | Finished | 1071966 | 1071966 | 100 | 33.3333 | 100 | 100 | 98.2585 | 100
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 100% | Finished | 1250627 | 1250627 | 100 | 47.1429 | 100 | 100 | 98.2585 | 100
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 2010-01-04 10:00 | 15d | 3080.96 | 0 | 0 | 582.4 | 0 | 3663.36 | 0 | 100% | Finished | 3080.96 | 3080.96 | 100 | 100 | 100 | 100 | 118.9032 | 100
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 99d | [5 empty] | 1092383.8923 |  | 100% |  | 520800.3072 | 520800.3072
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 | 2010-02-10 08:00 | 5d | 26237.0293 | 0 | 0 | 589.25 | 0 | 26826.2793 | 0 | 100% | Finished | 26237.0293 | 26237.0293 | 100 | 100 | 100 | 100 | 102.2459 | 100
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 | 2010-02-17 08:00 | 10d | 2554.8601 | 0 | 0 | 388.27 | 0 | 2943.1301 | 0 | 100% | Finished | 2554.8601 | 2554.8601 | 100 | 100 | 100 | 100 | 115.1973 | 100
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-03-03 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 | 2010-03-17 08:00 | 10d | 9851.1602 | 0 | 0 | 1082.6899 | 0 | 10933.8501 | 0 | 100% | Finished | 9851.1602 | 9851.1602 | 100 | 100 | 100 | 100 | 110.9905 | 100
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-08 08:00 | 4d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 133.3333 | 100 | 100 | 102.9952 | 100
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 | 2010-02-05 08:00 | 10d | 18002.3008 | 0 | 0 | 16267.6904 | 0 | 34269.9912 | 0 | 100% | Finished | 18002.3008 | 18002.3008 | 100 | 100 | 100 | 100 | 190.3645 | 100
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 80d | 1 | 0 | 0 | 530274.125 | 0 | 530275.125 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 53027512.5 | 100
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-18 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 99d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-14 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-10 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-04 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-12 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 13d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 130 | 100 | 100 | 102.9555 | 100
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-26 08:00 | 3d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 60 | 100 | 100 | 100.8628 | 100
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 100% | Finished | 38146.8906 | 38146.8906 | 100 | 100 | 100 | 100 | 105.6764 | 100
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 109d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 100 | 100 | 100 | 1881.0273 | 100
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 100 | 100 | 100 | 192.0797 | 100
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-04 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-18 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-01-21 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-06 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-27 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-01 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-05 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7249 |  | 100% |  | 559972.2264 | 559972.2264
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-08 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-13 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-18 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-05 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 119d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-21 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-10 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-15 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-26 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 8d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 200 | 100 | 100 | 1881.0273 | 100
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-01 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-09 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-30 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-04-02 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 129d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-24 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-29 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-10 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-18 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-04-12 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-04-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 125d | [5 empty] | 616571.4642 |  | 95.98% |  | 537473.2264 | 526163.4568
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-09 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-03-01 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-03 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-03-01 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-17 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-23 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-04-15 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 0 | 100 | 100 | 100 | 100 | 101.03 | 100
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 | 2010-04-20 08:00 | 9d | 1 | 0 | 4d | 17781.8594 | 0 | 17782.8594 | 0 | 69.23% | Started | 1 | 0 | 100 | 69.2308 | 69.2308 | 100 | 1778285.9375 | 69.2308
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 |  | 0 | 0 | 22500 | 5d | 0 | 0 | 0 | 22500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 122d | [5 empty] | 353439.4188 |  | 100% |  | 322737.5283 | 322737.5283
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 68850 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 64694.3984 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 100% | Finished | 52474.0508 | 52474.0508 | 100 | 100 | 100 | 100 | 101.4394 | 100
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 15d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 150 | 100 | 100 | 86.9899 | 100
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 45d | 75251.5078 | 0 | 0 | 12770.25 | 0 | 88021.7578 | 0 | 100% | Finished | 75251.5078 | 75251.5078 | 100 | 100 | 100 | 100 | 116.9701 | 100
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-18 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-04-12 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 | 2010-02-26 08:00 | 46d | 194720.8281 | 0 | 4d | 133669.8125 | 0 | 328390.6406 | 0 | 92% | Started | 194720.8281 | 194720.8281 | 100 | 92 | 92 | 100 | 168.6469 | 92
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 53d | [5 empty] | 681431.1211 |  | 100% |  | 422387.0078 | 422387.0078
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-02-17 08:00 | 20d | 99385.1797 | 0 | 0 | 56565.8711 | 0 | 155951.0508 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 156.9158 | 100
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-03-03 08:00 | 20d | 99385.1797 | 0 | 0 | 64849.9414 | 0 | 164235.1211 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 165.2511 | 100
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-04-15 08:00 | 12d | 99385.1797 | 0 | 8d | 56565.8711 | 0 | 155951.0508 | 0 | 60% | Started | 99385.1797 | 99385.1797 | 100 | 60 | 60 | 100 | 156.9158 | 60
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 | 2010-04-22 08:00 | 7d | 124231.4688 | 0 | 18d | 81062.4297 | 0 | 205293.8984 | 0 | 28% | Started | 124231.4688 | 124231.4688 | 100 | 28 | 28 | 100 | 165.2511 | 28

## TP18
| TP Status Date | 2010-05-31 17:00 |  | TP Name | 31/05, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Government Office Building | 2008-12-01 08:00 | 2010-06-07 17:00 | 352d |  |  | 19429810.5132 |  |  | 19429810.5132 |  | 344d | [5 empty] | 21546846.1819 |  | 100% |  | 19429810.5132 | 19407310.5132
456 | werfinrichting | 2008-12-01 08:00 | 2008-12-12 17:00 | 10d |  | 0 | 867102 | 0 | 0 | 867102 | 2008-12-01 08:00 | 10d | 867102 | 0 | 0 | 95406.2266 | 0 | 962508.2266 | 0 | 100% | Finished | 867102 | 867102 | 100 | 100 | 100 | 100 | 111.0029 | 100
468 | grondwerken en fundering ondergrondse werken | 2008-12-08 08:00 | 2009-08-25 17:00 | 155d |  |  | 533489.4428 |  |  | 533489.4428 |  | 155d | [5 empty] | 545329.4824 |  | 100% |  | 533489.4428 | 533489.4428
458 | installatie bronbemaling | 2008-12-08 08:00 | 2008-12-12 17:00 | 5d |  | 0 | 907.58 | 0 | 0 | 907.58 | 2008-12-08 08:00 | 5d | 907.58 | 0 | 0 | 194.13 | 0 | 1101.71 | 0 | 100% | Finished | 907.58 | 907.58 | 100 | 100 | 100 | 100 | 121.3899 | 100
459 | bronbemaling | 2008-12-15 08:00 | 2009-08-25 17:00 | 150d |  | 0 | 27227.4199 | 0 | 0 | 27227.4199 | 2008-12-15 08:00 | 150d | 27227.4199 | 0 | 0 | 5824.0298 | 0 | 33051.4497 | 0 | 100% | Finished | 27227.4199 | 27227.4199 | 100 | 100 | 100 | 100 | 121.3903 | 100
460 | grondwerken toren | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 104828.3281 | 0 | 0 | 104828.3281 | 2008-12-15 08:00 | 10d | 104828.3281 | 0 | 0 | 243.32 | 0 | 105071.6481 | 0 | 100% | Finished | 104828.3281 | 104828.3281 | 100 | 100 | 100 | 100 | 100.2321 | 100
461 | voorbereiding secanspalen parking | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2008-12-15 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
462 | secanspalen parking | 2009-01-12 08:00 | 2009-01-23 17:00 | 10d |  | 0 | 9333.3301 | 0 | 0 | 9333.3301 | 2009-01-12 08:00 | 10d | 9333.3301 | 0 | 0 | 784.72 | 0 | 10118.05 | 0 | 100% | Finished | 9333.3301 | 9333.3301 | 100 | 100 | 100 | 100 | 108.4077 | 100
463 | grondwerken parking | 2009-01-26 08:00 | 2009-02-25 17:00 | 23d |  | 0 | 241105.1562 | 0 | 0 | 241105.1562 | 2009-01-26 08:00 | 23d | 241105.1562 | 0 | 0 | 559.63 | 0 | 241664.7863 | 0 | 100% | Finished | 241105.1562 | 241105.1562 | 100 | 100 | 100 | 100 | 100.2321 | 100
464 | ankers secanspalen eerste rij | 2009-02-03 08:00 | 2009-02-09 17:00 | 5d |  | 0 | 4666.6699 | 0 | 0 | 4666.6699 | 2009-02-03 08:00 | 5d | 4666.6699 | 0 | 0 | 392.36 | 0 | 5059.0299 | 0 | 100% | Finished | 4666.6699 | 4666.6699 | 100 | 100 | 100 | 100 | 108.4077 | 100
457 | ankers secanspalen tweede rij | 2009-02-12 08:00 | 2009-02-18 17:00 | 5d |  | 0 | 4666.5698 | 0 | 0 | 4666.5698 | 2009-02-12 08:00 | 5d | 4666.5698 | 0 | 0 | 392.36 | 0 | 5058.9298 | 0 | 100% | Finished | 4666.5698 | 4666.5698 | 100 | 100 | 100 | 100 | 108.4079 | 100
465 | funderingsplaat gebouw | 2009-01-12 08:00 | 2009-01-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-01-12 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
466 | trekankers funderingsplaat parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-02-26 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
467 | funderingsplaat parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 20710.5293 | 0 | 0 | 20710.5293 | 2009-03-10 08:00 | 15d | 20710.5293 | 0 | 0 | 1177.08 | 0 | 21887.6093 | 0 | 100% | Finished | 20710.5293 | 20710.5293 | 100 | 100 | 100 | 100 | 105.6835 | 100
436 | 100 ruwbouw | 2008-12-15 08:00 | 2009-11-26 17:00 | 215d |  |  | 5887941.9712 |  |  | 5887941.9712 |  | 176d | [5 empty] | 6199805.6499 |  | 100% |  | 5887941.9712 | 5887941.9712
416 | 18 radier | 2008-12-15 08:00 | 2009-04-01 17:00 | 68d |  |  | 329571.4868 |  |  | 329571.4868 |  | 62d | [5 empty] | 332131.6968 |  | 100% |  | 329571.4868 | 329571.4868
1 | radier torengebouw | 2008-12-15 08:00 | 2009-01-26 17:00 | 21d |  | 0 | 9394.7402 | 0 | 0 | 9394.7402 | 2009-01-15 08:00 | 21d | 9394.7402 | 0 | 0 | 815.36 | 0 | 10210.1002 | 0 | 100% | Finished | 9394.7402 | 9394.7402 | 100 | 100 | 100 | 100 | 108.6789 | 100
2 | opstellen torenkraan TK2 | 2009-01-21 08:00 | 2009-01-22 17:00 | 2d |  | 0 | 26178.6699 | 0 | 0 | 26178.6699 | 2009-02-09 08:00 | 2d | 26178.6699 | 0 | 0 | -301.95 | 0 | 25876.7199 | 0 | 100% | Finished | 26178.6699 | 26178.6699 | 100 | 100 | 100 | 100 | 98.8466 | 100
3 | berlinerwand parking + einde grondwerken | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 152015.2188 | 0 | 0 | 152015.2188 | 2009-02-16 08:00 | 15d | 152015.2188 | 0 | 0 | 959.66 | 0 | 152974.8787 | 0 | 100% | Finished | 152015.2188 | 152015.2188 | 100 | 100 | 100 | 100 | 100.6313 | 100
4 | trekankers parking | 2009-02-26 08:00 | 2009-03-09 17:00 | 8d |  | 0 | 90000 | 0 | 0 | 90000 | 2009-03-09 08:00 | 8d | 90000 | 0 | 0 | 310.61 | 0 | 90310.61 | 0 | 100% | Finished | 90000 | 90000 | 100 | 100 | 100 | 100 | 100.3451 | 100
5 | radier parking | 2009-03-10 08:00 | 2009-03-30 17:00 | 15d |  | 0 | 6710.5298 | 0 | 0 | 6710.5298 | 2009-03-19 08:00 | 15d | 6710.5298 | 0 | 0 | 582.4 | 0 | 7292.9298 | 0 | 100% | Finished | 6710.5298 | 6710.5298 | 100 | 100 | 100 | 100 | 108.6789 | 100
6 | opstellen torenkraan TK1 in parking | 2009-03-26 08:00 | 2009-04-01 17:00 | 5d |  | 0 | 45272.3281 | 0 | 0 | 45272.3281 | 2009-04-06 08:00 | 5d | 45272.3281 | 0 | 0 | 194.13 | 0 | 45466.4581 | 0 | 100% | Finished | 45272.3281 | 45272.3281 | 100 | 100 | 100 | 100 | 100.4288 | 100
475 | 40 ruwbouw boven -2 toren | 2009-02-02 08:00 | 2009-02-20 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 53d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 353.3333 | 100 | 100 | 105.5646 | 100
476 | 45 ruwbouw boven -2 parking | 2009-03-31 08:00 | 2009-04-29 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 28d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 140 | 100 | 100 | 105.5646 | 100
477 | 50 ruwbouw boven -1 toren | 2009-03-09 08:00 | 2009-03-27 17:00 | 15d |  | 0 | 378979.8125 | 0 | 0 | 378979.8125 | 2009-02-16 08:00 | 56d | 378979.8125 | 0 | 0 | 21088.8691 | 0 | 400068.6816 | 0 | 100% | Finished | 378979.8125 | 378979.8125 | 100 | 373.3333 | 100 | 100 | 105.5646 | 100
478 | 55 ruwbouw boven -1 parking | 2009-04-30 08:00 | 2009-06-02 17:00 | 20d |  | 0 | 505306.4062 | 0 | 0 | 505306.4062 | 2009-04-09 08:00 | 42d | 505306.4062 | 0 | 0 | 28118.4902 | 0 | 533424.8965 | 0 | 100% | Finished | 505306.4062 | 505306.4062 | 100 | 210 | 100 | 100 | 105.5646 | 100
479 | 60 ruwbouw boven gelijkvloers | 2009-03-30 08:00 | 2009-04-10 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-04-08 08:00 | 21d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 210 | 100 | 100 | 105.5646 | 100
480 | 70 ruwbouw boven +1 | 2009-04-15 08:00 | 2009-04-28 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-05 08:00 | 14d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 140 | 100 | 100 | 105.5646 | 100
481 | 80 ruwbouw boven +2 | 2009-04-29 08:00 | 2009-05-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-05-19 08:00 | 10d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 100 | 100 | 100 | 105.5646 | 100
482 | 90 ruwbouw boven +3 | 2009-05-14 08:00 | 2009-05-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-05 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
483 | 100 ruwbouw boven +4 | 2009-06-02 08:00 | 2009-06-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-17 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
484 | 110 ruwbouw boven +5 | 2009-06-16 08:00 | 2009-06-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-06-29 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
485 | 120 ruwbouw boven +6 | 2009-06-30 08:00 | 2009-08-03 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-09 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
486 | 130 ruwbouw boven +7 | 2009-08-04 08:00 | 2009-08-18 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
487 | 140 ruwbouw boven +8 | 2009-08-19 08:00 | 2009-09-01 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-07-10 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
488 | 150 ruwbouw boven +9 | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-12 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
489 | 160 ruwbouw boven +10 | 2009-09-16 08:00 | 2009-09-29 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-08-25 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
490 | 170 ruwbouw boven +11 | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-04 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
491 | 180 ruwbouw boven +12 | 2009-10-14 08:00 | 2009-10-27 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-16 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
492 | 190 ruwbouw boven +13 | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-09-28 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
493 | 200 ruwbouw boven +14 | 2009-11-13 08:00 | 2009-11-26 17:00 | 10d |  | 0 | 252653.2031 | 0 | 0 | 252653.2031 | 2009-10-08 08:00 | 8d | 252653.2031 | 0 | 0 | 14059.25 | 0 | 266712.4531 | 0 | 100% | Finished | 252653.2031 | 252653.2031 | 100 | 80 | 100 | 100 | 105.5646 | 100
438 | 150 dak | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
437 | 301 dakwerken | 2009-06-03 08:00 | 2010-01-14 17:00 | 134d |  |  | 597815.1211 |  |  | 597815.1211 |  | 104d | [5 empty] | 598869.7309 |  | 100% |  | 597815.1211 | 597815.1211
182 | hellingsbeton | 2009-11-27 08:00 | 2009-12-03 17:00 | 5d |  | 0 | 66991.6562 | 0 | 0 | 66991.6562 | 2009-10-20 08:00 | 5d | 66991.6562 | 0 | 0 | 194.13 | 0 | 67185.7863 | 0 | 100% | Finished | 66991.6562 | 66991.6562 | 100 | 100 | 100 | 100 | 100.2898 | 100
183 | dakwerken niveau +2 | 2009-10-14 08:00 | 2009-10-20 17:00 | 5d |  | 0 | 46575.5195 | 0 | 0 | 46575.5195 | 2009-10-07 08:00 | 10d | 46575.5195 | 0 | 0 | -639.21 | 0 | 45936.3095 | 0 | 100% | Finished | 46575.5195 | 46575.5195 | 100 | 200 | 100 | 100 | 98.6276 | 100
184 | dakwerken gebouw | 2009-12-11 08:00 | 2010-01-14 17:00 | 15d |  | 0 | 139726.5469 | 0 | 0 | 139726.5469 | 2009-10-27 08:00 | 15d | 139726.5469 | 0 | 0 | -1917.63 | 0 | 137808.9169 | 0 | 100% | Finished | 139726.5469 | 139726.5469 | 100 | 100 | 100 | 100 | 98.6276 | 100
185 | installatie gevelreiniging | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 91163.3906 | 0 | 0 | 91163.3906 | 2009-11-19 08:00 | 10d | 91163.3906 | 0 | 0 | 6225.1099 | 0 | 97388.5005 | 0 | 100% | Finished | 91163.3906 | 91163.3906 | 100 | 200 | 100 | 100 | 106.8285 | 100
186 | dakwerken parkingdak | 2009-06-03 08:00 | 2009-07-07 17:00 | 25d |  | 0 | 232877.5781 | 0 | 0 | 232877.5781 | 2009-06-16 08:00 | 20d | 232877.5781 | 0 | 0 | -3196.0601 | 0 | 229681.5181 | 0 | 100% | Finished | 232877.5781 | 232877.5781 | 100 | 80 | 100 | 100 | 98.6276 | 100
187 | beschermbeton dak | 2009-07-08 08:00 | 2009-08-11 17:00 | 10d |  | 0 | 20480.4297 | 0 | 0 | 20480.4297 | 2009-08-04 08:00 | 10d | 20480.4297 | 0 | 0 | 388.27 | 0 | 20868.6997 | 0 | 100% | Finished | 20480.4297 | 20480.4297 | 100 | 100 | 100 | 100 | 101.8958 | 100
440 | 180 gevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3310363.4299
439 | 311 gordijngevel | 2009-06-30 08:00 | 2010-04-08 17:00 | 175d |  |  | 3310363.4299 |  |  | 3310363.4299 |  | 127d | [5 empty] | 3253773.5414 |  | 100% |  | 3310363.4299 | 3310363.4299
188 | montage hefsteigers | 2009-08-26 08:00 | 2009-09-08 17:00 | 10d |  | 0 | 2053.97 | 0 | 0 | 2053.97 | 2009-06-29 08:00 | 10d | 2053.97 | 0 | 0 | 388.27 | 0 | 2442.24 | 0 | 100% | Finished | 2053.97 | 2053.97 | 100 | 100 | 100 | 100 | 118.9034 | 100
189 | gevel 0 - 2 | 2009-06-30 08:00 | 2009-10-13 17:00 | 60d |  | 0 | 1071966 | 0 | 0 | 1071966 | 2010-01-04 08:00 | 20d | 1071966 | 0 | 0 | -18668.2891 | 0 | 1053297.7109 | 0 | 100% | Finished | 1071966 | 1071966 | 100 | 33.3333 | 100 | 100 | 98.2585 | 100
190 | gevel 3-5 | 2009-09-09 08:00 | 2009-10-16 12:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-08-03 09:00 | 42d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 152.7273 | 100 | 100 | 98.2585 | 100
191 | gevel 6-9 | 2009-10-16 13:00 | 2009-11-26 17:00 | 27d 4h |  | 0 | 491317.75 | 0 | 0 | 491317.75 | 2009-10-01 08:00 | 22d | 491317.75 | 0 | 0 | -8556.2998 | 0 | 482761.4502 | 0 | 100% | Finished | 491317.75 | 491317.75 | 100 | 80 | 100 | 100 | 98.2585 | 100
192 | gevel 9-boven | 2009-11-27 08:00 | 2010-03-18 17:00 | 70d |  | 0 | 1250627 | 0 | 0 | 1250627 | 2009-11-03 08:00 | 33d | 1250627 | 0 | 0 | -21779.6699 | 0 | 1228847.3301 | 0 | 100% | Finished | 1250627 | 1250627 | 100 | 47.1429 | 100 | 100 | 98.2585 | 100
193 | afbouw steigers | 2010-03-19 08:00 | 2010-04-08 17:00 | 15d |  | 0 | 3080.96 | 0 | 0 | 3080.96 | 2010-01-04 10:00 | 15d | 3080.96 | 0 | 0 | 582.4 | 0 | 3663.36 | 0 | 100% | Finished | 3080.96 | 3080.96 | 100 | 100 | 100 | 100 | 118.9032 | 100
441 | 205 gelijkvloers | 2009-09-07 08:00 | 2010-02-11 17:00 | 102d |  |  | 520800.3072 |  |  | 520800.3072 |  | 99d | [5 empty] | 1092383.8923 |  | 100% |  | 520800.3072 | 520800.3072
274 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
275 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-30 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
276 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-11-05 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
277 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
278 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
279 | technieken in vloer | 2009-12-04 08:00 | 2009-12-10 17:00 | 5d |  | 0 | 26237.0293 | 0 | 0 | 26237.0293 | 2010-02-10 08:00 | 5d | 26237.0293 | 0 | 0 | 589.25 | 0 | 26826.2793 | 0 | 100% | Finished | 26237.0293 | 26237.0293 | 100 | 100 | 100 | 100 | 102.2459 | 100
280 | chape | 2009-12-11 08:00 | 2010-01-07 17:00 | 10d |  | 0 | 2554.8601 | 0 | 0 | 2554.8601 | 2010-02-17 08:00 | 10d | 2554.8601 | 0 | 0 | 388.27 | 0 | 2943.1301 | 0 | 100% | Finished | 2554.8601 | 2554.8601 | 100 | 100 | 100 | 100 | 115.1973 | 100
281 | plaatsen convectoren | 2010-01-08 08:00 | 2010-01-21 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-03-03 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
282 | afwerking vloeren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 9851.1602 | 0 | 0 | 9851.1602 | 2010-03-17 08:00 | 10d | 9851.1602 | 0 | 0 | 1082.6899 | 0 | 10933.8501 | 0 | 100% | Finished | 9851.1602 | 9851.1602 | 100 | 100 | 100 | 100 | 110.9905 | 100
283 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
284 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
285 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
286 | sanitaire wanden | 2010-01-11 08:00 | 2010-01-13 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-08 08:00 | 4d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 133.3333 | 100 | 100 | 102.9952 | 100
287 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
288 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
289 | natuursteen inkomhal | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 18002.3008 | 0 | 0 | 18002.3008 | 2010-02-05 08:00 | 10d | 18002.3008 | 0 | 0 | 16267.6904 | 0 | 34269.9912 | 0 | 100% | Finished | 18002.3008 | 18002.3008 | 100 | 100 | 100 | 100 | 190.3645 | 100
290 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
291 | auditorium - verder te detailleren | 2009-09-21 08:00 | 2010-01-26 17:00 | 80d |  | 0 | 1 | 0 | 0 | 1 | 2009-11-12 08:00 | 80d | 1 | 0 | 0 | 530274.125 | 0 | 530275.125 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 53027512.5 | 100
292 | opkuis | 2010-01-27 08:00 | 2010-02-02 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-18 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
442 | 210 eerste verdieping | 2009-09-07 08:00 | 2010-02-23 17:00 | 110d |  |  | 559972.2264 |  |  | 559972.2264 |  | 99d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
258 | pleisterwerken | 2009-11-05 08:00 | 2009-11-12 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-14 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
259 | traceren plafond + boren ophangpunten | 2009-09-07 08:00 | 2009-09-09 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-27 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
260 | technieken in vals plafond | 2009-10-12 08:00 | 2009-10-30 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
261 | gk strook gevel structuur | 2009-11-23 08:00 | 2009-11-25 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-01 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
262 | structuur vp | 2009-11-30 08:00 | 2009-12-03 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-04 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
263 | vloergoten + verhoogde vloer + bekabeling | 2010-01-05 08:00 | 2010-01-18 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-10 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
264 | plaatsen convectoren | 2009-11-30 08:00 | 2009-12-11 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-04 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
265 | uitplamuren kolommen | 2009-12-03 08:00 | 2009-12-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-27 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
266 | metselwerken | 2009-09-07 08:00 | 2009-09-18 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-27 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
267 | binnenwanden | 2010-01-29 08:00 | 2010-02-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-05 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
268 | sanitaire wanden | 2010-01-14 08:00 | 2010-01-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-12 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
269 | binnenschrijnwerk | 2010-01-19 08:00 | 2010-01-22 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-24 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
270 | dichtleggen vp + gkstrook | 2010-01-19 08:00 | 2010-01-28 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-26 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
271 | schilderwerken | 2010-01-29 08:00 | 2010-02-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-04 08:00 | 13d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 130 | 100 | 100 | 102.9555 | 100
272 | tapijt | 2010-02-12 08:00 | 2010-02-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
273 | opkuis | 2010-02-17 08:00 | 2010-02-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-26 08:00 | 3d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 60 | 100 | 100 | 100.8628 | 100
443 | 220 tweede verdieping | 2009-10-21 08:00 | 2009-12-03 17:00 | 30d |  |  | 52785.1602 |  |  | 52785.1602 |  | 30d | [5 empty] | 55338.81 |  | 100% |  | 52785.1602 | 52785.1602
414 | tegels | 2009-10-21 08:00 | 2009-11-04 17:00 | 10d |  | 0 | 14638.2695 | 0 | 0 | 14638.2695 | 2009-10-21 08:00 | 10d | 14638.2695 | 0 | 0 | 388.27 | 0 | 15026.5395 | 0 | 100% | Finished | 14638.2695 | 14638.2695 | 100 | 100 | 100 | 100 | 102.6524 | 100
415 | bekleding kernen | 2009-11-05 08:00 | 2009-12-03 17:00 | 20d |  | 0 | 38146.8906 | 0 | 0 | 38146.8906 | 2009-11-05 08:00 | 20d | 38146.8906 | 0 | 0 | 2165.3799 | 0 | 40312.2705 | 0 | 100% | Finished | 38146.8906 | 38146.8906 | 100 | 100 | 100 | 100 | 105.6764 | 100
444 | 230 derde verdieping | 2009-09-09 08:00 | 2010-04-23 17:00 | 151d |  |  | 559972.2264 |  |  | 559972.2264 |  | 109d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
194 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
195 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-11 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
196 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-14 08:00 | 25d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 166.6667 | 100 | 100 | 108.3201 | 100
197 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
198 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
199 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
200 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
201 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
202 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
203 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 4d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 100 | 100 | 100 | 1881.0273 | 100
204 | sanitaire wanden | 2010-04-21 08:00 | 2010-04-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-09 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
205 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 4d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 100 | 100 | 100 | 192.0797 | 100
206 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
207 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-04 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
208 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-18 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
209 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-01-21 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
445 | 240 vierde verdieping | 2009-09-09 08:00 | 2010-01-26 17:00 | 88d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
210 | pleisterwerken | 2009-10-21 08:00 | 2009-10-27 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-19 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
211 | traceren plafond + boren ophangpunten | 2009-09-09 08:00 | 2009-09-11 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-14 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
212 | technieken in vals plafond | 2009-09-14 08:00 | 2009-10-02 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-20 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
213 | gk strook gevel structuur | 2009-11-13 08:00 | 2009-11-17 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-03 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
214 | structuur vp | 2009-11-18 08:00 | 2009-11-23 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-06 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
215 | vloergoten + verhoogde vloer + bekabeling | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-13 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
216 | plaatsen convectoren | 2009-11-18 08:00 | 2009-12-01 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-06 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
217 | uitplamuren kolommen | 2009-11-27 08:00 | 2009-11-30 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-11 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
218 | metselwerken | 2009-09-09 08:00 | 2009-09-22 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-11 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
219 | binnenwanden | 2009-12-18 08:00 | 2010-01-06 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2009-12-09 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
220 | sanitaire wanden | 2009-11-16 08:00 | 2009-11-18 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-14 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
221 | binnenschrijnwerk | 2009-12-08 08:00 | 2009-12-11 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2009-12-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
222 | dichtleggen vp + gkstrook | 2009-12-08 08:00 | 2009-12-17 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-11-27 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
223 | schilderwerken | 2009-12-18 08:00 | 2010-01-14 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-06 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
224 | tapijt | 2010-01-15 08:00 | 2010-01-19 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-01-27 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
225 | opkuis | 2010-01-20 08:00 | 2010-01-26 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-01 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
446 | 250 vijfde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
226 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
227 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-20 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
228 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-25 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
229 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
230 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
231 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
232 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
233 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
234 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
235 | sanitaire wanden | 2009-11-19 08:00 | 2009-11-23 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2009-12-17 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
236 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 6d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 150 | 100 | 100 | 1881.0273 | 100
237 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
238 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
239 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
240 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
241 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
447 | 260 zesde verdieping | 2009-09-02 08:00 | 2010-02-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
242 | pleisterwerken | 2009-10-28 08:00 | 2009-11-04 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-11-26 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
243 | traceren plafond + boren ophangpunten | 2009-09-02 08:00 | 2009-09-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
244 | technieken in vals plafond | 2009-09-28 08:00 | 2009-10-16 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-08-28 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
245 | gk strook gevel structuur | 2009-11-18 08:00 | 2009-11-20 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-06 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
246 | structuur vp | 2009-11-24 08:00 | 2009-11-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
247 | vloergoten + verhoogde vloer + bekabeling | 2009-12-08 08:00 | 2010-01-04 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-11-27 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
248 | plaatsen convectoren | 2009-11-24 08:00 | 2009-12-07 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
249 | uitplamuren kolommen | 2009-12-01 08:00 | 2009-12-02 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-20 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
250 | metselwerken | 2009-09-02 08:00 | 2009-09-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-20 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
251 | binnenwanden | 2010-01-15 08:00 | 2010-01-20 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-04 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
252 | sanitaire wanden | 2009-11-24 08:00 | 2009-11-26 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-05 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
253 | binnenschrijnwerk | 2010-01-05 08:00 | 2010-01-08 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-12 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
254 | dichtleggen vp + gkstrook | 2010-01-05 08:00 | 2010-01-14 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2009-12-09 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
255 | schilderwerken | 2010-01-15 08:00 | 2010-01-28 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-01-20 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
256 | tapijt | 2010-01-29 08:00 | 2010-02-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-10 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
257 | opkuis | 2010-02-03 08:00 | 2010-02-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
448 | 270 zevende verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7249 |  | 100% |  | 559972.2264 | 559972.2264
293 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
294 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-08-28 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
295 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-02 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
296 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.36 | 0 | 178.87 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8666 | 100
297 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
298 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
299 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
300 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
301 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
302 | sanitaire wanden | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-08 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
303 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
304 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
305 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
306 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
307 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
308 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
449 | 280 achtste verdieping | 2009-09-30 08:00 | 2010-03-09 17:00 | 103d |  |  | 559972.2264 |  |  | 559972.2264 |  | 123d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
309 | pleisterwerken | 2009-11-13 08:00 | 2009-11-19 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-03 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
310 | traceren plafond + boren ophangpunten | 2009-09-30 08:00 | 2009-10-02 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-03 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
311 | technieken in vals plafond | 2009-10-26 08:00 | 2009-11-17 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-08 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
312 | gk strook gevel structuur | 2009-11-26 08:00 | 2009-11-30 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-12 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
313 | structuur vp | 2009-12-04 08:00 | 2009-12-09 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-17 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
314 | vloergoten + verhoogde vloer + bekabeling | 2010-01-19 08:00 | 2010-02-01 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2009-12-11 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
315 | plaatsen convectoren | 2009-12-04 08:00 | 2009-12-17 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-17 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
316 | uitplamuren kolommen | 2009-12-07 08:00 | 2009-12-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-08-28 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
317 | metselwerken | 2009-09-30 08:00 | 2009-10-13 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-08-28 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
318 | binnenwanden | 2010-02-12 08:00 | 2010-02-17 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-14 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
319 | sanitaire wanden | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-13 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
320 | binnenschrijnwerk | 2010-02-02 08:00 | 2010-02-05 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-01-25 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
321 | dichtleggen vp + gkstrook | 2010-02-02 08:00 | 2010-02-11 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-04 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
322 | schilderwerken | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-02 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
323 | tapijt | 2010-02-26 08:00 | 2010-03-02 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-02-23 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
324 | opkuis | 2010-03-03 08:00 | 2010-03-09 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-02-26 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
450 | 290 negende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 116d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
325 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
326 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-15 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
327 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-18 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
328 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
329 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
330 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
331 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
332 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
333 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
334 | sanitaire wanden | 2009-12-07 08:00 | 2009-12-09 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-18 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
335 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
336 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
337 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
338 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
339 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
340 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-05 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
451 | 300 tiende verdieping | 2009-10-28 08:00 | 2010-03-23 17:00 | 93d |  |  | 559972.2264 |  |  | 559972.2264 |  | 119d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
341 | pleisterwerken | 2010-01-15 08:00 | 2010-01-21 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-10 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
342 | traceren plafond + boren ophangpunten | 2009-10-28 08:00 | 2009-10-30 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-09-25 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
343 | technieken in vals plafond | 2009-11-10 08:00 | 2009-12-01 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-09-30 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
344 | gk strook gevel structuur | 2010-01-12 08:00 | 2010-01-14 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2009-11-17 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
345 | structuur vp | 2010-01-22 08:00 | 2010-01-27 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2009-11-20 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
346 | vloergoten + verhoogde vloer + bekabeling | 2010-02-02 08:00 | 2010-02-15 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-01-08 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
347 | plaatsen convectoren | 2010-01-22 08:00 | 2010-02-04 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2009-11-20 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
348 | uitplamuren kolommen | 2009-12-18 08:00 | 2010-01-04 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-09-15 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
349 | metselwerken | 2009-10-28 08:00 | 2009-11-12 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-09-15 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
350 | binnenwanden | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-01-26 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
351 | sanitaire wanden | 2009-12-10 08:00 | 2009-12-14 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-21 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
352 | binnenschrijnwerk | 2010-02-16 08:00 | 2010-02-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-04 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
353 | dichtleggen vp + gkstrook | 2010-02-16 08:00 | 2010-02-25 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-01-14 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
354 | schilderwerken | 2010-02-26 08:00 | 2010-03-11 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-02-12 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
355 | tapijt | 2010-03-12 08:00 | 2010-03-16 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-05 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
356 | opkuis | 2010-03-17 08:00 | 2010-03-23 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-03-10 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
452 | 310 elfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 120d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
357 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
358 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-07 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
359 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-12 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
360 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
361 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
362 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-15 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
363 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
364 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
365 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
366 | sanitaire wanden | 2009-12-15 08:00 | 2009-12-17 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-26 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
367 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 8d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 200 | 100 | 100 | 1881.0273 | 100
368 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-01 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
369 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
370 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-09 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
371 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-03-30 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
372 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-04-02 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
453 | 320 twaalfde verdieping | 2009-11-27 08:00 | 2010-04-06 17:00 | 83d |  |  | 559972.2264 |  |  | 559972.2264 |  | 129d | [5 empty] | 621482.7349 |  | 100% |  | 559972.2264 | 559972.2264
373 | pleisterwerken | 2010-02-19 08:00 | 2010-02-25 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2009-12-17 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
374 | traceren plafond + boren ophangpunten | 2009-11-27 08:00 | 2009-12-01 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-19 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
375 | technieken in vals plafond | 2009-12-02 08:00 | 2010-01-05 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-22 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
376 | gk strook gevel structuur | 2010-02-03 08:00 | 2010-02-05 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-04 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
377 | structuur vp | 2010-02-08 08:00 | 2010-02-11 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-09 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
378 | vloergoten + verhoogde vloer + bekabeling | 2010-02-12 08:00 | 2010-02-25 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-02-24 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
379 | plaatsen convectoren | 2010-02-08 08:00 | 2010-02-19 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-09 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
380 | uitplamuren kolommen | 2010-01-05 08:00 | 2010-01-06 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-07 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
381 | metselwerken | 2009-11-27 08:00 | 2009-12-10 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-07 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
382 | binnenwanden | 2010-03-10 08:00 | 2010-03-15 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-02-17 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
383 | sanitaire wanden | 2009-12-18 08:00 | 2010-01-05 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-01-29 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
384 | binnenschrijnwerk | 2010-02-26 08:00 | 2010-03-03 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-10 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
385 | dichtleggen vp + gkstrook | 2010-02-26 08:00 | 2010-03-09 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-05 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
386 | schilderwerken | 2010-03-12 08:00 | 2010-03-25 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-18 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
387 | tapijt | 2010-03-26 08:00 | 2010-03-30 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-04-12 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
388 | opkuis | 2010-03-31 08:00 | 2010-04-06 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-04-15 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 22500 | 100 | 100 | 100 | 100 | 100.8628 | 100
454 | 330 dertiende verdieping | 2009-12-02 08:00 | 2010-06-07 17:00 | 124d |  |  | 559973.2264 |  |  | 559973.2264 |  | 134d | [5 empty] | 639265.5943 |  | 100% |  | 559973.2264 | 537473.2264
389 | pleisterwerken | 2010-03-05 08:00 | 2010-03-11 17:00 | 5d |  | 0 | 8611.6201 | 0 | 0 | 8611.6201 | 2010-01-07 08:00 | 5d | 8611.6201 | 0 | 0 | 194.13 | 0 | 8805.7501 | 0 | 100% | Finished | 8611.6201 | 8611.6201 | 100 | 100 | 100 | 100 | 102.2543 | 100
390 | traceren plafond + boren ophangpunten | 2009-12-02 08:00 | 2009-12-04 17:00 | 3d |  | 0 | 39378.6016 | 0 | 0 | 39378.6016 | 2009-10-22 08:00 | 3d | 39378.6016 | 0 | 0 | -17202.7598 | 0 | 22175.8418 | 0 | 100% | Finished | 39378.6016 | 39378.6016 | 100 | 100 | 100 | 100 | 56.3144 | 100
391 | technieken in vals plafond | 2009-12-16 08:00 | 2010-01-19 17:00 | 15d |  | 0 | 88472.6172 | 0 | 0 | 88472.6172 | 2009-10-27 08:00 | 15d | 88472.6172 | 0 | 0 | 7360.98 | 0 | 95833.5972 | 0 | 100% | Finished | 88472.6172 | 88472.6172 | 100 | 100 | 100 | 100 | 108.3201 | 100
392 | gk strook gevel structuur | 2010-03-18 08:00 | 2010-03-22 17:00 | 3d |  | 0 | 544.23 | 0 | 0 | 544.23 | 2010-02-09 08:00 | 3d | 544.23 | 0 | 0 | -365.35 | 0 | 178.88 | 0 | 100% | Finished | 544.23 | 544.23 | 100 | 100 | 100 | 100 | 32.8685 | 100
393 | structuur vp | 2010-03-23 08:00 | 2010-03-26 17:00 | 4d |  | 0 | 957.81 | 0 | 0 | 957.81 | 2010-02-12 08:00 | 4d | 957.81 | 0 | 0 | 155.3 | 0 | 1113.11 | 0 | 100% | Finished | 957.81 | 957.81 | 100 | 100 | 100 | 100 | 116.2141 | 100
394 | vloergoten + verhoogde vloer + bekabeling | 2010-03-29 08:00 | 2010-04-09 17:00 | 10d |  | 0 | 84509.5 | 0 | 0 | 84509.5 | 2010-03-01 08:00 | 10d | 84509.5 | 0 | 0 | 38412.4688 | 0 | 122921.9688 | 0 | 100% | Finished | 84509.5 | 84509.5 | 100 | 100 | 100 | 100 | 145.4534 | 100
395 | plaatsen convectoren | 2010-03-23 08:00 | 2010-04-05 17:00 | 10d |  | 0 | 187631.6875 | 0 | 0 | 187631.6875 | 2010-02-12 08:00 | 10d | 187631.6875 | 0 | 0 | -4288.9502 | 0 | 183342.7373 | 0 | 100% | Finished | 187631.6875 | 187631.6875 | 100 | 100 | 100 | 100 | 97.7142 | 100
396 | uitplamuren kolommen | 2010-01-07 08:00 | 2010-01-08 17:00 | 2d |  | 0 | 4682.9302 | 0 | 0 | 4682.9302 | 2009-10-22 08:00 | 2d | 4682.9302 | 0 | 0 | 77.65 | 0 | 4760.5802 | 0 | 100% | Finished | 4682.9302 | 4682.9302 | 100 | 100 | 100 | 100 | 101.6581 | 100
397 | metselwerken | 2009-12-02 08:00 | 2009-12-15 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-10-22 08:00 | 10d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 100 | 100 | 100 | 86.9899 | 100
398 | sanitaire wanden | 2010-01-06 08:00 | 2010-01-08 17:00 | 3d |  | 0 | 37201.2891 | 0 | 0 | 37201.2891 | 2010-02-03 08:00 | 3d | 37201.2891 | 0 | 0 | 1114.25 | 0 | 38315.5391 | 0 | 100% | Finished | 37201.2891 | 37201.2891 | 100 | 100 | 100 | 100 | 102.9952 | 100
399 | binnenwanden | 2010-04-26 08:00 | 2010-04-29 17:00 | 4d |  | 0 | 1037.39 | 0 | 0 | 1037.39 | 2010-03-01 08:00 | 7d | 1037.39 | 0 | 0 | 18476.1992 | 0 | 19513.5892 | 0 | 100% | Finished | 1037.39 | 1037.39 | 100 | 175 | 100 | 100 | 1881.0273 | 100
400 | binnenschrijnwerk | 2010-04-14 08:00 | 2010-04-19 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-03-15 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
401 | dichtleggen vp + gkstrook | 2010-04-14 08:00 | 2010-04-23 17:00 | 8d |  | 0 | 11668.21 | 0 | 0 | 11668.21 | 2010-02-17 08:00 | 8d | 11668.21 | 0 | 0 | 866.15 | 0 | 12534.36 | 0 | 100% | Finished | 11668.21 | 11668.21 | 100 | 100 | 100 | 100 | 107.4232 | 100
402 | schilderwerken | 2010-04-26 08:00 | 2010-05-07 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-03-23 08:00 | 15d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 150 | 100 | 100 | 102.9555 | 100
403 | tapijt | 2010-05-10 08:00 | 2010-05-12 17:00 | 3d |  | 0 | 11308.7695 | 0 | 0 | 11308.7695 | 2010-04-15 08:00 | 3d | 11308.7695 | 0 | 0 | 116.48 | 0 | 11425.2495 | 0 | 100% | Finished | 11308.7695 | 11308.7695 | 100 | 100 | 100 | 100 | 101.03 | 100
404 | verhoorkamer | 2010-05-13 08:00 | 2010-05-31 17:00 | 13d |  | 0 | 1 | 0 | 0 | 1 | 2010-04-20 08:00 | 13d | 1 | 0 | 0 | 17781.8594 | 0 | 17782.8594 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 1778285.9375 | 100
405 | opkuis | 2010-06-01 08:00 | 2010-06-07 17:00 | 5d |  | 0 | 22500 | 0 | 0 | 22500 | 2010-05-07 08:00 | 5d | 22500 | 0 | 0 | 194.13 | 0 | 22694.13 | 0 | 100% | Finished | 22500 | 0 | 100 | 100 | 100 | 100 | 100.8628 | 100
455 | 340 veertiende verdieping | 2009-12-15 17:00 | 2010-05-12 17:00 | 96d |  |  | 322737.5283 |  |  | 322737.5283 |  | 122d | [5 empty] | 353439.4188 |  | 100% |  | 322737.5283 | 322737.5283
406 | vlottende vloeren | 2010-01-08 08:00 | 2010-01-28 17:00 | 15d |  | 0 | 68850 | 0 | 0 | 68850 | 2009-10-20 08:00 | 15d | 68850 | 0 | 0 | 582.38 | 0 | 69432.38 | 0 | 100% | Finished | 68850 | 68850 | 100 | 100 | 100 | 100 | 100.8459 | 100
407 | polybetons | 2010-01-29 08:00 | 2010-02-04 17:00 | 5d |  | 0 | 64694.3984 | 0 | 0 | 64694.3984 | 2009-11-12 08:00 | 5d | 64694.3984 | 0 | 0 | 194.13 | 0 | 64888.5284 | 0 | 100% | Finished | 64694.3984 | 64694.3984 | 100 | 100 | 100 | 100 | 100.3001 | 100
408 | machines techn. Ruimtes | 2010-02-05 08:00 | 2010-02-18 17:00 | 10d |  | 0 | 52474.0508 | 0 | 0 | 52474.0508 | 2009-11-19 08:00 | 10d | 52474.0508 | 0 | 0 | 755.3 | 0 | 53229.3508 | 0 | 100% | Finished | 52474.0508 | 52474.0508 | 100 | 100 | 100 | 100 | 101.4394 | 100
409 | cv operationeel | 2009-12-15 17:00 | 2009-12-15 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2009-12-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
410 | metselwerken | 2010-02-19 08:00 | 2010-03-04 17:00 | 10d |  | 0 | 24999.8008 | 0 | 0 | 24999.8008 | 2009-12-03 08:00 | 15d | 24999.8008 | 0 | 0 | -3252.5 | 0 | 21747.3008 | 0 | 100% | Finished | 24999.8008 | 24999.8008 | 100 | 150 | 100 | 100 | 86.9899 | 100
411 | technieken aansluiten | 2010-02-19 08:00 | 2010-04-22 17:00 | 45d |  | 0 | 75251.5078 | 0 | 0 | 75251.5078 | 2009-12-03 08:00 | 45d | 75251.5078 | 0 | 0 | 12770.25 | 0 | 88021.7578 | 0 | 100% | Finished | 75251.5078 | 75251.5078 | 100 | 100 | 100 | 100 | 116.9701 | 100
412 | binnenschrijnwerk | 2010-04-23 08:00 | 2010-04-28 17:00 | 4d |  | 0 | 20841.1602 | 0 | 0 | 20841.1602 | 2010-02-18 08:00 | 6d | 20841.1602 | 0 | 0 | 19190.4805 | 0 | 40031.6406 | 0 | 100% | Finished | 20841.1602 | 20841.1602 | 100 | 150 | 100 | 100 | 192.0797 | 100
413 | schilderwerken | 2010-04-29 08:00 | 2010-05-12 17:00 | 10d |  | 0 | 15626.6104 | 0 | 0 | 15626.6104 | 2010-04-12 08:00 | 10d | 15626.6104 | 0 | 0 | 461.85 | 0 | 16088.4604 | 0 | 100% | Finished | 15626.6104 | 15626.6104 | 100 | 100 | 100 | 100 | 102.9555 | 100
469 | buitenaanleg | 2010-02-26 08:00 | 2010-05-06 17:00 | 50d |  | 0 | 194720.8281 | 0 | 0 | 194720.8281 | 2010-02-26 08:00 | 50d | 194720.8281 | 0 | 0 | 133669.8125 | 0 | 328390.6406 | 0 | 100% | Finished | 194720.8281 | 194720.8281 | 100 | 100 | 100 | 100 | 168.6469 | 100
474 | testen en opleveringen | 2010-02-17 08:00 | 2010-05-26 17:00 | 71d |  |  | 422387.0078 |  |  | 422387.0078 |  | 71d | [5 empty] | 681431.1211 |  | 100% |  | 422387.0078 | 422387.0078
470 | afregelen niveaus faze 1 tem +6 | 2010-02-17 08:00 | 2010-03-16 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-02-17 08:00 | 20d | 99385.1797 | 0 | 0 | 56565.8711 | 0 | 155951.0508 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 156.9158 | 100
471 | opleveringen faze 1 | 2010-03-03 08:00 | 2010-03-30 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-03-03 08:00 | 20d | 99385.1797 | 0 | 0 | 64849.9414 | 0 | 164235.1211 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 165.2511 | 100
472 | afregelen niveaus faze +2 | 2010-04-15 08:00 | 2010-05-12 17:00 | 20d |  | 0 | 99385.1797 | 0 | 0 | 99385.1797 | 2010-04-15 08:00 | 20d | 99385.1797 | 0 | 0 | 56565.8711 | 0 | 155951.0508 | 0 | 100% | Finished | 99385.1797 | 99385.1797 | 100 | 100 | 100 | 100 | 156.9158 | 100
473 | opleveringen faze 2 | 2010-04-22 08:00 | 2010-05-26 17:00 | 25d |  | 0 | 124231.4688 | 0 | 0 | 124231.4688 | 2010-04-22 08:00 | 25d | 124231.4688 | 0 | 0 | 81062.4297 | 0 | 205293.8984 | 0 | 100% | Finished | 124231.4688 | 124231.4688 | 100 | 100 | 100 | 100 | 165.2511 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2009-12-21
1:00 - 2:00 | No | Tuesday | Yes | 2009-12-22
2:00 - 3:00 | No | Wednesday | Yes | 2009-12-23
3:00 - 4:00 | No | Thursday | Yes | 2009-12-24
4:00 - 5:00 | No | Friday | Yes | 2009-12-25
5:00 - 6:00 | No | Saturday | No | 2009-12-28
6:00 - 7:00 | No | Sunday | No | 2009-12-29
7:00 - 8:00 | No |  |  | 2009-12-30
8:00 - 9:00 | Yes |  |  | 2009-12-31
9:00 - 10:00 | Yes |  |  | 2010-01-01
10:00 - 11:00 | Yes |  |  | 2008-12-22
11:00 - 12:00 | Yes |  |  | 2008-12-23
12:00 - 13:00 | No |  |  | 2008-12-24
13:00 - 14:00 | Yes |  |  | 2008-12-25
14:00 - 15:00 | Yes |  |  | 2008-12-26
15:00 - 16:00 | Yes |  |  | 2008-12-29
16:00 - 17:00 | Yes |  |  | 2008-12-30
17:00 - 18:00 | No |  |  | 2008-12-31
18:00 - 19:00 | No |  |  | 2009-01-01
19:00 - 20:00 | No |  |  | 2009-01-02
20:00 - 21:00 | No |  |  | 2009-07-30
21:00 - 22:00 | No |  |  | 2009-07-31
22:00 - 23:00 | No |  |  | 2009-07-13
23:00 - 0:00 | No |  |  | 2009-07-14
2009-07-15
2009-07-16
Generated by PMConverter v1.1.3 |  |  |  | 2009-07-17
2009-07-20
2009-07-21
2009-07-22
2009-07-23
2009-07-24
2009-07-27
2009-07-28
2009-07-29
2009-08-17
2009-11-02
2009-04-13
2009-05-01
2009-05-21
2009-06-01
2009-11-11
2009-04-14
2009-05-22

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
31/12, 2008 | 2008-12-01 08:00 | 2008-12-31 17:00 | 1018793.3984 | 1009398.6581 | 1111851.0845 | 2008-12-12 17:00 | -9394.7402 | 99.08% | -102452.4263 | 90.79% | -5d | 66.67% | 100% | 2010-06-08 09:00 | 2010-06-11 10:00 | 2010-08-02 11:00 | 2010-06-08 09:00 | 2010-06-11 10:00 | 2010-07-29 16:00 | 2010-06-14 17:00 | 2011-02-08 17:00 | 2011-04-22 09:00 | 19532262.9395 | 21401906.6857 | 19703706.5837 | 28742468.867 | 21590751.5986 | 31546934.4862 | 21037893.4522 | 22540485.8304 | 0.66667 | 0.90785 | 0.99078 | 1 | -5 | 0.90785 | 1 | 0.66667 | 1
31/01, 2009 | 2008-12-31 17:00 | 2009-01-31 17:00 | 1316121.0839 | 1289942.414 | 1395731.6302 | 2009-01-23 17:00 | -26178.6699 | 98.01% | -105789.2162 | 92.42% | -5d | 85.71% | 97.56% | 2010-06-08 12:00 | 2010-06-17 09:00 | 2010-07-28 14:00 | 2010-06-08 15:00 | 2010-06-17 09:00 | 2010-07-23 15:00 | 2010-06-14 17:00 | 2010-08-27 14:00 | 2010-10-11 12:00 | 19535599.7294 | 21023264.9215 | 19903738.3488 | 22558911.0793 | 21421594.8855 | 24294520.47 | 20788654.1136 | 21312302.8339 | 0.85714 | 0.92421 | 0.98011 | 0.97565 | -5 | 0.92421 | 1 | 0.85714 | 1
28/02, 2009 | 2009-01-31 17:00 | 2009-02-28 17:00 | 2036449.3549 | 2325429.1674 | 2475149.1619 | 2009-03-09 09:00 | 288979.8125 | 114.2% | -149719.9944 | 93.95% | 5d 1h | 109.3% | 96.27% | 2010-05-31 15:00 | 2010-04-07 10:00 | 2010-05-05 09:00 | 2010-05-27 10:00 | 2010-04-07 10:00 | 2010-04-29 14:00 | 2010-05-31 16:00 | 2010-04-26 17:00 | 2010-05-20 09:00 | 19579530.5076 | 20680775.7814 | 17453978.3801 | 18121568.6881 | 18418372.5052 | 19128944.8221 | 19928789.6169 | 20104080.4434 | 1.0932 | 0.93951 | 1.1419 | 0.96274 | 5.125 | 0.93951 | 1 | 1.0932 | 1
31/03, 2009 | 2009-02-28 17:00 | 2009-03-31 17:00 | 3246082.164 | 2442850.2265 | 2594640.3109 | 2009-03-25 17:00 | -803231.9375 | 75.26% | -151790.0844 | 94.15% | -4d | 94.81% | 100% | 2010-06-28 12:00 | 2010-11-16 15:00 | 2010-12-27 15:00 | 2010-07-02 17:00 | 2010-11-16 15:00 | 2010-12-20 17:00 | 2010-06-11 17:00 | 2010-07-05 10:00 | 2010-07-29 14:00 | 19581600.5976 | 20637110.3083 | 25167071.5672 | 20512392.9421 | 26569642.7149 | 21625738.8013 | 21391564.6059 | 20612028.1319 | 0.94805 | 0.9415 | 0.75255 | 1 | -4 | 0.9415 | 1 | 0.94805 | 1
30/04, 2009 | 2009-03-31 17:00 | 2009-04-30 17:00 | 4256694.9765 | 3751388.5703 | 3973669.0151 | 2009-04-29 17:00 | -505306.4062 | 88.13% | -222280.4449 | 94.41% | -1d | 98.97% | 86.53% | 2010-06-21 09:00 | 2010-08-12 11:00 | 2010-09-15 09:00 | 2010-06-23 12:00 | 2010-08-12 11:00 | 2010-09-07 11:00 | 2010-06-08 17:00 | 2010-06-11 14:00 | 2010-07-02 17:00 | 19652090.9581 | 20581082.0608 | 21763950.8466 | 19815407.8533 | 22818075.6556 | 20754075.9467 | 20804902.4687 | 20422082.7704 | 0.98969 | 0.94406 | 0.88129 | 0.8653 | -1 | 0.94406 | 1 | 0.98969 | 1
31/05, 2009 | 2009-04-30 17:00 | 2009-05-31 17:00 | 4509348.1796 | 4256694.9765 | 4507093.9214 | 2009-05-13 17:00 | -252653.2031 | 94.4% | -250398.9449 | 94.44% | -10d | 91.3% | 100% | 2010-06-14 14:00 | 2010-07-06 16:00 | 2010-08-05 16:00 | 2010-06-16 12:00 | 2010-07-06 16:00 | 2010-07-28 09:00 | 2010-06-21 17:00 | 2010-07-23 12:00 | 2010-08-16 11:00 | 19680209.4581 | 20572763.9263 | 20580799.2966 | 21125268.0806 | 21526330.7215 | 22102827.7362 | 20574370.3576 | 20680306.028 | 0.91304 | 0.94444 | 0.94397 | 1 | -10 | 0.94444 | 1 | 0.91304 | 1
30/06, 2009 | 2009-05-31 17:00 | 2009-06-30 17:00 | 6572151.3671 | 5249586.134 | 5539355.0388 | 2009-06-29 17:00 | -1322565.2332 | 79.88% | -289768.9048 | 94.77% | -1d | 99.26% | 100% | 2010-07-09 17:00 | 2010-10-08 14:00 | 2010-11-11 17:00 | 2010-07-15 11:00 | 2010-10-08 14:00 | 2010-11-02 12:00 | 2010-06-08 17:00 | 2010-06-10 14:00 | 2010-06-28 14:00 | 19719579.418 | 20502305.5194 | 23292103.2863 | 19824618.1171 | 24272027.0909 | 20613142.1896 | 20987843.3946 | 20361672.508 | 0.99265 | 0.94769 | 0.79876 | 1 | -1 | 0.94769 | 1 | 0.99265 | 1
31/07, 2009 | 2009-06-30 17:00 | 2009-08-03 09:00 | 6592631.7968 | 6007545.7433 | 6339492.3982 | 2009-06-29 17:00 | -585086.0535 | 91.13% | -331946.6548 | 94.76% | -9d 1h | 93.67% | 100% | 2010-06-22 14:00 | 2010-07-26 10:00 | 2010-08-24 14:00 | 2010-06-24 15:00 | 2010-07-26 10:00 | 2010-08-12 14:00 | 2010-06-21 09:00 | 2010-07-09 15:00 | 2010-07-28 14:00 | 19761757.168 | 20503403.7706 | 21068976.4982 | 20669002.8423 | 21882853.4428 | 21460779.2615 | 20613016.7899 | 20536216.6761 | 0.93669 | 0.94764 | 0.91125 | 1 | -9.125 | 0.94764 | 1 | 0.93669 | 1
31/08, 2009 | 2009-08-03 09:00 | 2009-08-31 17:00 | 7099992.173 | 7753530.1916 | 8029808.3377 | 2009-09-09 09:00 | 653538.0186 | 109.2% | -276278.1461 | 96.56% | 6d 1h | 103.7% | 85.41% | 2010-05-21 09:00 | 2010-04-27 11:00 | 2010-05-12 16:00 | 2010-05-17 16:00 | 2010-04-27 11:00 | 2010-05-04 17:00 | 2010-05-28 16:00 | 2010-05-20 11:00 | 2010-05-28 14:00 | 19706088.6593 | 20122144.443 | 18721905.5947 | 19285708.2509 | 19102892.4142 | 19686784.8037 | 19813505.4533 | 19945057.8308 | 1.0373 | 0.96559 | 1.092 | 0.85411 | 6.125 | 0.96559 | 1 | 1.0373 | 1
30/09, 2009 | 2009-08-31 17:00 | 2009-09-30 17:00 | 9218188.2199 | 9042881.5363 | 9332823.373 | 2009-09-29 17:00 | -175306.6836 | 98.1% | -289941.8367 | 96.89% | -1d | 99.46% | 86.41% | 2010-06-11 09:00 | 2010-06-16 16:00 | 2010-07-02 11:00 | 2010-06-11 12:00 | 2010-06-16 16:00 | 2010-06-24 11:00 | 2010-06-08 17:00 | 2010-06-09 16:00 | 2010-06-17 10:00 | 19719752.3499 | 20052788.3687 | 19921114.9426 | 19775897.912 | 20260607.2486 | 20110734.1255 | 20026192.3401 | 19996241.8259 | 0.99462 | 0.96893 | 0.98098 | 0.86412 | -1 | 0.96893 | 1 | 0.99462 | 1
31/10, 2009 | 2009-09-30 17:00 | 2009-10-31 17:00 | 10793119.9191 | 10822831.613 | 11044440.211 | 2009-11-05 09:00 | 29711.6938 | 100.3% | -221608.598 | 97.99% | 2d 1h | 101% | 88.48% | 2010-06-07 12:00 | 2010-06-04 17:00 | 2010-06-16 10:00 | 2010-06-07 11:00 | 2010-06-04 17:00 | 2010-06-09 17:00 | 2010-06-03 16:00 | 2010-06-02 12:00 | 2010-06-07 11:00 | 19651419.1112 | 19827655.848 | 19627790.5516 | 19564376.4929 | 19803543.4694 | 19738830.9427 | 19786941.6149 | 19773706.2536 | 1.0102 | 0.97993 | 1.0028 | 0.88475 | 2.125 | 0.97993 | 1 | 1.0102 | 1
30/11, 2009 | 2009-10-31 17:00 | 2009-11-30 17:00 | 14017136.3426 | 14317301.6808 | 15184272.3171 | 2009-12-04 09:00 | 300165.3383 | 102.1% | -866970.6363 | 94.29% | 3d 1h | 101.4% | 89.81% | 2010-05-31 12:00 | 2010-05-27 14:00 | 2010-06-25 12:00 | 2010-06-01 09:00 | 2010-05-27 14:00 | 2010-06-07 15:00 | 2010-06-02 16:00 | 2010-06-01 10:00 | 2010-06-10 12:00 | 20296781.1495 | 20606364.2772 | 20189596.2918 | 20227355.4456 | 20492688.9421 | 20532734.5657 | 20517549.2831 | 20526072.5426 | 1.0138 | 0.9429 | 1.0214 | 0.89808 | 3.125 | 0.9429 | 1 | 1.0138 | 1
31/12, 2009 | 2009-11-30 17:00 | 2009-12-31 17:00 | 15474629.0461 | 14816939.0976 | 15851825.6108 | 2009-12-04 17:00 | -657689.9485 | 95.75% | -1034886.5133 | 93.47% | -10d | 95.85% | 90.43% | 2010-06-23 16:00 | 2010-06-29 14:00 | 2010-08-04 10:00 | 2010-06-22 10:00 | 2010-06-29 14:00 | 2010-07-12 12:00 | 2010-06-21 17:00 | 2010-06-29 10:00 | 2010-07-09 17:00 | 20464697.0264 | 20786882.2216 | 20669451.8104 | 20664388.4297 | 21005938.0676 | 21000521.036 | 20762940.3796 | 20761887.1378 | 0.95851 | 0.93471 | 0.9575 | 0.90427 | -10 | 0.93471 | 1 | 0.95851 | 1
31/01, 2010 | 2009-12-31 17:00 | 2010-01-31 17:00 | 16907759.0059 | 16614471.1623 | 17911569.3714 | 2010-01-21 17:00 | -293287.8436 | 98.27% | -1297098.2091 | 92.76% | -6d | 97.7% | 95.92% | 2010-06-15 11:00 | 2010-06-16 10:00 | 2010-07-26 09:00 | 2010-06-14 12:00 | 2010-06-16 10:00 | 2010-06-25 15:00 | 2010-06-15 17:00 | 2010-06-18 10:00 | 2010-06-29 17:00 | 20726908.7223 | 20946703.3576 | 20776606.6512 | 20793152.0011 | 21000281.2231 | 21018118.2749 | 20911087.1995 | 20914697.721 | 0.97701 | 0.92758 | 0.98265 | 0.95921 | -6 | 0.92758 | 1 | 0.97701 | 1
28/02, 2010 | 2010-01-31 17:00 | 2010-02-28 17:00 | 18451257.5991 | 18442142.1876 | 20222835.0155 | 2010-02-25 17:00 | -9115.4114 | 99.95% | -1780692.8279 | 91.19% | -1d | 99.64% | 98.43% | 2010-06-08 09:00 | 2010-06-08 09:00 | 2010-07-26 09:00 | 2010-06-08 09:00 | 2010-06-08 09:00 | 2010-06-16 17:00 | 2010-06-08 17:00 | 2010-06-09 10:00 | 2010-06-18 10:00 | 21210503.3411 | 21305868.2876 | 21210991.5167 | 21214030.728 | 21306403.5993 | 21309736.2636 | 21285462.8761 | 21286164.0967 | 0.99644 | 0.91195 | 0.99951 | 0.98428 | -1 | 0.91195 | 1 | 0.99644 | 1
31/03, 2010 | 2010-02-28 17:00 | 2010-03-31 17:00 | 19049541.6652 | 19100448.7153 | 21060797.0238 | 2010-04-15 09:00 | 50907.0502 | 100.3% | -1960348.3085 | 90.69% | 10d 1h | 103.3% | 99.19% | 2010-06-07 09:00 | 2010-06-04 17:00 | 2010-07-27 09:00 | 2010-06-07 10:00 | 2010-06-04 17:00 | 2010-06-11 16:00 | 2010-05-24 16:00 | 2010-05-21 14:00 | 2010-05-27 11:00 | 21390158.8217 | 21423962.4172 | 21389280.9974 | 21379542.7033 | 21422994.4987 | 21412256.7281 | 21416452.381 | 21414114.8932 | 1.0333 | 0.90692 | 1.0027 | 0.99188 | 10.125 | 0.90692 | 1 | 1.0333 | 1
30/04, 2010 | 2010-03-31 17:00 | 2010-04-30 17:00 | 19396000.7437 | 19407310.5132 | 21524152.0519 | 2010-05-13 09:00 | 11309.7695 | 100.1% | -2116841.5387 | 90.17% | 8d 1h | 102.5% | 100% | 2010-06-07 15:00 | 2010-06-07 15:00 | 2010-07-30 09:00 | 2010-06-07 15:00 | 2010-06-07 15:00 | 2010-06-10 14:00 | 2010-05-26 16:00 | 2010-05-26 12:00 | 2010-05-28 11:00 | 21546652.0519 | 21549106.2268 | 21546638.9398 | 21546104.9138 | 21549091.6845 | 21548499.41 | 21548570.3853 | 21548442.059 | 1.0249 | 0.90165 | 1.0006 | 1 | 8.125 | 0.90165 | 1 | 1.0249 | 1
31/05, 2010 | 2010-04-30 17:00 | 2010-05-31 17:00 | 19407310.5132 | 19429810.5132 | 21546846.1819 | 2010-06-01 09:00 | 22500 | 100.1% | -2117035.6687 | 90.17% | 1h | 100% | 100% | 2010-06-07 14:00 | 2010-06-07 14:00 | 2010-07-29 16:00 | 2010-06-07 14:00 | 2010-06-07 14:00 | 2010-06-08 09:00 | 2010-06-07 16:00 | 2010-06-07 16:00 | 2010-06-08 11:00 | 21546846.1819 | 21546846.1819 | 21546846.1819 | 21546846.1819 | 21546846.1819 | 21546846.1819 | 21546846.1819 | 21546846.1819 | 1.0004 | 0.90175 | 1.0012 | 1 | 0.125 | 0.90175 | 1 | 1.0004 | 1