## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Urban Development Project | 1 |  |  | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 | 448.375
62 | Werfinrichting | 1.1 |  | FS63 | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 0.375
63 | Grondwerken | 1.2 | 62FS | FS64 | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 4.375
64 | Funderingen | 1.3 | 63FS | FS65-1w | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 18.375
65 | Wanden op V0 | 1.4 | 64FS-1w | FS66-1w | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 25.375
66 | Afdekking V0 | 1.5 | 65FS-1w | FS67-1w | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 18.375
67 | Wanden op V1 | 1.6 | 66FS-1w | FS68-1w | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 25.375
68 | Afdekking V1 | 1.7 | 67FS-1w | FS69 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 11.375
69 | Wanden op V2 | 1.8 | 68FS | FS1 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 11.375
1 | Afdekking V2 | 1.9 | 69FS | FS8;SS2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 4.375
2 | Gevelmetselwerk | 1.10 | 1SS | FS5;FS12 | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 46.375
3 | Voegwerk | 1.11 |  |  | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 25.375
4 | Opmeten dorpels | 1.12 |  | FS5 | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 0.375
5 | Plaatsen dorpels | 1.13 | 2FS;4FS | FS13 | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 4.375
6 | Plaatsen bordessen + prefabtrappen | 1.14 |  | SF7 | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 4.375
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 1.15 | 6SF |  | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 4.375
8 | Dakopstanden | 1.16 | 1FS | FS9 | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 25.375
9 | Technieken / leidingen in dak | 1.17 | 8FS | FS10 | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 43.375
10 | Schuimbeton | 1.18 | 9FS | FS11 | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 27.375
11 | Isolatie + roofing platte daken | 1.19 | 10FS | FS18;FS14 | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 27.375
12 | Opmeten ramen en deuren | 1.20 | 2FS | FS13 | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 0.375
13 | Plaatsen ramen en deuren | 1.21 | 12FS;5FS | FS22 | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 4.375
14 | Plaatsen gipsblokken_blok 1 | 1.22 | 11FS | FS15;FS18 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 6.375
15 | Plaatsen gipsblokken_blok 2 | 1.23 | 14FS | FS16;FS19 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 6.375
16 | Plaatsen gipsblokken_blok 3 | 1.24 | 15FS | FS17;FS20 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 6.375
17 | Plaatsen gipsblokken_blok 4 | 1.25 | 16FS | FS21 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 6.375
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 1.26 | 11FS;14FS | FS22 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 6.375
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 1.27 | 15FS | FS23 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 6.375
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 1.28 | 16FS | FS24 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 6.375
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 1.29 | 17FS | FS25 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 6.375
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 1.30 | 13FS;18FS | FS23;FS26;FS30 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 13.375
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 1.31 | 19FS;22FS | FS24;FS27;FS31 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 13.375
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 1.32 | 20FS;23FS | FS25;FS28;FS32 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 20.375
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 1.33 | 21FS;24FS | FS29;FS33 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 13.375
26 | Opmeten keukens_blok 1 | 1.34 | 22FS | FS54 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 0.375
27 | Opmeten keukens_blok 2 | 1.35 | 23FS | FS55 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 0.375
28 | Opmeten keukens_blok 3 | 1.36 | 24FS | FS56 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 0.375
29 | Opmeten keukens_blok 4 | 1.37 | 25FS | FS57 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 0.375
30 | Pleisterwerken_blok 1 | 1.38 | 22FS | FS31;FS34 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 7.375
31 | Pleisterwerken_blok 2 | 1.39 | 23FS;30FS | FS32;FS35 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 7.375
32 | Pleisterwerken_blok 3 | 1.40 | 24FS;31FS | FS33;FS36 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 7.375
33 | Pleisterwerken_blok 4 | 1.41 | 25FS;32FS | FS37 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 7.375
34 | Schuimbeton_blok 1 | 1.42 | 30FS | FS38 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 4.1667
35 | Schuimbeton_blok 2 | 1.43 | 31FS | FS39 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 11.1667
36 | Schuimbeton_blok 3 | 1.44 | 32FS | FS40 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 4.1667
37 | Schuimbeton_blok 4 | 1.45 | 33FS | FS41 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 4.1667
38 | Chape_blok 1 | 1.46 | 34FS | FS42;FS46;FS54 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2.1667
39 | Chape_blok 2 | 1.47 | 35FS | FS43;FS47;FS50;FS55 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2.1667
40 | Chape_blok 3 | 1.48 | 36FS | FS44;FS48;FS56 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2.1667
41 | Chape_blok 4 | 1.49 | 37FS | FS45;FS49;FS52;FS57 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2.1667
42 | Opmeten binnendeuren_blok 1 | 1.50 | 38FS | FS58 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 0.375
43 | Opmeten binnendeuren_blok 2 | 1.51 | 39FS | FS59 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 0.375
44 | Opmeten binnendeuren_blok 3 | 1.52 | 40FS | FS60 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 0.375
45 | Opmeten binnendeuren_blok 4 | 1.53 | 41FS | FS61 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 0.375
46 | Vloerafwerking_blok 1 | 1.54 | 38FS | FS47;FS50;FS58 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 18.1667
47 | Vloerafwerking_blok 2 | 1.55 | 39FS;46FS | FS51;FS59 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 8.375
48 | Vloerafwerking_blok 3 | 1.56 | 40FS | FS49;FS52;FS60 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 8.375
49 | Vloerafwerking_blok 4 | 1.57 | 41FS;48FS | FS53;FS61 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 8.375
50 | Plaatsen badkamers_blok 1 | 1.58 | 39FS;46FS |  | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 13.375
51 | Plaatsen badkamers_blok 2 | 1.59 | 47FS |  | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 11.375
52 | Plaatsen badkamers_blok 3 | 1.60 | 41FS;48FS |  | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 13.375
53 | Plaatsen badkamers_blok 4 | 1.61 | 49FS |  | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 25.375
54 | Plaatsen keukens_blok 1 | 1.62 | 38FS;26FS |  | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 20.375
55 | Plaatsen keukens_blok 2 | 1.63 | 39FS;27FS |  | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 13.375
56 | Plaatsen keukens_blok 3 | 1.64 | 40FS;28FS |  | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 13.375
57 | Plaatsen keukens_blok 4 | 1.65 | 41FS;29FS |  | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 13.375
58 | Plaatsen binnendeuren_blok 1 | 1.66 | 42FS;46FS | FS70 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 6.375
59 | Plaatsen binnendeuren_blok 2 | 1.67 | 43FS;47FS | FS70 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 4.375
60 | Plaatsen binnendeuren_blok 3 | 1.68 | 44FS;48FS | FS70 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 4.375
61 | Plaatsen binnendeuren_blok 4 | 1.69 | 45FS;49FS | FS70 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 4.375
70 | Schilderwerken | 1.70 | 58FS;59FS;60FS;61FS | FS71 | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 | 39.375
71 | Opkuis | 1.71 | 70FS |  | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 | 11.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Urban Development Project | 2328h |  |  |  |  | 99 | 100 | 101
62 | Werfinrichting | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Grondwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Funderingen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Wanden op V0 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Afdekking V0 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Wanden op V1 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Afdekking V1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Wanden op V2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Afdekking V2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Gevelmetselwerk | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Voegwerk | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Opmeten dorpels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Plaatsen dorpels | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Plaatsen bordessen + prefabtrappen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Dakopstanden | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Technieken / leidingen in dak | 256h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Schuimbeton | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Isolatie + roofing platte daken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Opmeten ramen en deuren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Plaatsen ramen en deuren | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Plaatsen gipsblokken_blok 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Plaatsen gipsblokken_blok 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Plaatsen gipsblokken_blok 3 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Plaatsen gipsblokken_blok 4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Opmeten keukens_blok 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Opmeten keukens_blok 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Opmeten keukens_blok 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Opmeten keukens_blok 4 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Pleisterwerken_blok 1 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Pleisterwerken_blok 2 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Pleisterwerken_blok 3 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Pleisterwerken_blok 4 | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Schuimbeton_blok 1 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Schuimbeton_blok 2 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Schuimbeton_blok 3 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Schuimbeton_blok 4 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Chape_blok 1 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Chape_blok 2 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Chape_blok 3 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Chape_blok 4 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Opmeten binnendeuren_blok 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Opmeten binnendeuren_blok 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Opmeten binnendeuren_blok 3 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Opmeten binnendeuren_blok 4 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Vloerafwerking_blok 1 | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Vloerafwerking_blok 2 | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Vloerafwerking_blok 3 | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Vloerafwerking_blok 4 | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Plaatsen badkamers_blok 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Plaatsen badkamers_blok 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Plaatsen badkamers_blok 3 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Plaatsen badkamers_blok 4 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Plaatsen keukens_blok 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Plaatsen keukens_blok 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Plaatsen keukens_blok 3 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Plaatsen keukens_blok 4 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Plaatsen binnendeuren_blok 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Plaatsen binnendeuren_blok 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Plaatsen binnendeuren_blok 3 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Plaatsen binnendeuren_blok 4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Schilderwerken | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Opkuis | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2007-12-31 17:00 |  | TP Name | 31/12, 2007
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 17d | [5 empty] | 216156.3497 |  | 13.75% |  | 211394.7297 | 138800.3
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 1047.49 | 0 | 137155.49 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 100.7696 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 1d | 72594.4297 | 0 | 14d | 3506.9299 | 0 | 76101.3596 | 0 | 6.667% | Started | 72594.4297 | 0 | 100 | 6.6667 | 6.6667 | 100 | 104.8309 | 6.6667
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 |  | 0 | 0 | 55480.9805 | 20d | 0 | 0 | 0 | 55480.9805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 |  | 0 | 0 | 46319.7109 | 15d | 0 | 0 | 0 | 46319.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 |  | 0 | 0 | 55480.9805 | 20d | 0 | 0 | 0 | 55480.9805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 |  | 0 | 0 | 30879.8105 | 10d | 0 | 0 | 0 | 30879.8105 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 |  | 0 | 0 | 27740.4902 | 10d | 0 | 0 | 0 | 27740.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 |  | 0 | 0 | 23742.4199 | 5d | 0 | 0 | 0 | 23742.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 |  | 0 | 0 | 128627.4375 | 35d | 0 | 0 | 0 | 128627.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 |  | 0 | 0 | 3583.3701 | 20d | 0 | 0 | 0 | 3583.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 |  | 0 | 0 | 382.03 | 1d | 0 | 0 | 0 | 382.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 |  | 0 | 0 | 1910.15 | 5d | 0 | 0 | 0 | 1910.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 |  | 0 | 0 | 26966.6191 | 5d | 0 | 0 | 0 | 26966.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 |  | 0 | 0 | 17353.25 | 5d | 0 | 0 | 0 | 17353.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 |  | 0 | 0 | 33210.0781 | 20d | 0 | 0 | 0 | 33210.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 |  | 0 | 0 | 10512.2002 | 32d | 0 | 0 | 0 | 10512.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 |  | 0 | 0 | 1379.79 | 5d | 0 | 0 | 0 | 1379.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 |  | 0 | 0 | 64503.3516 | 20d | 0 | 0 | 0 | 64503.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 |  | 0 | 0 | 23772.3008 | 1d | 0 | 0 | 0 | 23772.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 |  | 0 | 0 | 118861.5234 | 5d | 0 | 0 | 0 | 118861.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2008-02-28 17:00 |  | TP Name | 28/02, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 60d | [5 empty] | 381091.8616 |  | 23.98% |  | 368676.4016 | 368676.4016
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 2698.55 | 0 | 138806.55 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 101.9827 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5604.3398 | 0 | 78198.7695 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.7201 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 1469.89 | 0 | 56950.8705 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 102.6494 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 965.59 | 0 | 47285.301 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 102.0846 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 9d | 55480.9805 | 0 | 11d | 1469.89 | 0 | 56950.8705 | 0 | 45% | Started | 55480.9805 | 55480.9805 | 100 | 45 | 45 | 100 | 102.6494 | 45
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 |  | 0 | 0 | 30879.8105 | 10d | 0 | 0 | 0 | 30879.8105 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 |  | 0 | 0 | 27740.4902 | 10d | 0 | 0 | 0 | 27740.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 |  | 0 | 0 | 23742.4199 | 5d | 0 | 0 | 0 | 23742.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 |  | 0 | 0 | 128627.4375 | 35d | 0 | 0 | 0 | 128627.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 |  | 0 | 0 | 3583.3701 | 20d | 0 | 0 | 0 | 3583.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 |  | 0 | 0 | 382.03 | 1d | 0 | 0 | 0 | 382.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 |  | 0 | 0 | 1910.15 | 5d | 0 | 0 | 0 | 1910.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 |  | 0 | 0 | 26966.6191 | 5d | 0 | 0 | 0 | 26966.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 |  | 0 | 0 | 17353.25 | 5d | 0 | 0 | 0 | 17353.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 |  | 0 | 0 | 33210.0781 | 20d | 0 | 0 | 0 | 33210.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 |  | 0 | 0 | 10512.2002 | 32d | 0 | 0 | 0 | 10512.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 |  | 0 | 0 | 1379.79 | 5d | 0 | 0 | 0 | 1379.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 |  | 0 | 0 | 64503.3516 | 20d | 0 | 0 | 0 | 64503.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 |  | 0 | 0 | 23772.3008 | 1d | 0 | 0 | 0 | 23772.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 |  | 0 | 0 | 118861.5234 | 5d | 0 | 0 | 0 | 118861.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2008-03-31 17:00 |  | TP Name | 31/03, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 82d | [5 empty] | 447206.4123 |  | 27.79% |  | 427296.7024 | 427296.7024
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 3331.79 | 0 | 139439.79 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 102.4479 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5604.3398 | 0 | 78198.7695 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.7201 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 2957.26 | 0 | 58438.2405 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 105.3302 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 2023.9399 | 0 | 48343.6509 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 104.3695 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 2957.26 | 0 | 58438.2405 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 105.3302 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 1349.29 | 0 | 32229.1006 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 104.3695 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 1d | 27740.4902 | 0 | 9d | 1478.63 | 0 | 29219.1202 | 0 | 10% | Started | 27740.4902 | 27740.4902 | 100 | 10 | 10 | 100 | 105.3302 | 10
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 |  | 0 | 0 | 23742.4199 | 5d | 0 | 0 | 0 | 23742.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 |  | 0 | 0 | 128627.4375 | 35d | 0 | 0 | 0 | 128627.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 |  | 0 | 0 | 3583.3701 | 20d | 0 | 0 | 0 | 3583.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 |  | 0 | 0 | 382.03 | 1d | 0 | 0 | 0 | 382.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 |  | 0 | 0 | 1910.15 | 5d | 0 | 0 | 0 | 1910.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 |  | 0 | 0 | 26966.6191 | 5d | 0 | 0 | 0 | 26966.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 |  | 0 | 0 | 17353.25 | 5d | 0 | 0 | 0 | 17353.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 |  | 0 | 0 | 33210.0781 | 20d | 0 | 0 | 0 | 33210.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 |  | 0 | 0 | 10512.2002 | 32d | 0 | 0 | 0 | 10512.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 |  | 0 | 0 | 1379.79 | 5d | 0 | 0 | 0 | 1379.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 |  | 0 | 0 | 64503.3516 | 20d | 0 | 0 | 0 | 64503.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 |  | 0 | 0 | 23772.3008 | 1d | 0 | 0 | 0 | 23772.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 |  | 0 | 0 | 118861.5234 | 5d | 0 | 0 | 0 | 118861.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2008-04-23 17:00 |  | TP Name | 23/04, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 101d | [5 empty] | 600882.0797 |  | 37.7% |  | 579666.5598 | 579666.5598
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 3331.79 | 0 | 139439.79 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 102.4479 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5604.3398 | 0 | 78198.7695 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.7201 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 2957.26 | 0 | 58438.2405 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 105.3302 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 2023.9399 | 0 | 48343.6509 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 104.3695 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 2957.26 | 0 | 58438.2405 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 105.3302 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 1349.29 | 0 | 32229.1006 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 104.3695 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 1478.63 | 0 | 29219.1202 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 105.3302 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 674.65 | 0 | 24417.0699 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 102.8415 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 8d | 128627.4375 | 0 | 27d | 631.16 | 0 | 129258.5975 | 0 | 22.86% | Started | 128627.4375 | 128627.4375 | 100 | 22.8571 | 22.8571 | 100 | 100.4907 | 22.8571
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 |  | 0 | 0 | 3583.3701 | 20d | 0 | 0 | 0 | 3583.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 |  | 0 | 0 | 382.03 | 1d | 0 | 0 | 0 | 382.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 |  | 0 | 0 | 1910.15 | 5d | 0 | 0 | 0 | 1910.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 |  | 0 | 0 | 26966.6191 | 5d | 0 | 0 | 0 | 26966.6191 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 |  | 0 | 0 | 17353.25 | 5d | 0 | 0 | 0 | 17353.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 |  | 0 | 0 | 33210.0781 | 20d | 0 | 0 | 0 | 33210.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 |  | 0 | 0 | 10512.2002 | 32d | 0 | 0 | 0 | 10512.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 |  | 0 | 0 | 1379.79 | 5d | 0 | 0 | 0 | 1379.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 |  | 0 | 0 | 64503.3516 | 20d | 0 | 0 | 0 | 64503.3516 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 |  | 0 | 0 | 23772.3008 | 1d | 0 | 0 | 0 | 23772.3008 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 |  | 0 | 0 | 118861.5234 | 5d | 0 | 0 | 0 | 118861.5234 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 |  | 0 | 0 | 10562.0996 | 5d | 0 | 0 | 0 | 10562.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 |  | 0 | 0 | 22595.0996 | 5d | 0 | 0 | 0 | 22595.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2008-09-30 17:00 |  | TP Name | 30/09, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 198d | [5 empty] | 1100324.4797 |  | 66% |  | 1014730.0201 | 1037325.1197
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 10018.5898 | 0 | 146126.5898 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 107.3608 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5604.3398 | 0 | 78198.7695 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.7201 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4744.7002 | 0 | 51064.4111 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 110.2434 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3163.1299 | 0 | 34042.9404 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 110.2434 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2785.8501 | 0 | 30526.3403 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 110.0425 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 1906.39 | 0 | 25648.8099 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 108.0295 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 14826.0898 | 0 | 143453.5273 | 0 | 100% | Finished | 128627.4375 | 128627.4375 | 100 | 100 | 100 | 100 | 111.5264 | 100
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | 0 | 0 | 3583.3701 | 0 | 100% | Finished | 3583.3701 | 3583.3701 | 100 | 100 | 100 | 100 | 100 | 100
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | 46.92 | 0 | 428.95 | 0 | 100% | Finished | 382.03 | 382.03 | 100 | 100 | 100 | 100 | 112.2818 | 100
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | 234.61 | 0 | 2144.76 | 0 | 100% | Finished | 1910.15 | 1910.15 | 100 | 100 | 100 | 100 | 112.2823 | 100
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 2690.8201 | 0 | 29657.4392 | 0 | 100% | Finished | 26966.6191 | 26966.6191 | 100 | 100 | 100 | 100 | 109.9783 | 100
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1257.26 | 0 | 18610.51 | 0 | 100% | Finished | 17353.25 | 17353.25 | 100 | 100 | 100 | 100 | 107.2451 | 100
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 1299.3101 | 0 | 34509.3882 | 0 | 100% | Finished | 33210.0781 | 33210.0781 | 100 | 25 | 100 | 100 | 103.9124 | 100
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 835.92 | 0 | 11348.1202 | 0 | 100% | Finished | 10512.2002 | 10512.2002 | 100 | 15.625 | 100 | 100 | 107.9519 | 100
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 0 | 0 | 1379.79 | 0 | 100% | Finished | 1379.79 | 1379.79 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 5108.1299 | 0 | 69611.4814 | 0 | 100% | Finished | 64503.3516 | 64503.3516 | 100 | 100 | 100 | 100 | 107.9192 | 100
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 2407.1899 | 0 | 26179.4907 | 0 | 100% | Finished | 23772.3008 | 23772.3008 | 100 | 100 | 100 | 100 | 110.126 | 100
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 12035.9697 | 0 | 130897.4932 | 0 | 100% | Finished | 118861.5234 | 118861.5234 | 100 | 200 | 100 | 100 | 110.126 | 100
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 0 | 100 | 100 | 100 | 100 | 100.3368 | 100
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 45190.1992 | 100 |  | 0 | 100 |  | 0
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2008-10-21 17:00 |  | TP Name | 21/10, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 213d | [5 empty] | 1145666.8589 |  | 68.94% |  | 1059920.2193 | 1223163.4782
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 10018.5898 | 0 | 146126.5898 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 107.3608 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5604.3398 | 0 | 78198.7695 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.7201 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4744.7002 | 0 | 51064.4111 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 110.2434 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3163.1299 | 0 | 34042.9404 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 110.2434 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2785.8501 | 0 | 30526.3403 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 110.0425 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 1906.39 | 0 | 25648.8099 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 108.0295 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 14826.0898 | 0 | 143453.5273 | 0 | 100% | Finished | 128627.4375 | 128627.4375 | 100 | 100 | 100 | 100 | 111.5264 | 100
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | 0 | 0 | 3583.3701 | 0 | 100% | Finished | 3583.3701 | 3583.3701 | 100 | 100 | 100 | 100 | 100 | 100
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | 46.92 | 0 | 428.95 | 0 | 100% | Finished | 382.03 | 382.03 | 100 | 100 | 100 | 100 | 112.2818 | 100
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | 234.61 | 0 | 2144.76 | 0 | 100% | Finished | 1910.15 | 1910.15 | 100 | 100 | 100 | 100 | 112.2823 | 100
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 2690.8201 | 0 | 29657.4392 | 0 | 100% | Finished | 26966.6191 | 26966.6191 | 100 | 100 | 100 | 100 | 109.9783 | 100
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1257.26 | 0 | 18610.51 | 0 | 100% | Finished | 17353.25 | 17353.25 | 100 | 100 | 100 | 100 | 107.2451 | 100
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 1299.3101 | 0 | 34509.3882 | 0 | 100% | Finished | 33210.0781 | 33210.0781 | 100 | 25 | 100 | 100 | 103.9124 | 100
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 835.92 | 0 | 11348.1202 | 0 | 100% | Finished | 10512.2002 | 10512.2002 | 100 | 15.625 | 100 | 100 | 107.9519 | 100
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 0 | 0 | 1379.79 | 0 | 100% | Finished | 1379.79 | 1379.79 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 5108.1299 | 0 | 69611.4814 | 0 | 100% | Finished | 64503.3516 | 64503.3516 | 100 | 100 | 100 | 100 | 107.9192 | 100
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 2407.1899 | 0 | 26179.4907 | 0 | 100% | Finished | 23772.3008 | 23772.3008 | 100 | 100 | 100 | 100 | 110.126 | 100
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 12035.9697 | 0 | 130897.4932 | 0 | 100% | Finished | 118861.5234 | 118861.5234 | 100 | 200 | 100 | 100 | 110.126 | 100
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 76.09 | 0 | 22671.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 100.3368 | 100
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-10-13 08:00 | 7d | 45190.1992 | 0 | 3d | 152.18 | 0 | 45342.3792 | 0 | 70% | Started | 45190.1992 | 45190.1992 | 100 | 70 | 70 | 100 | 100.3368 | 70
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 45190.1992 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 45190.1992 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 1517.39 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 1517.39 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 13287.2803 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 13287.2803 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 689.89 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 3740.6699 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 877.83 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 22771.2695 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 15173.8604 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2008-10-31 17:00 |  | TP Name | 31/10, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 216d | [5 empty] | 1147890.8286 |  | 68.94% |  | 1059920.2193 | 1223853.3682
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 10772.5596 | 0 | 146880.5596 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 107.9147 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5604.3398 | 0 | 78198.7695 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.7201 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4744.7002 | 0 | 51064.4111 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 110.2434 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3163.1299 | 0 | 34042.9404 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 110.2434 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2785.8501 | 0 | 30526.3403 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 110.0425 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 1906.39 | 0 | 25648.8099 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 108.0295 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 14826.0898 | 0 | 143453.5273 | 0 | 100% | Finished | 128627.4375 | 128627.4375 | 100 | 100 | 100 | 100 | 111.5264 | 100
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | 0 | 0 | 3583.3701 | 0 | 100% | Finished | 3583.3701 | 3583.3701 | 100 | 100 | 100 | 100 | 100 | 100
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | 46.92 | 0 | 428.95 | 0 | 100% | Finished | 382.03 | 382.03 | 100 | 100 | 100 | 100 | 112.2818 | 100
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | 234.61 | 0 | 2144.76 | 0 | 100% | Finished | 1910.15 | 1910.15 | 100 | 100 | 100 | 100 | 112.2823 | 100
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 2690.8201 | 0 | 29657.4392 | 0 | 100% | Finished | 26966.6191 | 26966.6191 | 100 | 100 | 100 | 100 | 109.9783 | 100
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1257.26 | 0 | 18610.51 | 0 | 100% | Finished | 17353.25 | 17353.25 | 100 | 100 | 100 | 100 | 107.2451 | 100
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 1299.3101 | 0 | 34509.3882 | 0 | 100% | Finished | 33210.0781 | 33210.0781 | 100 | 25 | 100 | 100 | 103.9124 | 100
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 835.92 | 0 | 11348.1202 | 0 | 100% | Finished | 10512.2002 | 10512.2002 | 100 | 15.625 | 100 | 100 | 107.9519 | 100
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 0 | 0 | 1379.79 | 0 | 100% | Finished | 1379.79 | 1379.79 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 5108.1299 | 0 | 69611.4814 | 0 | 100% | Finished | 64503.3516 | 64503.3516 | 100 | 100 | 100 | 100 | 107.9192 | 100
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 2407.1899 | 0 | 26179.4907 | 0 | 100% | Finished | 23772.3008 | 23772.3008 | 100 | 100 | 100 | 100 | 110.126 | 100
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 12035.9697 | 0 | 130897.4932 | 0 | 100% | Finished | 118861.5234 | 118861.5234 | 100 | 200 | 100 | 100 | 110.126 | 100
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1243.5699 | 0 | 11805.6696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 111.7739 | 100
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 321.09 | 0 | 22916.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 101.4211 | 100
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 321.09 | 0 | 22916.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 101.4211 | 100
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 321.09 | 0 | 22916.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 101.4211 | 100
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 321.09 | 0 | 22916.1896 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 101.4211 | 100
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-10-13 08:00 | 10d | 45190.1992 | 0 | 0 | 642.18 | 0 | 45832.3792 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 101.4211 | 100
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 45190.1992 | 100 |  | 0 | 100 |  | 0
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 45190.1992 | 100 |  | 0 | 100 |  | 0
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 |  | 0 | 0 | 45190.1992 | 10d | 0 | 0 | 0 | 45190.1992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 1517.39 | 100 |  | 0 | 100 |  | 0
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 1517.39 | 100 |  | 0 | 100 |  | 0
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 |  | 0 | 0 | 1517.39 | 1d | 0 | 0 | 0 | 1517.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 13287.2803 | 100 |  | 0 | 100 |  | 0
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 13287.2803 | 100 |  | 0 | 100 |  | 0
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 |  | 0 | 0 | 13287.2803 | 6d | 0 | 0 | 0 | 13287.2803 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 689.89 | 100 |  | 0 | 100 |  | 0
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 689.89 | 100 |  | 0 | 100 |  | 0
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 |  | 0 | 0 | 689.89 | 2d 4h | 0 | 0 | 0 | 689.89 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 3740.6699 | 100 |  | 0 | 100 |  | 0
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 |  | 0 | 0 | 3740.6699 | 2d 4h | 0 | 0 | 0 | 3740.6699 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 877.83 | 100 |  | 0 | 100 |  | 0
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 |  | 0 | 0 | 877.83 | 1d | 0 | 0 | 0 | 877.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d 4h | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 22771.2695 | 100 |  | 0 | 100 |  | 0
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 |  | 0 | 0 | 22771.2695 | 7d | 0 | 0 | 0 | 22771.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 |  | 0 | 0 | 755.04 | 10d | 0 | 0 | 0 | 755.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 15173.8604 | 100 |  | 0 | 100 |  | 0
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 |  | 0 | 0 | 15173.8604 | 10d | 0 | 0 | 0 | 15173.8604 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 |  | 0 | 0 | 4389.1299 | 5d | 0 | 0 | 0 | 4389.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2009-03-31 17:00 |  | TP Name | 31/03, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 313d | [5 empty] | 1595319.6378 |  | 94.2% |  | 1448300.2569 | 1537398.5147
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 13450.9004 | 0 | 149558.9004 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 109.8825 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 207.2 | 0 | 2899.5 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 107.696 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5690.1899 | 0 | 78284.6196 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.8383 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4811.8901 | 0 | 51131.6011 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 110.3884 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5571.7002 | 0 | 61052.6807 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.0425 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3207.9199 | 0 | 34087.7305 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 110.3884 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2785.8501 | 0 | 30526.3403 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 110.0425 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 2217.4299 | 0 | 25959.8499 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 109.3395 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 14924.8096 | 0 | 143552.2471 | 0 | 100% | Finished | 128627.4375 | 128627.4375 | 100 | 100 | 100 | 100 | 111.6031 | 100
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | 56.41 | 0 | 3639.7801 | 0 | 100% | Finished | 3583.3701 | 3583.3701 | 100 | 100 | 100 | 100 | 101.5742 | 100
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | 46.92 | 0 | 428.95 | 0 | 100% | Finished | 382.03 | 382.03 | 100 | 100 | 100 | 100 | 112.2818 | 100
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | 234.61 | 0 | 2144.76 | 0 | 100% | Finished | 1910.15 | 1910.15 | 100 | 100 | 100 | 100 | 112.2823 | 100
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 3088.97 | 0 | 30055.5891 | 0 | 100% | Finished | 26966.6191 | 26966.6191 | 100 | 100 | 100 | 100 | 111.4548 | 100
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1415.25 | 0 | 18768.5 | 0 | 100% | Finished | 17353.25 | 17353.25 | 100 | 100 | 100 | 100 | 108.1555 | 100
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 2453.8701 | 0 | 35663.9482 | 0 | 100% | Finished | 33210.0781 | 33210.0781 | 100 | 25 | 100 | 100 | 107.3889 | 100
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 1117.26 | 0 | 11629.4602 | 0 | 100% | Finished | 10512.2002 | 10512.2002 | 100 | 15.625 | 100 | 100 | 110.6282 | 100
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 108.61 | 0 | 1488.4 | 0 | 100% | Finished | 1379.79 | 1379.79 | 100 | 100 | 100 | 100 | 107.8715 | 100
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 6262.6899 | 0 | 70766.0415 | 0 | 100% | Finished | 64503.3516 | 64503.3516 | 100 | 100 | 100 | 100 | 109.7091 | 100
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 3635.3301 | 0 | 27407.6309 | 0 | 100% | Finished | 23772.3008 | 23772.3008 | 100 | 100 | 100 | 100 | 115.2923 | 100
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 18176.6309 | 0 | 137038.1543 | 0 | 100% | Finished | 118861.5234 | 118861.5234 | 100 | 200 | 100 | 100 | 115.2923 | 100
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1277.97 | 0 | 11840.0696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.0996 | 100
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1277.97 | 0 | 11840.0696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.0996 | 100
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1277.97 | 0 | 11840.0696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.0996 | 100
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1277.97 | 0 | 11840.0696 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.0996 | 100
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.47 | 0 | 24842.5696 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.9467 | 100
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.47 | 0 | 24842.5696 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.9467 | 100
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.47 | 0 | 24842.5696 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.9467 | 100
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.47 | 0 | 24842.5696 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.9467 | 100
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-10-13 08:00 | 10d | 45190.1992 | 0 | 0 | 4494.9399 | 0 | 49685.1392 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9467 | 100
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-03 08:00 | 10d | 45190.1992 | 0 | 0 | 4494.9399 | 0 | 49685.1392 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9467 | 100
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-17 08:00 | 10d | 45190.1992 | 0 | 0 | 4494.9399 | 0 | 49685.1392 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9467 | 100
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-12-01 08:00 | 10d | 45190.1992 | 0 | 0 | 4494.9399 | 0 | 49685.1392 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9467 | 100
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 119.44 | 0 | 1636.83 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 107.8714 | 100
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 119.44 | 0 | 1636.83 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 107.8714 | 100
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 119.44 | 0 | 1636.83 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 107.8714 | 100
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 119.44 | 0 | 1636.83 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 107.8714 | 100
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-03 08:00 | 15d | 13287.2803 | 0 | 0 | 1045.75 | 0 | 14333.0303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 250 | 100 | 100 | 107.8703 | 100
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-24 08:00 | 10d | 13287.2803 | 0 | 0 | 1045.75 | 0 | 14333.0303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 166.6667 | 100 | 100 | 107.8703 | 100
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-12-08 08:00 | 15d | 13287.2803 | 0 | 0 | 1045.75 | 0 | 14333.0303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 250 | 100 | 100 | 107.8703 | 100
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2009-01-12 08:00 | 10d | 13287.2803 | 0 | 0 | 1045.75 | 0 | 14333.0303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 166.6667 | 100 | 100 | 107.8703 | 100
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-11-24 08:00 | 1d | 689.89 | 0 | 0 | 54.3 | 0 | 744.19 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 107.8708 | 100
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-12-08 08:00 | 1d | 689.89 | 0 | 0 | 54.3 | 0 | 744.19 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 107.8708 | 100
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-12 08:00 | 1d | 689.89 | 0 | 0 | 54.3 | 0 | 744.19 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 107.8708 | 100
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-26 08:00 | 1d | 689.89 | 0 | 0 | 54.3 | 0 | 744.19 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 107.8708 | 100
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-01 08:00 | 10d | 3740.6699 | 0 | 0 | 294.44 | 0 | 4035.1099 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 107.8713 | 100
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-16 08:00 | 10d | 3740.6699 | 0 | 0 | 294.44 | 0 | 4035.1099 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 107.8713 | 100
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-01-20 08:00 | 10d | 3740.6699 | 0 | 0 | 294.44 | 0 | 4035.1099 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 107.8713 | 100
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-02-03 08:00 | 10d | 3740.6699 | 0 | 0 | 294.44 | 0 | 4035.1099 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 107.8713 | 100
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2008-12-15 08:00 | 1d | 877.83 | 0 | 0 | 69.1 | 0 | 946.93 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 107.8717 | 100
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-01-13 08:00 | 1d | 877.83 | 0 | 0 | 69.1 | 0 | 946.93 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 107.8717 | 100
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-03 08:00 | 1d | 877.83 | 0 | 0 | 69.1 | 0 | 946.93 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 107.8717 | 100
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-17 08:00 | 1d | 877.83 | 0 | 0 | 69.1 | 0 | 946.93 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 107.8717 | 100
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2008-12-15 08:00 | 10d | 22771.2695 | 0 | 0 | 1792.37 | 0 | 24563.6395 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 133.3333 | 100 | 100 | 107.8712 | 100
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-01-13 08:00 | 10d | 22771.2695 | 0 | 0 | 1792.37 | 0 | 24563.6395 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 107.8712 | 100
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-03 08:00 | 10d | 22771.2695 | 0 | 0 | 1792.37 | 0 | 24563.6395 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 107.8712 | 100
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-17 08:00 | 10d | 22771.2695 | 0 | 0 | 1792.37 | 0 | 24563.6395 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 107.8712 | 100
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-12 08:00 | 5d | 755.04 | 0 | 0 | 59.43 | 0 | 814.47 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 107.8711 | 100
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-27 08:00 | 5d | 755.04 | 0 | 0 | 59.43 | 0 | 814.47 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 107.8711 | 100
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-02-17 08:00 | 5d | 755.04 | 0 | 0 | 59.43 | 0 | 814.47 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 107.8711 | 100
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-03-03 08:00 | 5d | 755.04 | 0 | 0 | 59.43 | 0 | 814.47 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 107.8711 | 100
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-17 08:00 | 5d | 15173.8604 | 0 | 0 | 1194.37 | 0 | 16368.2303 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 107.8712 | 100
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-24 08:00 | 5d | 15173.8604 | 0 | 0 | 1194.37 | 0 | 16368.2303 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 107.8712 | 100
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-03 08:00 | 5d | 15173.8604 | 0 | 0 | 1194.37 | 0 | 16368.2303 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 107.8712 | 100
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-10 08:00 | 5d | 15173.8604 | 0 | 0 | 1194.37 | 0 | 16368.2303 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 107.8712 | 100
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-03 08:00 | 10d | 4389.1299 | 0 | 0 | 348.48 | 0 | 4737.6099 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 107.9396 | 100
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-24 08:00 | 10d | 4389.1299 | 0 | 0 | 345.48 | 0 | 4734.6099 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 107.8713 | 100
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-11 08:00 | 10d | 4389.1299 | 0 | 0 | 345.48 | 0 | 4734.6099 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 107.8713 | 100
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-25 08:00 | 5d | 4389.1299 | 0 | 5d | 345.48 | 0 | 4734.6099 | 0 | 50% | Started | 4389.1299 | 4389.1299 | 100 | 100 | 50 | 100 | 107.8713 | 50
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 |  | 0 | 0 | 29804.9297 | 30d | 0 | 0 | 0 | 29804.9297 | 0% | Not Started | 0 | 29804.9297 | 100 |  | 0 | 100 |  | 0
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 59293.3281 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2009-04-30 17:00 |  | TP Name | 30/04, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 335d | [5 empty] | 1629744.949 |  | 96.14% |  | 1478105.1866 | 1537398.5147
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 13458.6104 | 0 | 149566.6104 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 109.8882 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 245.79 | 0 | 2938.09 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 109.1294 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5805.96 | 0 | 78400.3896 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.9978 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5728.1802 | 0 | 61209.1606 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.3246 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4927.6499 | 0 | 51247.3608 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 110.6383 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5728.1802 | 0 | 61209.1606 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.3246 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3285.1001 | 0 | 34164.9106 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 110.6383 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2864.0901 | 0 | 30604.5803 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 110.3246 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 2380.4199 | 0 | 26122.8398 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 110.026 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 15508.4297 | 0 | 144135.8672 | 0 | 100% | Finished | 128627.4375 | 128627.4375 | 100 | 100 | 100 | 100 | 112.0569 | 100
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | -2061.99 | 0 | 1521.3801 | 0 | 100% | Finished | 3583.3701 | 3583.3701 | 100 | 100 | 100 | 100 | 42.4567 | 100
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | -67.96 | 0 | 314.07 | 0 | 100% | Finished | 382.03 | 382.03 | 100 | 100 | 100 | 100 | 82.2108 | 100
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | -339.78 | 0 | 1570.37 | 0 | 100% | Finished | 1910.15 | 1910.15 | 100 | 100 | 100 | 100 | 82.2119 | 100
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 3127.5601 | 0 | 30094.1792 | 0 | 100% | Finished | 26966.6191 | 26966.6191 | 100 | 100 | 100 | 100 | 111.5979 | 100
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1447.55 | 0 | 18800.8 | 0 | 100% | Finished | 17353.25 | 17353.25 | 100 | 100 | 100 | 100 | 108.3417 | 100
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 3105.8401 | 0 | 36315.9182 | 0 | 100% | Finished | 33210.0781 | 33210.0781 | 100 | 25 | 100 | 100 | 109.3521 | 100
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 1372.48 | 0 | 11884.6802 | 0 | 100% | Finished | 10512.2002 | 10512.2002 | 100 | 15.625 | 100 | 100 | 113.0561 | 100
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 147.2 | 0 | 1526.99 | 0 | 100% | Finished | 1379.79 | 1379.79 | 100 | 100 | 100 | 100 | 110.6683 | 100
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 6914.6602 | 0 | 71418.0117 | 0 | 100% | Finished | 64503.3516 | 64503.3516 | 100 | 100 | 100 | 100 | 110.7198 | 100
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 3661.55 | 0 | 27433.8508 | 0 | 100% | Finished | 23772.3008 | 23772.3008 | 100 | 100 | 100 | 100 | 115.4026 | 100
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 18307.7402 | 0 | 137169.2637 | 0 | 100% | Finished | 118861.5234 | 118861.5234 | 100 | 200 | 100 | 100 | 115.4026 | 100
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-10-13 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-03 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-17 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-12-01 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-03 08:00 | 15d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 250 | 100 | 100 | 108.2195 | 100
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-24 08:00 | 10d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 166.6667 | 100 | 100 | 108.2195 | 100
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-12-08 08:00 | 15d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 250 | 100 | 100 | 108.2195 | 100
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2009-01-12 08:00 | 10d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 166.6667 | 100 | 100 | 108.2195 | 100
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-11-24 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-12-08 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-12 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-26 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-01 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-16 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-01-20 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-02-03 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2008-12-15 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-01-13 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-03 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-17 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2008-12-15 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 133.3333 | 100 | 100 | 108.1085 | 100
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-01-13 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 108.1085 | 100
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-03 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 108.1085 | 100
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-17 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 108.1085 | 100
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-12 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-27 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-02-17 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-03-03 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-17 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-24 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-03 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-10 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-03 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-24 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-11 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-25 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 | 2009-04-08 08:00 | 17d | 29804.9297 | 0 | 13d | 2562.3 | 0 | 32367.2297 | 0 | 56.67% | Started | 29804.9297 | 29804.9297 | 100 | 56.6667 | 56.6667 | 100 | 108.5969 | 56.6667
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 |  | 0 | 0 | 59293.3281 | 10d | 0 | 0 | 0 | 59293.3281 | 0% | Not Started | 0 | 59293.3281 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2009-06-04 17:00 |  | TP Name | 04/06, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Urban Development Project | 2007-12-07 08:00 | 2009-02-27 17:00 | 291d |  |  | 1537398.5147 |  |  | 1537398.5147 |  | 360d | [5 empty] | 1696971.7869 |  | 100% |  | 1537398.5147 | 1537398.5147
62 | Werfinrichting | 2007-12-07 08:00 | 2007-12-07 17:00 | 1d |  | 0 | 136108 | 0 | 0 | 136108 | 2007-12-07 08:00 | 1d | 136108 | 0 | 0 | 13458.6104 | 0 | 149566.6104 | 0 | 100% | Finished | 136108 | 136108 | 100 | 100 | 100 | 100 | 109.8882 | 100
63 | Grondwerken | 2007-12-17 08:00 | 2007-12-21 17:00 | 5d |  | 0 | 2692.3 | 0 | 0 | 2692.3 | 2007-12-10 08:00 | 5d | 2692.3 | 0 | 0 | 245.79 | 0 | 2938.09 | 0 | 100% | Finished | 2692.3 | 2692.3 | 100 | 100 | 100 | 100 | 109.1294 | 100
64 | Funderingen | 2008-01-07 08:00 | 2008-01-25 17:00 | 15d |  | 0 | 72594.4297 | 0 | 0 | 72594.4297 | 2007-12-31 08:00 | 15d | 72594.4297 | 0 | 0 | 5805.96 | 0 | 78400.3896 | 0 | 100% | Finished | 72594.4297 | 72594.4297 | 100 | 100 | 100 | 100 | 107.9978 | 100
65 | Wanden op V0 | 2008-01-21 08:00 | 2008-02-15 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-01-14 08:00 | 20d | 55480.9805 | 0 | 0 | 5728.1802 | 0 | 61209.1606 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.3246 | 100
66 | Afdekking V0 | 2008-02-11 08:00 | 2008-02-29 17:00 | 15d |  | 0 | 46319.7109 | 0 | 0 | 46319.7109 | 2008-02-04 08:00 | 15d | 46319.7109 | 0 | 0 | 4927.6499 | 0 | 51247.3608 | 0 | 100% | Finished | 46319.7109 | 46319.7109 | 100 | 100 | 100 | 100 | 110.6383 | 100
67 | Wanden op V1 | 2008-02-25 08:00 | 2008-03-21 17:00 | 20d |  | 0 | 55480.9805 | 0 | 0 | 55480.9805 | 2008-02-18 08:00 | 20d | 55480.9805 | 0 | 0 | 5728.1802 | 0 | 61209.1606 | 0 | 100% | Finished | 55480.9805 | 55480.9805 | 100 | 100 | 100 | 100 | 110.3246 | 100
68 | Afdekking V1 | 2008-03-17 08:00 | 2008-03-28 17:00 | 10d |  | 0 | 30879.8105 | 0 | 0 | 30879.8105 | 2008-03-10 08:00 | 10d | 30879.8105 | 0 | 0 | 3285.1001 | 0 | 34164.9106 | 0 | 100% | Finished | 30879.8105 | 30879.8105 | 100 | 100 | 100 | 100 | 110.6383 | 100
69 | Wanden op V2 | 2008-03-31 08:00 | 2008-04-11 17:00 | 10d |  | 0 | 27740.4902 | 0 | 0 | 27740.4902 | 2008-03-31 08:00 | 10d | 27740.4902 | 0 | 0 | 2864.0901 | 0 | 30604.5803 | 0 | 100% | Finished | 27740.4902 | 27740.4902 | 100 | 100 | 100 | 100 | 110.3246 | 100
1 | Afdekking V2 | 2008-04-21 08:00 | 2008-04-25 17:00 | 5d |  | 0 | 23742.4199 | 0 | 0 | 23742.4199 | 2008-04-14 08:00 | 10d | 23742.4199 | 0 | 0 | 2380.4199 | 0 | 26122.8398 | 0 | 100% | Finished | 23742.4199 | 23742.4199 | 100 | 200 | 100 | 100 | 110.026 | 100
2 | Gevelmetselwerk | 2008-04-21 08:00 | 2008-06-06 17:00 | 35d |  | 0 | 128627.4375 | 0 | 0 | 128627.4375 | 2008-04-14 08:00 | 35d | 128627.4375 | 0 | 0 | 15508.4297 | 0 | 144135.8672 | 0 | 100% | Finished | 128627.4375 | 128627.4375 | 100 | 100 | 100 | 100 | 112.0569 | 100
3 | Voegwerk | 2008-05-26 08:00 | 2008-06-20 17:00 | 20d |  | 0 | 3583.3701 | 0 | 0 | 3583.3701 | 2008-05-12 08:00 | 20d | 3583.3701 | 0 | 0 | -2061.99 | 0 | 1521.3801 | 0 | 100% | Finished | 3583.3701 | 3583.3701 | 100 | 100 | 100 | 100 | 42.4567 | 100
4 | Opmeten dorpels | 2008-06-02 08:00 | 2008-06-02 17:00 | 1d |  | 0 | 382.03 | 0 | 0 | 382.03 | 2008-05-19 08:00 | 1d | 382.03 | 0 | 0 | -67.96 | 0 | 314.07 | 0 | 100% | Finished | 382.03 | 382.03 | 100 | 100 | 100 | 100 | 82.2108 | 100
5 | Plaatsen dorpels | 2008-06-09 08:00 | 2008-06-13 17:00 | 5d |  | 0 | 1910.15 | 0 | 0 | 1910.15 | 2008-06-17 08:00 | 5d | 1910.15 | 0 | 0 | -339.78 | 0 | 1570.37 | 0 | 100% | Finished | 1910.15 | 1910.15 | 100 | 100 | 100 | 100 | 82.2119 | 100
6 | Plaatsen bordessen + prefabtrappen | 2008-06-02 08:00 | 2008-06-06 17:00 | 5d |  | 0 | 26966.6191 | 0 | 0 | 26966.6191 | 2008-05-19 08:00 | 5d | 26966.6191 | 0 | 0 | 3127.5601 | 0 | 30094.1792 | 0 | 100% | Finished | 26966.6191 | 26966.6191 | 100 | 100 | 100 | 100 | 111.5979 | 100
7 | Plaatsen RW afvoerbuizen + voorlopige aansluiting | 2008-05-26 08:00 | 2008-05-30 17:00 | 5d |  | 0 | 17353.25 | 0 | 0 | 17353.25 | 2008-05-12 08:00 | 5d | 17353.25 | 0 | 0 | 1447.55 | 0 | 18800.8 | 0 | 100% | Finished | 17353.25 | 17353.25 | 100 | 100 | 100 | 100 | 108.3417 | 100
8 | Dakopstanden | 2008-04-28 08:00 | 2008-05-23 17:00 | 20d |  | 0 | 33210.0781 | 0 | 0 | 33210.0781 | 2008-04-28 08:00 | 5d | 33210.0781 | 0 | 0 | 3105.8401 | 0 | 36315.9182 | 0 | 100% | Finished | 33210.0781 | 33210.0781 | 100 | 25 | 100 | 100 | 109.3521 | 100
9 | Technieken / leidingen in dak | 2008-05-26 08:00 | 2008-07-08 17:00 | 32d |  | 0 | 10512.2002 | 0 | 0 | 10512.2002 | 2008-05-12 08:00 | 5d | 10512.2002 | 0 | 0 | 1372.48 | 0 | 11884.6802 | 0 | 100% | Finished | 10512.2002 | 10512.2002 | 100 | 15.625 | 100 | 100 | 113.0561 | 100
10 | Schuimbeton | 2008-07-09 08:00 | 2008-08-05 17:00 | 5d |  | 0 | 1379.79 | 0 | 0 | 1379.79 | 2008-05-19 08:00 | 5d | 1379.79 | 0 | 0 | 147.2 | 0 | 1526.99 | 0 | 100% | Finished | 1379.79 | 1379.79 | 100 | 100 | 100 | 100 | 110.6683 | 100
11 | Isolatie + roofing platte daken | 2008-08-06 08:00 | 2008-09-02 17:00 | 20d |  | 0 | 64503.3516 | 0 | 0 | 64503.3516 | 2008-06-09 08:00 | 20d | 64503.3516 | 0 | 0 | 6914.6602 | 0 | 71418.0117 | 0 | 100% | Finished | 64503.3516 | 64503.3516 | 100 | 100 | 100 | 100 | 110.7198 | 100
12 | Opmeten ramen en deuren | 2008-06-09 08:00 | 2008-06-09 17:00 | 1d |  | 0 | 23772.3008 | 0 | 0 | 23772.3008 | 2008-06-02 08:00 | 1d | 23772.3008 | 0 | 0 | 3661.55 | 0 | 27433.8508 | 0 | 100% | Finished | 23772.3008 | 23772.3008 | 100 | 100 | 100 | 100 | 115.4026 | 100
13 | Plaatsen ramen en deuren | 2008-06-16 08:00 | 2008-06-20 17:00 | 5d |  | 0 | 118861.5234 | 0 | 0 | 118861.5234 | 2008-08-19 08:00 | 10d | 118861.5234 | 0 | 0 | 18307.7402 | 0 | 137169.2637 | 0 | 100% | Finished | 118861.5234 | 118861.5234 | 100 | 200 | 100 | 100 | 115.4026 | 100
14 | Plaatsen gipsblokken_blok 1 | 2008-09-03 08:00 | 2008-09-09 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-07-07 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
15 | Plaatsen gipsblokken_blok 2 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-11 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
16 | Plaatsen gipsblokken_blok 3 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-08-25 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
17 | Plaatsen gipsblokken_blok 4 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 10562.0996 | 0 | 0 | 10562.0996 | 2008-09-08 08:00 | 10d | 10562.0996 | 0 | 0 | 1316.5601 | 0 | 11878.6597 | 0 | 100% | Finished | 10562.0996 | 10562.0996 | 100 | 200 | 100 | 100 | 112.4649 | 100
18 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-10 08:00 | 2008-09-16 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-11 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
19 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 2 | 2008-09-17 08:00 | 2008-09-23 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-08-25 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
20 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 3 | 2008-09-24 08:00 | 2008-09-30 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-08 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
21 | Voorbereidingen elektriciteit / sanitair / HVAC_blok 4 | 2008-10-01 08:00 | 2008-10-07 17:00 | 5d |  | 0 | 22595.0996 | 0 | 0 | 22595.0996 | 2008-09-22 08:00 | 5d | 22595.0996 | 0 | 0 | 2247.98 | 0 | 24843.0796 | 0 | 100% | Finished | 22595.0996 | 22595.0996 | 100 | 100 | 100 | 100 | 109.949 | 100
22 | Plaatsen elektriciteit / sanitair / HVAC_blok 1 | 2008-09-17 08:00 | 2008-09-30 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-10-13 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
23 | Plaatsen elektriciteit / sanitair / HVAC_blok 2 | 2008-10-01 08:00 | 2008-10-14 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-03 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
24 | Plaatsen elektriciteit / sanitair / HVAC_blok 3 | 2008-10-15 08:00 | 2008-11-04 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-11-17 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
25 | Plaatsen elektriciteit / sanitair / HVAC_blok 4 | 2008-11-05 08:00 | 2008-11-18 17:00 | 10d |  | 0 | 45190.1992 | 0 | 0 | 45190.1992 | 2008-12-01 08:00 | 10d | 45190.1992 | 0 | 0 | 4495.9502 | 0 | 49686.1494 | 0 | 100% | Finished | 45190.1992 | 45190.1992 | 100 | 100 | 100 | 100 | 109.9489 | 100
26 | Opmeten keukens_blok 1 | 2008-10-01 08:00 | 2008-10-01 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
27 | Opmeten keukens_blok 2 | 2008-10-15 08:00 | 2008-10-15 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-12 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
28 | Opmeten keukens_blok 3 | 2008-11-05 08:00 | 2008-11-05 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
29 | Opmeten keukens_blok 4 | 2008-11-19 08:00 | 2008-11-19 17:00 | 1d |  | 0 | 1517.39 | 0 | 0 | 1517.39 | 2009-01-26 08:00 | 1d | 1517.39 | 0 | 0 | 127.15 | 0 | 1644.54 | 0 | 100% | Finished | 1517.39 | 1517.39 | 100 | 100 | 100 | 100 | 108.3795 | 100
30 | Pleisterwerken_blok 1 | 2008-10-01 08:00 | 2008-10-08 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-03 08:00 | 15d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 250 | 100 | 100 | 108.2195 | 100
31 | Pleisterwerken_blok 2 | 2008-10-15 08:00 | 2008-10-22 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-11-24 08:00 | 10d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 166.6667 | 100 | 100 | 108.2195 | 100
32 | Pleisterwerken_blok 3 | 2008-11-05 08:00 | 2008-11-12 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2008-12-08 08:00 | 15d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 250 | 100 | 100 | 108.2195 | 100
33 | Pleisterwerken_blok 4 | 2008-11-19 08:00 | 2008-11-26 17:00 | 6d |  | 0 | 13287.2803 | 0 | 0 | 13287.2803 | 2009-01-12 08:00 | 10d | 13287.2803 | 0 | 0 | 1092.15 | 0 | 14379.4303 | 0 | 100% | Finished | 13287.2803 | 13287.2803 | 100 | 166.6667 | 100 | 100 | 108.2195 | 100
34 | Schuimbeton_blok 1 | 2008-10-09 08:00 | 2008-10-13 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-11-24 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
35 | Schuimbeton_blok 2 | 2008-10-23 08:00 | 2008-11-03 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2008-12-08 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
36 | Schuimbeton_blok 3 | 2008-11-13 08:00 | 2008-11-17 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-12 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
37 | Schuimbeton_blok 4 | 2008-11-27 08:00 | 2008-12-01 12:00 | 2d 4h |  | 0 | 689.89 | 0 | 0 | 689.89 | 2009-01-26 08:00 | 1d | 689.89 | 0 | 0 | 73.6 | 0 | 763.49 | 0 | 100% | Finished | 689.89 | 689.89 | 100 | 40 | 100 | 100 | 110.6684 | 100
38 | Chape_blok 1 | 2008-10-13 13:00 | 2008-10-15 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-01 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
39 | Chape_blok 2 | 2008-11-03 13:00 | 2008-11-05 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2008-12-16 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
40 | Chape_blok 3 | 2008-11-17 13:00 | 2008-11-19 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-01-20 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
41 | Chape_blok 4 | 2008-12-01 13:00 | 2008-12-03 17:00 | 2d 4h |  | 0 | 3740.6699 | 0 | 0 | 3740.6699 | 2009-02-03 08:00 | 10d | 3740.6699 | 0 | 0 | 313.73 | 0 | 4054.3999 | 0 | 100% | Finished | 3740.6699 | 3740.6699 | 100 | 400 | 100 | 100 | 108.387 | 100
42 | Opmeten binnendeuren_blok 1 | 2008-10-16 08:00 | 2008-10-16 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2008-12-15 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
43 | Opmeten binnendeuren_blok 2 | 2008-11-06 08:00 | 2008-11-06 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-01-13 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
44 | Opmeten binnendeuren_blok 3 | 2008-11-20 08:00 | 2008-11-20 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-03 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
45 | Opmeten binnendeuren_blok 4 | 2008-12-04 08:00 | 2008-12-04 17:00 | 1d |  | 0 | 877.83 | 0 | 0 | 877.83 | 2009-02-17 08:00 | 1d | 877.83 | 0 | 0 | 76.81 | 0 | 954.64 | 0 | 100% | Finished | 877.83 | 877.83 | 100 | 100 | 100 | 100 | 108.75 | 100
46 | Vloerafwerking_blok 1 | 2008-10-16 08:00 | 2008-11-03 12:00 | 7d 4h |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2008-12-15 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 133.3333 | 100 | 100 | 108.1085 | 100
47 | Vloerafwerking_blok 2 | 2008-11-06 08:00 | 2008-11-14 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-01-13 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 108.1085 | 100
48 | Vloerafwerking_blok 3 | 2008-11-20 08:00 | 2008-11-28 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-03 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 108.1085 | 100
49 | Vloerafwerking_blok 4 | 2008-12-04 08:00 | 2008-12-12 17:00 | 7d |  | 0 | 22771.2695 | 0 | 0 | 22771.2695 | 2009-02-17 08:00 | 10d | 22771.2695 | 0 | 0 | 1846.4 | 0 | 24617.6696 | 0 | 100% | Finished | 22771.2695 | 22771.2695 | 100 | 142.8571 | 100 | 100 | 108.1085 | 100
50 | Plaatsen badkamers_blok 1 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-12 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
51 | Plaatsen badkamers_blok 2 | 2008-11-17 08:00 | 2008-11-28 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-01-27 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
52 | Plaatsen badkamers_blok 3 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-02-17 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
53 | Plaatsen badkamers_blok 4 | 2008-12-15 08:00 | 2009-01-09 17:00 | 10d |  | 0 | 755.04 | 0 | 0 | 755.04 | 2009-03-03 08:00 | 5d | 755.04 | 0 | 0 | 136.61 | 0 | 891.65 | 0 | 100% | Finished | 755.04 | 755.04 | 100 | 50 | 100 | 100 | 118.0931 | 100
54 | Plaatsen keukens_blok 1 | 2008-10-16 08:00 | 2008-11-05 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-17 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
55 | Plaatsen keukens_blok 2 | 2008-11-06 08:00 | 2008-11-19 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-02-24 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
56 | Plaatsen keukens_blok 3 | 2008-11-20 08:00 | 2008-12-03 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-03 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
57 | Plaatsen keukens_blok 4 | 2008-12-04 08:00 | 2008-12-17 17:00 | 10d |  | 0 | 15173.8604 | 0 | 0 | 15173.8604 | 2009-03-10 08:00 | 5d | 15173.8604 | 0 | 0 | 1271.54 | 0 | 16445.4004 | 0 | 100% | Finished | 15173.8604 | 15173.8604 | 100 | 50 | 100 | 100 | 108.3798 | 100
58 | Plaatsen binnendeuren_blok 1 | 2008-11-04 08:00 | 2008-11-10 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-03 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
59 | Plaatsen binnendeuren_blok 2 | 2008-11-17 08:00 | 2008-11-21 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-02-24 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
60 | Plaatsen binnendeuren_blok 3 | 2008-12-01 08:00 | 2008-12-05 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-11 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
61 | Plaatsen binnendeuren_blok 4 | 2008-12-15 08:00 | 2008-12-19 17:00 | 5d |  | 0 | 4389.1299 | 0 | 0 | 4389.1299 | 2009-03-25 08:00 | 10d | 4389.1299 | 0 | 0 | 384.07 | 0 | 4773.1999 | 0 | 100% | Finished | 4389.1299 | 4389.1299 | 100 | 200 | 100 | 100 | 108.7505 | 100
70 | Schilderwerken | 2009-01-05 08:00 | 2009-02-13 17:00 | 30d |  | 0 | 29804.9297 | 0 | 0 | 29804.9297 | 2009-04-08 08:00 | 30d | 29804.9297 | 0 | 0 | 2562.3 | 0 | 32367.2297 | 0 | 100% | Finished | 29804.9297 | 29804.9297 | 100 | 100 | 100 | 100 | 108.5969 | 100
71 | Opkuis | 2009-02-16 08:00 | 2009-02-27 17:00 | 10d |  | 0 | 59293.3281 | 0 | 0 | 59293.3281 | 2009-05-22 08:00 | 10d | 59293.3281 | 0 | 0 | 7933.5098 | 0 | 67226.8379 | 0 | 100% | Finished | 59293.3281 | 59293.3281 | 100 | 100 | 100 | 100 | 113.3801 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2008-07-14
1:00 - 2:00 | No | Tuesday | Yes | 2008-07-15
2:00 - 3:00 | No | Wednesday | Yes | 2008-07-16
3:00 - 4:00 | No | Thursday | Yes | 2008-07-17
4:00 - 5:00 | No | Friday | Yes | 2008-07-18
5:00 - 6:00 | No | Saturday | No | 2008-07-19
6:00 - 7:00 | No | Sunday | No | 2008-07-20
7:00 - 8:00 | No |  |  | 2008-07-21
8:00 - 9:00 | Yes |  |  | 2008-07-22
9:00 - 10:00 | Yes |  |  | 2008-07-23
10:00 - 11:00 | Yes |  |  | 2008-07-24
11:00 - 12:00 | Yes |  |  | 2008-07-25
12:00 - 13:00 | No |  |  | 2008-07-26
13:00 - 14:00 | Yes |  |  | 2008-07-27
14:00 - 15:00 | Yes |  |  | 2008-07-28
15:00 - 16:00 | Yes |  |  | 2008-07-29
16:00 - 17:00 | Yes |  |  | 2008-07-30
17:00 - 18:00 | No |  |  | 2008-07-31
18:00 - 19:00 | No |  |  | 2008-08-01
19:00 - 20:00 | No |  |  | 2008-08-02
20:00 - 21:00 | No |  |  | 2008-08-03
21:00 - 22:00 | No |  |  | 2008-10-05
22:00 - 23:00 | No |  |  | 2008-10-27
23:00 - 0:00 | No |  |  | 2008-10-28
2008-10-29
2008-10-30
Generated by PMConverter v1.1.3 |  |  |  | 2008-10-31
2008-12-22
2008-12-23
2008-12-24
2008-12-25
2008-12-26
2008-12-27
2008-12-29
2008-12-30
2008-12-31
2009-01-01
2009-01-02
2009-01-03

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
31/12, 2007 | 2007-12-07 08:00 | 2007-12-31 17:00 | 138800.3 | 211394.7297 | 216156.3497 | 2008-01-07 09:00 | 72594.4297 | 152.3% | -4761.6199 | 97.8% | 4d 1h | 124.3% | 100% | 2009-02-10 10:00 | 2008-09-22 09:00 | 2008-09-26 11:00 | 2009-02-17 09:00 | 2008-09-22 09:00 | 2008-09-25 17:00 | 2009-02-23 16:00 | 2008-11-27 09:00 | 2008-12-04 09:00 | 1542160.1347 | 1572028.0791 | 1086801.1545 | 1283236.3187 | 1106412.2378 | 1307272.0609 | 1436053.6781 | 1502406.5919 | 1.2426 | 0.97797 | 1.523 | 1 | 4.125 | 0.97797 | 1 | 1.2426 | 1
28/02, 2008 | 2007-12-31 17:00 | 2008-02-28 17:00 | 368676.4016 | 368676.4016 | 381091.8616 | 2008-02-28 17:00 | 0 | 100% | -12415.4599 | 96.74% | 0 | 100% | 100% | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-13 15:00 | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-11 15:00 | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-11 15:00 | 1549813.9747 | 1589171.5862 | 1549813.9747 | 1549813.9747 | 1589171.5862 | 1589171.5862 | 1581089.419 | 1581089.419 | 1 | 0.96742 | 1 | 1 | 0 | 0.96742 | 1 | 1 | 1
31/03, 2008 | 2008-02-28 17:00 | 2008-03-31 17:00 | 427296.7024 | 427296.7024 | 447206.4123 | 2008-03-31 17:00 | 0 | 100% | -19909.7099 | 95.55% | 0 | 100% | 100% | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-19 12:00 | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-13 15:00 | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-13 15:00 | 1557308.2246 | 1609032.951 | 1557308.2246 | 1557308.2246 | 1609032.951 | 1609032.951 | 1598305.9514 | 1598305.9514 | 1 | 0.95548 | 1 | 1 | 0 | 0.95548 | 1 | 1 | 1
23/04, 2008 | 2008-03-31 17:00 | 2008-04-23 17:00 | 579666.5598 | 579666.5598 | 600882.0797 | 2008-04-23 17:00 | 0 | 100% | -21215.5199 | 96.47% | 0 | 100% | 100% | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-16 14:00 | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-10 17:00 | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-03-10 17:00 | 1558614.0346 | 1593666.5678 | 1558614.0346 | 1558614.0346 | 1593666.5678 | 1593666.5678 | 1586452.2878 | 1586452.2878 | 1 | 0.96469 | 1 | 1 | 0 | 0.96469 | 1 | 1 | 1
30/09, 2008 | 2008-04-23 17:00 | 2008-09-30 17:00 | 1037325.1197 | 1014730.0201 | 1100324.4797 | 2008-09-23 17:00 | -22595.0996 | 97.82% | -85594.4595 | 92.22% | -5d | 97.47% | 95.5% | 2009-03-06 10:00 | 2009-03-10 12:00 | 2009-04-14 14:00 | 2009-03-06 11:00 | 2009-03-10 12:00 | 2009-03-20 16:00 | 2009-03-06 17:00 | 2009-03-11 12:00 | 2009-03-23 17:00 | 1622992.9743 | 1667081.0829 | 1634631.2884 | 1636533.6089 | 1679701.1115 | 1681763.8964 | 1660279.5869 | 1660696.2818 | 0.97475 | 0.92221 | 0.97822 | 0.955 | -5 | 0.92221 | 1 | 0.97475 | 1
21/10, 2008 | 2008-09-30 17:00 | 2008-10-21 17:00 | 1223163.4782 | 1059920.2193 | 1145666.8589 | 2008-09-30 17:00 | -163243.2589 | 86.65% | -85746.6395 | 92.52% | -15d | 92.96% | 100% | 2009-04-13 16:00 | 2009-05-01 16:00 | 2009-06-09 17:00 | 2009-04-09 11:00 | 2009-05-01 16:00 | 2009-05-15 15:00 | 2009-03-20 17:00 | 2009-03-31 17:00 | 2009-04-13 09:00 | 1623145.1543 | 1661772.7401 | 1696683.8146 | 1659317.7524 | 1741260.6152 | 1700871.6705 | 1668396.5123 | 1661279.867 | 0.92958 | 0.92516 | 0.86654 | 1 | -15 | 0.92516 | 1 | 0.92958 | 1
31/10, 2008 | 2008-10-21 17:00 | 2008-10-31 17:00 | 1223853.3682 | 1059920.2193 | 1147890.8286 | 2008-09-30 17:00 | -163933.1489 | 86.61% | -87970.6093 | 92.34% | -18d | 91.67% | 100% | 2009-04-13 17:00 | 2009-05-01 17:00 | 2009-06-10 16:00 | 2009-04-09 16:00 | 2009-05-01 17:00 | 2009-05-15 17:00 | 2009-03-25 17:00 | 2009-04-07 12:00 | 2009-04-17 16:00 | 1625369.124 | 1664998.5752 | 1699218.5695 | 1668776.2418 | 1744977.3317 | 1712008.3703 | 1671498.4659 | 1665749.7186 | 0.91667 | 0.92336 | 0.86605 | 1 | -18 | 0.92336 | 1 | 0.91667 | 1
31/03, 2009 | 2008-10-31 17:00 | 2009-03-31 17:00 | 1537398.5147 | 1448300.2569 | 1595319.6378 | 2008-12-19 17:00 | -89098.2578 | 94.2% | -147019.3809 | 90.78% | -62d | 80.19% | 100% | 2009-03-24 16:00 | 2009-03-25 16:00 | 2009-05-08 10:00 | 2009-04-27 09:00 | 2009-04-28 10:00 | 2009-04-30 10:00 | 2009-05-26 17:00 | 2009-06-09 16:00 | 2009-06-16 17:00 | 1684417.8956 | 1693462.4088 | 1689899.1482 | 1706426.2302 | 1699500.0725 | 1717704.8462 | 1692728.4381 | 1695807.3733 | 0.80192 | 0.90784 | 0.94205 | 1 | -62 | 0.90784 | 1 | 0.80192 | 1
30/04, 2009 | 2009-03-31 17:00 | 2009-04-30 17:00 | 1537398.5147 | 1478105.1866 | 1629744.949 | 2009-02-13 17:00 | -59293.3281 | 96.14% | -151639.7624 | 90.7% | -54d | 83.88% | 100% | 2009-03-17 10:00 | 2009-03-17 14:00 | 2009-04-29 15:00 | 2009-05-19 16:00 | 2009-05-20 12:00 | 2009-05-21 16:00 | 2009-05-14 17:00 | 2009-05-18 16:00 | 2009-05-20 09:00 | 1689038.2771 | 1695121.2178 | 1691416.7944 | 1700432.7245 | 1697743.7487 | 1707684.6289 | 1694345.1538 | 1696118.6875 | 0.83881 | 0.90695 | 0.96143 | 1 | -54 | 0.90695 | 1 | 0.83881 | 1
04/06, 2009 | 2009-04-30 17:00 | 2009-06-04 17:00 | 1537398.5147 | 1537398.5147 | 1696971.7869 | 2009-02-27 17:00 | 0 | 100% | -159573.2721 | 90.6% | -69d | 80.83% | 100% | 2009-02-27 17:00 | 2009-02-27 17:00 | 2009-04-13 10:00 | 2009-06-04 17:00 | 2009-06-04 17:00 | 2009-06-04 17:00 | 2009-06-04 17:00 | 2009-06-04 17:00 | 2009-06-04 17:00 | 1696971.7869 | 1696971.7869 | 1696971.7869 | 1696971.7869 | 1696971.7869 | 1696971.7869 | 1696971.7869 | 1696971.7869 | 0.80833 | 0.90597 | 1 | 1 | -69 | 0.90597 | 1 | 0.80833 | 1