## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Recreation Complex | 1 |  |  | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 | 572.375
1 | START DER WERKEN SPORTHAL | 1.1 |  | FS4;FS6 | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
2 | Totale uitvoeringstermijn | 1.2 |  |  | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 | 572.375
3 | WERFINRICHTING | 1.2.1 |  |  | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 | 3.375
4 | Plaatsen van de werfketen en werfuitrusting | 1.2.1.1 | 1FS |  | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 3.375
5 | VOORBEREIDENDE WERKEN | 1.2.2 |  |  | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 | 142.375
6 | Opzoeken ondergrondse leidingen | 1.2.2.1 | 1FS | FS12-2d | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2.375
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 1.2.2.2 |  |  | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 | 63.375
265 | Voorstel materiaal nieuwe muur | 1.2.2.2.1 | 15FS | FS266+1w | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 1.2.2.2.2 | 265FS+1w | FS267 | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 3.375
267 | Fundering nieuwe te metsen muur | 1.2.2.2.3 | 266FS |  | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 6.375
8 | Aanleggen onderfundering parking (zone P) | 1.2.2.2.4 | 15FS | FS9;FS22 | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 5.375
9 | Metselwerk omgeving nieuwe parking | 1.2.2.2.5 | 8FS | FS10-3d | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 20.375
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 1.2.2.2.6 | 9FS-3d |  | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 41.375
11 | AFBRAAKWERKEN | 1.2.2.3 |  |  | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 | 141.375
12 | Verwijderen vegetatie en bomen | 1.2.2.3.1 | 6FS-2d | FS13 | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 6.375
13 | Afbraak verhardingen / funderingen | 1.2.2.3.2 | 12FS | SS15+3d | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 134.375
14 | GRONDWERKEN | 1.2.2.4 |  |  | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 | 12.375
15 | Uitgraving - grondverzet nieuwe sporthal | 1.2.2.4.1 | 13SS+3d | FS8;FS18;FS265 | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 12.375
16 | STABILITEIT | 1.2.3 |  |  | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 | 347.375
17 | GRONDWERKEN EN FUNDERINGEN | 1.2.3.1 |  |  | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 | 20.375
18 | Uitzetten palen / gebouw | 1.2.3.1.1 | 15FS | FS19;FS22 | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 1.375
19 | Uitvoeren funderingspalen + afkappen | 1.2.3.1.2 | 18FS | FS20 | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 14.375
20 | Uitgraving en aanvuling voor funderingen - riolering | 1.2.3.1.3 | 19FS | FS61 | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 1.375
21 | SONDERINGEN | 1.2.3.2 |  |  | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 | 6.375
22 | Verkenningsputten bestaande fundering | 1.2.3.2.1 | 8FS;18FS |  | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 6.375
23 | OPEN RUWBOUW ALGEMEEN | 1.2.3.3 |  |  | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 | 347.375
163 | Liftput | 1.2.3.3.1 |  |  | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 1.375
24 | Werkvloer fundering paalkoppen | 1.2.3.3.2 | 61FS-1w 3d | SS164;FS165 | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 1.375
164 | Aardingslus | 1.2.3.3.3 | 24SS | SS165 | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 0.375
165 | Afkappen palen | 1.2.3.3.4 | 24FS;164SS | SS166+1d | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2.375
166 | Bekisting funderingszolen en paalkoppen | 1.2.3.3.5 | 165SS+1d | FS167-2w 3d | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 20.375
167 | Montage torenkraan | 1.2.3.3.6 | 166FS-2w 3d | FS168 | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 1.375
168 | Wapening paalkoppen en balken | 1.2.3.3.7 | 167FS | SS169 | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 13.375
169 | Randbekisting vloerplaat | 1.2.3.3.8 | 168SS | FS170-1d | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 6.375
170 | Bekisting paalkoppen, balken + beton | 1.2.3.3.9 | 169FS-1d | FS171 | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 13.375
171 | Grondwerk vloerplaat + werkvloer | 1.2.3.3.10 | 170FS | FS38-1w 2d | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 9.375
38 | Wapening vloerplaat | 1.2.3.3.11 | 171FS-1w 2d | FS173-4d | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 4.375
172 | GOEDKEURING ANKERPLATEN | 1.2.3.3.12 |  | FS173 | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
173 | Plaatsen isolatie + ankers staalconstructie | 1.2.3.3.13 | 38FS-4d;172FS | FS174-3d | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 12.375
174 | Beton vloerplaat fase 1 | 1.2.3.3.14 | 173FS-3d | FS40-1w 1d | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 1.375
40 | Ontkisten randbekisting vloerplaat | 1.2.3.3.15 | 174FS-1w 1d | SS175 | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 0.375
175 | Plaatsen neopreen + isolatie | 1.2.3.3.16 | 40SS | FS176 | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 0.375
176 | Beton vloerplaat fase 2 | 1.2.3.3.17 | 175FS | FS177 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 1.375
177 | Ontkisten vloerplaat fase 2 | 1.2.3.3.18 | 176FS | FS179 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2.375
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 1.2.3.3.19 |  | FS179 | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
179 | Plaatsen plinten | 1.2.3.3.20 | 177FS;178FS | FS180-3d | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 7.375
180 | Bekisting wanden | 1.2.3.3.21 | 179FS-3d | SS181+2d | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 30.375
181 | Metselwerken | 1.2.3.3.22 | 180SS+2d | SS184+2d | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 39.375
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 1.2.3.3.23 |  | FS184 | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 1.2.3.3.24 |  | FS184 | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
184 | Plaatsen metalen kolommen tribune | 1.2.3.3.25 | 181SS+2d;182FS;183FS | FS185 | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 1.375
185 | Plaatsen prefabconstructies | 1.2.3.3.26 | 184FS | FS42-2w 1d | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 9.375
188 | Ruwbouw sporthal | 1.2.3.3.27 |  |  | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 | 103.375
43 | Staalstructuur sporthal | 1.2.3.3.27.1 | 42FS |  | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 16.375
187 | Gelameleerde liggers sporthal + staalconstructie dak | 1.2.3.3.27.2 | 45FS | FS189;FS205;FS146;FS142;FS138;FS131 | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 6.375
189 | Steeldeck sporthal | 1.2.3.3.27.3 | 187FS | FS190;FS192 | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 11.375
190 | Dakopstanden sporthal | 1.2.3.3.27.4 | 189FS | FS220 | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 1.375
192 | Afvoer hemelwater sporthal/berging | 1.2.3.3.27.5 | 189FS | FS223 | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2.375
205 | Staalconstructie technisch lokaal fase 1 | 1.2.3.3.27.6 | 187FS | FS206 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2.375
206 | Welfsels technisch lokaal fase 1 | 1.2.3.3.27.7 | 205FS | FS207 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 0.375
207 | Wapening en bekisting technisch lokaal | 1.2.3.3.27.8 | 206FS | FS208 | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 4.375
208 | Bekisting / storten ringbalk / beton welfsels | 1.2.3.3.27.9 | 207FS | FS209 | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 1.375
209 | Luchtgroep technisch lokaal | 1.2.3.3.27.10 | 208FS | FS210 | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 0.375
210 | Metselwerk technisch lokaal fase 1 | 1.2.3.3.27.11 | 209FS |  | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 4.375
201 | Ruwbouw cafetaria | 1.2.3.3.28 |  |  | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 | 123.375
42 | Staalstructuur nv 0 | 1.2.3.3.28.1 | 185FS-2w 1d | FS202;FS43;FS211;FS45+2w 4d | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 11.375
211 | Opgieten voetplaten cafetaria | 1.2.3.3.28.2 | 42FS |  | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 1.375
45 | Staalstructuur nv 1 | 1.2.3.3.28.3 | 42FS+2w 4d;202FS | FS187;FS213-2d;FS203 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 9.375
202 | Welfsels fase 1 (boven +0) | 1.2.3.3.28.4 | 42FS | FS212;FS45 | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 7.375
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 1.2.3.3.28.5 | 202FS |  | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 0.375
213 | Wapening / bekisting welfsels boven +0 | 1.2.3.3.28.6 | 45FS-2d | FS214 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 5.375
203 | Beton op welfsels boven +0 | 1.2.3.3.28.7 | 45FS | FS214;FS66 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 3.375
214 | Welfsels fase 3 (boven +1) | 1.2.3.3.28.8 | 203FS;213FS | FS215-2d | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2.375
215 | Wapening / bekisting welfsels boven +1 | 1.2.3.3.28.9 | 214FS-2d | FS216 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 5.375
216 | Beton op welfsels boven +1 | 1.2.3.3.28.10 | 215FS | FS217 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 0.375
50 | Dragend metselwerk nv 1 | 1.2.3.3.28.11 |  |  | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 4.375
217 | Timmerwerk cafetaria, houtbouw | 1.2.3.3.28.12 | 216FS | FS218;FS219+1w;FS234;FS239 | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 7.375
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 1.2.3.3.28.13 | 217FS;220FS | FS232 | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 14.375
56 | UPN gevelprofielen | 1.2.3.3.28.14 | 239FS-7w |  | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 6.375
219 | AFBRAAK TORENKRAAN | 1.2.3.3.28.15 | 217FS+1w |  | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 0.375
57 | ARCHITECTUUR | 1.2.4 |  |  | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 | 572.375
58 | AFBRAAKWERKEN | 1.2.4.1 |  |  | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 | 9.375
59 | Maken nieuwe deuropeningen in bestaande sporthal | 1.2.4.1.1 | 238SF |  | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 9.375
60 | RIOLERINGSNET | 1.2.4.2 |  |  | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 | 20.375
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 1.2.4.2.1 | 20FS | FS24-1w 3d | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 20.375
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 1.2.4.3 |  |  | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 | 20.375
66 | Plinten, dorpels en vloerplaten | 1.2.4.3.1 | 203FS | FS241 | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 20.375
221 | SPORTHAL OPBOUW | 1.2.4.4 |  |  | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 | 82.375
220 | Dakopstanden lichtstraat sporthal | 1.2.4.4.1 | 190FS | FS218;FS226 | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 3.375
223 | Dampremmende laag | 1.2.4.4.2 | 192FS;226FS | FS224 | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 0.375
224 | Isolatie | 1.2.4.4.3 | 223FS | FS225 | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 7.375
225 | Dakdichting | 1.2.4.4.4 | 224FS | FS235;SS227;FS79+1w;FS113+4w;FS115+3w | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 13.375
226 | Lichtstraat sporthal | 1.2.4.4.5 | 220FS | FS223 | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 0.375
227 | Dak en wandbeplating sporthal | 1.2.4.4.6 | 225SS | FS228;FS240 | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 19.375
228 | Grondbussen sporthal | 1.2.4.4.7 | 227FS | FS229 | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 1.375
229 | Scheidingswanden sporthal | 1.2.4.4.8 | 228FS | SS230-3d | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 5.375
230 | Elektriciteit sporthal, constructies voor verlichting | 1.2.4.4.9 | 229SS-3d | SS231 | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 7.375
231 | Kanalen sporthal door gelamelleerde liggers | 1.2.4.4.10 | 230SS | SS222 | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 7.375
222 | Sanitair sporthal | 1.2.4.4.11 | 231SS |  | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 7.375
233 | CAFETARIA OPBOUW | 1.2.4.5 |  |  | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 | 399.375
232 | Plaatsing rookkoepels | 1.2.4.5.1 | 218FS | FS76 | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 1.375
234 | Hellingsbeton | 1.2.4.5.2 | 217FS | FS235 | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 3.375
235 | Isolatie | 1.2.4.5.3 | 234FS;225FS | FS236 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 6.375
236 | EPDM dakdichting | 1.2.4.5.4 | 235FS | SS240;FS78-2d;FS150+4w | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 18.375
237 | Opmeting buitenschrijnwerk | 1.2.4.5.5 |  | FS239+3w;FS76 | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
238 | Houten buitenschrijnwerk | 1.2.4.5.6 | 239SS | SF59 | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 4.375
239 | Aluminium buitenschrijnwerk | 1.2.4.5.7 | 217FS;237FS+3w | SS238;SS241;FS242+1w;FS101-2w 2d;FS153;FS56-7w | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 13.375
240 | Dak en wandbeplating cafetaria | 1.2.4.5.8 | 227FS;236SS |  | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 29.375
241 | Zelfdragend profilit glas | 1.2.4.5.9 | 239SS;66FS |  | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 13.375
242 | Terrasbeplanking | 1.2.4.5.10 | 239FS+1w |  | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 5.375
75 | DAKBEDEKKINGEN - resterende afdekkingen | 1.2.4.6 |  |  | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 | 32.375
76 | Berging sporthal + luifel boven fietsstalling | 1.2.4.6.1 | 232FS;237FS | FS90 | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 32.375
77 | DAKBEDEKKINGSTOEBEHOREN | 1.2.4.7 |  |  | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 | 21.375
78 | Dakrandprofielen | 1.2.4.7.1 | 236FS-2d |  | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 21.375
79 | Valbeveiliging | 1.2.4.7.2 | 225FS+1w |  | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 7.375
89 | BINNENSCHRIJNWERK | 1.2.4.8 |  |  | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 | 44.375
90 | Binnenschrijnwerk (deuren,…) | 1.2.4.8.1 | 111FS-1w 2d;76FS | FS98;FS118-2w | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 | 29.375
91 | Akoestische voorzetwand | 1.2.4.8.2 | 113FS-2w | FS95 | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 | 23.375
92 | BEGLAZING EN SPIEGELS | 1.2.4.9 |  |  | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 | 14.375
93 | Spiegelwand | 1.2.4.9.1 | 112SS-4d |  | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 14.375
94 | IJZERWERK | 1.2.4.10 |  |  | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 | 50.375
95 | Roosters / RVS gaasvulling | 1.2.4.10.1 | 91FS |  | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 30.375
96 | Borstweringen en handgrepen | 1.2.4.10.2 | 111FS+2w |  | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 | 15.375
97 | DEMONTEERBARE WANDEN | 1.2.4.11 |  |  | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 | 6.375
98 | Beglaasde wand | 1.2.4.11.1 | 90FS |  | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 | 3.375
99 | Sanitaire wanden | 1.2.4.11.2 | 111FS+2w |  | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 | 6.375
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 1.2.4.12 |  |  | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 | 36.375
101 | Cementering / bepleistering | 1.2.4.12.1 | 239FS-2w 2d | FS106-3w | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 36.375
102 | VERLAAGDE PLAFONDS | 1.2.4.13 |  |  | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 | 76.375
103 | Structuur verlaagde plafonds | 1.2.4.13.1 | 106FS-2w 2d | FS104+4w | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 | 20.375
104 | Afwerken verlaagde plafonds | 1.2.4.13.2 | 103FS+4w |  | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 | 25.375
105 | DEKVLOEREN EN TOEBEHOREN | 1.2.4.14 |  |  | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 | 36.375
106 | Dekvloeren | 1.2.4.14.1 | 101FS-3w | FS112+1w;FS103-2w 2d;FS111-1w | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 36.375
107 | TEGELWERKEN | 1.2.4.15 |  |  | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 | 13.375
108 | Buiten | 1.2.4.15.1 | 109FS |  | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 6.375
109 | Binnen | 1.2.4.15.2 | 111FS+1w | FS108 | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 6.375
110 | VLOERBEKLEDINGEN | 1.2.4.16 |  |  | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 | 54.375
111 | Gietvloeren | 1.2.4.16.1 | 106FS-1w | FS96+2w;FS99+2w;FS109+1w;FS116+3w;FS90-1w 2d | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 | 29.375
112 | Dansvloer | 1.2.4.16.2 | 106FS+1w | FS264;SS93-4d | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 | 7.375
264 | Plaatsen isolatie sporthal | 1.2.4.16.3 | 112FS |  | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 8.375
113 | Sportvloer | 1.2.4.16.4 | 225FS+4w | FS91-2w | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 | 36.375
114 | MEUBILAIR | 1.2.4.17 |  |  | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 | 50.375
115 | Ophijsbare scheidingswand | 1.2.4.17.1 | 225FS+3w |  | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 14.375
116 | Meubilair | 1.2.4.17.2 | 111FS+3w |  | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 7.375
117 | SCHILDERWERKEN | 1.2.4.18 |  |  | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 | 61.375
118 | Schilderwerk | 1.2.4.18.1 | 90FS-2w | FS120-1w;FS160-3d | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 | 61.375
119 | DIVERSE TOEBEHOREN | 1.2.4.19 |  |  | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 | 25.375
120 | Signalisatie | 1.2.4.19.1 | 118FS-1w |  | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 | 25.375
121 | OMGEVINGSWERKEN | 1.2.4.20 |  |  | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 | 572.375
122 | Aanleg toegangsweg naar zwembad | 1.2.4.20.1 |  | SS123 | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 22.375
123 | Aanleg finse piste tussen parking en zwembad | 1.2.4.20.2 | 122SS | FS124+1w;SS126;SS246 | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 24.375
124 | Aanleg finse piste in bos | 1.2.4.20.3 | 123FS+1w | FS125;FS127 | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 13.375
125 | Aanleg finse piste rond voetbaldveld | 1.2.4.20.4 | 124FS |  | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 10.375
126 | Drainageleiding rond nieuwe sporthal | 1.2.4.20.5 | 123SS | FS243 | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 12.375
127 | Planten bomen / haag rond parking | 1.2.4.20.6 | 124FS | SS243 | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 10.375
243 | Afwerken teelaarde | 1.2.4.20.7 | 127SS;126FS | FS247 | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 9.375
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 1.2.4.20.8 |  | FS251;FS245 | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 12.375
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 1.2.4.20.9 | 244FS |  | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 13.375
246 | Riolering voor kolken achter nieuwe sporthal | 1.2.4.20.10 | 123SS |  | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 11.375
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 1.2.4.20.11 | 243FS | SS248 | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 9.375
248 | Grondwerk rond sporthal | 1.2.4.20.12 | 247SS | FS249 | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 9.375
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 1.2.4.20.13 | 248FS | SS250 | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 32.375
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 1.2.4.20.14 | 249SS | FS252 | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 32.375
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 1.2.4.20.15 | 244FS | FS259 | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 11.375
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 1.2.4.20.16 | 250FS | FS253 | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 9.375
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 1.2.4.20.17 | 252FS | SS254 | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 11.375
254 | Pl riolering voor waterafvoer | 1.2.4.20.18 | 253SS | FS255 | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 11.375
255 | Fundering wegenis van sporthal nr ingang | 1.2.4.20.19 | 254FS | FS256;FS260 | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 9.375
256 | Pl boordstenen voor paadje langs scheidingsmuur | 1.2.4.20.20 | 255FS | FS257 | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 8.375
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 1.2.4.20.21 | 256FS | FS258;FS261 | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 8.375
258 | Plaatsen betonstraatstenen | 1.2.4.20.22 | 257FS |  | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 | 41.375
259 | Plaatsen betontegels | 1.2.4.20.23 | 251FS |  | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 8.375
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 1.2.4.20.24 | 255FS | FS261 | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 | 8.375
261 | Plaatsen asfalt | 1.2.4.20.25 | 260FS;257FS | FS262 | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 | 27.375
262 | Boomspiegels | 1.2.4.20.26 | 261FS | FS263 | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 10.375
263 | Diverse acodrains plaatsen ( bij akkoord ) | 1.2.4.20.27 | 262FS |  | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 8.375
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 1.2.5 |  |  | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 | 49.375
131 | Afbraakwerken thv technisch lokaal | 1.2.5.1 | 187FS | FS132+2d | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 6.375
132 | Structuurwerken technisch lokaal | 1.2.5.2 | 131FS+2d | FS133 | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 6.375
133 | Technische uitrusting technisch lokaal | 1.2.5.3 | 132FS | FS134 | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 13.375
134 | Dakwerken thv technisch lokaal | 1.2.5.4 | 133FS | FS135+1w | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 6.375
135 | Ventilatieroosters | 1.2.5.5 | 134FS+1w |  | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2.375
136 | TECHNIEKEN | 1.2.6 |  |  | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 | 149.375
137 | SANITAIR / BRANDBESTRIJDING | 1.2.6.1 |  |  | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 | 149.375
138 | Werken in ruwbouwfase | 1.2.6.1.1 | 187FS | FS139-4w | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 92.375
139 | Opbouw en inbouw in lichte wanden en plafonds | 1.2.6.1.2 | 138FS-4w | FS140-1w 3d | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 62.375
140 | Plaatsen toestellen en afwerking | 1.2.6.1.3 | 139FS-1w 3d | FS160 | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 | 32.375
141 | HVAC | 1.2.6.2 |  |  | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 | 149.375
142 | Werken in ruwbouwfase | 1.2.6.2.1 | 187FS | FS143-4w | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 92.375
143 | Opbouw en inbouw in lichte wanden en plafonds | 1.2.6.2.2 | 142FS-4w | FS144-1w 3d | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 62.375
144 | Plaatsen toestellen en afwerking | 1.2.6.2.3 | 143FS-1w 3d | FS160 | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 32.375
145 | ELEKTRICITEIT | 1.2.6.3 |  |  | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 | 149.375
146 | Werken in ruwbouwfase | 1.2.6.3.1 | 187FS | FS147-4w | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 92.375
147 | Opbouw en inbouw in lichte wanden en plafonds | 1.2.6.3.2 | 146FS-4w | FS148-1w 3d | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 62.375
148 | Plaatsen toestellen en afwerking | 1.2.6.3.3 | 147FS-1w 3d | FS160 | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 32.375
149 | LIFTEN | 1.2.6.4 |  |  | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 | 36.375
150 | Werken in de schachten en machinekamers | 1.2.6.4.1 | 236FS+4w | FS151 | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 22.375
151 | Afwerken liftkooien en deuren | 1.2.6.4.2 | 150FS |  | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 | 11.375
152 | TESTEN | 1.2.7 |  |  | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 | 146.375
153 | Indicatieve blowerdoortest | 1.2.7.1 | 239FS |  | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 1.375
154 | Finale blowerdoortest | 1.2.7.2 | 161FS-2w |  | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 1.375
155 | Thermografische onderzoek | 1.2.7.3 | 161FS-2w |  | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 0.375
156 | EINDE VAN DE WERKEN EN OPLEVERING | 1.2.8 |  |  | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 | 35.375
157 | Opmaak van de plaatsbeschrijving na de werken | 1.2.8.1 | 160FF |  | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 | 1.375
158 | Opbraak van werfuitrustingen | 1.2.8.2 | 160FF-2d |  | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 | 2.375
159 | Voorbereiding oplevering | 1.2.8.3 | 160FF-2d |  | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 | 2.375
160 | Eindopkuis | 1.2.8.4 | 118FS-3d;148FS;144FS;140FS | FF157;FS161;FF158-2d;FF159-2d | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 | 32.375
161 | Oplevering | 1.2.8.5 | 160FS | FS154-2w;FS155-2w | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Recreation Complex | 2872h |  |  |  |  | 99 | 100 | 101
1 | START DER WERKEN SPORTHAL | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Totale uitvoeringstermijn | 2872h |  |  |  |  | 99 | 100 | 101
3 | WERFINRICHTING | 32h |  |  |  |  | 99 | 100 | 101
4 | Plaatsen van de werfketen en werfuitrusting | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | VOORBEREIDENDE WERKEN | 768h |  |  |  |  | 99 | 100 | 101
6 | Opzoeken ondergrondse leidingen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 368h |  |  |  |  | 99 | 100 | 101
265 | Voorstel materiaal nieuwe muur | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
267 | Fundering nieuwe te metsen muur | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Aanleggen onderfundering parking (zone P) | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Metselwerk omgeving nieuwe parking | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | AFBRAAKWERKEN | 760h |  |  |  |  | 99 | 100 | 101
12 | Verwijderen vegetatie en bomen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Afbraak verhardingen / funderingen | 720h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | GRONDWERKEN | 64h |  |  |  |  | 99 | 100 | 101
15 | Uitgraving - grondverzet nieuwe sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | STABILITEIT | 1728h |  |  |  |  | 99 | 100 | 101
17 | GRONDWERKEN EN FUNDERINGEN | 120h |  |  |  |  | 99 | 100 | 101
18 | Uitzetten palen / gebouw | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Uitvoeren funderingspalen + afkappen | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Uitgraving en aanvuling voor funderingen - riolering | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | SONDERINGEN | 40h |  |  |  |  | 99 | 100 | 101
22 | Verkenningsputten bestaande fundering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | OPEN RUWBOUW ALGEMEEN | 1728h |  |  |  |  | 99 | 100 | 101
163 | Liftput | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Werkvloer fundering paalkoppen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | Aardingslus | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | Afkappen palen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | Bekisting funderingszolen en paalkoppen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | Montage torenkraan | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | Wapening paalkoppen en balken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
169 | Randbekisting vloerplaat | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | Bekisting paalkoppen, balken + beton | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | Grondwerk vloerplaat + werkvloer | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Wapening vloerplaat | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | GOEDKEURING ANKERPLATEN | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | Plaatsen isolatie + ankers staalconstructie | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | Beton vloerplaat fase 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Ontkisten randbekisting vloerplaat | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | Plaatsen neopreen + isolatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | Beton vloerplaat fase 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | Ontkisten vloerplaat fase 2 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
179 | Plaatsen plinten | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
180 | Bekisting wanden | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | Metselwerken | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | Plaatsen metalen kolommen tribune | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
185 | Plaatsen prefabconstructies | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
188 | Ruwbouw sporthal | 552h |  |  |  |  | 99 | 100 | 101
43 | Staalstructuur sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
187 | Gelameleerde liggers sporthal + staalconstructie dak | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | Steeldeck sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | Dakopstanden sporthal | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | Afvoer hemelwater sporthal/berging | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
205 | Staalconstructie technisch lokaal fase 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
206 | Welfsels technisch lokaal fase 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
207 | Wapening en bekisting technisch lokaal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
208 | Bekisting / storten ringbalk / beton welfsels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
209 | Luchtgroep technisch lokaal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
210 | Metselwerk technisch lokaal fase 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
201 | Ruwbouw cafetaria | 656h |  |  |  |  | 99 | 100 | 101
42 | Staalstructuur nv 0 | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
211 | Opgieten voetplaten cafetaria | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Staalstructuur nv 1 | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
202 | Welfsels fase 1 (boven +0) | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
213 | Wapening / bekisting welfsels boven +0 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
203 | Beton op welfsels boven +0 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
214 | Welfsels fase 3 (boven +1) | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
215 | Wapening / bekisting welfsels boven +1 | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
216 | Beton op welfsels boven +1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Dragend metselwerk nv 1 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
217 | Timmerwerk cafetaria, houtbouw | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | UPN gevelprofielen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
219 | AFBRAAK TORENKRAAN | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | ARCHITECTUUR | 2872h |  |  |  |  | 99 | 100 | 101
58 | AFBRAAKWERKEN | 64h |  |  |  |  | 99 | 100 | 101
59 | Maken nieuwe deuropeningen in bestaande sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | RIOLERINGSNET | 120h |  |  |  |  | 99 | 100 | 101
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 120h |  |  |  |  | 99 | 100 | 101
66 | Plinten, dorpels en vloerplaten | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
221 | SPORTHAL OPBOUW | 456h |  |  |  |  | 99 | 100 | 101
220 | Dakopstanden lichtstraat sporthal | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
223 | Dampremmende laag | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
224 | Isolatie | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
225 | Dakdichting | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
226 | Lichtstraat sporthal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
227 | Dak en wandbeplating sporthal | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
228 | Grondbussen sporthal | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
229 | Scheidingswanden sporthal | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
230 | Elektriciteit sporthal, constructies voor verlichting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
231 | Kanalen sporthal door gelamelleerde liggers | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
222 | Sanitair sporthal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
233 | CAFETARIA OPBOUW | 2008h |  |  |  |  | 99 | 100 | 101
232 | Plaatsing rookkoepels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
234 | Hellingsbeton | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
235 | Isolatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
236 | EPDM dakdichting | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
237 | Opmeting buitenschrijnwerk | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
238 | Houten buitenschrijnwerk | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
239 | Aluminium buitenschrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
240 | Dak en wandbeplating cafetaria | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
241 | Zelfdragend profilit glas | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
242 | Terrasbeplanking | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | DAKBEDEKKINGEN - resterende afdekkingen | 176h |  |  |  |  | 99 | 100 | 101
76 | Berging sporthal + luifel boven fietsstalling | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | DAKBEDEKKINGSTOEBEHOREN | 120h |  |  |  |  | 99 | 100 | 101
78 | Dakrandprofielen | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | Valbeveiliging | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | BINNENSCHRIJNWERK | 248h |  |  |  |  | 99 | 100 | 101
90 | Binnenschrijnwerk (deuren,…) | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Akoestische voorzetwand | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | BEGLAZING EN SPIEGELS | 80h |  |  |  |  | 99 | 100 | 101
93 | Spiegelwand | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | IJZERWERK | 176h |  |  |  |  | 99 | 100 | 101
95 | Roosters / RVS gaasvulling | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Borstweringen en handgrepen | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | DEMONTEERBARE WANDEN | 40h |  |  |  |  | 99 | 100 | 101
98 | Beglaasde wand | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | Sanitaire wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 208h |  |  |  |  | 99 | 100 | 101
101 | Cementering / bepleistering | 208h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | VERLAAGDE PLAFONDS | 416h |  |  |  |  | 99 | 100 | 101
103 | Structuur verlaagde plafonds | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | Afwerken verlaagde plafonds | 144h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | DEKVLOEREN EN TOEBEHOREN | 200h |  |  |  |  | 99 | 100 | 101
106 | Dekvloeren | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | TEGELWERKEN | 80h |  |  |  |  | 99 | 100 | 101
108 | Buiten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Binnen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | VLOERBEKLEDINGEN | 288h |  |  |  |  | 99 | 100 | 101
111 | Gietvloeren | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Dansvloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
264 | Plaatsen isolatie sporthal | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | Sportvloer | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | MEUBILAIR | 280h |  |  |  |  | 99 | 100 | 101
115 | Ophijsbare scheidingswand | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | Meubilair | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | SCHILDERWERKEN | 232h |  |  |  |  | 99 | 100 | 101
118 | Schilderwerk | 232h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | DIVERSE TOEBEHOREN | 24h |  |  |  |  | 99 | 100 | 101
120 | Signalisatie | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | OMGEVINGSWERKEN | 2872h |  |  |  |  | 99 | 100 | 101
122 | Aanleg toegangsweg naar zwembad | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | Aanleg finse piste tussen parking en zwembad | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | Aanleg finse piste in bos | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Aanleg finse piste rond voetbaldveld | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Drainageleiding rond nieuwe sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | Planten bomen / haag rond parking | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
243 | Afwerken teelaarde | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
246 | Riolering voor kolken achter nieuwe sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
248 | Grondwerk rond sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
254 | Pl riolering voor waterafvoer | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
255 | Fundering wegenis van sporthal nr ingang | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
256 | Pl boordstenen voor paadje langs scheidingsmuur | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
258 | Plaatsen betonstraatstenen | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
259 | Plaatsen betontegels | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
261 | Plaatsen asfalt | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
262 | Boomspiegels | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
263 | Diverse acodrains plaatsen ( bij akkoord ) | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 280h |  |  |  |  | 99 | 100 | 101
131 | Afbraakwerken thv technisch lokaal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Structuurwerken technisch lokaal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | Technische uitrusting technisch lokaal | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Dakwerken thv technisch lokaal | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | Ventilatieroosters | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | TECHNIEKEN | 832h |  |  |  |  | 99 | 100 | 101
137 | SANITAIR / BRANDBESTRIJDING | 832h |  |  |  |  | 99 | 100 | 101
138 | Werken in ruwbouwfase | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | Opbouw en inbouw in lichte wanden en plafonds | 336h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Plaatsen toestellen en afwerking | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | HVAC | 832h |  |  |  |  | 99 | 100 | 101
142 | Werken in ruwbouwfase | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | Opbouw en inbouw in lichte wanden en plafonds | 336h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | Plaatsen toestellen en afwerking | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | ELEKTRICITEIT | 832h |  |  |  |  | 99 | 100 | 101
146 | Werken in ruwbouwfase | 520h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | Opbouw en inbouw in lichte wanden en plafonds | 336h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | Plaatsen toestellen en afwerking | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | LIFTEN | 200h |  |  |  |  | 99 | 100 | 101
150 | Werken in de schachten en machinekamers | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | Afwerken liftkooien en deuren | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | TESTEN | 688h |  |  |  |  | 99 | 100 | 101
153 | Indicatieve blowerdoortest | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | Finale blowerdoortest | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | Thermografische onderzoek | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | EINDE VAN DE WERKEN EN OPLEVERING | 208h |  |  |  |  | 99 | 100 | 101
157 | Opmaak van de plaatsbeschrijving na de werken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Opbraak van werfuitrustingen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | Voorbereiding oplevering | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | Eindopkuis | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | Oplevering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2011-08-11 17:00 |  | TP Name | 11/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 15d | [5 empty] | 433762.439 |  | 7.915% |  | 433762.439 | 222522.9083
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 15d | [5 empty] | 433762.439 |  | 7.915% |  | 433762.439 | 222522.9083
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 140380.5469 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 0 | 0 | 140380.5469 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 100 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 15d | [5 empty] | 249549.8614 |  | 68.06% |  | 249549.8614 | 34856.1895
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 0 | 0 | 685.68 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 |  | 0 | 0 | 704.8 | 2d | 0 | 0 | 0 | 704.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 |  | 0 | 0 | 914.24 | 4d | 0 | 0 | 0 | 914.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 |  | 0 | 0 | 70567.4375 | 15d | 0 | 0 | 0 | 70567.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 |  | 0 | 0 | 43804.2812 | 30d | 0 | 0 | 0 | 43804.2812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 15d | [5 empty] | 34170.5095 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 0 | 0 | 1761.99 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 100 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 6d | 32408.5195 | 0 | 84d | 0 | 0 | 32408.5195 | 0 | 6.667% | Started | 32408.5195 | 32408.5195 | 100 | 6.6667 | 6.6667 | 100 | 100 | 6.6667
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 214693.6719 |  | 100% |  | 214693.6719 | 0
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | 0 | 0 | 214693.6719 | 0 | 100% | Finished | 214693.6719 | 0 | 100 | 50 | 100 | 100 | 100 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 5d | [5 empty] | 43832.0308 |  | 2.516% |  | 43832.0308 | 0
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 5d | [5 empty] | 43832.0308 |  | 44.95% |  | 43832.0308 | 0
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | 0 | 0 | 6743.3901 | 0 | 100% | Finished | 6743.3901 | 0 | 100 | 50 | 100 | 100 | 100 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 4d | 37088.6406 | 0 | 3d | 0 | 0 | 37088.6406 | 0 | 57.14% | Started | 37088.6406 | 0 | 100 | 36.3636 | 57.1429 | 100 | 100 | 57.1429
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 |  | 0 | 0 | 53673.4219 | 2d | 0 | 0 | 0 | 53673.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 |  | 0 | 0 | 2423.4199 | 2d | 0 | 0 | 0 | 2423.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 |  | 0 | 0 | 10115.0801 | 3d | 0 | 0 | 0 | 10115.0801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 |  | 0 | 0 | 47202.8086 | 15d | 0 | 0 | 0 | 47202.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 |  | 0 | 0 | 48212.0312 | 10d | 0 | 0 | 0 | 48212.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 |  | 0 | 0 | 15734.2695 | 5d | 0 | 0 | 0 | 15734.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 |  | 0 | 0 | 38941.5391 | 10d | 0 | 0 | 0 | 38941.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 |  | 0 | 0 | 165891.9375 | 6d | 0 | 0 | 0 | 165891.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 |  | 0 | 0 | 24106.0195 | 5d | 0 | 0 | 0 | 24106.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 |  | 0 | 0 | 2076.48 | 8d | 0 | 0 | 0 | 2076.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 |  | 0 | 0 | 2570.79 | 1d | 0 | 0 | 0 | 2570.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 |  | 0 | 0 | 7712.3799 | 3d | 0 | 0 | 0 | 7712.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 |  | 0 | 0 | 2794.79 | 6d | 0 | 0 | 0 | 2794.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 |  | 0 | 0 | 62937.0781 | 20d | 0 | 0 | 0 | 62937.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 |  | 0 | 0 | 94089.9219 | 20d | 0 | 0 | 0 | 94089.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 |  | 0 | 0 | 519.12 | 2d | 0 | 0 | 0 | 519.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 |  | 0 | 0 | 68166.2578 | 8d | 0 | 0 | 0 | 68166.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 |  | 0 | 0 | 24822.4199 | 17d | 0 | 0 | 0 | 24822.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 |  | 0 | 0 | 3885.53 | 17d | 0 | 0 | 0 | 3885.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 |  | 0 | 0 | 5185.0098 | 8d | 0 | 0 | 0 | 5185.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-08-31 17:00 |  | TP Name | 31/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 28d | [5 empty] | 477009.2202 |  | 9.135% |  | 500660.0409 | 556096.5084
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 28d | [5 empty] | 477009.2202 |  | 9.135% |  | 500660.0409 | 556096.5084
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 134079.5767 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | -6300.9702 | 0 | 134079.5767 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 95.5115 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 28d | [5 empty] | 235928.501 |  | 68.06% |  | 249549.8614 | 321031.5389
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 21.97 | 0 | 707.65 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 103.2041 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 10d | [5 empty] | 0 |  | 0% |  | 0 | 71481.6775
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 |  | 0 | 0 | 704.8 | 2d | 0 | 0 | 0 | 704.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 |  | 0 | 0 | 914.24 | 4d | 0 | 0 | 0 | 914.24 | 0% | Not Started | 0 | 914.24 | 100 |  | 0 | 100 |  | 0
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 |  | 0 | 0 | 70567.4375 | 15d | 0 | 0 | 0 | 70567.4375 | 0% | Not Started | 0 | 70567.4375 | 100 |  | 0 | 100 |  | 0
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 |  | 0 | 0 | 43804.2812 | 30d | 0 | 0 | 0 | 43804.2812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 28d | [5 empty] | 24876.3993 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | -489.16 | 0 | 1272.83 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 72.2382 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 19d | 32408.5195 | 0 | 71d | -8804.9502 | 0 | 23603.5693 | 0 | 21.11% | Started | 32408.5195 | 32408.5195 | 100 | 21.1111 | 21.1111 | 100 | 72.8314 | 21.1111
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210344.4517 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4349.2202 | 0 | 210344.4517 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 97.9742 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 18d | [5 empty] | 107001.1426 |  | 6.357% |  | 110729.6326 | 47398.2507
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 94242.4326 |  | 100% |  | 97505.4526 | 43832.0308
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -334.73 | 0 | 6408.6601 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 95.0362 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -1840.99 | 0 | 35247.6506 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 95.0362 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1087.3 | 0 | 52586.1218 | 0 | 100% | Finished | 53673.4219 | 0 | 100 | 100 | 100 | 100 | 97.9742 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 1142.8 | 100 |  | 0 | 100 |  | 0
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 5d | [5 empty] | 12758.71 |  | 0.8047% |  | 13224.18 | 2423.4199
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 14.65 | 0 | 2438.0699 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.6045 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 14.65 | 0 | 471.77 | 0 | 100% | Finished | 457.12 | 0 | 100 | 100 | 100 | 100 | 103.2048 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 7.32 | 0 | 235.88 | 0 | 100% | Finished | 228.56 | 0 | 100 | 100 | 100 | 100 | 103.2027 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 1d | 10115.0801 | 0 | 2d | -502.09 | 0 | 9612.9901 | 0 | 33.33% | Started | 10115.0801 | 0 | 100 | 33.3333 | 33.3333 | 100 | 95.0362 | 33.3333
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 |  | 0 | 0 | 47202.8086 | 15d | 0 | 0 | 0 | 47202.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 |  | 0 | 0 | 48212.0312 | 10d | 0 | 0 | 0 | 48212.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 |  | 0 | 0 | 15734.2695 | 5d | 0 | 0 | 0 | 15734.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 |  | 0 | 0 | 38941.5391 | 10d | 0 | 0 | 0 | 38941.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 |  | 0 | 0 | 165891.9375 | 6d | 0 | 0 | 0 | 165891.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 |  | 0 | 0 | 24106.0195 | 5d | 0 | 0 | 0 | 24106.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 |  | 0 | 0 | 2076.48 | 8d | 0 | 0 | 0 | 2076.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 |  | 0 | 0 | 2570.79 | 1d | 0 | 0 | 0 | 2570.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 |  | 0 | 0 | 7712.3799 | 3d | 0 | 0 | 0 | 7712.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 |  | 0 | 0 | 2794.79 | 6d | 0 | 0 | 0 | 2794.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 |  | 0 | 0 | 62937.0781 | 20d | 0 | 0 | 0 | 62937.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 |  | 0 | 0 | 94089.9219 | 20d | 0 | 0 | 0 | 94089.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 |  | 0 | 0 | 519.12 | 2d | 0 | 0 | 0 | 519.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 |  | 0 | 0 | 68166.2578 | 8d | 0 | 0 | 0 | 68166.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 |  | 0 | 0 | 24822.4199 | 17d | 0 | 0 | 0 | 24822.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 |  | 0 | 0 | 3885.53 | 17d | 0 | 0 | 0 | 3885.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 |  | 0 | 0 | 5185.0098 | 8d | 0 | 0 | 0 | 5185.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-09-02 17:00 |  | TP Name | 02/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 30d | [5 empty] | 524326.9788 |  | 9.997% |  | 547862.8495 | 556801.3083
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 30d | [5 empty] | 524326.9788 |  | 9.997% |  | 547862.8495 | 556801.3083
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 134079.5767 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | -6300.9702 | 0 | 134079.5767 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 95.5115 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 30d | [5 empty] | 235928.501 |  | 68.06% |  | 249549.8614 | 321736.3389
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 21.97 | 0 | 707.65 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 103.2041 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 12d | [5 empty] | 0 |  | 0% |  | 0 | 72186.4775
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 |  | 0 | 0 | 704.8 | 2d | 0 | 0 | 0 | 704.8 | 0% | Not Started | 0 | 704.8 | 100 |  | 0 | 100 |  | 0
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 |  | 0 | 0 | 914.24 | 4d | 0 | 0 | 0 | 914.24 | 0% | Not Started | 0 | 914.24 | 100 |  | 0 | 100 |  | 0
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 |  | 0 | 0 | 70567.4375 | 15d | 0 | 0 | 0 | 70567.4375 | 0% | Not Started | 0 | 70567.4375 | 100 |  | 0 | 100 |  | 0
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 |  | 0 | 0 | 43804.2812 | 30d | 0 | 0 | 0 | 43804.2812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 30d | [5 empty] | 24876.3993 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | -489.16 | 0 | 1272.83 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 72.2382 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 21d | 32408.5195 | 0 | 69d | -8804.9502 | 0 | 23603.5693 | 0 | 23.33% | Started | 32408.5195 | 32408.5195 | 100 | 23.3333 | 23.3333 | 100 | 72.8314 | 23.3333
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210344.4517 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4349.2202 | 0 | 210344.4517 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 97.9742 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 20d | [5 empty] | 154318.9012 |  | 9.066% |  | 157932.4412 | 47398.2507
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 94242.4326 |  | 100% |  | 97505.4526 | 43832.0308
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -334.73 | 0 | 6408.6601 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 95.0362 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -1840.99 | 0 | 35247.6506 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 95.0362 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1087.3 | 0 | 52586.1218 | 0 | 100% | Finished | 53673.4219 | 0 | 100 | 100 | 100 | 100 | 97.9742 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 1142.8 | 100 |  | 0 | 100 |  | 0
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 7d | [5 empty] | 60076.4686 |  | 3.677% |  | 60426.9886 | 2423.4199
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 14.65 | 0 | 2438.0699 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.6045 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 14.65 | 0 | 471.77 | 0 | 100% | Finished | 457.12 | 0 | 100 | 100 | 100 | 100 | 103.2048 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 7.32 | 0 | 235.88 | 0 | 100% | Finished | 228.56 | 0 | 100 | 100 | 100 | 100 | 103.2027 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -502.09 | 0 | 9612.9901 | 0 | 100% | Finished | 10115.0801 | 0 | 100 | 100 | 100 | 100 | 95.0362 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 2d | 47202.8086 | 0 | 13d | 114.95 | 0 | 47317.7586 | 0 | 13.33% | Started | 47202.8086 | 0 | 100 | 13.3333 | 13.3333 | 100 | 100.2435 | 13.3333
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 |  | 0 | 0 | 48212.0312 | 10d | 0 | 0 | 0 | 48212.0312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 |  | 0 | 0 | 15734.2695 | 5d | 0 | 0 | 0 | 15734.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 |  | 0 | 0 | 38941.5391 | 10d | 0 | 0 | 0 | 38941.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 |  | 0 | 0 | 165891.9375 | 6d | 0 | 0 | 0 | 165891.9375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 |  | 0 | 0 | 24106.0195 | 5d | 0 | 0 | 0 | 24106.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 |  | 0 | 0 | 2076.48 | 8d | 0 | 0 | 0 | 2076.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 |  | 0 | 0 | 2570.79 | 1d | 0 | 0 | 0 | 2570.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 |  | 0 | 0 | 7712.3799 | 3d | 0 | 0 | 0 | 7712.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 |  | 0 | 0 | 2794.79 | 6d | 0 | 0 | 0 | 2794.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 |  | 0 | 0 | 62937.0781 | 20d | 0 | 0 | 0 | 62937.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 |  | 0 | 0 | 94089.9219 | 20d | 0 | 0 | 0 | 94089.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 |  | 0 | 0 | 519.12 | 2d | 0 | 0 | 0 | 519.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 |  | 0 | 0 | 68166.2578 | 8d | 0 | 0 | 0 | 68166.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 |  | 0 | 0 | 24822.4199 | 17d | 0 | 0 | 0 | 24822.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 |  | 0 | 0 | 3885.53 | 17d | 0 | 0 | 0 | 3885.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 |  | 0 | 0 | 5185.0098 | 8d | 0 | 0 | 0 | 5185.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-09-30 17:00 |  | TP Name | 30/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 50d | [5 empty] | 929878.4556 |  | 17.07% |  | 935376.1057 | 716853.7901
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 50d | [5 empty] | 929878.4556 |  | 17.07% |  | 935376.1057 | 716853.7901
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 140466.1069 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 85.56 | 0 | 140466.1069 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 100.0609 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 50d | [5 empty] | 366443.8902 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 7.65 | 0 | 693.33 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 101.1157 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 32d | [5 empty] | 118401.5687 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | -28.19 | 0 | 676.61 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 96.0003 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 12.75 | 0 | 1155.55 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 101.1157 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 10.2 | 0 | 924.44 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 101.1157 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 8d | 70567.4375 | 0 | 12d | 1196.72 | 0 | 71764.1575 | 0 | 40% | Started | 70567.4375 | 70567.4375 | 100 | 53.3333 | 40 | 100 | 101.6959 | 40
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 4d | 43804.2812 | 0 | 21d | 76.53 | 0 | 43880.8112 | 0 | 16% | Started | 43804.2812 | 43804.2812 | 100 | 13.3333 | 16 | 100 | 100.1747 | 16
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 50d | [5 empty] | 32831.4496 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | -70.48 | 0 | 1691.51 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 96 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 41d | 32408.5195 | 0 | 49d | -1268.58 | 0 | 31139.9396 | 0 | 45.56% | Started | 32408.5195 | 32408.5195 | 100 | 45.5556 | 45.5556 | 100 | 96.0857 | 45.5556
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 214517.5419 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -176.13 | 0 | 214517.5419 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 99.918 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 40d | [5 empty] | 422968.4586 |  | 24.59% |  | 428312.1386 | 159075.2413
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95832.2126 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -250.65 | 0 | 6492.7401 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 96.283 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -1378.5601 | 0 | 35710.0806 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 96.2831 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -44.03 | 0 | 53629.3919 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 99.918 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1155.55 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 12.75 | 0 | 1155.55 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 101.1157 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 27d | [5 empty] | 325980.6959 |  | 20.06% |  | 329663.8859 | 60426.9886
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 5.1 | 0 | 2428.5199 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.2104 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 5.1 | 0 | 462.22 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 101.1157 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 2.55 | 0 | 231.11 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 101.1157 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -375.97 | 0 | 9739.1101 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 96.2831 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -1541.58 | 0 | 45661.2286 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 96.7341 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 5.1 | 0 | 462.22 | 0 | 100% | Finished | 457.12 | 0 | 100 | 100 | 100 | 100 | 101.1157 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | 322.65 | 0 | 48534.6812 | 0 | 100% | Finished | 48212.0312 | 0 | 100 | 100 | 100 | 100 | 100.6692 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -513.86 | 0 | 15220.4095 | 0 | 100% | Finished | 15734.2695 | 0 | 100 | 100 | 100 | 100 | 96.7341 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | -1442.05 | 0 | 37499.489 | 0 | 100% | Finished | 38941.5391 | 0 | 100 | 100 | 100 | 100 | 96.2969 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 4d | 165891.9375 | 0 | 2d | -150.23 | 0 | 165741.7075 | 0 | 66.67% | Started | 165891.9375 | 0 | 100 | 66.6667 | 66.6667 | 100 | 99.9094 | 66.6667
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 |  | 0 | 0 | 24106.0195 | 5d | 0 | 0 | 0 | 24106.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 |  | 0 | 0 | 2076.48 | 8d | 0 | 0 | 0 | 2076.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 |  | 0 | 0 | 2570.79 | 1d | 0 | 0 | 0 | 2570.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 |  | 0 | 0 | 21229.2793 | 2d | 0 | 0 | 0 | 21229.2793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 |  | 0 | 0 | 7712.3799 | 3d | 0 | 0 | 0 | 7712.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 |  | 0 | 0 | 2794.79 | 6d | 0 | 0 | 0 | 2794.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 |  | 0 | 0 | 62937.0781 | 20d | 0 | 0 | 0 | 62937.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 |  | 0 | 0 | 94089.9219 | 20d | 0 | 0 | 0 | 94089.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 |  | 0 | 0 | 519.12 | 2d | 0 | 0 | 0 | 519.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 |  | 0 | 0 | 68166.2578 | 8d | 0 | 0 | 0 | 68166.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 |  | 0 | 0 | 24822.4199 | 17d | 0 | 0 | 0 | 24822.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 |  | 0 | 0 | 3885.53 | 17d | 0 | 0 | 0 | 3885.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 |  | 0 | 0 | 5185.0098 | 8d | 0 | 0 | 0 | 5185.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-10-31 17:00 |  | TP Name | 31/10, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 70d | [5 empty] | 1016558.1937 |  | 18.56% |  | 1017323.6837 | 1010196.707
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 70d | [5 empty] | 1016558.1937 |  | 18.56% |  | 1017323.6837 | 1010196.707
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 147874.8867 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 7494.3398 | 0 | 147874.8867 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 105.3386 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 70d | [5 empty] | 366550.5101 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | -2.46 | 0 | 683.22 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.6412 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 52d | [5 empty] | 117918.7788 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | -33.9 | 0 | 670.9 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 95.1901 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | -4.1 | 0 | 1138.7 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.6412 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | -3.28 | 0 | 910.96 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 99.6412 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | 2890.6499 | 0 | 73458.0874 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 104.0963 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 24d | 43804.2812 | 0 | 1d | -2064.1499 | 0 | 41740.1313 | 0 | 96% | Started | 43804.2812 | 43804.2812 | 100 | 80 | 96 | 100 | 95.2878 | 96
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 70d | [5 empty] | 32560.0795 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | -84.76 | 0 | 1677.23 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 95.1895 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 61d | 32408.5195 | 0 | 29d | -1525.67 | 0 | 30882.8495 | 0 | 67.78% | Started | 32408.5195 | 32408.5195 | 100 | 67.7778 | 67.7778 | 100 | 95.2924 | 67.7778
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 215388.4319 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | 694.76 | 0 | 215388.4319 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 100.3236 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 60d | [5 empty] | 502132.7968 |  | 29.29% |  | 510259.7167 | 452418.1581
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96945.3626 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -112.89 | 0 | 6630.5001 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.3259 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -620.89 | 0 | 36467.7506 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.3259 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | 173.69 | 0 | 53847.1119 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 100.3236 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1138.7 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | -4.1 | 0 | 1138.7 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.6412 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 47d | [5 empty] | 404048.7341 |  | 25.05% |  | 411611.464 | 353769.9055
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | -1.64 | 0 | 2421.7799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 99.9323 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | -1.64 | 0 | 455.48 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 99.6412 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | -0.82 | 0 | 227.74 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 99.6412 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -169.33 | 0 | 9945.7501 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.326 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -4573.2598 | 0 | 42629.5488 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 90.3115 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | -1.64 | 0 | 455.48 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 99.6412 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | 369.66 | 0 | 48581.6913 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 100.7667 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -1524.42 | 0 | 14209.8495 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 90.3115 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | -7097.5 | 0 | 31844.0391 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 81.774 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | 579.97 | 0 | 166471.9075 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 100.3496 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | 184.83 | 0 | 24290.8495 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 100.7667 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | -6.56 | 0 | 2069.92 | 0 | 100% | Finished | 2076.48 | 0 | 100 | 100 | 100 | 100 | 99.6841 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | 2569.74 | 0 | 23799.0193 | 0 | 100% | Finished | 21229.2793 | 0 | 100 | 100 | 100 | 100 | 112.1047 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -113.53 | 0 | 2457.26 | 0 | 100% | Finished | 2570.79 | 0 | 100 | 500 | 100 | 100 | 95.5838 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | -0.82 | 0 | 227.74 | 0 | 100% | Finished | 228.56 | 0 | 100 | 100 | 100 | 100 | 99.6412 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | 2569.74 | 0 | 23799.0193 | 0 | 100% | Finished | 21229.2793 | 0 | 100 | 100 | 100 | 100 | 112.1047 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -340.59 | 0 | 7371.7899 | 0 | 100% | Finished | 7712.3799 | 0 | 100 | 100 | 100 | 100 | 95.5839 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 3d | 2794.79 | 0 | 3d | -4.92 | 0 | 2789.87 | 0 | 50% | Started | 2794.79 | 0 | 100 | 50 | 50 | 100 | 99.824 | 50
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 |  | 0 | 0 | 62937.0781 | 20d | 0 | 0 | 0 | 62937.0781 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 |  | 0 | 0 | 94089.9219 | 20d | 0 | 0 | 0 | 94089.9219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 |  | 0 | 0 | 519.12 | 2d | 0 | 0 | 0 | 519.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 |  | 0 | 0 | 68166.2578 | 8d | 0 | 0 | 0 | 68166.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 |  | 0 | 0 | 24822.4199 | 17d | 0 | 0 | 0 | 24822.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 |  | 0 | 0 | 3885.53 | 17d | 0 | 0 | 0 | 3885.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 |  | 0 | 0 | 5185.0098 | 8d | 0 | 0 | 0 | 5185.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-11-30 17:00 |  | TP Name | 30/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 94d | [5 empty] | 1233100.8019 |  | 22.68% |  | 1243036.0615 | 1225065.2655
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 94d | [5 empty] | 1233100.8019 |  | 22.68% |  | 1243036.0615 | 1225065.2655
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 140817.5269 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 436.98 | 0 | 140817.5269 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 100.3113 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 87d | [5 empty] | 369017.6702 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 0.24 | 0 | 685.92 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.035 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 114288.5888 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 144.18 | 0 | 848.98 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 120.4569 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 0.32 | 0 | 914.56 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.035 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -952.74 | 0 | 69614.6975 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 98.6499 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2037.13 | 0 | 41767.1512 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 95.3495 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 87d | [5 empty] | 40326.2195 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 360.44 | 0 | 2122.43 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 120.4564 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 78d | 32408.5195 | 0 | 12d | 5795.27 | 0 | 38203.7896 | 0 | 86.67% | Started | 32408.5195 | 32408.5195 | 100 | 86.6667 | 86.6667 | 100 | 117.8819 | 86.6667
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 213716.9419 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -976.73 | 0 | 213716.9419 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 99.5451 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 84d | [5 empty] | 723265.6048 |  | 42.25% |  | 735972.0945 | 667286.7167
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96439.1426 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -126.48 | 0 | 6616.9101 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.1244 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -695.65 | 0 | 36392.9906 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.1244 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -244.18 | 0 | 53429.2419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 99.5451 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1143.2 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 71d | [5 empty] | 625683.2622 |  | 38.78% |  | 637323.8418 | 568638.464
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 0.16 | 0 | 2423.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.0066 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 0.16 | 0 | 457.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.035 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -189.72 | 0 | 9925.3601 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.1244 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -2142.5601 | 0 | 45060.2485 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 95.4609 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 583.16 | 0 | 1040.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 227.5726 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5909.9102 | 0 | 42302.1211 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 87.7418 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -714.19 | 0 | 15020.0795 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 95.4609 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 25236.6309 | 0 | 64178.1699 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 164.8065 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -506.13 | 0 | 165385.8075 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 99.6949 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2954.95 | 0 | 21151.0696 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 87.7419 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 0.64 | 0 | 2077.12 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 100.0308 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -11.25 | 0 | 2559.54 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 99.5624 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -33.76 | 0 | 7678.6199 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 99.5623 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 0.48 | 0 | 2795.27 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 100.0172 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 17d | 62937.0781 | 0 | 3d | -2856.75 | 0 | 60080.3281 | 0 | 85% | Started | 62937.0781 | 62937.0781 | 100 | 85 | 85 | 100 | 95.4609 | 85
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 15d | 94089.9219 | 0 | 5d | -1270.3199 | 0 | 92819.6019 | 0 | 75% | Started | 94089.9219 | 94089.9219 | 100 | 75 | 75 | 100 | 98.6499 | 75
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 0.16 | 0 | 519.28 | 0 | 100% | Finished | 519.12 | 0 | 100 | 100 | 100 | 100 | 100.0308 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | -1156.6899 | 0 | 67009.5679 | 0 | 100% | Finished | 68166.2578 | 0 | 100 | 225 | 100 | 100 | 98.3031 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 |  | 0 | 0 | 24822.4199 | 17d | 0 | 0 | 0 | 24822.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 |  | 0 | 0 | 3885.53 | 17d | 0 | 0 | 0 | 3885.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 |  | 0 | 0 | 5185.0098 | 8d | 0 | 0 | 0 | 5185.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2011-12-08 17:00 |  | TP Name | 08/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 94d | [5 empty] | 1267876.4316 |  | 23.33% |  | 1278757.5012 | 1293750.6433
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 94d | [5 empty] | 1267876.4316 |  | 23.33% |  | 1278757.5012 | 1293750.6433
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 140817.5269 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 436.98 | 0 | 140817.5269 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 100.3113 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 93d | [5 empty] | 369017.6702 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 0.24 | 0 | 685.92 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.035 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 114288.5888 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 144.18 | 0 | 848.98 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 120.4569 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 0.32 | 0 | 914.56 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.035 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -952.74 | 0 | 69614.6975 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 98.6499 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2037.13 | 0 | 41767.1512 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 95.3495 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 93d | [5 empty] | 40326.2195 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 360.44 | 0 | 2122.43 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 120.4564 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 84d | 32408.5195 | 0 | 6d | 5795.27 | 0 | 38203.7896 | 0 | 93.33% | Started | 32408.5195 | 32408.5195 | 100 | 93.3333 | 93.3333 | 100 | 117.8819 | 93.3333
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 213716.9419 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -976.73 | 0 | 213716.9419 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 99.5451 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 84d | [5 empty] | 723265.6048 |  | 42.25% |  | 735972.0945 | 735972.0945
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96439.1426 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -126.48 | 0 | 6616.9101 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.1244 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -695.65 | 0 | 36392.9906 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.1244 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -244.18 | 0 | 53429.2419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 99.5451 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1143.2 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 71d | [5 empty] | 625683.2622 |  | 38.78% |  | 637323.8418 | 637323.8418
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 0.16 | 0 | 2423.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.0066 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 0.16 | 0 | 457.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.035 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -189.72 | 0 | 9925.3601 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.1244 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -2142.5601 | 0 | 45060.2485 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 95.4609 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 583.16 | 0 | 1040.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 227.5726 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5909.9102 | 0 | 42302.1211 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 87.7418 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -714.19 | 0 | 15020.0795 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 95.4609 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 25236.6309 | 0 | 64178.1699 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 164.8065 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -506.13 | 0 | 165385.8075 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 99.6949 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2954.95 | 0 | 21151.0696 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 87.7419 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 0.64 | 0 | 2077.12 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 100.0308 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -11.25 | 0 | 2559.54 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 99.5624 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -33.76 | 0 | 7678.6199 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 99.5623 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 0.48 | 0 | 2795.27 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 100.0172 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -2856.75 | 0 | 60080.3281 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 95.4609 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -1270.3199 | 0 | 92819.6019 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 98.6499 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 0.16 | 0 | 519.28 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 100.0308 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | -1156.6899 | 0 | 67009.5679 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 98.3031 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 6d | [5 empty] | 34775.6297 |  | 1.601% |  | 35721.4397 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 6d | [5 empty] | 34775.6297 |  | 3.971% |  | 35721.4397 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 6d | 24822.4199 | 0 | 11d | -1154.38 | 0 | 23668.0399 | 0 | 35.29% | Started | 24822.4199 | 0 | 100 | 35.2941 | 35.2941 | 100 | 95.3494 | 35.2941
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 6d | 3885.53 | 0 | 11d | 1.37 | 0 | 3886.9 | 0 | 35.29% | Started | 3885.53 | 0 | 100 | 35.2941 | 35.2941 | 100 | 100.0353 | 35.2941
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 6d | 5185.0098 | 0 | 2d | 206.56 | 0 | 5391.5698 | 0 | 75% | Started | 5185.0098 | 0 | 100 | 75 | 75 | 100 | 103.9838 | 75
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 6d | 1828.48 | 0 | 2d | 0.64 | 0 | 1829.12 | 0 | 75% | Started | 1828.48 | 0 | 100 | 75 | 75 | 100 | 100.035 | 75
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2011-12-09 17:00 |  | TP Name | 09/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 94d | [5 empty] | 1267876.4316 |  | 23.33% |  | 1278757.5012 | 1383558.1199
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 94d | [5 empty] | 1267876.4316 |  | 23.33% |  | 1278757.5012 | 1383558.1199
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 140817.5269 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 436.98 | 0 | 140817.5269 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 100.3113 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 94d | [5 empty] | 369017.6702 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 0.24 | 0 | 685.92 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.035 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 114288.5888 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 144.18 | 0 | 848.98 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 120.4569 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 0.32 | 0 | 914.56 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.035 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -952.74 | 0 | 69614.6975 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 98.6499 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2037.13 | 0 | 41767.1512 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 95.3495 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 94d | [5 empty] | 40326.2195 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 360.44 | 0 | 2122.43 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 120.4564 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 85d | 32408.5195 | 0 | 5d | 5795.27 | 0 | 38203.7896 | 0 | 94.44% | Started | 32408.5195 | 32408.5195 | 100 | 94.4444 | 94.4444 | 100 | 117.8819 | 94.4444
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 213716.9419 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -976.73 | 0 | 213716.9419 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 99.5451 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 84d | [5 empty] | 723265.6048 |  | 42.25% |  | 735972.0945 | 825779.571
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96439.1426 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -126.48 | 0 | 6616.9101 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.1244 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -695.65 | 0 | 36392.9906 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.1244 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -244.18 | 0 | 53429.2419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 99.5451 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1143.2 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 71d | [5 empty] | 625683.2622 |  | 38.78% |  | 637323.8418 | 727131.3184
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 0.16 | 0 | 2423.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.0066 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 0.16 | 0 | 457.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.035 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -189.72 | 0 | 9925.3601 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.1244 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -2142.5601 | 0 | 45060.2485 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 95.4609 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 583.16 | 0 | 1040.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 227.5726 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5909.9102 | 0 | 42302.1211 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 87.7418 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -714.19 | 0 | 15020.0795 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 95.4609 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 25236.6309 | 0 | 64178.1699 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 164.8065 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -506.13 | 0 | 165385.8075 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 99.6949 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2954.95 | 0 | 21151.0696 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 87.7419 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 0.64 | 0 | 2077.12 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 100.0308 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -11.25 | 0 | 2559.54 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 99.5624 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -33.76 | 0 | 7678.6199 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 99.5623 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 0.48 | 0 | 2795.27 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 100.0172 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -2856.75 | 0 | 60080.3281 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 95.4609 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -1270.3199 | 0 | 92819.6019 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 98.6499 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 0.16 | 0 | 519.28 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 100.0308 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | -1156.6899 | 0 | 67009.5679 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 98.3031 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 89807.4766
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 89807.4766 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 7d | [5 empty] | 34775.6297 |  | 1.601% |  | 35721.4397 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 7d | [5 empty] | 34775.6297 |  | 3.971% |  | 35721.4397 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 7d | 24822.4199 | 0 | 10d | -1154.38 | 0 | 23668.0399 | 0 | 41.18% | Started | 24822.4199 | 0 | 100 | 41.1765 | 41.1765 | 100 | 95.3494 | 41.1765
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 7d | 3885.53 | 0 | 10d | 1.37 | 0 | 3886.9 | 0 | 41.18% | Started | 3885.53 | 0 | 100 | 41.1765 | 41.1765 | 100 | 100.0353 | 41.1765
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 7d | 5185.0098 | 0 | 1d | 206.56 | 0 | 5391.5698 | 0 | 87.5% | Started | 5185.0098 | 0 | 100 | 87.5 | 87.5 | 100 | 103.9838 | 87.5
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 7d | 1828.48 | 0 | 1d | 0.64 | 0 | 1829.12 | 0 | 87.5% | Started | 1828.48 | 0 | 100 | 87.5 | 87.5 | 100 | 100.035 | 87.5
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2011-12-16 17:00 |  | TP Name | 16/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 99d | [5 empty] | 1357684.7982 |  | 24.97% |  | 1368564.9778 | 1383558.1199
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 99d | [5 empty] | 1357684.7982 |  | 24.97% |  | 1368564.9778 | 1383558.1199
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 140817.5269 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 436.98 | 0 | 140817.5269 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 100.3113 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 369017.6702 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 0.24 | 0 | 685.92 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.035 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 114288.5888 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 144.18 | 0 | 848.98 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 120.4569 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 0.32 | 0 | 914.56 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.035 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -952.74 | 0 | 69614.6975 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 98.6499 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2037.13 | 0 | 41767.1512 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 95.3495 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 40326.2195 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 360.44 | 0 | 2122.43 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 120.4564 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 5795.27 | 0 | 38203.7896 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 117.8819 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 213716.9419 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -976.73 | 0 | 213716.9419 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 99.5451 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 89d | [5 empty] | 813073.9714 |  | 47.41% |  | 825779.571 | 825779.571
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96439.1426 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -126.48 | 0 | 6616.9101 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.1244 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -695.65 | 0 | 36392.9906 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.1244 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -244.18 | 0 | 53429.2419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 99.5451 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1143.2 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 0.4 | 0 | 1143.2 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.035 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 76d | [5 empty] | 715491.6287 |  | 44.25% |  | 727131.3184 | 727131.3184
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 0.16 | 0 | 2423.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.0066 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 0.16 | 0 | 457.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.035 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -189.72 | 0 | 9925.3601 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.1244 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -2142.5601 | 0 | 45060.2485 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 95.4609 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 583.16 | 0 | 1040.28 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 227.5726 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5909.9102 | 0 | 42302.1211 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 87.7418 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -714.19 | 0 | 15020.0795 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 95.4609 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 25236.6309 | 0 | 64178.1699 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 164.8065 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -506.13 | 0 | 165385.8075 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 99.6949 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2954.95 | 0 | 21151.0696 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 87.7419 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 0.64 | 0 | 2077.12 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 100.0308 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -11.25 | 0 | 2559.54 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 99.5624 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 0.08 | 0 | 228.64 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.035 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -9857.9502 | 0 | 11371.3291 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 53.5644 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -33.76 | 0 | 7678.6199 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 99.5623 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 0.48 | 0 | 2795.27 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 100.0172 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -2856.75 | 0 | 60080.3281 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 95.4609 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -1270.3199 | 0 | 92819.6019 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 98.6499 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 0.16 | 0 | 519.28 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 100.0308 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | -1156.6899 | 0 | 67009.5679 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 98.3031 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 5d | [5 empty] | 89808.3666 |  | 23.38% |  | 89807.4766 | 0
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 0.89 | 0 | 89808.3666 | 0 | 100% | Finished | 89807.4766 | 0 | 100 | 62.5 | 100 | 100 | 100.001 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 89807.4766
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 89807.4766 | 100 |  | 0 | 100 |  | 0
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 12d | [5 empty] | 34775.6297 |  | 1.601% |  | 35721.4397 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 12d | [5 empty] | 34775.6297 |  | 3.971% |  | 35721.4397 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 12d | 24822.4199 | 0 | 5d | -1154.38 | 0 | 23668.0399 | 0 | 70.59% | Started | 24822.4199 | 0 | 100 | 70.5882 | 70.5882 | 100 | 95.3494 | 70.5882
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 12d | 3885.53 | 0 | 5d | 1.37 | 0 | 3886.9 | 0 | 70.59% | Started | 3885.53 | 0 | 100 | 70.5882 | 70.5882 | 100 | 100.0353 | 70.5882
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | 206.56 | 0 | 5391.5698 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 103.9838 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 8d | 1828.48 | 0 | 0 | 0.64 | 0 | 1829.12 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 100.035 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2011-12-31 17:00 |  | TP Name | 31/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 104d | [5 empty] | 1443590.0747 |  | 26.61% |  | 1458372.4543 | 1473365.5964
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 104d | [5 empty] | 1443590.0747 |  | 26.61% |  | 1458372.4543 | 1473365.5964
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 147745.9868 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 7365.4399 | 0 | 147745.9868 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 105.2468 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 365223.5703 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 2.54 | 0 | 688.22 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.3704 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 109393.8689 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 145.71 | 0 | 850.51 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 120.674 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 4.24 | 0 | 1147.04 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.371 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 3.39 | 0 | 917.63 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.3708 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -5878.9199 | 0 | 64688.5176 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 91.6691 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2014.11 | 0 | 41790.1713 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 95.402 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 40399.1196 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 364.28 | 0 | 2126.27 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 120.6744 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 5864.3301 | 0 | 38272.8496 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 118.095 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 214742.3619 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | 48.69 | 0 | 214742.3619 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 100.0227 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 94d | [5 empty] | 895769.6378 |  | 52.56% |  | 915587.0476 | 915587.0476
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96705.4626 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -124.95 | 0 | 6618.4401 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.1471 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -687.21 | 0 | 36401.4306 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.1471 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | 12.17 | 0 | 53685.5919 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 100.0227 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1147.04 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 4.24 | 0 | 1147.04 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.371 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 81d | [5 empty] | 797917.1352 |  | 49.71% |  | 816938.7949 | 816938.7949
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 1.7 | 0 | 2425.1199 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.0701 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 1.7 | 0 | 458.82 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.3719 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.85 | 0 | 229.41 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.3719 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -187.42 | 0 | 9927.6601 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.1471 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -1288.28 | 0 | 45914.5286 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 97.2708 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 584.7 | 0 | 1041.82 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 227.9095 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5033.3101 | 0 | 43178.7212 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 89.5601 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -429.43 | 0 | 15304.8395 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 97.2707 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 25323.4805 | 0 | 64265.0195 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 165.0295 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | 262.93 | 0 | 166154.8675 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 100.1585 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2516.6499 | 0 | 21589.3696 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 89.5601 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 665.93 | 0 | 2742.41 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 132.0701 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -11657.6201 | 0 | 9571.6592 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 45.0871 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -10.49 | 0 | 2560.3 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 99.592 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 83.24 | 0 | 311.8 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 136.4193 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -11657.6201 | 0 | 9571.6592 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 45.0871 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -31.46 | 0 | 7680.9199 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 99.5921 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 5.09 | 0 | 2799.88 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 100.1821 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -1717.71 | 0 | 61219.3682 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 97.2708 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -7838.5601 | 0 | 86251.3618 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 91.6691 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 1.7 | 0 | 520.82 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 100.3275 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | -3630.99 | 0 | 64535.2678 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 94.6733 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 10d | [5 empty] | 89830.7566 |  | 23.38% |  | 89807.4766 | 89807.4766
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 23.28 | 0 | 89830.7566 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 100.0259 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 |  | 0 | 0 | 56129.6797 | 5d | 0 | 0 | 0 | 56129.6797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 |  | 0 | 0 | 2578.22 | 8d | 0 | 0 | 0 | 2578.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 |  | 0 | 0 | 685.68 | 3d | 0 | 0 | 0 | 685.68 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 |  | 0 | 0 | 33677.8086 | 3d | 0 | 0 | 0 | 33677.8086 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 |  | 0 | 0 | 38697.4805 | 5d | 0 | 0 | 0 | 38697.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 5d | [5 empty] | 89830.7566 |  | 14.44% |  | 89807.4766 | 89807.4766
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 23.28 | 0 | 89830.7566 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 100.0259 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 |  | 0 | 0 | 2114.3301 | 2d | 0 | 0 | 0 | 2114.3301 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 |  | 0 | 0 | 89807.4766 | 8d | 0 | 0 | 0 | 89807.4766 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 |  | 0 | 0 | 4611.79 | 6d | 0 | 0 | 0 | 4611.79 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 |  | 0 | 0 | 768.63 | 1d | 0 | 0 | 0 | 768.63 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 |  | 0 | 0 | 22309.4199 | 2d | 0 | 0 | 0 | 22309.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 |  | 0 | 0 | 2305.8999 | 3d | 0 | 0 | 0 | 2305.8999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 |  | 0 | 0 | 33118.2695 | 4d | 0 | 0 | 0 | 33118.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 |  | 0 | 0 | 11154.71 | 1d | 0 | 0 | 0 | 11154.71 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 |  | 0 | 0 | 23522.4805 | 5d | 0 | 0 | 0 | 23522.4805 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 |  | 0 | 0 | 115165.7109 | 6d | 0 | 0 | 0 | 115165.7109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 17d | [5 empty] | 34850.8797 |  | 1.601% |  | 35721.4397 | 50714.5818
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 |  | 0 | 0 | 6986.9902 | 15d | 0 | 0 | 0 | 6986.9902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 17d | [5 empty] | 34850.8797 |  | 3.971% |  | 35721.4397 | 47286.1719
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1141.33 | 0 | 23681.09 | 0 | 100% | Finished | 24822.4199 | 0 | 100 | 100 | 100 | 100 | 95.402 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 14.42 | 0 | 3899.95 | 0 | 100% | Finished | 3885.53 | 0 | 100 | 100 | 100 | 100 | 100.3711 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | 249.57 | 0 | 5434.5798 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 104.8133 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 8d | 1828.48 | 0 | 0 | 6.78 | 0 | 1835.26 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 100.3708 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2012-01-31 17:00 |  | TP Name | 31/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 126d | [5 empty] | 1896956.5809 |  | 35.48% |  | 1944309.5203 | 1672259.4431
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 126d | [5 empty] | 1896956.5809 |  | 35.48% |  | 1944309.5203 | 1672259.4431
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 144893.4668 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 4512.9199 | 0 | 144893.4668 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 103.2148 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 355186.84 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | -9.03 | 0 | 676.65 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 98.6831 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 99984.0486 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 136.73 | 0 | 841.53 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 119.3998 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | -15.05 | 0 | 1127.75 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 98.6831 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | -12.04 | 0 | 902.2 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 98.6831 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -15129.29 | 0 | 55438.1475 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 78.5605 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2129.8601 | 0 | 41674.4211 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 95.1378 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39972.3295 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 341.82 | 0 | 2103.81 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 119.3997 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 5460 | 0 | 37868.5195 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 116.8474 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 214553.8119 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -139.86 | 0 | 214553.8119 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 99.9349 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 116d | [5 empty] | 1351001.1541 |  | 79.61% |  | 1386766.0833 | 1089658.4744
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96608.1726 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -132.66 | 0 | 6610.7301 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 98.0327 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -729.65 | 0 | 36358.9906 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 98.0327 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -34.97 | 0 | 53638.4519 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 99.9348 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1127.75 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | -15.05 | 0 | 1127.75 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 98.6831 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 103d | [5 empty] | 1253265.2314 |  | 78.39% |  | 1288117.8306 | 991010.2217
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 287.83 | 0 | 2711.2499 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 111.877 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | -6.02 | 0 | 451.1 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 98.6831 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | -3.01 | 0 | 225.55 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 98.6831 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -199 | 0 | 9916.0801 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 98.0326 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | 3122.3301 | 0 | 50325.1387 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 106.6147 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1296.65 | 0 | 1753.77 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 383.6564 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -4137.25 | 0 | 44074.7812 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 91.4186 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | 1040.78 | 0 | 16775.0496 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 106.6147 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 31112.2207 | 0 | 70053.7598 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 179.8947 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | 121.16 | 0 | 166013.0975 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 100.073 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2068.6201 | 0 | 22037.3994 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 91.4187 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 635.06 | 0 | 2711.54 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 130.5835 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13389.8896 | 0 | 7839.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 36.9273 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | 254.05 | 0 | 2824.84 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 109.8822 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 79.38 | 0 | 307.94 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 134.7305 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13389.8896 | 0 | 7839.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 36.9273 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | 762.14 | 0 | 8474.5199 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 109.882 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | -18.06 | 0 | 2776.73 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 99.3538 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | 4163.1099 | 0 | 67100.188 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 106.6147 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -20172.3809 | 0 | 73917.541 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 78.5605 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -6.02 | 0 | 513.1 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 98.8403 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | -4026.75 | 0 | 64139.5078 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 94.0928 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 32d | [5 empty] | 225854.4353 |  | 58.04% |  | 222989.5253 | 145937.1562
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 1959.92 | 0 | 91767.3966 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.1824 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 1224.95 | 0 | 57354.6296 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 102.1824 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -24.08 | 0 | 2554.14 | 0 | 100% | Finished | 2578.22 | 0 | 100 | 62.5 | 100 | 100 | 99.066 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 1d | 644.55 | 0 | 1d | -6.02 | 0 | 638.53 | 0 | 50% | Started | 644.55 | 0 | 100 | 50 | 50 | 100 | 99.066 | 50
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 1d | 685.68 | 0 | 2d | -9.03 | 0 | 676.65 | 0 | 33.33% | Started | 685.68 | 0 | 100 | 33.3333 | 33.3333 | 100 | 98.6831 | 33.3333
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 734.97 | 0 | 34412.7786 | 0 | 100% | Finished | 33677.8086 | 0 | 100 | 100 | 100 | 100 | 102.1824 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -3.01 | 0 | 765.62 | 0 | 100% | Finished | 768.63 | 0 | 100 | 100 | 100 | 100 | 99.6084 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 2d | 38697.4805 | 0 | 3d | -1012.79 | 0 | 37684.6905 | 0 | 40% | Started | 38697.4805 | 0 | 100 | 40 | 40 | 100 | 97.3828 | 40
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 |  | 0 | 0 | 28146.0098 | 2d | 0 | 0 | 0 | 28146.0098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 |  | 0 | 0 | 118942.6016 | 1d | 0 | 0 | 0 | 118942.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 |  | 0 | 0 | 14113.4902 | 3d | 0 | 0 | 0 | 14113.4902 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 27d | [5 empty] | 404629.1339 |  | 68.8% |  | 427804.4635 | 207749.2236
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 1959.92 | 0 | 91767.3966 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.1824 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 76.4 | 0 | 2190.7301 | 0 | 100% | Finished | 2114.3301 | 0 | 100 | 100 | 100 | 100 | 103.6134 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 1959.92 | 0 | 91767.3966 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 102.1824 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -18.06 | 0 | 4593.73 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 99.6084 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -3.01 | 0 | 765.62 | 0 | 100% | Finished | 768.63 | 0 | 100 | 100 | 100 | 100 | 99.6084 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -810.24 | 0 | 32308.0295 | 0 | 100% | Finished | 33118.2695 | 0 | 100 | 100 | 100 | 100 | 97.5535 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13389.8896 | 0 | 8919.5303 | 0 | 100% | Finished | 22309.4199 | 0 | 100 | 100 | 100 | 100 | 39.981 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -9.03 | 0 | 2296.8699 | 0 | 100% | Finished | 2305.8999 | 0 | 100 | 100 | 100 | 100 | 99.6084 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -810.24 | 0 | 32308.0295 | 0 | 100% | Finished | 33118.2695 | 0 | 100 | 100 | 100 | 100 | 97.5535 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6694.9399 | 0 | 4459.77 | 0 | 100% | Finished | 11154.71 | 0 | 100 | 100 | 100 | 100 | 39.981 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 1d | 23522.4805 | 0 | 4d | -5043.1001 | 0 | 18479.3804 | 0 | 20% | Started | 23522.4805 | 23522.4805 | 100 | 20 | 20 | 100 | 78.5605 | 20
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 1d | 115165.7109 | 0 | 3d | -393.06 | 0 | 114772.6509 | 0 | 25% | Started | 115165.7109 | 0 | 100 | 16.6667 | 25 | 100 | 99.6587 | 25
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 39d | [5 empty] | 45875.12 |  | 2.262% |  | 50479.47 | 75537.0017
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 7d | [5 empty] | 6941.8402 |  | 100% |  | 6986.9902 | 0
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 7d | 6986.9902 | 0 | 2d | -45.15 | 0 | 6941.8402 | 0 | 77.78% | Started | 6986.9902 | 0 | 100 | 46.6667 | 77.7778 | 100 | 99.3538 | 77.7778
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 22d | [5 empty] | 0 |  | 0% |  | 0 | 0
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 39d | [5 empty] | 38933.2798 |  | 4.835% |  | 43492.4797 | 72108.5918
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1206.92 | 0 | 23615.4999 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 95.1378 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | -51.17 | 0 | 3834.36 | 0 | 100% | Finished | 3885.53 | 0 | 100 | 100 | 100 | 100 | 98.6831 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | -30.1 | 0 | 2255.5001 | 0 | 100% | Finished | 2285.6001 | 0 | 100 | 100 | 100 | 100 | 98.6831 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 7d | 1828.48 | 0 | 1d | -24.08 | 0 | 1804.4 | 0 | 87.5% | Started | 1828.48 | 0 | 100 | 87.5 | 87.5 | 100 | 98.6831 | 87.5
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3174.6899 | 0 | 2010.3198 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 38.7718 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 7d | 1828.48 | 0 | 1d | -24.08 | 0 | 1804.4 | 0 | 87.5% | Started | 1828.48 | 0 | 100 | 87.5 | 87.5 | 100 | 98.6831 | 87.5
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 7d | 1828.48 | 0 | 1d | -24.08 | 0 | 1804.4 | 0 | 87.5% | Started | 1828.48 | 0 | 100 | 87.5 | 87.5 | 100 | 98.6831 | 87.5
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 |  | 0 | 0 | 38626.6719 | 8d | 0 | 0 | 0 | 38626.6719 | 0% | Not Started | 0 | 38626.6719 | 100 |  | 0 | 100 |  | 0
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 8d | 1828.48 | 0 | 0 | -24.08 | 0 | 1804.4 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 98.6831 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2012-02-29 17:00 |  | TP Name | 29/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 147d | [5 empty] | 2124144.4423 |  | 39.12% |  | 2144138.2937 | 2206828.5316
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 147d | [5 empty] | 2124144.4423 |  | 39.12% |  | 2144138.2937 | 2206828.5316
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 154463.0273 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 14082.4805 | 0 | 154463.0273 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 110.0316 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 356886.23 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | -4.36 | 0 | 681.32 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.3641 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 101700.0186 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 130.73 | 0 | 835.53 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 118.5485 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | -7.26 | 0 | 1135.54 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.3647 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | -5.81 | 0 | 908.43 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 99.3645 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -12644.2002 | 0 | 57923.2373 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 82.0821 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2907 | 0 | 40897.2812 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 93.3637 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39687.6696 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 326.83 | 0 | 2088.82 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 118.5489 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 5190.3301 | 0 | 37598.8496 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 116.0153 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 214817.2219 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | 123.55 | 0 | 214817.2219 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 100.0575 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 137d | [5 empty] | 1535144.7233 |  | 88.86% |  | 1547968.1848 | 1315442.9642
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96595.9726 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -144.67 | 0 | 6598.7201 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.8546 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -795.7 | 0 | 36292.9406 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.8546 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | 30.89 | 0 | 53704.3119 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 100.0576 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1135.54 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | -7.26 | 0 | 1135.54 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.3647 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 124d | [5 empty] | 1437413.2107 |  | 88.2% |  | 1449319.9321 | 1216794.7115
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 290.95 | 0 | 2714.3699 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 112.0058 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | -2.9 | 0 | 454.22 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 99.3656 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | -1.45 | 0 | 227.11 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 99.3656 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -217.01 | 0 | 9898.0701 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.8546 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | 4475.4199 | 0 | 51678.2285 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 109.4813 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1299.76 | 0 | 1756.88 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 384.3367 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6695.2402 | 0 | 41516.791 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 86.1129 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | 1491.8101 | 0 | 17226.0796 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 109.4813 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 31600.2793 | 0 | 70541.8184 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 181.148 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | 346.05 | 0 | 166237.9875 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 100.2086 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3347.6201 | 0 | 20758.3994 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 86.1129 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1079.52 | 0 | 3156 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 151.988 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13586.9004 | 0 | 7642.3789 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 35.9992 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | 295.58 | 0 | 2866.37 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 111.4976 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 134.94 | 0 | 363.5 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 159.0392 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13586.9004 | 0 | 7642.3789 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 35.9992 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | 886.73 | 0 | 8599.1099 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 111.4975 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | -8.71 | 0 | 2786.08 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 99.6883 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | 5967.23 | 0 | 68904.3081 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 109.4813 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -16858.9297 | 0 | 77230.9922 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 82.0821 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -2.9 | 0 | 516.22 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 99.4414 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 23661.7109 | 0 | 91827.9688 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 134.7118 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 400536.3365 |  | 100% |  | 384191.6268 | 149845.6062
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 2472.3799 | 0 | 92279.8564 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.753 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 31606.7402 | 0 | 87736.4199 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 156.3102 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -79.35 | 0 | 2498.87 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 96.9223 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -19.84 | 0 | 624.71 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 96.9219 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | -4.36 | 0 | 681.32 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.3641 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 927.14 | 0 | 34604.9486 | 0 | 100% | Finished | 33677.8086 | 0 | 100 | 100 | 100 | 100 | 102.753 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -1.45 | 0 | 767.18 | 0 | 100% | Finished | 768.63 | 0 | 100 | 100 | 100 | 100 | 99.8114 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -1848.55 | 0 | 36848.9304 | 0 | 100% | Finished | 38697.4805 | 0 | 100 | 100 | 100 | 100 | 95.2231 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -12987.2803 | 0 | 15158.7295 | 0 | 100% | Finished | 28146.0098 | 0 | 100 | 100 | 100 | 100 | 53.8575 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1191.88 | 0 | 117750.7216 | 0 | 100% | Finished | 118942.6016 | 0 | 100 | 100 | 100 | 100 | 98.9979 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -2528.8401 | 0 | 11584.6501 | 0 | 100% | Finished | 14113.4902 | 0 | 100 | 100 | 100 | 100 | 82.0821 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 48d | [5 empty] | 382331.6129 |  | 68.8% |  | 427804.4635 | 429625.2635
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 2472.3799 | 0 | 92279.8564 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.753 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 79.51 | 0 | 2193.8401 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 103.7605 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 2472.3799 | 0 | 92279.8564 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 102.753 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -8.71 | 0 | 4603.08 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 99.8111 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -1.45 | 0 | 767.18 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.8114 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -1478.84 | 0 | 31639.4296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 95.5347 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13586.9004 | 0 | 8722.5195 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 39.0979 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -4.36 | 0 | 2301.5399 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 99.8109 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -1478.84 | 0 | 31639.4296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 95.5347 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6793.4502 | 0 | 4361.2598 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 39.0979 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -4214.73 | 0 | 19307.7505 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 82.0821 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -22929.8398 | 0 | 92235.8711 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 80.0897 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 |  | 0 | 0 | 191942.8438 | 10d | 0 | 0 | 0 | 191942.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 1820.8 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 60d | [5 empty] | 77650.4616 |  | 3.993% |  | 89106.1418 | 273145.4931
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 2819.1799 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 6965.2102 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | -21.78 | 0 | 6965.2102 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 99.6883 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2473.03
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 |  | 0 | 0 | 644.55 | 2d | 0 | 0 | 0 | 644.55 | 0% | Not Started | 0 | 644.55 | 100 |  | 0 | 100 |  | 0
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 228.56 | 100 |  | 0 | 100 |  | 0
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 1371.36 | 100 |  | 0 | 100 |  | 0
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 |  | 0 | 0 | 116301.5078 | 10d | 0 | 0 | 0 | 116301.5078 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 228.56 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 43d | [5 empty] | 0 |  | 0% |  | 0 | 179615.2812
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 |  | 0 | 0 | 231412.7969 | 2d | 0 | 0 | 0 | 231412.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 |  | 0 | 0 | 3903.4399 | 4d | 0 | 0 | 0 | 3903.4399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 41378.1406 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 |  | 0 | 0 | 138237.1406 | 10d | 0 | 0 | 0 | 138237.1406 | 0% | Not Started | 0 | 138237.1406 | 100 |  | 0 | 100 |  | 0
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 60d | [5 empty] | 70685.2514 |  | 9.128% |  | 82119.1516 | 77822.6018
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1647.3 | 0 | 23175.1199 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 93.3637 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | -24.69 | 0 | 3860.84 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 99.3646 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | -14.52 | 0 | 2271.0801 | 0 | 100% | Finished | 2285.6001 | 0 | 100 | 100 | 100 | 100 | 99.3647 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 99.3645 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3162.23 | 0 | 2022.7798 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 39.0121 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 99.3645 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 99.3645 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 13d | 38626.6719 | 0 | 7d | -6538.6802 | 0 | 32087.9917 | 0 | 65% | Started | 38626.6719 | 38626.6719 | 100 | 162.5 | 65 | 100 | 83.0721 | 65
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 |  | 0 | 0 | 85207.8281 | 10d | 0 | 0 | 0 | 85207.8281 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 99.3645 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1761.99
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 |  | 0 | 0 | 1761.99 | 5d | 0 | 0 | 0 | 1761.99 | 0% | Not Started | 0 | 1761.99 | 100 |  | 0 | 100 |  | 0
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 109414.1172
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 79701.2578
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 |  | 0 | 0 | 79701.2578 | 65d | 0 | 0 | 0 | 79701.2578 | 0% | Not Started | 0 | 79701.2578 | 100 |  | 0 | 100 |  | 0
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14856.4297
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 14856.4297 | 100 |  | 0 | 100 |  | 0
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14856.4297
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 |  | 0 | 0 | 14856.4297 | 65d | 0 | 0 | 0 | 14856.4297 | 0% | Not Started | 0 | 14856.4297 | 100 |  | 0 | 100 |  | 0
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2012-03-15 17:00 |  | TP Name | 15/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 158d | [5 empty] | 3028512.459 |  | 55.7% |  | 3052817.2978 | 2444846.728
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 158d | [5 empty] | 3028512.459 |  | 55.7% |  | 3052817.2978 | 2444846.728
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 154463.0273 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 14082.4805 | 0 | 154463.0273 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 110.0316 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 356886.23 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | -4.36 | 0 | 681.32 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.3641 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 101700.0186 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 130.73 | 0 | 835.53 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 118.5485 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | -7.26 | 0 | 1135.54 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.3647 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | -5.81 | 0 | 908.43 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 99.3645 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -12644.2002 | 0 | 57923.2373 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 82.0821 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2907 | 0 | 40897.2812 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 93.3637 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39687.6696 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 326.83 | 0 | 2088.82 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 118.5489 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 5190.3301 | 0 | 37598.8496 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 116.0153 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 214817.2219 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | 123.55 | 0 | 214817.2219 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 100.0575 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 148d | [5 empty] | 1689098.2786 |  | 99.9% |  | 1740139.5886 | 1349349.3328
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 96595.9726 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -144.67 | 0 | 6598.7201 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.8546 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -795.7 | 0 | 36292.9406 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.8546 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | 30.89 | 0 | 53704.3119 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 100.0576 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1135.54 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | -7.26 | 0 | 1135.54 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.3647 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 135d | [5 empty] | 1591366.766 |  | 99.89% |  | 1641491.3359 | 1250701.0801
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 290.95 | 0 | 2714.3699 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 112.0058 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | -2.9 | 0 | 454.22 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 99.3656 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | -1.45 | 0 | 227.11 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 99.3656 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -217.01 | 0 | 9898.0701 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.8546 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | 4475.4199 | 0 | 51678.2285 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 109.4813 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1299.76 | 0 | 1756.88 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 384.3367 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6695.2402 | 0 | 41516.791 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 86.1129 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | 1491.8101 | 0 | 17226.0796 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 109.4813 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 31600.2793 | 0 | 70541.8184 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 181.148 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | 346.05 | 0 | 166237.9875 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 100.2086 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3347.6201 | 0 | 20758.3994 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 86.1129 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1079.52 | 0 | 3156 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 151.988 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13586.9004 | 0 | 7642.3789 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 35.9992 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | 295.58 | 0 | 2866.37 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 111.4976 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 134.94 | 0 | 363.5 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 159.0392 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13586.9004 | 0 | 7642.3789 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 35.9992 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | 886.73 | 0 | 8599.1099 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 111.4975 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | -8.71 | 0 | 2786.08 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 99.6883 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | 5967.23 | 0 | 68904.3081 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 109.4813 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -16858.9297 | 0 | 77230.9922 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 82.0821 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -2.9 | 0 | 516.22 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 99.4414 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 23661.7109 | 0 | 91827.9688 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 134.7118 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 400536.3365 |  | 100% |  | 384191.6268 | 183523.4148
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 2472.3799 | 0 | 92279.8564 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.753 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 31606.7402 | 0 | 87736.4199 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 156.3102 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -79.35 | 0 | 2498.87 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 96.9223 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -19.84 | 0 | 624.71 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 96.9219 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | -4.36 | 0 | 681.32 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.3641 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 927.14 | 0 | 34604.9486 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 102.753 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -1.45 | 0 | 767.18 | 0 | 100% | Finished | 768.63 | 0 | 100 | 100 | 100 | 100 | 99.8114 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -1848.55 | 0 | 36848.9304 | 0 | 100% | Finished | 38697.4805 | 0 | 100 | 100 | 100 | 100 | 95.2231 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -12987.2803 | 0 | 15158.7295 | 0 | 100% | Finished | 28146.0098 | 0 | 100 | 100 | 100 | 100 | 53.8575 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1191.88 | 0 | 117750.7216 | 0 | 100% | Finished | 118942.6016 | 0 | 100 | 100 | 100 | 100 | 98.9979 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -2528.8401 | 0 | 11584.6501 | 0 | 100% | Finished | 14113.4902 | 0 | 100 | 100 | 100 | 100 | 82.0821 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 59d | [5 empty] | 536285.1682 |  | 99.71% |  | 619975.8672 | 429853.8235
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 2472.3799 | 0 | 92279.8564 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.753 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 79.51 | 0 | 2193.8401 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 103.7605 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 2472.3799 | 0 | 92279.8564 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 102.753 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -8.71 | 0 | 4603.08 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 99.8111 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -1.45 | 0 | 767.18 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.8114 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -1478.84 | 0 | 31639.4296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 95.5347 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13586.9004 | 0 | 8722.5195 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 39.0979 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -4.36 | 0 | 2301.5399 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 99.8109 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -1478.84 | 0 | 31639.4296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 95.5347 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6793.4502 | 0 | 4361.2598 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 39.0979 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -4214.73 | 0 | 19307.7505 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 82.0821 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -22929.8398 | 0 | 92235.8711 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 80.0897 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 5d | 191942.8438 | 0 | 1d | -38216.3984 | 0 | 153726.4453 | 0 | 83.33% | Started | 191942.8438 | 0 | 100 | 50 | 83.3333 | 100 | 80.0897 | 83.3333
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 |  | 0 | 0 | 1820.8 | 5d | 0 | 0 | 0 | 1820.8 | 0% | Not Started | 0 | 1820.8 | 100 |  | 0 | 100 |  | 0
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | -1.45 | 0 | 227.11 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 99.3656 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 71d | [5 empty] | 715709.6458 |  | 31.06% |  | 693294.835 | 476114.5209
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 2819.1799 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 |  | 0 | 0 | 3428.4099 | 15d | 0 | 0 | 0 | 3428.4099 | 0% | Not Started | 0 | 3428.4099 | 100 |  | 0 | 100 |  | 0
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 6965.2102 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | -21.78 | 0 | 6965.2102 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 99.6883 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 11d | [5 empty] | 119416.1978 |  | 48.31% |  | 118545.9778 | 118774.5378
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -19.84 | 0 | 624.71 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 96.9219 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 4d | 228.56 | 0 | 5d | 134.94 | 0 | 363.5 | 0 | 44.44% | Started | 228.56 | 228.56 | 100 | 400 | 44.4444 | 100 | 159.0392 | 44.4444
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 4d | 1371.36 | 0 | 5d | 809.64 | 0 | 2181 | 0 | 44.44% | Started | 1371.36 | 1371.36 | 100 | 66.6667 | 44.4444 | 100 | 159.0392 | 44.4444
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 4d | 116301.5078 | 0 | 5d | -54.52 | 0 | 116246.9878 | 0 | 44.44% | Started | 116301.5078 | 116301.5078 | 100 | 40 | 44.4444 | 100 | 99.9531 | 44.4444
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 228.56 | 100 |  | 0 | 100 |  | 0
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 |  | 0 | 0 | 93216.1875 | 14d | 0 | 0 | 0 | 93216.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 54d | [5 empty] | 403858.0176 |  | 53.74% |  | 400434.8872 | 210400.231
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2198.8999 | 0 | 229213.897 | 0 | 100% | Finished | 231412.7969 | 0 | 100 | 100 | 100 | 100 | 99.0498 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 11605.6904 | 0 | 15509.1304 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 397.3196 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 |  | 0 | 0 | 1142.8 | 5d | 0 | 0 | 0 | 1142.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 41378.1406 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 4d | 138237.1406 | 0 | 6d | -5969.1401 | 0 | 132268.0005 | 0 | 40% | Started | 138237.1406 | 138237.1406 | 100 | 40 | 40 | 100 | 95.682 | 40
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 |  | 0 | 0 | 133165.9844 | 20d | 0 | 0 | 0 | 133165.9844 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 4d | 26881.5098 | 0 | 6d | -14.52 | 0 | 26866.9898 | 0 | 40% | Started | 26881.5098 | 26881.5098 | 100 | 40 | 40 | 100 | 99.946 | 40
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 |  | 0 | 0 | 1933.66 | 6d | 0 | 0 | 0 | 1933.66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 55882.5703 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 71d | [5 empty] | 185470.2202 |  | 18.6% |  | 167326.9797 | 77822.6018
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1647.3 | 0 | 23175.1199 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 93.3637 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | -24.69 | 0 | 3860.84 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 99.3646 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | -14.52 | 0 | 2271.0801 | 0 | 100% | Finished | 2285.6001 | 0 | 100 | 100 | 100 | 100 | 99.3647 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 99.3645 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3162.23 | 0 | 2022.7798 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 39.0121 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 99.3645 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 99.3645 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -6538.6802 | 0 | 32087.9917 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 83.0721 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 4d | 85207.8281 | 0 | 6d | 29577.1406 | 0 | 114784.9688 | 0 | 40% | Started | 85207.8281 | 0 | 100 | 40 | 40 | 100 | 134.7118 | 40
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 8d | 1828.48 | 0 | 0 | -11.62 | 0 | 1816.86 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 99.3645 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 |  | 0 | 0 | 214498.8438 | 8d | 0 | 0 | 0 | 214498.8438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 11d | [5 empty] | 3224.36 |  | 0.752% |  | 2904.79 | 2904.79
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 326.83 | 0 | 2088.82 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 118.5489 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 4d | 1142.8 | 0 | 1d | -7.26 | 0 | 1135.54 | 0 | 80% | Started | 1142.8 | 1142.8 | 100 | 80 | 80 | 100 | 99.3647 | 80
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 |  | 0 | 0 | 34647.6914 | 10d | 0 | 0 | 0 | 34647.6914 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 11d | [5 empty] | 109130.9172 |  | 18.4% |  | 109414.1172 | 109414.1172
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 11d | [5 empty] | 79606.8578 |  | 29.43% |  | 79701.2578 | 79701.2578
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 11d | 79701.2578 | 0 | 54d | -94.4 | 0 | 79606.8578 | 0 | 16.92% | Started | 79701.2578 | 79701.2578 | 100 | 16.9231 | 16.9231 | 100 | 99.8816 | 16.9231
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 11d | [5 empty] | 14762.0297 |  | 10.68% |  | 14856.4297 | 14856.4297
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 11d | 14856.4297 | 0 | 54d | -94.4 | 0 | 14762.0297 | 0 | 16.92% | Started | 14856.4297 | 14856.4297 | 100 | 16.9231 | 16.9231 | 100 | 99.3646 | 16.9231
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 11d | [5 empty] | 14762.0297 |  | 10.68% |  | 14856.4297 | 14856.4297
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 11d | 14856.4297 | 0 | 54d | -94.4 | 0 | 14762.0297 | 0 | 16.92% | Started | 14856.4297 | 14856.4297 | 100 | 16.9231 | 16.9231 | 100 | 99.3646 | 16.9231
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2012-03-31 17:00 |  | TP Name | 31/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 169d | [5 empty] | 3494943.7461 |  | 64.57% |  | 3538728.7148 | 3043593.2877
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 169d | [5 empty] | 3494943.7461 |  | 64.57% |  | 3538728.7148 | 3043593.2877
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 135871.7568 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | -4508.79 | 0 | 135871.7568 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 96.7882 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 358931.1603 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | -27.28 | 0 | 658.4 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 96.0215 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 106825.3789 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 116.78 | 0 | 821.58 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 116.5692 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | -45.47 | 0 | 1097.33 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 96.0212 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | -36.38 | 0 | 877.86 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 96.0207 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -6969.5298 | 0 | 63597.9077 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 90.1236 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -3373.5801 | 0 | 40430.7012 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 92.2985 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39024.6595 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 291.94 | 0 | 2053.93 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.5688 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4562.21 | 0 | 36970.7295 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 114.0772 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 212422.7219 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -2270.95 | 0 | 212422.7219 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 98.9422 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1698097.5895 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95897.9926 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -159.96 | 0 | 6583.4301 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.6279 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -879.76 | 0 | 36208.8806 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.628 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -567.74 | 0 | 53105.6819 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 98.9422 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1097.33 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | -45.47 | 0 | 1097.33 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 96.0212 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1601102.2668 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 275.66 | 0 | 2699.0799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 111.3748 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | -18.19 | 0 | 438.93 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 96.0207 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | -9.09 | 0 | 219.47 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 96.0229 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -239.94 | 0 | 9875.1401 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.6279 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | 5435.3701 | 0 | 52638.1787 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 111.5149 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1284.48 | 0 | 1741.6 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 380.994 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5152.73 | 0 | 43059.3013 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 89.3124 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | 1811.79 | 0 | 17546.0596 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 111.5149 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 32609.5801 | 0 | 71551.1191 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 183.7398 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -1505.35 | 0 | 164386.5875 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 99.0926 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2576.3601 | 0 | 21529.6594 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 89.3124 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1018.39 | 0 | 3094.87 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 149.0441 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13518.54 | 0 | 7710.7393 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 36.3212 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | 437.8 | 0 | 3008.59 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 117.0298 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 127.3 | 0 | 355.86 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 155.6965 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13518.54 | 0 | 7710.7393 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 36.3212 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | 1318.41 | 0 | 9030.7899 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 117.0947 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | -54.57 | 0 | 2740.22 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 98.0474 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | 7247.1602 | 0 | 70184.2383 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 111.5149 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -9292.71 | 0 | 84797.2119 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 90.1236 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -18.19 | 0 | 500.93 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 96.496 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 18040.1309 | 0 | 86206.3887 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 126.4649 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 399829.9164 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 2055.25 | 0 | 91862.7266 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.2885 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 31346.0293 | 0 | 87475.709 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 155.8457 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -140.49 | 0 | 2437.73 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 94.5509 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -35.12 | 0 | 609.43 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 94.5512 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | -27.28 | 0 | 658.4 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 96.0215 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 770.72 | 0 | 34448.5286 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 102.2885 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -9.09 | 0 | 759.54 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 98.8174 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -719.1 | 0 | 37978.3805 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 98.1417 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -12775.6396 | 0 | 15370.3701 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 54.6094 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -3433.0801 | 0 | 115509.5215 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 97.1137 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -1393.91 | 0 | 12719.5802 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 90.1236 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 540246.6475 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 2055.25 | 0 | 91862.7266 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 102.2885 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 47.04 | 0 | 2161.3701 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 102.2248 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 2055.25 | 0 | 91862.7266 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 102.2885 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -54.57 | 0 | 4557.22 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 98.8167 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -9.09 | 0 | 759.54 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 98.8174 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -575.28 | 0 | 32542.9895 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 98.263 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13518.54 | 0 | 8790.8799 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 39.4043 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -27.28 | 0 | 2278.6199 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 98.8169 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -575.28 | 0 | 32542.9895 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 98.263 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6759.27 | 0 | 4395.4399 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 39.4043 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -2323.1799 | 0 | 21199.3005 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 90.1236 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -22924.6895 | 0 | 92241.0215 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 80.0942 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -38207.8203 | 0 | 153735.0234 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 80.0942 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -723.47 | 0 | 1097.3301 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 60.2664 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | -9.09 | 0 | 219.47 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 96.0229 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 82d | [5 empty] | 1157672.4908 |  | 51.2% |  | 1142737.7606 | 645533.8234
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 2819.1799 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 10d | [5 empty] | 3291.9899 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 10d | 3428.4099 | 0 | 5d | -136.42 | 0 | 3291.9899 | 0 | 66.67% | Started | 3428.4099 | 3428.4099 | 100 | 66.6667 | 66.6667 | 100 | 96.0209 | 66.6667
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 6850.5702 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | -136.42 | 0 | 6850.5702 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 98.0475 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 22d | [5 empty] | 211938.3753 |  | 86.38% |  | 211990.7253 | 118774.5378
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -35.12 | 0 | 609.43 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 94.5512 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 127.3 | 0 | 355.86 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 155.6965 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 763.79 | 0 | 2135.15 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 155.6958 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -693.67 | 0 | 115607.8378 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 99.4036 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 6d | 228.56 | 0 | 3d | -9.09 | 0 | 219.47 | 0 | 66.67% | Started | 228.56 | 228.56 | 100 | 600 | 66.6667 | 100 | 96.0229 | 66.6667
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 10d | 93216.1875 | 0 | 10d | -205.56 | 0 | 93010.6275 | 0 | 50% | Started | 93216.1875 | 0 | 100 | 71.4286 | 50 | 100 | 99.7795 | 50
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 |  | 0 | 0 | 994.24 | 4d | 0 | 0 | 0 | 994.24 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 |  | 0 | 0 | 20492.0508 | 5d | 0 | 0 | 0 | 20492.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 |  | 0 | 0 | 3240.6299 | 5d | 0 | 0 | 0 | 3240.6299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 |  | 0 | 0 | 8228.6904 | 5d | 0 | 0 | 0 | 8228.6904 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 65d | [5 empty] | 538949.9719 |  | 71.76% |  | 534743.6716 | 351104.8435
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -7023.8599 | 0 | 224388.937 | 0 | 100% | Finished | 231412.7969 | 0 | 100 | 100 | 100 | 100 | 96.9648 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 11727.6602 | 0 | 15631.1001 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 400.4442 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 636.49 | 0 | 1779.29 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 155.6957 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 |  | 0 | 0 | 139561.8125 | 12d | 0 | 0 | 0 | 139561.8125 | 0% | Not Started | 0 | 139561.8125 | 100 |  | 0 | 100 |  | 0
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 |  | 0 | 0 | 41378.1406 | 3d | 0 | 0 | 0 | 41378.1406 | 0% | Not Started | 0 | 41378.1406 | 100 |  | 0 | 100 |  | 0
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | -749.4 | 0 | 137487.7406 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 99.4579 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 5d | 133165.9844 | 0 | 5d | -293.65 | 0 | 132872.3344 | 0 | 50% | Started | 133165.9844 | 0 | 100 | 25 | 50 | 100 | 99.7795 | 50
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -90.94 | 0 | 26790.5698 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 99.6617 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 |  | 0 | 0 | 29478.8203 | 3d | 0 | 0 | 0 | 29478.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 |  | 0 | 0 | 7090.1001 | 22d | 0 | 0 | 0 | 7090.1001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 6d | [5 empty] | 1828.29 |  | 28.57% |  | 1933.66 | 0
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 |  | 0 | 0 | 4834.1602 | 15d | 0 | 0 | 0 | 4834.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | -105.37 | 0 | 1828.29 | 0 | 100% | Finished | 1933.66 | 0 | 100 | 100 | 100 | 100 | 94.5507 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 |  | 0 | 0 | 55882.5703 | 26d | 0 | 0 | 0 | 55882.5703 | 0% | Not Started | 0 | 55882.5703 | 100 |  | 0 | 100 |  | 0
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 26429.0898 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 82d | [5 empty] | 394813.2935 |  | 42.65% |  | 383654.3035 | 80108.2019
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1911.6899 | 0 | 22910.73 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 92.2985 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | -154.6 | 0 | 3730.93 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 96.0211 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | -90.94 | 0 | 2194.6601 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 96.0212 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -72.75 | 0 | 1755.73 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 96.0213 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3147.1899 | 0 | 2037.8198 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 39.3021 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -72.75 | 0 | 1755.73 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 96.0213 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -72.75 | 0 | 1755.73 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 96.0213 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -3516.51 | 0 | 35110.1619 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 90.8962 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 22550.1699 | 0 | 107757.998 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 126.4649 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | -72.75 | 0 | 1755.73 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 96.0213 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 5d | 1828.48 | 0 | 10d | -72.75 | 0 | 1755.73 | 0 | 33.33% | Started | 1828.48 | 0 | 100 | 62.5 | 33.3333 | 100 | 96.0213 | 33.3333
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 5d | 214498.8438 | 0 | 7d | -2206.5 | 0 | 212292.3438 | 0 | 41.67% | Started | 214498.8438 | 0 | 100 | 62.5 | 41.6667 | 100 | 98.9713 | 41.6667
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 |  | 0 | 0 | 2880.76 | 8d | 0 | 0 | 0 | 2880.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 22d | [5 empty] | 38496.4715 |  | 9.721% |  | 37552.4814 | 39163.8715
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 291.94 | 0 | 2053.93 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.5688 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | -45.47 | 0 | 1097.33 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 96.0212 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 697.52 | 0 | 35345.2114 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 102.0132 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 |  | 0 | 0 | 1611.39 | 5d | 0 | 0 | 0 | 1611.39 | 0% | Not Started | 0 | 1611.39 | 100 |  | 0 | 100 |  | 0
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 |  | 0 | 0 | 347119.1875 | 3d | 0 | 0 | 0 | 347119.1875 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 22d | [5 empty] | 105874.2771 |  | 18.4% |  | 109414.1172 | 109414.1172
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 22d | [5 empty] | 77343.6777 |  | 29.43% |  | 79701.2578 | 79701.2578
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 22d | 79701.2578 | 0 | 43d | -2357.5801 | 0 | 77343.6777 | 0 | 33.85% | Started | 79701.2578 | 79701.2578 | 100 | 33.8462 | 33.8462 | 100 | 97.042 | 33.8462
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 22d | [5 empty] | 14265.2997 |  | 10.68% |  | 14856.4297 | 14856.4297
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 22d | 14856.4297 | 0 | 43d | -591.13 | 0 | 14265.2997 | 0 | 33.85% | Started | 14856.4297 | 14856.4297 | 100 | 33.8462 | 33.8462 | 100 | 96.021 | 33.8462
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 22d | [5 empty] | 14265.2997 |  | 10.68% |  | 14856.4297 | 14856.4297
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 22d | 14856.4297 | 0 | 43d | -591.13 | 0 | 14265.2997 | 0 | 33.85% | Started | 14856.4297 | 14856.4297 | 100 | 33.8462 | 33.8462 | 100 | 96.021 | 33.8462
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 457.12
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 457.12 | 100 |  | 0 | 100 |  | 0
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2012-04-30 17:00 |  | TP Name | 30/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 189d | [5 empty] | 4329939.7159 |  | 76.78% |  | 4207920.9474 | 3964948.002
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 189d | [5 empty] | 4329939.7159 |  | 76.78% |  | 4207920.9474 | 3964948.002
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 134360.8066 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | -6019.7402 | 0 | 134360.8066 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 95.7118 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 354840.2096 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 114.96 | 0 | 800.64 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 116.7658 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 103350.4486 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 196.93 | 0 | 901.73 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 127.9413 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 191.6 | 0 | 1334.4001 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 116.7658 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 153.28 | 0 | 1067.52 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 116.7658 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -13434.9502 | 0 | 57132.4873 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 80.9615 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -889.97 | 0 | 42914.3113 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 97.9683 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 42831.9394 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 492.32 | 0 | 2254.31 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 127.9411 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 8169.1099 | 0 | 40577.6294 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 125.2067 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 207857.1816 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -6836.4902 | 0 | 207857.1816 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 96.8157 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1788928.2855 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95372.9927 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -65.13 | 0 | 6678.2601 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 99.0342 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -358.21 | 0 | 36730.4306 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 99.0342 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1709.12 | 0 | 51964.3019 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 96.8157 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1334.4001 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 191.6 | 0 | 1334.4001 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 116.7658 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1692220.8928 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 370.49 | 0 | 2793.9099 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 115.2879 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 76.65 | 0 | 533.77 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 116.768 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 38.32 | 0 | 266.88 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 116.7658 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -97.69 | 0 | 10017.3901 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 99.0342 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | 4471 | 0 | 51673.8086 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 109.4719 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1379.3101 | 0 | 1836.4301 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 401.7392 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5167.8799 | 0 | 43044.1514 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 89.2809 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | 1490.33 | 0 | 17224.5995 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 109.4719 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 30129 | 0 | 69070.5391 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 177.3698 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -4826.8198 | 0 | 161065.1177 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 97.0904 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2583.9399 | 0 | 21522.0796 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 89.2809 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1397.7 | 0 | 3474.1799 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 167.311 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13791.25 | 0 | 7438.0293 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 35.0367 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | 357.68 | 0 | 2928.47 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 113.9132 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 174.71 | 0 | 403.27 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 176.4395 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13791.25 | 0 | 7438.0293 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 35.0367 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | 1073.05 | 0 | 8785.4299 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 113.9133 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 469.64 | 0 | 3264.4301 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 116.8041 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | 5961.3301 | 0 | 68898.4082 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 109.4719 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -17913.2598 | 0 | 76176.6621 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 80.9616 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 76.64 | 0 | 595.76 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 114.7634 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 54027.4414 | 0 | 122193.6992 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 179.2583 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 436833.9092 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 20578.5605 | 0 | 110386.0371 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 122.9141 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 42923.1016 | 0 | 99052.7812 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 176.4713 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | 238.82 | 0 | 2817.04 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 109.263 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | 59.71 | 0 | 704.26 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 109.2638 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | 114.96 | 0 | 800.64 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 116.7658 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 7716.96 | 0 | 41394.7686 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 122.9141 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | 38.32 | 0 | 806.95 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 104.9855 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -1285.2 | 0 | 37412.2805 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 96.6789 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -13271.7598 | 0 | 14874.25 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 52.8467 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1784.2 | 0 | 117158.4016 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 98.4999 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -2686.99 | 0 | 11426.5002 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 80.9615 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 574741.9397 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 20578.5605 | 0 | 110386.0371 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 122.9141 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 161.43 | 0 | 2275.7601 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 107.635 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 20578.5605 | 0 | 110386.0371 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 122.9141 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | 229.92 | 0 | 4841.71 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 104.9855 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | 38.32 | 0 | 806.95 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 104.9855 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -1028.16 | 0 | 32090.1095 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 96.8955 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13791.25 | 0 | 8518.1699 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 38.1819 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | 114.96 | 0 | 2420.8599 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 104.9855 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -1028.16 | 0 | 32090.1095 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 96.8955 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6895.6201 | 0 | 4259.0898 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 38.182 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -4478.3198 | 0 | 19044.1606 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 80.9615 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -22907.5801 | 0 | 92258.1309 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 80.109 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -38179.3086 | 0 | 153763.5352 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 80.109 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -486.4 | 0 | 1334.4001 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 73.2865 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | 38.32 | 0 | 266.88 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 116.7658 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 102d | [5 empty] | 1556499.3881 |  | 65.54% |  | 1462742.2956 | 1081021.9986
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 |  | 0 | 0 | 2819.1799 | 8d | 0 | 0 | 0 | 2819.1799 | 0% | Not Started | 0 | 2819.1799 | 100 |  | 0 | 100 |  | 0
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 4003.1999 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | 574.79 | 0 | 4003.1999 | 0 | 100% | Finished | 3428.4099 | 3428.4099 | 100 | 100 | 100 | 100 | 116.7655 | 100
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 8161.1002 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 1174.11 | 0 | 8161.1002 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 116.8042 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 268869.0267 |  | 100% |  | 245403.4564 | 243952.0964
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | 59.71 | 0 | 704.26 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 109.2638 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 174.71 | 0 | 403.27 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 176.4395 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1048.27 | 0 | 2419.63 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 176.4402 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -54.99 | 0 | 116246.5178 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 99.9527 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | 38.32 | 0 | 266.88 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 116.7658 | 100
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 851.66 | 0 | 94067.8475 | 0 | 100% | Finished | 93216.1875 | 93216.1875 | 100 | 142.8571 | 100 | 100 | 100.9136 | 100
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | 76.64 | 0 | 533.76 | 0 | 100% | Finished | 457.12 | 0 | 100 | 100 | 100 | 100 | 116.7658 | 100
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | 105.28 | 0 | 1099.52 | 0 | 100% | Finished | 994.24 | 0 | 100 | 100 | 100 | 100 | 110.589 | 100
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -5388.0098 | 0 | 15104.041 | 0 | 100% | Finished | 20492.0508 | 20492.0508 | 100 | 200 | 100 | 100 | 73.7068 | 100
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28331.5801 | 0 | 31572.21 | 0 | 100% | Finished | 3240.6299 | 3240.6299 | 100 | 200 | 100 | 100 | 974.2615 | 100
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -1777.6 | 0 | 6451.0905 | 0 | 100% | Finished | 8228.6904 | 8228.6904 | 100 | 200 | 100 | 100 | 78.3975 | 100
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 745570.8342 |  | 100% |  | 745162.4451 | 611996.4607
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2097.3601 | 0 | 229315.4368 | 0 | 100% | Finished | 231412.7969 | 231412.7969 | 100 | 100 | 100 | 100 | 99.0937 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 11182.25 | 0 | 15085.6899 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 386.4717 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 873.56 | 0 | 2016.36 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 176.4403 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | -65.98 | 0 | 139495.8325 | 0 | 100% | Finished | 139561.8125 | 139561.8125 | 100 | 100 | 100 | 100 | 99.9527 | 100
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 2099.3401 | 0 | 43477.4807 | 0 | 100% | Finished | 41378.1406 | 41378.1406 | 100 | 100 | 100 | 100 | 105.0735 | 100
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | 6997.8101 | 0 | 145234.9507 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 105.0622 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 1216.66 | 0 | 134382.6444 | 0 | 100% | Finished | 133165.9844 | 0 | 100 | 50 | 100 | 100 | 100.9136 | 100
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -20032.7109 | 0 | 6848.7988 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 25.4777 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 234.82 | 0 | 29713.6403 | 0 | 100% | Finished | 29478.8203 | 29478.8203 | 100 | 100 | 100 | 100 | 100.7966 | 100
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 8d | [5 empty] | 7746.8601 |  | 100% |  | 7090.1001 | 7090.1001
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 8d | 7090.1001 | 0 | 17d | 656.76 | 0 | 7746.8601 | 0 | 32% | Started | 7090.1001 | 7090.1001 | 100 | 36.3636 | 32 | 100 | 109.2631 | 32
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 26d | [5 empty] | 7394.7302 |  | 100% |  | 6767.8202 | 6767.8202
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 5d | 4834.1602 | 0 | 10d | 447.79 | 0 | 5281.9502 | 0 | 33.33% | Started | 4834.1602 | 4834.1602 | 100 | 33.3333 | 33.3333 | 100 | 109.263 | 33.3333
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | 179.12 | 0 | 2112.78 | 0 | 100% | Finished | 1933.66 | 1933.66 | 100 | 100 | 100 | 100 | 109.2633 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 20d | [5 empty] | 67994.5508 |  | 100% |  | 55882.5703 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 20d | 55882.5703 | 0 | 6d | 12111.9805 | 0 | 67994.5508 | 0 | 76.92% | Started | 55882.5703 | 55882.5703 | 100 | 76.9231 | 76.9231 | 100 | 121.674 | 76.9231
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10760.8496
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 10760.8496 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 |  | 0 | 0 | 26429.0898 | 25d | 0 | 0 | 0 | 26429.0898 | 0% | Not Started | 0 | 26429.0898 | 100 |  | 0 | 100 |  | 0
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 21143.2695
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 21143.2695 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 102d | [5 empty] | 446759.086 |  | 43.58% |  | 392020.5034 | 83765.1619
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -504.32 | 0 | 24318.0999 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 97.9683 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 651.43 | 0 | 4536.96 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 116.7655 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | 383.19 | 0 | 2668.7901 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 116.7654 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 116.7658 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -2767.8799 | 0 | 2417.1299 | 0 | 100% | Finished | 5185.0098 | 0 | 100 | 100 | 100 | 100 | 46.6177 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 116.7658 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 116.7658 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -7023.4302 | 0 | 31603.2417 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 81.8171 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 67534.3125 | 0 | 152742.1406 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 179.2583 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 116.7658 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 187.5 | 100 | 100 | 116.7658 | 100
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -6713.3398 | 0 | 207785.5039 | 0 | 100% | Finished | 214498.8438 | 0 | 100 | 150 | 100 | 100 | 96.8702 | 100
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 112.5 | 100 | 100 | 116.7658 | 100
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | 306.56 | 0 | 2135.04 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 75 | 100 | 100 | 116.7658 | 100
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 7d | 1828.48 | 0 | 3d | 306.56 | 0 | 2135.04 | 0 | 70% | Started | 1828.48 | 1828.48 | 100 | 87.5 | 70 | 100 | 116.7658 | 70
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 7d | 2880.76 | 0 | 1d | 726.14 | 0 | 3606.9 | 0 | 87.5% | Started | 2880.76 | 0 | 100 | 87.5 | 87.5 | 100 | 125.2065 | 87.5
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 |  | 0 | 0 | 214560.4219 | 8d | 0 | 0 | 0 | 214560.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 |  | 0 | 0 | 6831.02 | 7d | 0 | 0 | 0 | 6831.02 | 0% | Not Started | 0 | 6831.02 | 100 |  | 0 | 100 |  | 0
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 376998.2287 |  | 100% |  | 386283.059 | 386283.059
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 492.32 | 0 | 2254.31 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 127.9411 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | 191.6 | 0 | 1334.4001 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 116.7658 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | -6971.9702 | 0 | 27675.7212 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 79.8775 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | 149.26 | 0 | 1760.65 | 0 | 100% | Finished | 1611.39 | 1611.39 | 100 | 100 | 100 | 100 | 109.2628 | 100
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -3146.04 | 0 | 343973.1475 | 0 | 100% | Finished | 347119.1875 | 347119.1875 | 100 | 100 | 100 | 100 | 99.0937 | 100
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 42d | [5 empty] | 116266.6372 |  | 18.4% |  | 109414.1172 | 248161.4688
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 42d | [5 empty] | 81572.2378 |  | 29.43% |  | 79701.2578 | 153883.5312
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 42d | 79701.2578 | 0 | 23d | 1870.98 | 0 | 81572.2378 | 0 | 64.62% | Started | 79701.2578 | 79701.2578 | 100 | 64.6154 | 64.6154 | 100 | 102.3475 | 64.6154
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 |  | 0 | 0 | 74182.2734 | 42d | 0 | 0 | 0 | 74182.2734 | 0% | Not Started | 0 | 74182.2734 | 100 |  | 0 | 100 |  | 0
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 42d | [5 empty] | 17347.1997 |  | 10.68% |  | 14856.4297 | 47138.9688
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 42d | 14856.4297 | 0 | 23d | 2490.77 | 0 | 17347.1997 | 0 | 64.62% | Started | 14856.4297 | 14856.4297 | 100 | 64.6154 | 64.6154 | 100 | 116.7656 | 64.6154
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 32282.5391 | 100 |  | 0 | 100 |  | 0
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 42d | [5 empty] | 17347.1997 |  | 10.68% |  | 14856.4297 | 47138.9688
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 42d | 14856.4297 | 0 | 23d | 2490.77 | 0 | 17347.1997 | 0 | 64.62% | Started | 14856.4297 | 14856.4297 | 100 | 64.6154 | 64.6154 | 100 | 116.7656 | 64.6154
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 |  | 0 | 0 | 32282.5391 | 42d | 0 | 0 | 0 | 32282.5391 | 0% | Not Started | 0 | 32282.5391 | 100 |  | 0 | 100 |  | 0
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 |  | 0 | 0 | 18175.6309 | 15d | 0 | 0 | 0 | 18175.6309 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 8d | [5 empty] | 2046.16 |  | 40% |  | 457.12 | 457.12
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1589.04 | 0 | 2046.16 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 447.6199 | 100
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2012-05-31 17:00 |  | TP Name | 31/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 209d | [5 empty] | 4695563.0519 |  | 84.28% |  | 4619140.6014 | 4247568.795
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 209d | [5 empty] | 4695563.0519 |  | 84.28% |  | 4619140.6014 | 4247568.795
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 146252.417 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 5871.8701 | 0 | 146252.417 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 104.1828 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 363657.6597 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 0.21 | 0 | 685.89 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.0306 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 113548.5688 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 117.08 | 0 | 821.88 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 116.6118 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 0.35 | 0 | 1143.15 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.0306 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 0.28 | 0 | 914.52 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.0306 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -958.7 | 0 | 69608.7375 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 98.6414 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2744 | 0 | 41060.2812 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 93.7358 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39039.2493 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 292.71 | 0 | 2054.7 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.6125 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4576.0298 | 0 | 36984.5493 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 114.1198 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210383.9517 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4309.7202 | 0 | 210383.9517 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 97.9926 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1761267.7292 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95507.4426 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -141.63 | 0 | 6601.7601 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.8997 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -778.95 | 0 | 36309.6906 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.8998 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1077.4301 | 0 | 52595.9918 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 97.9926 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1143.15 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 0.35 | 0 | 1143.15 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.0306 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1664617.1366 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | 0.51 | 0 | 2423.9299 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 100.021 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 0.14 | 0 | 457.26 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.0306 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.07 | 0 | 228.63 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.0306 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -212.44 | 0 | 9902.6401 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.8998 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | 3103.6001 | 0 | 50306.4087 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 106.575 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1302.8101 | 0 | 1759.9301 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 385.004 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -5918.2202 | 0 | 42293.811 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 87.7246 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | 1034.53 | 0 | 16768.7996 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 106.575 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 30971.0703 | 0 | 69912.6094 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 179.5322 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -2915.45 | 0 | 162976.4875 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 98.2426 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -2959.1101 | 0 | 21146.9094 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 87.7246 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1695.99 | 0 | 3772.47 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 181.6762 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13517.0098 | 0 | 7712.2695 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 36.3285 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | 254.98 | 0 | 2825.77 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 109.9184 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 212 | 0 | 440.56 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 192.7546 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13517.0098 | 0 | 7712.2695 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 36.3285 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | 764.95 | 0 | 8477.3299 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 109.9185 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 240.15 | 0 | 3034.94 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 108.5928 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | 4138.1401 | 0 | 67075.2183 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 106.575 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -1278.27 | 0 | 92811.6519 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 98.6414 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | 0.14 | 0 | 519.26 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 100.027 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 9308.5703 | 0 | 77474.8281 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 113.6557 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 438929.0563 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 20624.0703 | 0 | 110431.5469 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 122.9648 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 42951.5391 | 0 | 99081.2188 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 176.522 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -189.83 | 0 | 2388.39 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 92.6372 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -47.46 | 0 | 597.09 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 92.6367 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | 0.21 | 0 | 685.89 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.0306 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 7734.02 | 0 | 41411.8286 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 122.9647 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | 0.07 | 0 | 768.7 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 100.0091 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -1924.9301 | 0 | 36772.5504 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 95.0257 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -13103.3398 | 0 | 15042.6699 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 53.4451 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1115.1801 | 0 | 117827.4215 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 99.0624 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -191.74 | 0 | 13921.7502 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 98.6414 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 575654.0974 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 20624.0703 | 0 | 110431.5469 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 122.9648 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 87.01 | 0 | 2201.3401 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 104.1153 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 20624.0703 | 0 | 110431.5469 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 122.9648 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | 0.42 | 0 | 4612.21 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 100.0091 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | 0.07 | 0 | 768.7 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 100.0091 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -1539.9399 | 0 | 31578.3296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 95.3502 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13517.0098 | 0 | 8792.4102 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 39.4112 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | 0.21 | 0 | 2306.1099 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 100.0091 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -1539.9399 | 0 | 31578.3296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 95.3502 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6758.5098 | 0 | 4396.2002 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 39.4112 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -319.57 | 0 | 23202.9105 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 98.6414 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -23672.1992 | 0 | 91493.5117 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 79.4451 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -39453.6719 | 0 | 152489.1719 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 79.4451 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -677.65 | 0 | 1143.15 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 62.7828 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | 0.07 | 0 | 228.63 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.0306 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 122d | [5 empty] | 1773507.5275 |  | 76.93% |  | 1717038.9672 | 1345467.1608
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 14d | [5 empty] | 3287.5099 |  | 100% |  | 2819.1799 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 2012-05-10 08:00 | 4d | 2819.1799 | 0 | 4d | 468.33 | 0 | 3287.5099 | 0 | 50% | Started | 2819.1799 | 2819.1799 | 100 | 50 | 50 | 100 | 116.6123 | 50
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 3429.4699 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | 1.06 | 0 | 3429.4699 | 0 | 100% | Finished | 3428.4099 | 3428.4099 | 100 | 100 | 100 | 100 | 100.0309 | 100
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 7587.3702 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 600.38 | 0 | 7587.3702 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 108.5928 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 276263.3763 |  | 100% |  | 245403.4564 | 245403.4564
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -47.46 | 0 | 597.09 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 92.6367 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 212 | 0 | 440.56 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 192.7546 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1272 | 0 | 2643.36 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 192.7546 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | 4667.0698 | 0 | 120968.5776 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 104.0129 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | 0.07 | 0 | 228.63 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 100.0306 | 100
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 243.71 | 0 | 93459.8975 | 0 | 100% | Finished | 93216.1875 | 93216.1875 | 100 | 142.8571 | 100 | 100 | 100.2614 | 100
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | 0.14 | 0 | 457.26 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.0306 | 100
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | -71.72 | 0 | 922.52 | 0 | 100% | Finished | 994.24 | 994.24 | 100 | 100 | 100 | 100 | 92.7864 | 100
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -1587.38 | 0 | 18904.6708 | 0 | 100% | Finished | 20492.0508 | 20492.0508 | 100 | 200 | 100 | 100 | 92.2537 | 100
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28140.3301 | 0 | 31380.96 | 0 | 100% | Finished | 3240.6299 | 3240.6299 | 100 | 200 | 100 | 100 | 968.3599 | 100
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -1968.84 | 0 | 6259.8505 | 0 | 100% | Finished | 8228.6904 | 8228.6904 | 100 | 200 | 100 | 100 | 76.0735 | 100
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 761570.2354 |  | 100% |  | 745162.4451 | 745162.4451
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -259.53 | 0 | 231153.2669 | 0 | 100% | Finished | 231412.7969 | 231412.7969 | 100 | 100 | 100 | 100 | 99.8878 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 11734.8896 | 0 | 15638.3296 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 400.6294 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 1060 | 0 | 2202.8 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 192.7546 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | 5600.48 | 0 | 145162.2925 | 0 | 100% | Finished | 139561.8125 | 139561.8125 | 100 | 100 | 100 | 100 | 104.0129 | 100
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 4204.3701 | 0 | 45582.5107 | 0 | 100% | Finished | 41378.1406 | 41378.1406 | 100 | 100 | 100 | 100 | 110.1608 | 100
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | 14014.5498 | 0 | 152251.6904 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 110.138 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 348.15 | 0 | 133514.1344 | 0 | 100% | Finished | 133165.9844 | 133165.9844 | 100 | 50 | 100 | 100 | 100.2614 | 100
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -20415.1992 | 0 | 6466.3105 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 24.0549 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 120.08 | 0 | 29598.9003 | 0 | 100% | Finished | 29478.8203 | 29478.8203 | 100 | 100 | 100 | 100 | 100.4073 | 100
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 25d | [5 empty] | 6568.0501 |  | 100% |  | 7090.1001 | 7090.1001
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 25d | 7090.1001 | 0 | 0 | -522.05 | 0 | 6568.0501 | 0 | 100% | Finished | 7090.1001 | 7090.1001 | 100 | 113.6364 | 100 | 100 | 92.6369 | 100
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 36d | [5 empty] | 6269.5002 |  | 100% |  | 6767.8202 | 6767.8202
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 15d | 4834.1602 | 0 | 0 | -355.94 | 0 | 4478.2202 | 0 | 100% | Finished | 4834.1602 | 4834.1602 | 100 | 100 | 100 | 100 | 92.637 | 100
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | -142.38 | 0 | 1791.28 | 0 | 100% | Finished | 1933.66 | 1933.66 | 100 | 100 | 100 | 100 | 92.6368 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 35453.8789
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 35453.8789 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 26881.5098
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 |  | 0 | 0 | 26881.5098 | 10d | 0 | 0 | 0 | 26881.5098 | 0% | Not Started | 0 | 26881.5098 | 100 |  | 0 | 100 |  | 0
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 26d | [5 empty] | 44788.1299 |  | 100% |  | 55882.5703 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 26d | 55882.5703 | 0 | 0 | -11094.4404 | 0 | 44788.1299 | 0 | 100% | Finished | 55882.5703 | 55882.5703 | 100 | 100 | 100 | 100 | 80.1469 | 100
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10760.8496
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 |  | 0 | 0 | 10760.8496 | 14d | 0 | 0 | 0 | 10760.8496 | 0% | Not Started | 0 | 10760.8496 | 100 |  | 0 | 100 |  | 0
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 14d | [5 empty] | 27516.7299 |  | 100% |  | 26429.0898 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 2012-05-10 08:00 | 14d | 26429.0898 | 0 | 11d | 1087.64 | 0 | 27516.7299 | 0 | 56% | Started | 26429.0898 | 26429.0898 | 100 | 56 | 56 | 100 | 104.1153 | 56
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 81165.0889
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 |  | 0 | 0 | 21143.2695 | 20d | 0 | 0 | 0 | 21143.2695 | 0% | Not Started | 0 | 21143.2695 | 100 |  | 0 | 100 |  | 0
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 |  | 0 | 0 | 10003.6396 | 5d | 0 | 0 | 0 | 10003.6396 | 0% | Not Started | 0 | 10003.6396 | 100 |  | 0 | 100 |  | 0
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 50018.1797 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2285.6001
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 2285.6001 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 122d | [5 empty] | 636227.1557 |  | 68.59% |  | 617068.9053 | 88950.1716
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1554.9301 | 0 | 23267.4899 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 93.7358 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 1.2 | 0 | 3886.73 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 100.0309 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | 0.71 | 0 | 2286.3101 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 100.0311 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.0312 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3073.8701 | 0 | 2111.1396 | 0 | 100% | Finished | 5185.0098 | 5185.0098 | 100 | 100 | 100 | 100 | 40.7162 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.0312 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 100 | 100 | 100 | 100.0312 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -391.15 | 0 | 38235.5219 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 98.9874 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 11635.71 | 0 | 96843.5381 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 113.6557 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.0312 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 187.5 | 100 | 100 | 100.0312 | 100
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -4173.1802 | 0 | 210325.6636 | 0 | 100% | Finished | 214498.8438 | 0 | 100 | 150 | 100 | 100 | 98.0545 | 100
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 112.5 | 100 | 100 | 100.0312 | 100
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 75 | 100 | 100 | 100.0312 | 100
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 10d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.0312 | 100
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 8d | 2880.76 | 0 | 0 | 406.76 | 0 | 3287.52 | 0 | 100% | Finished | 2880.76 | 0 | 100 | 100 | 100 | 100 | 114.1199 | 100
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 2012-05-03 08:00 | 9d | 214560.4219 | 0 | 0 | -4234.75 | 0 | 210325.6719 | 0 | 100% | Finished | 214560.4219 | 0 | 100 | 112.5 | 100 | 100 | 98.0263 | 100
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-03 08:00 | 9d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 112.5 | 100 | 100 | 100.0312 | 100
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-16 08:00 | 10d | 1828.48 | 0 | 0 | 0.57 | 0 | 1829.05 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 125 | 100 | 100 | 100.0312 | 100
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 |  | 0 | 0 | 58330.2695 | 30d | 0 | 0 | 0 | 58330.2695 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 2012-05-07 08:00 | 15d | 6831.02 | 0 | 0 | 20536.0508 | 0 | 27367.0708 | 0 | 100% | Finished | 6831.02 | 6831.02 | 100 | 214.2857 | 100 | 100 | 400.6293 | 100
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 |  | 0 | 0 | 188607.2344 | 7d | 0 | 0 | 0 | 188607.2344 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 |  | 0 | 0 | 29202.8496 | 20d | 0 | 0 | 0 | 29202.8496 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 383564.7089 |  | 100% |  | 386283.059 | 386283.059
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 292.71 | 0 | 2054.7 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.6125 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | 0.35 | 0 | 1143.15 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.0306 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 646.53 | 0 | 35294.2214 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 101.866 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | -118.65 | 0 | 1492.74 | 0 | 100% | Finished | 1611.39 | 1611.39 | 100 | 100 | 100 | 100 | 92.6368 | 100
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -3539.29 | 0 | 343579.8975 | 0 | 100% | Finished | 347119.1875 | 347119.1875 | 100 | 100 | 100 | 100 | 98.9804 | 100
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 62d | [5 empty] | 265343.3496 |  | 44.78% |  | 266337.0996 | 266337.0996
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 62d | [5 empty] | 152870.8212 |  | 56.83% |  | 153883.5312 | 153883.5312
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 62d | 79701.2578 | 0 | 3d | -615.2 | 0 | 79086.0578 | 0 | 95.38% | Started | 79701.2578 | 79701.2578 | 100 | 95.3846 | 95.3846 | 100 | 99.2281 | 95.3846
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 2012-05-07 08:00 | 17d | 74182.2734 | 0 | 25d | -397.51 | 0 | 73784.7634 | 0 | 40.48% | Started | 74182.2734 | 74182.2734 | 100 | 40.4762 | 40.4762 | 100 | 99.4641 | 40.4762
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 |  | 0 | 0 | 116911.4219 | 25d | 0 | 0 | 0 | 116911.4219 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 62d | [5 empty] | 47146.5288 |  | 33.89% |  | 47138.9688 | 47138.9688
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 62d | 14856.4297 | 0 | 3d | 4.59 | 0 | 14861.0197 | 0 | 95.38% | Started | 14856.4297 | 14856.4297 | 100 | 95.3846 | 95.3846 | 100 | 100.0309 | 95.3846
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 17d | 32282.5391 | 0 | 25d | 2.97 | 0 | 32285.5091 | 0 | 40.48% | Started | 32282.5391 | 32282.5391 | 100 | 40.4762 | 40.4762 | 100 | 100.0092 | 40.4762
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 62d | [5 empty] | 47146.5288 |  | 33.89% |  | 47138.9688 | 47138.9688
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 62d | 14856.4297 | 0 | 3d | 4.59 | 0 | 14861.0197 | 0 | 95.38% | Started | 14856.4297 | 14856.4297 | 100 | 95.3846 | 95.3846 | 100 | 100.0309 | 95.3846
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 17d | 32282.5391 | 0 | 25d | 2.97 | 0 | 32285.5091 | 0 | 40.48% | Started | 32282.5391 | 32282.5391 | 100 | 40.4762 | 40.4762 | 100 | 100.0092 | 40.4762
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 |  | 0 | 0 | 91971.1094 | 25d | 0 | 0 | 0 | 91971.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 3d | [5 empty] | 18179.4709 |  | 39.74% |  | 18175.6309 | 18175.6309
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 2012-05-29 08:00 | 3d | 18175.6309 | 0 | 12d | 3.84 | 0 | 18179.4709 | 0 | 20% | Started | 18175.6309 | 18175.6309 | 100 | 20 | 20 | 100 | 100.0211 | 20
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 |  | 0 | 0 | 27558.4199 | 10d | 0 | 0 | 0 | 27558.4199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 28d | [5 empty] | 1969.66 |  | 40% |  | 457.12 | 457.12
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1512.54 | 0 | 1969.66 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 430.8847 | 100
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2012-06-30 17:00 |  | TP Name | 30/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 230d | [5 empty] | 5343006.7048 |  | 96.63% |  | 5295682.1241 | 4857170.1488
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 230d | [5 empty] | 5343006.7048 |  | 96.63% |  | 5295682.1241 | 4857170.1488
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 144514.0869 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 4133.54 | 0 | 144514.0869 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 102.9445 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 361015.6798 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | -2.27 | 0 | 683.41 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.6689 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 110780.0784 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 115.43 | 0 | 820.23 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 116.3777 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | -3.78 | 0 | 1139.02 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.6692 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | -3.02 | 0 | 911.22 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 99.6697 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | 3692.96 | 0 | 74260.3975 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 105.2332 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -10155.0703 | 0 | 33649.2109 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 76.8172 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 38960.6996 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 288.57 | 0 | 2050.56 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.3775 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4501.6201 | 0 | 36910.1396 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 113.8902 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210591.4917 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4102.1802 | 0 | 210591.4917 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 98.0893 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1765301.4601 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95548.5826 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -143.28 | 0 | 6600.1101 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.8753 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -788.04 | 0 | 36300.6006 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.8753 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1025.55 | 0 | 52647.8718 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 98.0893 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1139.02 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | -3.78 | 0 | 1139.02 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.6692 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1668613.8574 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | -13.22 | 0 | 2410.1999 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 99.4545 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | -1.51 | 0 | 455.61 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 99.6697 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | -0.76 | 0 | 227.8 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 99.6675 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -214.92 | 0 | 9900.1601 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.8753 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -11757.2803 | 0 | 35445.5283 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 75.092 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1301.15 | 0 | 1758.27 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 384.6408 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6351.4902 | 0 | 41860.541 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 86.8259 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -3919.0901 | 0 | 11815.1794 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 75.092 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 22577.4805 | 0 | 61519.0195 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 157.9779 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -2966.3 | 0 | 162925.6375 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 98.2119 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3175.74 | 0 | 20930.2795 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 86.8259 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1689.38 | 0 | 3765.86 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 181.3579 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13215.9297 | 0 | 8013.3496 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.7467 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -735.74 | 0 | 1835.05 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 71.3808 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 211.17 | 0 | 439.73 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 192.3915 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13215.9297 | 0 | 8013.3496 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.7467 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -2207.22 | 0 | 5505.1599 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 71.3808 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 2528.3501 | 0 | 5323.1401 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 190.4665 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -15676.3701 | 0 | 47260.708 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 75.092 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | 4923.9502 | 0 | 99013.8721 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 105.2332 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -1.51 | 0 | 517.61 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 99.7091 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 7563.73 | 0 | 75729.9878 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 111.096 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 446217.6973 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 26692.6992 | 0 | 116500.1758 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 129.7221 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 46744.4414 | 0 | 102874.1211 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 183.2794 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | 821.28 | 0 | 3399.5 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 131.8545 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | 205.32 | 0 | 849.87 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 131.8548 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | -2.27 | 0 | 683.41 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 99.6689 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 10009.7598 | 0 | 43687.5684 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 129.7221 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -8.44 | 0 | 760.19 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 98.9019 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -7091.0601 | 0 | 31606.4204 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 81.6757 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -14797.4199 | 0 | 13348.5898 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 47.4262 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1286.83 | 0 | 117655.7716 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 98.9181 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | 738.59 | 0 | 14852.0803 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 105.2332 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 617730.1176 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 26692.6992 | 0 | 116500.1758 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 129.7221 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 16.53 | 0 | 2130.8601 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 100.7818 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 26692.6992 | 0 | 116500.1758 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 129.7221 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -50.62 | 0 | 4561.17 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 98.9024 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -8.44 | 0 | 760.19 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 98.9019 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -5703.5698 | 0 | 27414.6997 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 82.7782 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13231.2998 | 0 | 9078.1201 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 40.6919 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -25.31 | 0 | 2280.5899 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 98.9024 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -5703.5698 | 0 | 27414.6997 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 82.7782 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6615.6499 | 0 | 4539.0601 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 40.6919 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | 1230.99 | 0 | 24753.4705 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 105.2332 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -10004.4297 | 0 | 105161.2812 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 91.313 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -16674.0391 | 0 | 175268.8047 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 91.313 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -681.78 | 0 | 1139.02 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 62.556 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | -0.76 | 0 | 227.8 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 99.6675 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 143d | [5 empty] | 2097048.0993 |  | 92.53% |  | 2065168.4294 | 1626656.454
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 8d | [5 empty] | 3280.8999 |  | 100% |  | 2819.1799 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 2012-05-10 08:00 | 8d | 2819.1799 | 0 | 0 | 461.72 | 0 | 3280.8999 | 0 | 100% | Finished | 2819.1799 | 2819.1799 | 100 | 100 | 100 | 100 | 116.3778 | 100
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 3417.0699 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | -11.34 | 0 | 3417.0699 | 0 | 100% | Finished | 3428.4099 | 3428.4099 | 100 | 100 | 100 | 100 | 99.6692 | 100
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 13307.8604 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 6320.8701 | 0 | 13307.8604 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 190.4663 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 256680.6455 |  | 100% |  | 245403.4564 | 245403.4564
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | 205.32 | 0 | 849.87 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 131.8548 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 211.17 | 0 | 439.73 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 192.3915 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1267.03 | 0 | 2638.39 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 192.3922 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -20331.6504 | 0 | 95969.8574 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 82.5182 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | -0.76 | 0 | 227.8 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 99.6675 | 100
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 5472.8901 | 0 | 98689.0776 | 0 | 100% | Finished | 93216.1875 | 93216.1875 | 100 | 142.8571 | 100 | 100 | 105.8712 | 100
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | -1.51 | 0 | 455.61 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 99.6697 | 100
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | -75.02 | 0 | 919.22 | 0 | 100% | Finished | 994.24 | 994.24 | 100 | 100 | 100 | 100 | 92.4545 | 100
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -1505.09 | 0 | 18986.9608 | 0 | 100% | Finished | 20492.0508 | 20492.0508 | 100 | 200 | 100 | 100 | 92.6552 | 100
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28136.1992 | 0 | 31376.8291 | 0 | 100% | Finished | 3240.6299 | 3240.6299 | 100 | 200 | 100 | 100 | 968.2324 | 100
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -2101.3899 | 0 | 6127.3005 | 0 | 100% | Finished | 8228.6904 | 8228.6904 | 100 | 200 | 100 | 100 | 74.4626 | 100
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 758126.9945 |  | 100% |  | 745162.4451 | 745162.4451
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2740.8501 | 0 | 228671.9468 | 0 | 100% | Finished | 231412.7969 | 231412.7969 | 100 | 100 | 100 | 100 | 98.8156 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 12339.1299 | 0 | 16242.5698 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 416.1091 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 1055.86 | 0 | 2198.66 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 192.3924 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | -24397.9805 | 0 | 115163.832 | 0 | 100% | Finished | 139561.8125 | 139561.8125 | 100 | 100 | 100 | 100 | 82.5182 | 100
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 7601.5801 | 0 | 48979.7207 | 0 | 100% | Finished | 41378.1406 | 41378.1406 | 100 | 100 | 100 | 100 | 118.371 | 100
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | 2118.5901 | 0 | 140355.7307 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 101.5326 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 7818.4199 | 0 | 140984.4043 | 0 | 100% | Finished | 133165.9844 | 133165.9844 | 100 | 50 | 100 | 100 | 105.8712 | 100
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | 1069.26 | 0 | 27950.7698 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 103.9777 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 8100.54 | 0 | 37579.3604 | 0 | 100% | Finished | 29478.8203 | 29478.8203 | 100 | 100 | 100 | 100 | 127.4792 | 100
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 25d | [5 empty] | 9348.6301 |  | 100% |  | 7090.1001 | 7090.1001
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 25d | 7090.1001 | 0 | 0 | 2258.53 | 0 | 9348.6301 | 0 | 100% | Finished | 7090.1001 | 7090.1001 | 100 | 113.6364 | 100 | 100 | 131.8547 | 100
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 36d | [5 empty] | 8923.6902 |  | 100% |  | 6767.8202 | 6767.8202
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 15d | 4834.1602 | 0 | 0 | 1539.91 | 0 | 6374.0702 | 0 | 100% | Finished | 4834.1602 | 4834.1602 | 100 | 100 | 100 | 100 | 131.8548 | 100
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | 615.96 | 0 | 2549.6201 | 0 | 100% | Finished | 1933.66 | 1933.66 | 100 | 100 | 100 | 100 | 131.8546 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 39567.9688
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 35453.8789 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 4114.0898 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 9d | [5 empty] | 27950.7698 |  | 100% |  | 26881.5098 | 26881.5098
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-06-19 08:00 | 9d | 26881.5098 | 0 | 1d | 1069.26 | 0 | 27950.7698 | 0 | 90% | Started | 26881.5098 | 26881.5098 | 100 | 90 | 90 | 100 | 103.9777 | 90
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2742.73
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 2742.73 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 11507.1699
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 5376.2998 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 6130.8701 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 26d | [5 empty] | 44780.1602 |  | 100% |  | 55882.5703 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 26d | 55882.5703 | 0 | 0 | -11102.4102 | 0 | 44780.1602 | 0 | 100% | Finished | 55882.5703 | 55882.5703 | 100 | 100 | 100 | 100 | 80.1326 | 100
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 10d | [5 empty] | 10642.7296 |  | 43.75% |  | 10760.8496 | 24596.2197
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 | 2012-06-18 08:00 | 10d | 10760.8496 | 0 | 4d | -118.12 | 0 | 10642.7296 | 0 | 71.43% | Started | 10760.8496 | 10760.8496 | 100 | 71.4286 | 71.4286 | 100 | 98.9023 | 71.4286
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 13835.3701 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 25d | [5 empty] | 26635.6498 |  | 100% |  | 26429.0898 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 2012-05-10 08:00 | 25d | 26429.0898 | 0 | 0 | 206.56 | 0 | 26635.6498 | 0 | 100% | Finished | 26429.0898 | 26429.0898 | 100 | 100 | 100 | 100 | 100.7816 | 100
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10571.6396
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 5285.8198 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 5285.8198 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 15d | [5 empty] | 31114.2092 |  | 37.63% |  | 31146.9092 | 82765.0089
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 | 2012-06-11 08:00 | 15d | 21143.2695 | 0 | 10d | 165.25 | 0 | 21308.5195 | 0 | 60% | Started | 21143.2695 | 21143.2695 | 100 | 75 | 60 | 100 | 100.7816 | 60
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 | 2012-06-25 08:00 | 5d | 10003.6396 | 0 | 0 | -197.95 | 0 | 9805.6897 | 0 | 100% | Finished | 10003.6396 | 10003.6396 | 100 | 100 | 100 | 100 | 98.0212 | 100
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 1599.92 | 100 |  | 0 | 100 |  | 0
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 50018.1797 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3656.9601
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 2285.6001 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 1371.36 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 13634.25
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 13634.25 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 143d | [5 empty] | 902838.7901 |  | 99.64% |  | 896409.0989 | 310762.9353
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -5754.54 | 0 | 19067.8799 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 76.8172 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | -12.85 | 0 | 3872.68 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 99.6693 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | -7.56 | 0 | 2278.0401 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 99.6692 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 99.6691 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3080.48 | 0 | 2104.5298 | 0 | 100% | Finished | 5185.0098 | 5185.0098 | 100 | 100 | 100 | 100 | 40.5887 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 99.6691 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 99.6691 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | 2085.5801 | 0 | 40712.252 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 105.3993 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 9454.6602 | 0 | 94662.4883 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 111.096 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 99.6691 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 187.5 | 100 | 100 | 99.6691 | 100
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -3965.6399 | 0 | 210533.2039 | 0 | 100% | Finished | 214498.8438 | 214498.8438 | 100 | 150 | 100 | 100 | 98.1512 | 100
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 112.5 | 100 | 100 | 99.6691 | 100
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 75 | 100 | 100 | 99.6691 | 100
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 10d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 99.6691 | 100
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 8d | 2880.76 | 0 | 0 | 400.14 | 0 | 3280.9 | 0 | 100% | Finished | 2880.76 | 0 | 100 | 100 | 100 | 100 | 113.8901 | 100
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 2012-05-03 08:00 | 9d | 214560.4219 | 0 | 0 | -4027.21 | 0 | 210533.2119 | 0 | 100% | Finished | 214560.4219 | 0 | 100 | 112.5 | 100 | 100 | 98.123 | 100
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-03 08:00 | 9d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 112.5 | 100 | 100 | 99.6691 | 100
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-16 08:00 | 10d | 1828.48 | 0 | 0 | -6.05 | 0 | 1822.43 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 125 | 100 | 100 | 99.6691 | 100
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-01 08:00 | 10d | 1599.92 | 0 | 0 | -5.29 | 0 | 1594.63 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 99.6694 | 100
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-15 08:00 | 10d | 1599.92 | 0 | 0 | -5.29 | 0 | 1594.63 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 99.6694 | 100
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 | 2012-06-29 08:00 | 1d | 58330.2695 | 0 | 29d | -300.23 | 0 | 58030.0395 | 0 | 3.333% | Started | 58330.2695 | 0 | 100 | 3.3333 | 3.3333 | 100 | 99.4853 | 3.3333
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 2012-05-07 08:00 | 15d | 6831.02 | 0 | 0 | 21593.4707 | 0 | 28424.4907 | 0 | 100% | Finished | 6831.02 | 6831.02 | 100 | 214.2857 | 100 | 100 | 416.109 | 100
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 | 2012-06-01 08:00 | 10d | 188607.2344 | 0 | 0 | -3114.52 | 0 | 185492.7144 | 0 | 100% | Finished | 188607.2344 | 0 | 100 | 142.8571 | 100 | 100 | 98.3487 | 100
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 | 2012-06-29 08:00 | 1d | 29202.8496 | 0 | 19d | -6770.0498 | 0 | 22432.7998 | 0 | 5% | Started | 29202.8496 | 0 | 100 | 5 | 5 | 100 | 76.8172 | 5
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 383798.2489 |  | 100% |  | 386283.059 | 386283.059
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 288.57 | 0 | 2050.56 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.3775 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | -3.78 | 0 | 1139.02 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 99.6692 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 828.37 | 0 | 35476.0614 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 102.3908 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | 513.3 | 0 | 2124.69 | 0 | 100% | Finished | 1611.39 | 1611.39 | 100 | 100 | 100 | 100 | 131.8545 | 100
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -4111.27 | 0 | 343007.9175 | 0 | 100% | Finished | 347119.1875 | 347119.1875 | 100 | 100 | 100 | 100 | 98.8156 | 100
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 83d | [5 empty] | 589361.1198 |  | 100% |  | 594749.1602 | 594749.1602
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 83d | [5 empty] | 267824.793 |  | 100% |  | 270794.9531 | 270794.9531
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 65d | 79701.2578 | 0 | 0 | -2338.3401 | 0 | 77362.9177 | 0 | 100% | Finished | 79701.2578 | 79701.2578 | 100 | 100 | 100 | 100 | 97.0661 | 100
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 2012-05-07 08:00 | 38d | 74182.2734 | 0 | 4d | -1833.54 | 0 | 72348.7334 | 0 | 90.48% | Started | 74182.2734 | 74182.2734 | 100 | 90.4762 | 90.4762 | 100 | 97.5283 | 90.4762
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 | 2012-06-26 08:00 | 4d | 116911.4219 | 0 | 26d | 1201.72 | 0 | 118113.1418 | 0 | 13.33% | Started | 116911.4219 | 116911.4219 | 100 | 16 | 13.3333 | 100 | 101.0279 | 13.3333
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 83d | [5 empty] | 140788.7381 |  | 100% |  | 139110.0781 | 139110.0781
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | -49.15 | 0 | 14807.2797 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 99.6692 | 100
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 38d | 32282.5391 | 0 | 4d | -354.37 | 0 | 31928.1691 | 0 | 90.48% | Started | 32282.5391 | 32282.5391 | 100 | 90.4762 | 90.4762 | 100 | 98.9023 | 90.4762
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 4d | 91971.1094 | 0 | 26d | 2082.1799 | 0 | 94053.2893 | 0 | 13.33% | Started | 91971.1094 | 91971.1094 | 100 | 16 | 13.3333 | 100 | 102.264 | 13.3333
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 83d | [5 empty] | 140788.7381 |  | 100% |  | 139110.0781 | 139110.0781
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | -49.15 | 0 | 14807.2797 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 99.6692 | 100
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 38d | 32282.5391 | 0 | 4d | -354.37 | 0 | 31928.1691 | 0 | 90.48% | Started | 32282.5391 | 32282.5391 | 100 | 90.4762 | 90.4762 | 100 | 98.9023 | 90.4762
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 4d | 91971.1094 | 0 | 26d | 2082.1799 | 0 | 94053.2893 | 0 | 13.33% | Started | 91971.1094 | 91971.1094 | 100 | 16 | 13.3333 | 100 | 102.264 | 13.3333
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 24d | [5 empty] | 39958.8507 |  | 100% |  | 45734.0508 | 45734.0508
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 2012-05-29 08:00 | 15d | 18175.6309 | 0 | 0 | -99.12 | 0 | 18076.5109 | 0 | 100% | Finished | 18175.6309 | 18175.6309 | 100 | 100 | 100 | 100 | 99.4547 | 100
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 | 2012-06-19 08:00 | 9d | 27558.4199 | 0 | 1d | -5676.0801 | 0 | 21882.3398 | 0 | 90% | Started | 27558.4199 | 27558.4199 | 100 | 90 | 90 | 100 | 79.4035 | 90
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 49d | [5 empty] | 1968.01 |  | 40% |  | 457.12 | 457.12
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1510.89 | 0 | 1968.01 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 430.5237 | 100
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2012-07-31 17:00 |  | TP Name | 31/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 237d | [5 empty] | 5308149.8729 |  | 96.66% |  | 5297282.0442 | 4891780.839
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 237d | [5 empty] | 5308149.8729 |  | 96.66% |  | 5297282.0442 | 4891780.839
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 149650.4971 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 9269.9502 | 0 | 149650.4971 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 106.6034 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 358462.3806 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.4084 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 107985.739 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 118.81 | 0 | 823.61 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 116.8573 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 3.73 | 0 | 917.97 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.408 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -6499.1499 | 0 | 64068.2876 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 90.7902 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2775.8799 | 0 | 41028.4014 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 93.663 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39121.2097 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.8571 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4653.6802 | 0 | 37062.1997 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 114.3594 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210666.9519 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4026.72 | 0 | 210666.9519 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 98.1244 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1686917.0672 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95589.4126 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -139.9 | 0 | 6603.4901 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.9254 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -769.46 | 0 | 36319.1806 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.9253 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1006.68 | 0 | 52666.7419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 98.1244 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1147.47 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1590180.1846 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | -9.84 | 0 | 2413.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 99.594 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.4091 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.4069 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -209.85 | 0 | 9905.2301 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.9254 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -14512.9805 | 0 | 32689.8281 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 69.254 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1304.53 | 0 | 1761.65 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 385.3802 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6556.02 | 0 | 41656.0112 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 86.4017 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -4837.6602 | 0 | 10896.6094 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 69.254 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 20358.6797 | 0 | 59300.2188 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 152.2801 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -2695.74 | 0 | 163196.1975 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 98.375 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3278.01 | 0 | 20828.0095 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 86.4017 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1454.9 | 0 | 3531.38 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 170.0657 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.403 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -928.26 | 0 | 1642.53 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 63.892 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 193.1309 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.403 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -2784.77 | 0 | 4927.6099 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 63.8922 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 3927.4199 | 0 | 6722.21 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 240.5265 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -19350.6406 | 0 | 43586.4375 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 69.254 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -8665.5303 | 0 | 85424.3916 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 90.7902 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -60.13 | 0 | 458.99 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 88.4169 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 6665.6899 | 0 | 74831.9478 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 109.7786 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 409520.537 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 111.81 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 36690.3906 | 0 | 92820.0703 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 165.3672 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -149.87 | 0 | 2428.35 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 94.1871 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 94.1866 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.4084 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 3977.3301 | 0 | 37655.1387 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 111.8099 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.758 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -8120.3398 | 0 | 30577.1406 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 79.0158 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -15231.4004 | 0 | 12914.6094 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 45.8843 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1107.0601 | 0 | 117835.5415 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 99.0692 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -1299.83 | 0 | 12813.6603 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 90.7902 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 599876.137 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 111.81 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 91.22 | 0 | 2205.5501 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 104.3144 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 111.81 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -11.15 | 0 | 4600.64 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 99.7582 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.758 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 80.3509 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13294.4697 | 0 | 9014.9502 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 40.4087 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -5.57 | 0 | 2300.3299 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 99.7584 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 80.3509 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6647.2402 | 0 | 4507.4697 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 40.4087 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -2166.3799 | 0 | 21356.1006 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 90.7902 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -2778.8401 | 0 | 112386.8708 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 97.5871 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -4631.3999 | 0 | 187311.4438 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 97.5871 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -673.33 | 0 | 1147.47 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 63.0201 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.4069 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 150d | [5 empty] | 2134600.5989 |  | 92.6% |  | 2066768.3494 | 1645853.944
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 8d | [5 empty] | 3294.4099 |  | 100% |  | 2819.1799 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 2012-05-10 08:00 | 8d | 2819.1799 | 0 | 0 | 475.23 | 0 | 3294.4099 | 0 | 100% | Finished | 2819.1799 | 2819.1799 | 100 | 100 | 100 | 100 | 116.857 | 100
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 3442.4099 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | 14 | 0 | 3442.4099 | 0 | 100% | Finished | 3428.4099 | 3428.4099 | 100 | 100 | 100 | 100 | 100.4084 | 100
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 16805.54 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 9818.5498 | 0 | 16805.54 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 240.5262 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 271542.2072 |  | 100% |  | 245403.4564 | 245403.4564
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 94.1866 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 193.1309 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1277.17 | 0 | 2648.53 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 193.1316 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -11243.8496 | 0 | 105057.6582 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 90.3322 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 100.4069 | 100
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 11738.3301 | 0 | 104954.5176 | 0 | 100% | Finished | 93216.1875 | 93216.1875 | 100 | 142.8571 | 100 | 100 | 112.5926 | 100
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.4091 | 100
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | -76.27 | 0 | 917.97 | 0 | 100% | Finished | 994.24 | 994.24 | 100 | 100 | 100 | 100 | 92.3288 | 100
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -1910.4301 | 0 | 18581.6207 | 0 | 100% | Finished | 20492.0508 | 20492.0508 | 100 | 200 | 100 | 100 | 90.6772 | 100
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28144.6504 | 0 | 31385.2803 | 0 | 100% | Finished | 3240.6299 | 3240.6299 | 100 | 200 | 100 | 100 | 968.4932 | 100
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -1969.04 | 0 | 6259.6504 | 0 | 100% | Finished | 8228.6904 | 8228.6904 | 100 | 200 | 100 | 100 | 76.071 | 100
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 780586.304 |  | 100% |  | 745162.4451 | 745162.4451
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2215.8 | 0 | 229196.9968 | 0 | 100% | Finished | 231412.7969 | 231412.7969 | 100 | 100 | 100 | 100 | 99.0425 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 12196.1104 | 0 | 16099.5503 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 412.4452 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 1064.3101 | 0 | 2207.1101 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 193.1318 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | -13492.6201 | 0 | 126069.1924 | 0 | 100% | Finished | 139561.8125 | 139561.8125 | 100 | 100 | 100 | 100 | 90.3322 | 100
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 10415.5098 | 0 | 51793.6504 | 0 | 100% | Finished | 41378.1406 | 41378.1406 | 100 | 100 | 100 | 100 | 125.1715 | 100
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | -405.28 | 0 | 137831.8606 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 99.7068 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 16769.0391 | 0 | 149935.0234 | 0 | 100% | Finished | 133165.9844 | 133165.9844 | 100 | 50 | 100 | 100 | 112.5926 | 100
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 95.1074 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 12407.7998 | 0 | 41886.6201 | 0 | 100% | Finished | 29478.8203 | 29478.8203 | 100 | 100 | 100 | 100 | 142.0906 | 100
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 25d | [5 empty] | 6677.9701 |  | 100% |  | 7090.1001 | 7090.1001
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 25d | 7090.1001 | 0 | 0 | -412.13 | 0 | 6677.9701 | 0 | 100% | Finished | 7090.1001 | 7090.1001 | 100 | 113.6364 | 100 | 100 | 94.1872 | 100
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 36d | [5 empty] | 6374.4202 |  | 100% |  | 6767.8202 | 6767.8202
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 15d | 4834.1602 | 0 | 0 | -281 | 0 | 4553.1602 | 0 | 100% | Finished | 4834.1602 | 4834.1602 | 100 | 100 | 100 | 100 | 94.1872 | 100
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | -112.4 | 0 | 1821.26 | 0 | 100% | Finished | 1933.66 | 1933.66 | 100 | 100 | 100 | 100 | 94.1872 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 39567.9688
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 |  | 0 | 0 | 35453.8789 | 20d | 0 | 0 | 0 | 35453.8789 | 0% | Not Started | 0 | 35453.8789 | 100 |  | 0 | 100 |  | 0
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 |  | 0 | 0 | 4114.0898 | 18d | 0 | 0 | 0 | 4114.0898 | 0% | Not Started | 0 | 4114.0898 | 100 |  | 0 | 100 |  | 0
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 10d | [5 empty] | 25566.2998 |  | 100% |  | 26881.5098 | 26881.5098
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-06-19 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 95.1074 | 100
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 4571.21
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 |  | 0 | 0 | 2742.73 | 12d | 0 | 0 | 0 | 2742.73 | 0% | Not Started | 0 | 2742.73 | 100 |  | 0 | 100 |  | 0
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 11507.1699
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 5376.2998 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 |  | 0 | 0 | 6130.8701 | 5d | 0 | 0 | 0 | 6130.8701 | 0% | Not Started | 0 | 6130.8701 | 100 |  | 0 | 100 |  | 0
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 26d | [5 empty] | 43167.8701 |  | 100% |  | 55882.5703 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 26d | 55882.5703 | 0 | 0 | -12714.7002 | 0 | 43167.8701 | 0 | 100% | Finished | 55882.5703 | 55882.5703 | 100 | 100 | 100 | 100 | 77.2475 | 100
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 17d | [5 empty] | 10734.8396 |  | 43.75% |  | 10760.8496 | 24596.2197
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 | 2012-06-18 08:00 | 14d | 10760.8496 | 0 | 0 | -26.01 | 0 | 10734.8396 | 0 | 100% | Finished | 10760.8496 | 10760.8496 | 100 | 100 | 100 | 100 | 99.7583 | 100
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 |  | 0 | 0 | 13835.3701 | 18d | 0 | 0 | 0 | 13835.3701 | 0% | Not Started | 0 | 13835.3701 | 100 |  | 0 | 100 |  | 0
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 25d | [5 empty] | 27569.3699 |  | 100% |  | 26429.0898 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 2012-05-10 08:00 | 25d | 26429.0898 | 0 | 0 | 1140.28 | 0 | 27569.3699 | 0 | 100% | Finished | 26429.0898 | 26429.0898 | 100 | 100 | 100 | 100 | 104.3145 | 100
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 10571.6396
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 5285.8198 | 100 |  | 0 | 100 |  | 0
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 |  | 0 | 0 | 5285.8198 | 5d | 0 | 0 | 0 | 5285.8198 | 0% | Not Started | 0 | 5285.8198 | 100 |  | 0 | 100 |  | 0
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 22d | [5 empty] | 26292.9093 |  | 39.57% |  | 32746.8292 | 82765.0089
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 | 2012-06-11 08:00 | 22d | 21143.2695 | 0 | 3d | 912.22 | 0 | 22055.4895 | 0 | 88% | Started | 21143.2695 | 21143.2695 | 100 | 110 | 88 | 100 | 104.3145 | 88
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 | 2012-06-25 08:00 | 5d | 10003.6396 | 0 | 0 | -8856.1699 | 0 | 1147.4697 | 0 | 100% | Finished | 10003.6396 | 10003.6396 | 100 | 100 | 100 | 100 | 11.4705 | 100
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-07-02 08:00 | 7d | 1599.92 | 0 | 0 | 1490.03 | 0 | 3089.9501 | 0 | 100% | Finished | 1599.92 | 1599.92 | 100 | 100 | 100 | 100 | 193.1315 | 100
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 |  | 0 | 0 | 50018.1797 | 25d | 0 | 0 | 0 | 50018.1797 | 0% | Not Started | 0 | 50018.1797 | 100 |  | 0 | 100 |  | 0
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3656.9601
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 |  | 0 | 0 | 2285.6001 | 10d | 0 | 0 | 0 | 2285.6001 | 0% | Not Started | 0 | 2285.6001 | 100 |  | 0 | 100 |  | 0
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 |  | 0 | 0 | 1371.36 | 6d | 0 | 0 | 0 | 1371.36 | 0% | Not Started | 0 | 1371.36 | 100 |  | 0 | 100 |  | 0
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 13634.25
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 |  | 0 | 0 | 13634.25 | 29d | 0 | 0 | 0 | 13634.25 | 0% | Not Started | 0 | 13634.25 | 100 |  | 0 | 100 |  | 0
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14488.25
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 14488.25 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 150d | [5 empty] | 912546.0488 |  | 99.64% |  | 896409.0989 | 313643.6953
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1573 | 0 | 23249.4199 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 93.663 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 15.87 | 0 | 3901.4 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 100.4084 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | 9.33 | 0 | 2294.9301 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 100.4082 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3066.97 | 0 | 2118.0398 | 0 | 100% | Finished | 5185.0098 | 5185.0098 | 100 | 100 | 100 | 100 | 40.8493 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -3355.99 | 0 | 35270.6819 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 91.3117 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 8332.1104 | 0 | 93539.9385 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 109.7786 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 187.5 | 100 | 100 | 100.4085 | 100
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -3890.1699 | 0 | 210608.6738 | 0 | 100% | Finished | 214498.8438 | 214498.8438 | 100 | 150 | 100 | 100 | 98.1864 | 100
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 112.5 | 100 | 100 | 100.4085 | 100
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 75 | 100 | 100 | 100.4085 | 100
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 8d | 2880.76 | 0 | 0 | 413.66 | 0 | 3294.42 | 0 | 100% | Finished | 2880.76 | 2880.76 | 100 | 100 | 100 | 100 | 114.3594 | 100
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 2012-05-03 08:00 | 9d | 214560.4219 | 0 | 0 | -3951.75 | 0 | 210608.6719 | 0 | 100% | Finished | 214560.4219 | 0 | 100 | 112.5 | 100 | 100 | 98.1582 | 100
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-03 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 112.5 | 100 | 100 | 100.4085 | 100
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-16 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 0 | 100 | 125 | 100 | 100 | 100.4085 | 100
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-01 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-15 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 | 2012-06-29 08:00 | 8d | 58330.2695 | 0 | 22d | 6671.98 | 0 | 65002.2495 | 0 | 26.67% | Started | 58330.2695 | 0 | 100 | 26.6667 | 26.6667 | 100 | 111.4383 | 26.6667
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 2012-05-07 08:00 | 15d | 6831.02 | 0 | 0 | 21343.1895 | 0 | 28174.2095 | 0 | 100% | Finished | 6831.02 | 6831.02 | 100 | 214.2857 | 100 | 100 | 412.4451 | 100
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 | 2012-06-01 08:00 | 10d | 188607.2344 | 0 | 0 | -3048.48 | 0 | 185558.7544 | 0 | 100% | Finished | 188607.2344 | 0 | 100 | 142.8571 | 100 | 100 | 98.3837 | 100
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 | 2012-06-29 08:00 | 12d | 29202.8496 | 0 | 8d | -1850.59 | 0 | 27352.2596 | 0 | 60% | Started | 29202.8496 | 0 | 100 | 60 | 60 | 100 | 93.663 | 60
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 |  | 0 | 0 | 1599.92 | 7d | 0 | 0 | 0 | 1599.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 383185.069 |  | 100% |  | 386283.059 | 386283.059
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.8571 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 17.69 | 0 | 34665.3814 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 100.0511 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | -93.67 | 0 | 1517.72 | 0 | 100% | Finished | 1611.39 | 1611.39 | 100 | 100 | 100 | 100 | 94.187 | 100
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -3323.7 | 0 | 343795.4875 | 0 | 100% | Finished | 347119.1875 | 347119.1875 | 100 | 100 | 100 | 100 | 99.0425 | 100
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 90d | [5 empty] | 593362.8701 |  | 100% |  | 594749.1602 | 594749.1602
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 90d | [5 empty] | 269455.4231 |  | 100% |  | 270794.9531 | 270794.9531
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 65d | 79701.2578 | 0 | 0 | -617.71 | 0 | 79083.5478 | 0 | 100% | Finished | 79701.2578 | 79701.2578 | 100 | 100 | 100 | 100 | 99.225 | 100
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 2012-05-07 08:00 | 42d | 74182.2734 | 0 | 0 | -516.37 | 0 | 73665.9034 | 0 | 100% | Finished | 74182.2734 | 74182.2734 | 100 | 100 | 100 | 100 | 99.3039 | 100
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 | 2012-06-26 08:00 | 11d | 116911.4219 | 0 | 19d | -205.45 | 0 | 116705.9719 | 0 | 36.67% | Started | 116911.4219 | 116911.4219 | 100 | 44 | 36.6667 | 100 | 99.8243 | 36.6667
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 90d | [5 empty] | 139148.1781 |  | 100% |  | 139110.0781 | 139110.0781
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 100.4084 | 100
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 100% | Finished | 32282.5391 | 32282.5391 | 100 | 100 | 100 | 100 | 99.7583 | 100
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 11d | 91971.1094 | 0 | 19d | 55.46 | 0 | 92026.5694 | 0 | 36.67% | Started | 91971.1094 | 91971.1094 | 100 | 44 | 36.6667 | 100 | 100.0603 | 36.6667
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 90d | [5 empty] | 139148.1781 |  | 100% |  | 139110.0781 | 139110.0781
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 100.4084 | 100
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 100% | Finished | 32282.5391 | 32282.5391 | 100 | 100 | 100 | 100 | 99.7583 | 100
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 11d | 91971.1094 | 0 | 19d | 55.46 | 0 | 92026.5694 | 0 | 36.67% | Started | 91971.1094 | 91971.1094 | 100 | 44 | 36.6667 | 100 | 100.0603 | 36.6667
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 25d | [5 empty] | 45611.0908 |  | 100% |  | 45734.0508 | 45734.0508
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 2012-05-29 08:00 | 15d | 18175.6309 | 0 | 0 | -73.78 | 0 | 18101.8509 | 0 | 100% | Finished | 18175.6309 | 18175.6309 | 100 | 100 | 100 | 100 | 99.5941 | 100
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 | 2012-06-19 08:00 | 10d | 27558.4199 | 0 | 0 | -49.18 | 0 | 27509.2399 | 0 | 100% | Finished | 27558.4199 | 27558.4199 | 100 | 100 | 100 | 100 | 99.8215 | 100
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 56d | [5 empty] | 1971.39 |  | 40% |  | 457.12 | 457.12
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1514.27 | 0 | 1971.39 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 431.2631 | 100
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 15413.2002
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 |  | 0 | 0 | 15413.2002 | 25d | 0 | 0 | 0 | 15413.2002 | 0% | Not Started | 0 | 15413.2002 | 100 |  | 0 | 100 |  | 0
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2012-08-31 17:00 |  | TP Name | 31/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 262d | [5 empty] | 5426562.1434 |  | 99.55% |  | 5456053.0529 | 5112545.8008
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 262d | [5 empty] | 5426562.1434 |  | 99.55% |  | 5456053.0529 | 5112545.8008
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 149650.4971 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 9269.9502 | 0 | 149650.4971 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 106.6034 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 358462.3806 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.4084 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 107985.739 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 118.81 | 0 | 823.61 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 116.8573 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 3.73 | 0 | 917.97 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.408 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -6499.1499 | 0 | 64068.2876 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 90.7902 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2775.8799 | 0 | 41028.4014 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 93.663 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39121.2097 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.8571 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4653.6802 | 0 | 37062.1997 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 114.3594 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210666.9519 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4026.72 | 0 | 210666.9519 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 98.1244 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1686917.0672 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95589.4126 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -139.9 | 0 | 6603.4901 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.9254 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -769.46 | 0 | 36319.1806 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.9253 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1006.68 | 0 | 52666.7419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 98.1244 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1147.47 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1590180.1846 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | -9.84 | 0 | 2413.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 99.594 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.4091 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.4069 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -209.85 | 0 | 9905.2301 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.9254 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -14512.9805 | 0 | 32689.8281 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 69.254 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1304.53 | 0 | 1761.65 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 385.3802 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6556.02 | 0 | 41656.0112 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 86.4017 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -4837.6602 | 0 | 10896.6094 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 69.254 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 20358.6797 | 0 | 59300.2188 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 152.2801 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -2695.74 | 0 | 163196.1975 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 98.375 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3278.01 | 0 | 20828.0095 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 86.4017 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1454.9 | 0 | 3531.38 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 170.0657 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.403 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -928.26 | 0 | 1642.53 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 63.892 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 193.1309 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.403 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -2784.77 | 0 | 4927.6099 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 63.8922 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 3927.4199 | 0 | 6722.21 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 240.5265 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -19350.6406 | 0 | 43586.4375 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 69.254 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -8665.5303 | 0 | 85424.3916 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 90.7902 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -60.13 | 0 | 458.99 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 88.4169 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 6665.6899 | 0 | 74831.9478 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 109.7786 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 409520.537 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 111.81 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 36690.3906 | 0 | 92820.0703 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 165.3672 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -149.87 | 0 | 2428.35 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 94.1871 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 94.1866 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.4084 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 3977.3301 | 0 | 37655.1387 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 111.8099 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.758 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -8120.3398 | 0 | 30577.1406 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 79.0158 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -15231.4004 | 0 | 12914.6094 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 45.8843 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1107.0601 | 0 | 117835.5415 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 99.0692 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -1299.83 | 0 | 12813.6603 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 90.7902 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 599876.137 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 111.81 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 91.22 | 0 | 2205.5501 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 104.3144 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 111.81 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -11.15 | 0 | 4600.64 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 99.7582 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.758 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 80.3509 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13294.4697 | 0 | 9014.9502 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 40.4087 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -5.57 | 0 | 2300.3299 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 99.7584 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 80.3509 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6647.2402 | 0 | 4507.4697 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 40.4087 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -2166.3799 | 0 | 21356.1006 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 90.7902 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -2778.8401 | 0 | 112386.8708 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 97.5871 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -4631.3999 | 0 | 187311.4438 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 97.5871 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -673.33 | 0 | 1147.47 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 63.0201 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.4069 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 175d | [5 empty] | 2234148.4692 |  | 99.03% |  | 2210126.1579 | 1864071.3259
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 8d | [5 empty] | 3294.4099 |  | 100% |  | 2819.1799 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 2012-05-10 08:00 | 8d | 2819.1799 | 0 | 0 | 475.23 | 0 | 3294.4099 | 0 | 100% | Finished | 2819.1799 | 2819.1799 | 100 | 100 | 100 | 100 | 116.857 | 100
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 3442.4099 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | 14 | 0 | 3442.4099 | 0 | 100% | Finished | 3428.4099 | 3428.4099 | 100 | 100 | 100 | 100 | 100.4084 | 100
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 16805.54 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 9818.5498 | 0 | 16805.54 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 240.5262 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 271542.2072 |  | 100% |  | 245403.4564 | 245403.4564
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 94.1866 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 193.1309 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1277.17 | 0 | 2648.53 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 193.1316 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -11243.8496 | 0 | 105057.6582 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 90.3322 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 100.4069 | 100
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 11738.3301 | 0 | 104954.5176 | 0 | 100% | Finished | 93216.1875 | 93216.1875 | 100 | 142.8571 | 100 | 100 | 112.5926 | 100
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.4091 | 100
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | -76.27 | 0 | 917.97 | 0 | 100% | Finished | 994.24 | 994.24 | 100 | 100 | 100 | 100 | 92.3288 | 100
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -1910.4301 | 0 | 18581.6207 | 0 | 100% | Finished | 20492.0508 | 20492.0508 | 100 | 200 | 100 | 100 | 90.6772 | 100
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28144.6504 | 0 | 31385.2803 | 0 | 100% | Finished | 3240.6299 | 3240.6299 | 100 | 200 | 100 | 100 | 968.4932 | 100
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -1969.04 | 0 | 6259.6504 | 0 | 100% | Finished | 8228.6904 | 8228.6904 | 100 | 200 | 100 | 100 | 76.071 | 100
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 780586.304 |  | 100% |  | 745162.4451 | 745162.4451
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2215.8 | 0 | 229196.9968 | 0 | 100% | Finished | 231412.7969 | 231412.7969 | 100 | 100 | 100 | 100 | 99.0425 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 12196.1104 | 0 | 16099.5503 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 412.4452 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 1064.3101 | 0 | 2207.1101 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 193.1318 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | -13492.6201 | 0 | 126069.1924 | 0 | 100% | Finished | 139561.8125 | 139561.8125 | 100 | 100 | 100 | 100 | 90.3322 | 100
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 10415.5098 | 0 | 51793.6504 | 0 | 100% | Finished | 41378.1406 | 41378.1406 | 100 | 100 | 100 | 100 | 125.1715 | 100
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | -405.28 | 0 | 137831.8606 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 99.7068 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 16769.0391 | 0 | 149935.0234 | 0 | 100% | Finished | 133165.9844 | 133165.9844 | 100 | 50 | 100 | 100 | 112.5926 | 100
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 95.1074 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 12407.7998 | 0 | 41886.6201 | 0 | 100% | Finished | 29478.8203 | 29478.8203 | 100 | 100 | 100 | 100 | 142.0906 | 100
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 25d | [5 empty] | 6677.9701 |  | 100% |  | 7090.1001 | 7090.1001
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 25d | 7090.1001 | 0 | 0 | -412.13 | 0 | 6677.9701 | 0 | 100% | Finished | 7090.1001 | 7090.1001 | 100 | 113.6364 | 100 | 100 | 94.1872 | 100
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 36d | [5 empty] | 6374.4202 |  | 100% |  | 6767.8202 | 6767.8202
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 15d | 4834.1602 | 0 | 0 | -281 | 0 | 4553.1602 | 0 | 100% | Finished | 4834.1602 | 4834.1602 | 100 | 100 | 100 | 100 | 94.1872 | 100
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | -112.4 | 0 | 1821.26 | 0 | 100% | Finished | 1933.66 | 1933.66 | 100 | 100 | 100 | 100 | 94.1872 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 23d | [5 empty] | 39603.4387 |  | 100% |  | 39567.9688 | 39567.9688
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 | 2012-08-01 08:00 | 23d | 35453.8789 | 0 | 7d | 18.67 | 0 | 35472.5489 | 0 | 76.67% | Started | 35453.8789 | 35453.8789 | 100 | 115 | 76.6667 | 100 | 100.0527 | 76.6667
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 | 2012-08-01 08:00 | 23d | 4114.0898 | 0 | 2d | 16.8 | 0 | 4130.8898 | 0 | 92% | Started | 4114.0898 | 4114.0898 | 100 | 127.7778 | 92 | 100 | 100.4084 | 92
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 10d | [5 empty] | 25566.2998 |  | 100% |  | 26881.5098 | 26881.5098
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-06-19 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 95.1074 | 100
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 10d | [5 empty] | 2753.93 |  | 60% |  | 2742.73 | 4571.21
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 |  | 0 | 0 | 1828.48 | 8d | 0 | 0 | 0 | 1828.48 | 0% | Not Started | 0 | 1828.48 | 100 |  | 0 | 100 |  | 0
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 | 2012-08-20 08:00 | 10d | 2742.73 | 0 | 2d | 11.2 | 0 | 2753.93 | 0 | 83.33% | Started | 2742.73 | 2742.73 | 100 | 83.3333 | 83.3333 | 100 | 100.4084 | 83.3333
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 10d | [5 empty] | 6083.3501 |  | 53.28% |  | 6130.8701 | 11507.1699
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 |  | 0 | 0 | 5376.2998 | 2d | 0 | 0 | 0 | 5376.2998 | 0% | Not Started | 0 | 5376.2998 | 100 |  | 0 | 100 |  | 0
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 | 2012-08-20 08:00 | 10d | 6130.8701 | 0 | 2d | -47.52 | 0 | 6083.3501 | 0 | 83.33% | Started | 6130.8701 | 6130.8701 | 100 | 200 | 83.3333 | 100 | 99.2249 | 83.3333
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 26d | [5 empty] | 43167.8701 |  | 100% |  | 55882.5703 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 26d | 55882.5703 | 0 | 0 | -12714.7002 | 0 | 43167.8701 | 0 | 100% | Finished | 55882.5703 | 55882.5703 | 100 | 100 | 100 | 100 | 77.2475 | 100
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 40d | [5 empty] | 24536.7697 |  | 100% |  | 24596.2197 | 24596.2197
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 | 2012-06-18 08:00 | 14d | 10760.8496 | 0 | 0 | -26.01 | 0 | 10734.8396 | 0 | 100% | Finished | 10760.8496 | 10760.8496 | 100 | 100 | 100 | 100 | 99.7583 | 100
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 | 2012-08-24 08:00 | 6d | 13835.3701 | 0 | 12d | -33.44 | 0 | 13801.9301 | 0 | 33.33% | Started | 13835.3701 | 13835.3701 | 100 | 33.3333 | 33.3333 | 100 | 99.7583 | 33.3333
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 25d | [5 empty] | 27569.3699 |  | 100% |  | 26429.0898 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 2012-05-10 08:00 | 25d | 26429.0898 | 0 | 0 | 1140.28 | 0 | 27569.3699 | 0 | 100% | Finished | 26429.0898 | 26429.0898 | 100 | 100 | 100 | 100 | 104.3145 | 100
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 10d | [5 empty] | 11027.7596 |  | 100% |  | 10571.6396 | 10571.6396
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 2012-08-20 08:00 | 5d | 5285.8198 | 0 | 0 | 228.06 | 0 | 5513.8798 | 0 | 100% | Finished | 5285.8198 | 5285.8198 | 100 | 100 | 100 | 100 | 104.3146 | 100
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 2012-08-13 08:00 | 5d | 5285.8198 | 0 | 0 | 228.06 | 0 | 5513.8798 | 0 | 100% | Finished | 5285.8198 | 5285.8198 | 100 | 100 | 100 | 100 | 104.3146 | 100
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 45d | [5 empty] | 32030.2609 |  | 100% |  | 82765.0089 | 82765.0089
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 | 2012-06-11 08:00 | 25d | 21143.2695 | 0 | 0 | 912.22 | 0 | 22055.4895 | 0 | 100% | Finished | 21143.2695 | 21143.2695 | 100 | 125 | 100 | 100 | 104.3145 | 100
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 | 2012-06-25 08:00 | 5d | 10003.6396 | 0 | 0 | -8856.1699 | 0 | 1147.4697 | 0 | 100% | Finished | 10003.6396 | 10003.6396 | 100 | 100 | 100 | 100 | 11.4705 | 100
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-07-02 08:00 | 7d | 1599.92 | 0 | 0 | 1490.03 | 0 | 3089.9501 | 0 | 100% | Finished | 1599.92 | 1599.92 | 100 | 100 | 100 | 100 | 193.1315 | 100
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 | 2012-08-22 08:00 | 8d | 50018.1797 | 0 | 17d | -44280.8281 | 0 | 5737.3516 | 0 | 32% | Started | 50018.1797 | 50018.1797 | 100 | 32 | 32 | 100 | 11.4705 | 32
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 8d | [5 empty] | 3671.8901 |  | 100% |  | 3656.9601 | 3656.9601
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-08-22 08:00 | 8d | 2285.6001 | 0 | 2d | 9.33 | 0 | 2294.9301 | 0 | 80% | Started | 2285.6001 | 2285.6001 | 100 | 80 | 80 | 100 | 100.4082 | 80
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-08-27 08:00 | 5d | 1371.36 | 0 | 1d | 5.6 | 0 | 1376.96 | 0 | 83.33% | Started | 1371.36 | 1371.36 | 100 | 83.3333 | 83.3333 | 100 | 100.4084 | 83.3333
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 8d | [5 empty] | 13655.32 |  | 100% |  | 13634.25 | 13634.25
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 | 2012-08-22 08:00 | 8d | 13634.25 | 0 | 11d | 21.07 | 0 | 13655.32 | 0 | 42.11% | Started | 13634.25 | 13634.25 | 100 | 27.5862 | 42.1053 | 100 | 100.1545 | 42.1053
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 14488.25
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 |  | 0 | 0 | 14488.25 | 3d | 0 | 0 | 0 | 14488.25 | 0% | Not Started | 0 | 14488.25 | 100 |  | 0 | 100 |  | 0
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 175d | [5 empty] | 915758.9489 |  | 100% |  | 899608.939 | 531861.0771
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1573 | 0 | 23249.4199 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 93.663 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 15.87 | 0 | 3901.4 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 100.4084 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | 9.33 | 0 | 2294.9301 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 100.4082 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3066.97 | 0 | 2118.0398 | 0 | 100% | Finished | 5185.0098 | 5185.0098 | 100 | 100 | 100 | 100 | 40.8493 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -3355.99 | 0 | 35270.6819 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 91.3117 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 8332.1104 | 0 | 93539.9385 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 109.7786 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 187.5 | 100 | 100 | 100.4085 | 100
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -3890.1699 | 0 | 210608.6738 | 0 | 100% | Finished | 214498.8438 | 214498.8438 | 100 | 150 | 100 | 100 | 98.1864 | 100
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 112.5 | 100 | 100 | 100.4085 | 100
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 75 | 100 | 100 | 100.4085 | 100
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 8d | 2880.76 | 0 | 0 | 413.66 | 0 | 3294.42 | 0 | 100% | Finished | 2880.76 | 2880.76 | 100 | 100 | 100 | 100 | 114.3594 | 100
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 2012-05-03 08:00 | 9d | 214560.4219 | 0 | 0 | -3951.75 | 0 | 210608.6719 | 0 | 100% | Finished | 214560.4219 | 214560.4219 | 100 | 112.5 | 100 | 100 | 98.1582 | 100
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-03 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 112.5 | 100 | 100 | 100.4085 | 100
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-16 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-01 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-15 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 | 2012-06-29 08:00 | 30d | 58330.2695 | 0 | 0 | 6671.98 | 0 | 65002.2495 | 0 | 100% | Finished | 58330.2695 | 0 | 100 | 100 | 100 | 100 | 111.4383 | 100
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 2012-05-07 08:00 | 15d | 6831.02 | 0 | 0 | 21343.1895 | 0 | 28174.2095 | 0 | 100% | Finished | 6831.02 | 6831.02 | 100 | 214.2857 | 100 | 100 | 412.4451 | 100
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 | 2012-06-01 08:00 | 10d | 188607.2344 | 0 | 0 | -3048.48 | 0 | 185558.7544 | 0 | 100% | Finished | 188607.2344 | 0 | 100 | 142.8571 | 100 | 100 | 98.3837 | 100
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 | 2012-06-29 08:00 | 20d | 29202.8496 | 0 | 0 | -1850.59 | 0 | 27352.2596 | 0 | 100% | Finished | 29202.8496 | 0 | 100 | 100 | 100 | 100 | 93.663 | 100
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-08-17 08:00 | 3d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 42.8571 | 100 | 100 | 100.4081 | 100
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-08-22 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 383185.069 |  | 100% |  | 386283.059 | 386283.059
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.8571 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 17.69 | 0 | 34665.3814 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 100.0511 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | -93.67 | 0 | 1517.72 | 0 | 100% | Finished | 1611.39 | 1611.39 | 100 | 100 | 100 | 100 | 94.187 | 100
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -3323.7 | 0 | 343795.4875 | 0 | 100% | Finished | 347119.1875 | 347119.1875 | 100 | 100 | 100 | 100 | 99.0425 | 100
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 109d | [5 empty] | 593362.8701 |  | 100% |  | 594749.1602 | 594749.1602
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 109d | [5 empty] | 269455.4231 |  | 100% |  | 270794.9531 | 270794.9531
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 65d | 79701.2578 | 0 | 0 | -617.71 | 0 | 79083.5478 | 0 | 100% | Finished | 79701.2578 | 79701.2578 | 100 | 100 | 100 | 100 | 99.225 | 100
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 2012-05-07 08:00 | 42d | 74182.2734 | 0 | 0 | -516.37 | 0 | 73665.9034 | 0 | 100% | Finished | 74182.2734 | 74182.2734 | 100 | 100 | 100 | 100 | 99.3039 | 100
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 | 2012-06-26 08:00 | 30d | 116911.4219 | 0 | 0 | -205.45 | 0 | 116705.9719 | 0 | 100% | Finished | 116911.4219 | 116911.4219 | 100 | 120 | 100 | 100 | 99.8243 | 100
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 109d | [5 empty] | 139148.1781 |  | 100% |  | 139110.0781 | 139110.0781
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 100.4084 | 100
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 100% | Finished | 32282.5391 | 32282.5391 | 100 | 100 | 100 | 100 | 99.7583 | 100
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 30d | 91971.1094 | 0 | 0 | 55.46 | 0 | 92026.5694 | 0 | 100% | Finished | 91971.1094 | 91971.1094 | 100 | 120 | 100 | 100 | 100.0603 | 100
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 109d | [5 empty] | 139148.1781 |  | 100% |  | 139110.0781 | 139110.0781
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 100.4084 | 100
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 100% | Finished | 32282.5391 | 32282.5391 | 100 | 100 | 100 | 100 | 99.7583 | 100
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 30d | 91971.1094 | 0 | 0 | 55.46 | 0 | 92026.5694 | 0 | 100% | Finished | 91971.1094 | 91971.1094 | 100 | 120 | 100 | 100 | 100.0603 | 100
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 25d | [5 empty] | 45611.0908 |  | 100% |  | 45734.0508 | 45734.0508
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 2012-05-29 08:00 | 15d | 18175.6309 | 0 | 0 | -73.78 | 0 | 18101.8509 | 0 | 100% | Finished | 18175.6309 | 18175.6309 | 100 | 100 | 100 | 100 | 99.5941 | 100
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 | 2012-06-19 08:00 | 10d | 27558.4199 | 0 | 0 | -49.18 | 0 | 27509.2399 | 0 | 100% | Finished | 27558.4199 | 27558.4199 | 100 | 100 | 100 | 100 | 99.8215 | 100
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 79d | [5 empty] | 1971.39 |  | 40% |  | 457.12 | 1142.8
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1514.27 | 0 | 1971.39 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 431.2631 | 100
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 |  | 0 | 0 | 457.12 | 2d | 0 | 0 | 0 | 457.12 | 0% | Not Started | 0 | 457.12 | 100 |  | 0 | 100 |  | 0
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 |  | 0 | 0 | 228.56 | 1d | 0 | 0 | 0 | 228.56 | 0% | Not Started | 0 | 228.56 | 100 |  | 0 | 100 |  | 0
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 4d | [5 empty] | 18864.4001 |  | 88.07% |  | 15413.2002 | 17275.1002
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 |  | 0 | 0 | 450.5 | 2d | 0 | 0 | 0 | 450.5 | 0% | Not Started | 0 | 450.5 | 100 |  | 0 | 100 |  | 0
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 |  | 0 | 0 | 735.65 | 3d | 0 | 0 | 0 | 735.65 | 0% | Not Started | 0 | 735.65 | 100 |  | 0 | 100 |  | 0
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 |  | 0 | 0 | 675.75 | 3d | 0 | 0 | 0 | 675.75 | 0% | Not Started | 0 | 675.75 | 100 |  | 0 | 100 |  | 0
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 | 2012-08-28 08:00 | 4d | 15413.2002 | 0 | 16d | 3451.2 | 0 | 18864.4001 | 0 | 20% | Started | 15413.2002 | 15413.2002 | 100 | 16 | 20 | 100 | 122.3912 | 20
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 |  | 0 | 0 | 225.25 | 1d | 0 | 0 | 0 | 225.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2012-09-30 17:00 |  | TP Name | 30/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Recreation Complex | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 277d | [5 empty] | 5451028.0032 |  | 100% |  | 5480518.9127 | 5392111.2444
1 | START DER WERKEN SPORTHAL | 2011-07-08 17:00 | 2011-07-08 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-01 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
2 | Totale uitvoeringstermijn | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 5480518.9127 |  |  | 5480518.9127 |  | 277d | [5 empty] | 5451028.0032 |  | 100% |  | 5480518.9127 | 5392111.2444
3 | WERFINRICHTING | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  |  | 140380.5469 |  |  | 140380.5469 |  | 1d | [5 empty] | 149650.4971 |  | 100% |  | 140380.5469 | 140380.5469
4 | Plaatsen van de werfketen en werfuitrusting | 2011-08-01 08:00 | 2011-08-04 17:00 | 4d |  | 0 | 140380.5469 | 0 | 0 | 140380.5469 | 2011-07-08 08:00 | 1d | 140380.5469 | 0 | 0 | 9269.9502 | 0 | 149650.4971 | 0 | 100% | Finished | 140380.5469 | 140380.5469 | 100 | 25 | 100 | 100 | 106.6034 | 100
5 | VOORBEREIDENDE WERKEN | 2011-08-01 08:00 | 2011-12-21 17:00 | 96d |  |  | 366683.4202 |  |  | 366683.4202 |  | 99d | [5 empty] | 358462.3806 |  | 100% |  | 366683.4202 | 366683.4202
6 | Opzoeken ondergrondse leidingen | 2011-08-01 08:00 | 2011-08-03 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2011-08-01 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.4084 | 100
7 | WERKEN NIEUWE PARKEERZONE (ZONE P) | 2011-08-25 08:00 | 2011-10-27 17:00 | 46d |  |  | 117133.5588 |  |  | 117133.5588 |  | 53d | [5 empty] | 107985.739 |  | 100% |  | 117133.5588 | 117133.5588
265 | Voorstel materiaal nieuwe muur | 2011-08-25 17:00 | 2011-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-08-18 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
266 | Afbraak gemeenschappelijke muur thv nieuwe parking | 2011-09-02 08:00 | 2011-09-05 17:00 | 2d |  | 0 | 704.8 | 0 | 0 | 704.8 | 2011-09-12 08:00 | 2d | 704.8 | 0 | 0 | 118.81 | 0 | 823.61 | 0 | 100% | Finished | 704.8 | 704.8 | 100 | 100 | 100 | 100 | 116.8573 | 100
267 | Fundering nieuwe te metsen muur | 2011-09-06 08:00 | 2011-09-12 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-14 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
8 | Aanleggen onderfundering parking (zone P) | 2011-08-25 08:00 | 2011-08-30 17:00 | 4d |  | 0 | 914.24 | 0 | 0 | 914.24 | 2011-09-21 08:00 | 4d | 914.24 | 0 | 0 | 3.73 | 0 | 917.97 | 0 | 100% | Finished | 914.24 | 914.24 | 100 | 100 | 100 | 100 | 100.408 | 100
9 | Metselwerk omgeving nieuwe parking | 2011-08-31 08:00 | 2011-09-20 17:00 | 15d |  | 0 | 70567.4375 | 0 | 0 | 70567.4375 | 2011-09-21 08:00 | 20d | 70567.4375 | 0 | 0 | -6499.1499 | 0 | 64068.2876 | 0 | 100% | Finished | 70567.4375 | 70567.4375 | 100 | 133.3333 | 100 | 100 | 90.7902 | 100
10 | Aanleggen van bestrating nieuwe parking+tijdelijke toegang | 2011-09-16 08:00 | 2011-10-27 17:00 | 30d |  | 0 | 43804.2812 | 0 | 0 | 43804.2812 | 2011-09-27 08:00 | 25d | 43804.2812 | 0 | 0 | -2775.8799 | 0 | 41028.4014 | 0 | 100% | Finished | 43804.2812 | 43804.2812 | 100 | 83.3333 | 100 | 100 | 93.663 | 100
11 | AFBRAAKWERKEN | 2011-08-02 08:00 | 2011-12-21 17:00 | 95d |  |  | 34170.5095 |  |  | 34170.5095 |  | 99d | [5 empty] | 39121.2097 |  | 100% |  | 34170.5095 | 34170.5095
12 | Verwijderen vegetatie en bomen | 2011-08-02 08:00 | 2011-08-08 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2011-07-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.8571 | 100
13 | Afbraak verhardingen / funderingen | 2011-08-09 08:00 | 2011-12-21 17:00 | 90d |  | 0 | 32408.5195 | 0 | 0 | 32408.5195 | 2011-08-04 08:00 | 90d | 32408.5195 | 0 | 0 | 4653.6802 | 0 | 37062.1997 | 0 | 100% | Finished | 32408.5195 | 32408.5195 | 100 | 100 | 100 | 100 | 114.3594 | 100
14 | GRONDWERKEN | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  |  | 214693.6719 |  |  | 214693.6719 |  | 4d | [5 empty] | 210666.9519 |  | 100% |  | 214693.6719 | 214693.6719
15 | Uitgraving - grondverzet nieuwe sporthal | 2011-08-12 08:00 | 2011-08-24 17:00 | 8d |  | 0 | 214693.6719 | 0 | 0 | 214693.6719 | 2011-08-04 08:00 | 4d | 214693.6719 | 0 | 0 | -4026.72 | 0 | 210666.9519 | 0 | 100% | Finished | 214693.6719 | 214693.6719 | 100 | 50 | 100 | 100 | 98.1244 | 100
16 | STABILITEIT | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1741960.3886 |  |  | 1741960.3886 |  | 159d | [5 empty] | 1686917.0672 |  | 100% |  | 1741960.3886 | 1741960.3886
17 | GRONDWERKEN EN FUNDERINGEN | 2011-08-25 08:00 | 2011-09-14 17:00 | 15d |  |  | 97505.4526 |  |  | 97505.4526 |  | 10d | [5 empty] | 95589.4126 |  | 100% |  | 97505.4526 | 97505.4526
18 | Uitzetten palen / gebouw | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 6743.3901 | 0 | 0 | 6743.3901 | 2011-08-05 08:00 | 1d | 6743.3901 | 0 | 0 | -139.9 | 0 | 6603.4901 | 0 | 100% | Finished | 6743.3901 | 6743.3901 | 100 | 50 | 100 | 100 | 97.9254 | 100
19 | Uitvoeren funderingspalen + afkappen | 2011-08-29 08:00 | 2011-09-12 17:00 | 11d |  | 0 | 37088.6406 | 0 | 0 | 37088.6406 | 2011-08-08 08:00 | 7d | 37088.6406 | 0 | 0 | -769.46 | 0 | 36319.1806 | 0 | 100% | Finished | 37088.6406 | 37088.6406 | 100 | 63.6364 | 100 | 100 | 97.9253 | 100
20 | Uitgraving en aanvuling voor funderingen - riolering | 2011-09-13 08:00 | 2011-09-14 17:00 | 2d |  | 0 | 53673.4219 | 0 | 0 | 53673.4219 | 2011-08-18 08:00 | 2d | 53673.4219 | 0 | 0 | -1006.68 | 0 | 52666.7419 | 0 | 100% | Finished | 53673.4219 | 53673.4219 | 100 | 100 | 100 | 100 | 98.1244 | 100
21 | SONDERINGEN | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  |  | 1142.8 |  |  | 1142.8 |  | 5d | [5 empty] | 1147.47 |  | 100% |  | 1142.8 | 1142.8
22 | Verkenningsputten bestaande fundering | 2011-08-31 08:00 | 2011-09-06 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2011-09-21 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
23 | OPEN RUWBOUW ALGEMEEN | 2011-04-29 08:00 | 2012-04-10 17:00 | 216d |  |  | 1643312.1359 |  |  | 1643312.1359 |  | 146d | [5 empty] | 1590180.1846 |  | 100% |  | 1643312.1359 | 1643312.1359
163 | Liftput | 2011-08-25 08:00 | 2011-08-26 17:00 | 2d |  | 0 | 2423.4199 | 0 | 0 | 2423.4199 | 2011-08-25 08:00 | 2d | 2423.4199 | 0 | 0 | -9.84 | 0 | 2413.5799 | 0 | 100% | Finished | 2423.4199 | 2423.4199 | 100 | 100 | 100 | 100 | 99.594 | 100
24 | Werkvloer fundering paalkoppen | 2011-09-26 08:00 | 2011-09-27 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-08-29 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.4091 | 100
164 | Aardingslus | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-08-29 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.4069 | 100
165 | Afkappen palen | 2011-09-28 08:00 | 2011-09-30 17:00 | 3d |  | 0 | 10115.0801 | 0 | 0 | 10115.0801 | 2011-08-31 08:00 | 3d | 10115.0801 | 0 | 0 | -209.85 | 0 | 9905.2301 | 0 | 100% | Finished | 10115.0801 | 10115.0801 | 100 | 100 | 100 | 100 | 97.9254 | 100
166 | Bekisting funderingszolen en paalkoppen | 2011-09-29 08:00 | 2011-10-19 17:00 | 15d |  | 0 | 47202.8086 | 0 | 0 | 47202.8086 | 2011-09-01 08:00 | 15d | 47202.8086 | 0 | 0 | -14512.9805 | 0 | 32689.8281 | 0 | 100% | Finished | 47202.8086 | 47202.8086 | 100 | 100 | 100 | 100 | 69.254 | 100
167 | Montage torenkraan | 2011-10-03 08:00 | 2011-10-04 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2011-09-05 08:00 | 2d | 457.12 | 0 | 0 | 1304.53 | 0 | 1761.65 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 385.3802 | 100
168 | Wapening paalkoppen en balken | 2011-10-05 08:00 | 2011-10-18 17:00 | 10d |  | 0 | 48212.0312 | 0 | 0 | 48212.0312 | 2011-09-07 08:00 | 10d | 48212.0312 | 0 | 0 | -6556.02 | 0 | 41656.0112 | 0 | 100% | Finished | 48212.0312 | 48212.0312 | 100 | 100 | 100 | 100 | 86.4017 | 100
169 | Randbekisting vloerplaat | 2011-10-05 08:00 | 2011-10-11 17:00 | 5d |  | 0 | 15734.2695 | 0 | 0 | 15734.2695 | 2011-09-07 08:00 | 5d | 15734.2695 | 0 | 0 | -4837.6602 | 0 | 10896.6094 | 0 | 100% | Finished | 15734.2695 | 15734.2695 | 100 | 100 | 100 | 100 | 69.254 | 100
170 | Bekisting paalkoppen, balken + beton | 2011-10-11 08:00 | 2011-10-24 17:00 | 10d |  | 0 | 38941.5391 | 0 | 0 | 38941.5391 | 2011-09-13 08:00 | 10d | 38941.5391 | 0 | 0 | 20358.6797 | 0 | 59300.2188 | 0 | 100% | Finished | 38941.5391 | 38941.5391 | 100 | 100 | 100 | 100 | 152.2801 | 100
171 | Grondwerk vloerplaat + werkvloer | 2011-10-25 08:00 | 2011-11-03 17:00 | 6d |  | 0 | 165891.9375 | 0 | 0 | 165891.9375 | 2011-09-27 08:00 | 6d | 165891.9375 | 0 | 0 | -2695.74 | 0 | 163196.1975 | 0 | 100% | Finished | 165891.9375 | 165891.9375 | 100 | 100 | 100 | 100 | 98.375 | 100
38 | Wapening vloerplaat | 2011-10-24 08:00 | 2011-10-28 17:00 | 5d |  | 0 | 24106.0195 | 0 | 0 | 24106.0195 | 2011-10-04 08:00 | 7d | 24106.0195 | 0 | 0 | -3278.01 | 0 | 20828.0095 | 0 | 100% | Finished | 24106.0195 | 24106.0195 | 100 | 140 | 100 | 100 | 86.4017 | 100
172 | GOEDKEURING ANKERPLATEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-19 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
173 | Plaatsen isolatie + ankers staalconstructie | 2011-11-04 08:00 | 2011-11-16 17:00 | 8d |  | 0 | 2076.48 | 0 | 0 | 2076.48 | 2011-10-07 08:00 | 8d | 2076.48 | 0 | 0 | 1454.9 | 0 | 3531.38 | 0 | 100% | Finished | 2076.48 | 2076.48 | 100 | 100 | 100 | 100 | 170.0657 | 100
174 | Beton vloerplaat fase 1 | 2011-11-14 08:00 | 2011-11-15 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-14 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.403 | 100
40 | Ontkisten randbekisting vloerplaat | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 2570.79 | 0 | 0 | 2570.79 | 2011-10-18 08:00 | 5d | 2570.79 | 0 | 0 | -928.26 | 0 | 1642.53 | 0 | 100% | Finished | 2570.79 | 2570.79 | 100 | 500 | 100 | 100 | 63.892 | 100
175 | Plaatsen neopreen + isolatie | 2011-11-08 08:00 | 2011-11-08 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2011-10-18 08:00 | 1d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 193.1309 | 100
176 | Beton vloerplaat fase 2 | 2011-11-09 08:00 | 2011-11-10 17:00 | 2d |  | 0 | 21229.2793 | 0 | 0 | 21229.2793 | 2011-10-19 08:00 | 2d | 21229.2793 | 0 | 0 | -13288.8896 | 0 | 7940.3896 | 0 | 100% | Finished | 21229.2793 | 21229.2793 | 100 | 100 | 100 | 100 | 37.403 | 100
177 | Ontkisten vloerplaat fase 2 | 2011-11-14 08:00 | 2011-11-16 17:00 | 3d |  | 0 | 7712.3799 | 0 | 0 | 7712.3799 | 2011-10-21 08:00 | 3d | 7712.3799 | 0 | 0 | -2784.77 | 0 | 4927.6099 | 0 | 100% | Finished | 7712.3799 | 7712.3799 | 100 | 100 | 100 | 100 | 63.8922 | 100
178 | GOEDKEURING UITVOERINGSPLAN PLINTEN | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
179 | Plaatsen plinten | 2011-11-17 08:00 | 2011-11-24 17:00 | 6d |  | 0 | 2794.79 | 0 | 0 | 2794.79 | 2011-10-26 08:00 | 6d | 2794.79 | 0 | 0 | 3927.4199 | 0 | 6722.21 | 0 | 100% | Finished | 2794.79 | 2794.79 | 100 | 100 | 100 | 100 | 240.5265 | 100
180 | Bekisting wanden | 2011-11-22 08:00 | 2011-12-22 17:00 | 20d |  | 0 | 62937.0781 | 0 | 0 | 62937.0781 | 2011-11-02 08:00 | 20d | 62937.0781 | 0 | 0 | -19350.6406 | 0 | 43586.4375 | 0 | 100% | Finished | 62937.0781 | 62937.0781 | 100 | 100 | 100 | 100 | 69.254 | 100
181 | Metselwerken | 2011-11-24 08:00 | 2012-01-02 17:00 | 20d |  | 0 | 94089.9219 | 0 | 0 | 94089.9219 | 2011-11-04 08:00 | 20d | 94089.9219 | 0 | 0 | -8665.5303 | 0 | 85424.3916 | 0 | 100% | Finished | 94089.9219 | 94089.9219 | 100 | 100 | 100 | 100 | 90.7902 | 100
182 | GOEDKEURING PLANNEN STAALCONSTRUCTIE | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-30 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
183 | GOEDKEURING PLANNEN PREFAB (trappen, tribunes, ...) | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-09-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
184 | Plaatsen metalen kolommen tribune | 2011-12-01 08:00 | 2011-12-02 17:00 | 2d |  | 0 | 519.12 | 0 | 0 | 519.12 | 2011-11-08 08:00 | 2d | 519.12 | 0 | 0 | -60.13 | 0 | 458.99 | 0 | 100% | Finished | 519.12 | 519.12 | 100 | 100 | 100 | 100 | 88.4169 | 100
185 | Plaatsen prefabconstructies | 2011-12-05 08:00 | 2011-12-14 17:00 | 8d |  | 0 | 68166.2578 | 0 | 0 | 68166.2578 | 2011-11-10 08:00 | 18d | 68166.2578 | 0 | 0 | 6665.6899 | 0 | 74831.9478 | 0 | 100% | Finished | 68166.2578 | 68166.2578 | 100 | 225 | 100 | 100 | 109.7786 | 100
188 | Ruwbouw sporthal | 2011-12-21 08:00 | 2012-04-02 17:00 | 69d |  |  | 384191.6268 |  |  | 384191.6268 |  | 41d | [5 empty] | 409520.537 |  | 100% |  | 384191.6268 | 384191.6268
43 | Staalstructuur sporthal | 2011-12-21 08:00 | 2012-01-06 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-12 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 111.81 | 100
187 | Gelameleerde liggers sporthal + staalconstructie dak | 2012-01-27 08:00 | 2012-02-02 17:00 | 5d |  | 0 | 56129.6797 | 0 | 0 | 56129.6797 | 2012-01-17 08:00 | 5d | 56129.6797 | 0 | 0 | 36690.3906 | 0 | 92820.0703 | 0 | 100% | Finished | 56129.6797 | 56129.6797 | 100 | 100 | 100 | 100 | 165.3672 | 100
189 | Steeldeck sporthal | 2012-02-03 08:00 | 2012-02-14 17:00 | 8d |  | 0 | 2578.22 | 0 | 0 | 2578.22 | 2012-01-24 08:00 | 5d | 2578.22 | 0 | 0 | -149.87 | 0 | 2428.35 | 0 | 100% | Finished | 2578.22 | 2578.22 | 100 | 62.5 | 100 | 100 | 94.1871 | 100
190 | Dakopstanden sporthal | 2012-02-15 08:00 | 2012-02-16 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-01-31 08:00 | 2d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 100 | 100 | 100 | 94.1866 | 100
192 | Afvoer hemelwater sporthal/berging | 2012-02-15 08:00 | 2012-02-17 17:00 | 3d |  | 0 | 685.68 | 0 | 0 | 685.68 | 2012-01-31 08:00 | 3d | 685.68 | 0 | 0 | 2.8 | 0 | 688.48 | 0 | 100% | Finished | 685.68 | 685.68 | 100 | 100 | 100 | 100 | 100.4084 | 100
205 | Staalconstructie technisch lokaal fase 1 | 2012-03-13 08:00 | 2012-03-15 17:00 | 3d |  | 0 | 33677.8086 | 0 | 0 | 33677.8086 | 2012-01-24 08:00 | 3d | 33677.8086 | 0 | 0 | 3977.3301 | 0 | 37655.1387 | 0 | 100% | Finished | 33677.8086 | 33677.8086 | 100 | 100 | 100 | 100 | 111.8099 | 100
206 | Welfsels technisch lokaal fase 1 | 2012-03-16 08:00 | 2012-03-16 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-27 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.758 | 100
207 | Wapening en bekisting technisch lokaal | 2012-03-19 08:00 | 2012-03-23 17:00 | 5d |  | 0 | 38697.4805 | 0 | 0 | 38697.4805 | 2012-01-30 08:00 | 5d | 38697.4805 | 0 | 0 | -8120.3398 | 0 | 30577.1406 | 0 | 100% | Finished | 38697.4805 | 38697.4805 | 100 | 100 | 100 | 100 | 79.0158 | 100
208 | Bekisting / storten ringbalk / beton welfsels | 2012-03-26 08:00 | 2012-03-27 17:00 | 2d |  | 0 | 28146.0098 | 0 | 0 | 28146.0098 | 2012-02-06 08:00 | 2d | 28146.0098 | 0 | 0 | -15231.4004 | 0 | 12914.6094 | 0 | 100% | Finished | 28146.0098 | 28146.0098 | 100 | 100 | 100 | 100 | 45.8843 | 100
209 | Luchtgroep technisch lokaal | 2012-03-28 08:00 | 2012-03-28 17:00 | 1d |  | 0 | 118942.6016 | 0 | 0 | 118942.6016 | 2012-02-08 08:00 | 1d | 118942.6016 | 0 | 0 | -1107.0601 | 0 | 117835.5415 | 0 | 100% | Finished | 118942.6016 | 118942.6016 | 100 | 100 | 100 | 100 | 99.0692 | 100
210 | Metselwerk technisch lokaal fase 1 | 2012-03-29 08:00 | 2012-04-02 17:00 | 3d |  | 0 | 14113.4902 | 0 | 0 | 14113.4902 | 2012-02-09 08:00 | 3d | 14113.4902 | 0 | 0 | -1299.83 | 0 | 12813.6603 | 0 | 100% | Finished | 14113.4902 | 14113.4902 | 100 | 100 | 100 | 100 | 90.7902 | 100
201 | Ruwbouw cafetaria | 2011-12-09 08:00 | 2012-04-10 17:00 | 82d |  |  | 621796.6673 |  |  | 621796.6673 |  | 70d | [5 empty] | 599876.137 |  | 100% |  | 621796.6673 | 621796.6673
42 | Staalstructuur nv 0 | 2011-12-09 08:00 | 2011-12-20 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2011-12-19 08:00 | 5d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 62.5 | 100 | 100 | 111.81 | 100
211 | Opgieten voetplaten cafetaria | 2012-02-13 08:00 | 2012-02-14 17:00 | 2d |  | 0 | 2114.3301 | 0 | 0 | 2114.3301 | 2012-01-02 08:00 | 2d | 2114.3301 | 0 | 0 | 91.22 | 0 | 2205.5501 | 0 | 100% | Finished | 2114.3301 | 2114.3301 | 100 | 100 | 100 | 100 | 104.3144 | 100
45 | Staalstructuur nv 1 | 2012-01-17 08:00 | 2012-01-26 17:00 | 8d |  | 0 | 89807.4766 | 0 | 0 | 89807.4766 | 2012-01-09 08:00 | 6d | 89807.4766 | 0 | 0 | 10606.2197 | 0 | 100413.6963 | 0 | 100% | Finished | 89807.4766 | 89807.4766 | 100 | 75 | 100 | 100 | 111.81 | 100
202 | Welfsels fase 1 (boven +0) | 2012-01-02 08:00 | 2012-01-09 17:00 | 6d |  | 0 | 4611.79 | 0 | 0 | 4611.79 | 2012-01-02 08:00 | 5d | 4611.79 | 0 | 0 | -11.15 | 0 | 4600.64 | 0 | 100% | Finished | 4611.79 | 4611.79 | 100 | 83.3333 | 100 | 100 | 99.7582 | 100
212 | Welfsels fase 2 (berging + cafetaria aan best. Sporthal) | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 768.63 | 0 | 0 | 768.63 | 2012-01-09 08:00 | 1d | 768.63 | 0 | 0 | -1.86 | 0 | 766.77 | 0 | 100% | Finished | 768.63 | 768.63 | 100 | 100 | 100 | 100 | 99.758 | 100
213 | Wapening / bekisting welfsels boven +0 | 2012-02-01 08:00 | 2012-02-06 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-13 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 80.3509 | 100
203 | Beton op welfsels boven +0 | 2012-02-03 08:00 | 2012-02-06 17:00 | 2d |  | 0 | 22309.4199 | 0 | 0 | 22309.4199 | 2012-01-19 08:00 | 2d | 22309.4199 | 0 | 0 | -13294.4697 | 0 | 9014.9502 | 0 | 100% | Finished | 22309.4199 | 22309.4199 | 100 | 100 | 100 | 100 | 40.4087 | 100
214 | Welfsels fase 3 (boven +1) | 2012-02-07 08:00 | 2012-02-09 17:00 | 3d |  | 0 | 2305.8999 | 0 | 0 | 2305.8999 | 2012-01-23 08:00 | 3d | 2305.8999 | 0 | 0 | -5.57 | 0 | 2300.3299 | 0 | 100% | Finished | 2305.8999 | 2305.8999 | 100 | 100 | 100 | 100 | 99.7584 | 100
215 | Wapening / bekisting welfsels boven +1 | 2012-02-08 08:00 | 2012-02-13 17:00 | 4d |  | 0 | 33118.2695 | 0 | 0 | 33118.2695 | 2012-01-24 08:00 | 4d | 33118.2695 | 0 | 0 | -6507.4399 | 0 | 26610.8296 | 0 | 100% | Finished | 33118.2695 | 33118.2695 | 100 | 100 | 100 | 100 | 80.3509 | 100
216 | Beton op welfsels boven +1 | 2012-02-14 08:00 | 2012-02-14 17:00 | 1d |  | 0 | 11154.71 | 0 | 0 | 11154.71 | 2012-01-30 08:00 | 1d | 11154.71 | 0 | 0 | -6647.2402 | 0 | 4507.4697 | 0 | 100% | Finished | 11154.71 | 11154.71 | 100 | 100 | 100 | 100 | 40.4087 | 100
50 | Dragend metselwerk nv 1 | 2012-01-23 08:00 | 2012-01-27 17:00 | 5d |  | 0 | 23522.4805 | 0 | 0 | 23522.4805 | 2012-01-31 08:00 | 5d | 23522.4805 | 0 | 0 | -2166.3799 | 0 | 21356.1006 | 0 | 100% | Finished | 23522.4805 | 23522.4805 | 100 | 100 | 100 | 100 | 90.7902 | 100
217 | Timmerwerk cafetaria, houtbouw | 2012-02-15 08:00 | 2012-02-22 17:00 | 6d |  | 0 | 115165.7109 | 0 | 0 | 115165.7109 | 2012-01-31 08:00 | 20d | 115165.7109 | 0 | 0 | -2778.8401 | 0 | 112386.8708 | 0 | 100% | Finished | 115165.7109 | 115165.7109 | 100 | 333.3333 | 100 | 100 | 97.5871 | 100
218 | Houtskeletbouw cafetaria (UPN, Technieken boven, dakopstanden) | 2012-03-27 08:00 | 2012-04-10 17:00 | 10d |  | 0 | 191942.8438 | 0 | 0 | 191942.8438 | 2012-03-09 08:00 | 6d | 191942.8438 | 0 | 0 | -4631.3999 | 0 | 187311.4438 | 0 | 100% | Finished | 191942.8438 | 191942.8438 | 100 | 60 | 100 | 100 | 97.5871 | 100
56 | UPN gevelprofielen | 2012-02-22 08:00 | 2012-02-28 17:00 | 5d |  | 0 | 1820.8 | 0 | 0 | 1820.8 | 2012-03-26 08:00 | 5d | 1820.8 | 0 | 0 | -673.33 | 0 | 1147.47 | 0 | 100% | Finished | 1820.8 | 1820.8 | 100 | 100 | 100 | 100 | 63.0201 | 100
219 | AFBRAAK TORENKRAAN | 2012-03-01 08:00 | 2012-03-01 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-01 08:00 | 1d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100.4069 | 100
57 | ARCHITECTUUR | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 2231819.1877 |  |  | 2231819.1877 |  | 190d | [5 empty] | 2255841.499 |  | 100% |  | 2231819.1877 | 2143411.5195
58 | AFBRAAKWERKEN | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  |  | 2819.1799 |  |  | 2819.1799 |  | 8d | [5 empty] | 3294.4099 |  | 100% |  | 2819.1799 | 2819.1799
59 | Maken nieuwe deuropeningen in bestaande sporthal | 2012-02-13 08:00 | 2012-02-22 17:00 | 8d |  | 0 | 2819.1799 | 0 | 0 | 2819.1799 | 2012-05-10 08:00 | 8d | 2819.1799 | 0 | 0 | 475.23 | 0 | 3294.4099 | 0 | 100% | Finished | 2819.1799 | 2819.1799 | 100 | 100 | 100 | 100 | 116.857 | 100
60 | RIOLERINGSNET | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  |  | 3428.4099 |  |  | 3428.4099 |  | 15d | [5 empty] | 3442.4099 |  | 100% |  | 3428.4099 | 3428.4099
61 | Rioleringswerk onder en rondom de nieuwe sporthal, regenputten | 2011-09-15 08:00 | 2011-10-05 17:00 | 15d |  | 0 | 3428.4099 | 0 | 0 | 3428.4099 | 2012-03-19 08:00 | 15d | 3428.4099 | 0 | 0 | 14 | 0 | 3442.4099 | 0 | 100% | Finished | 3428.4099 | 3428.4099 | 100 | 100 | 100 | 100 | 100.4084 | 100
65 | NATUURSTENEN EN BETON BEKLEDINGEN | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  |  | 6986.9902 |  |  | 6986.9902 |  | 9d | [5 empty] | 16805.54 |  | 100% |  | 6986.9902 | 6986.9902
66 | Plinten, dorpels en vloerplaten | 2012-02-08 08:00 | 2012-02-28 17:00 | 15d |  | 0 | 6986.9902 | 0 | 0 | 6986.9902 | 2012-01-23 08:00 | 9d | 6986.9902 | 0 | 0 | 9818.5498 | 0 | 16805.54 | 0 | 100% | Finished | 6986.9902 | 6986.9902 | 100 | 60 | 100 | 100 | 240.5262 | 100
221 | SPORTHAL OPBOUW | 2012-02-17 08:00 | 2012-05-09 17:00 | 57d |  |  | 245403.4564 |  |  | 245403.4564 |  | 41d | [5 empty] | 271542.2072 |  | 100% |  | 245403.4564 | 245403.4564
220 | Dakopstanden lichtstraat sporthal | 2012-02-17 08:00 | 2012-02-20 17:00 | 2d |  | 0 | 644.55 | 0 | 0 | 644.55 | 2012-03-01 08:00 | 6d | 644.55 | 0 | 0 | -37.47 | 0 | 607.08 | 0 | 100% | Finished | 644.55 | 644.55 | 100 | 300 | 100 | 100 | 94.1866 | 100
223 | Dampremmende laag | 2012-02-22 08:00 | 2012-02-22 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-12 08:00 | 9d | 228.56 | 0 | 0 | 212.86 | 0 | 441.42 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 193.1309 | 100
224 | Isolatie | 2012-02-23 08:00 | 2012-03-01 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-03-12 08:00 | 9d | 1371.36 | 0 | 0 | 1277.17 | 0 | 2648.53 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 150 | 100 | 100 | 193.1316 | 100
225 | Dakdichting | 2012-03-02 08:00 | 2012-03-15 17:00 | 10d |  | 0 | 116301.5078 | 0 | 0 | 116301.5078 | 2012-03-12 08:00 | 9d | 116301.5078 | 0 | 0 | -11243.8496 | 0 | 105057.6582 | 0 | 100% | Finished | 116301.5078 | 116301.5078 | 100 | 90 | 100 | 100 | 90.3322 | 100
226 | Lichtstraat sporthal | 2012-02-21 08:00 | 2012-02-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-03-23 08:00 | 9d | 228.56 | 0 | 0 | 0.93 | 0 | 229.49 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 900 | 100 | 100 | 100.4069 | 100
227 | Dak en wandbeplating sporthal | 2012-04-11 08:00 | 2012-04-30 17:00 | 14d |  | 0 | 93216.1875 | 0 | 0 | 93216.1875 | 2012-03-19 08:00 | 20d | 93216.1875 | 0 | 0 | 11738.3301 | 0 | 104954.5176 | 0 | 100% | Finished | 93216.1875 | 93216.1875 | 100 | 142.8571 | 100 | 100 | 112.5926 | 100
228 | Grondbussen sporthal | 2012-05-02 08:00 | 2012-05-03 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-17 08:00 | 2d | 457.12 | 0 | 0 | 1.87 | 0 | 458.99 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100.4091 | 100
229 | Scheidingswanden sporthal | 2012-05-04 08:00 | 2012-05-09 17:00 | 4d |  | 0 | 994.24 | 0 | 0 | 994.24 | 2012-04-19 08:00 | 4d | 994.24 | 0 | 0 | -76.27 | 0 | 917.97 | 0 | 100% | Finished | 994.24 | 994.24 | 100 | 100 | 100 | 100 | 92.3288 | 100
230 | Elektriciteit sporthal, constructies voor verlichting | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 20492.0508 | 0 | 0 | 20492.0508 | 2012-04-16 08:00 | 10d | 20492.0508 | 0 | 0 | -1910.4301 | 0 | 18581.6207 | 0 | 100% | Finished | 20492.0508 | 20492.0508 | 100 | 200 | 100 | 100 | 90.6772 | 100
231 | Kanalen sporthal door gelamelleerde liggers | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 3240.6299 | 0 | 0 | 3240.6299 | 2012-04-16 08:00 | 10d | 3240.6299 | 0 | 0 | 28144.6504 | 0 | 31385.2803 | 0 | 100% | Finished | 3240.6299 | 3240.6299 | 100 | 200 | 100 | 100 | 968.4932 | 100
222 | Sanitair sporthal | 2012-04-30 08:00 | 2012-05-07 17:00 | 5d |  | 0 | 8228.6904 | 0 | 0 | 8228.6904 | 2012-04-16 08:00 | 10d | 8228.6904 | 0 | 0 | -1969.04 | 0 | 6259.6504 | 0 | 100% | Finished | 8228.6904 | 8228.6904 | 100 | 200 | 100 | 100 | 76.071 | 100
233 | CAFETARIA OPBOUW | 2011-04-29 08:00 | 2012-06-01 17:00 | 251d |  |  | 745162.4451 |  |  | 745162.4451 |  | 77d | [5 empty] | 780586.304 |  | 100% |  | 745162.4451 | 745162.4451
232 | Plaatsing rookkoepels | 2012-04-11 08:00 | 2012-04-12 17:00 | 2d |  | 0 | 231412.7969 | 0 | 0 | 231412.7969 | 2012-03-05 08:00 | 2d | 231412.7969 | 0 | 0 | -2215.8 | 0 | 229196.9968 | 0 | 100% | Finished | 231412.7969 | 231412.7969 | 100 | 100 | 100 | 100 | 99.0425 | 100
234 | Hellingsbeton | 2012-03-05 08:00 | 2012-03-08 17:00 | 4d |  | 0 | 3903.4399 | 0 | 0 | 3903.4399 | 2012-03-09 08:00 | 1d | 3903.4399 | 0 | 0 | 12196.1104 | 0 | 16099.5503 | 0 | 100% | Finished | 3903.4399 | 3903.4399 | 100 | 25 | 100 | 100 | 412.4452 | 100
235 | Isolatie | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-26 08:00 | 5d | 1142.8 | 0 | 0 | 1064.3101 | 0 | 2207.1101 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 193.1318 | 100
236 | EPDM dakdichting | 2012-03-23 08:00 | 2012-04-10 17:00 | 12d |  | 0 | 139561.8125 | 0 | 0 | 139561.8125 | 2012-04-02 08:00 | 12d | 139561.8125 | 0 | 0 | -13492.6201 | 0 | 126069.1924 | 0 | 100% | Finished | 139561.8125 | 139561.8125 | 100 | 100 | 100 | 100 | 90.3322 | 100
237 | Opmeting buitenschrijnwerk | 2011-04-29 08:00 | 2011-04-28 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-01-02 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
238 | Houten buitenschrijnwerk | 2012-02-23 08:00 | 2012-02-27 17:00 | 3d |  | 0 | 41378.1406 | 0 | 0 | 41378.1406 | 2012-04-04 08:00 | 3d | 41378.1406 | 0 | 0 | 10415.5098 | 0 | 51793.6504 | 0 | 100% | Finished | 41378.1406 | 41378.1406 | 100 | 100 | 100 | 100 | 125.1715 | 100
239 | Aluminium buitenschrijnwerk | 2012-02-23 08:00 | 2012-03-07 17:00 | 10d |  | 0 | 138237.1406 | 0 | 0 | 138237.1406 | 2012-03-12 08:00 | 10d | 138237.1406 | 0 | 0 | -405.28 | 0 | 137831.8606 | 0 | 100% | Finished | 138237.1406 | 138237.1406 | 100 | 100 | 100 | 100 | 99.7068 | 100
240 | Dak en wandbeplating cafetaria | 2012-05-03 08:00 | 2012-06-01 17:00 | 20d |  | 0 | 133165.9844 | 0 | 0 | 133165.9844 | 2012-03-26 08:00 | 10d | 133165.9844 | 0 | 0 | 16769.0391 | 0 | 149935.0234 | 0 | 100% | Finished | 133165.9844 | 133165.9844 | 100 | 50 | 100 | 100 | 112.5926 | 100
241 | Zelfdragend profilit glas | 2012-03-08 08:00 | 2012-03-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-03-12 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 95.1074 | 100
242 | Terrasbeplanking | 2012-04-05 08:00 | 2012-04-10 17:00 | 3d |  | 0 | 29478.8203 | 0 | 0 | 29478.8203 | 2012-04-02 08:00 | 3d | 29478.8203 | 0 | 0 | 12407.7998 | 0 | 41886.6201 | 0 | 100% | Finished | 29478.8203 | 29478.8203 | 100 | 100 | 100 | 100 | 142.0906 | 100
75 | DAKBEDEKKINGEN - resterende afdekkingen | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  |  | 7090.1001 |  |  | 7090.1001 |  | 25d | [5 empty] | 6677.9701 |  | 100% |  | 7090.1001 | 7090.1001
76 | Berging sporthal + luifel boven fietsstalling | 2012-04-13 08:00 | 2012-05-15 17:00 | 22d |  | 0 | 7090.1001 | 0 | 0 | 7090.1001 | 2012-04-19 08:00 | 25d | 7090.1001 | 0 | 0 | -412.13 | 0 | 6677.9701 | 0 | 100% | Finished | 7090.1001 | 7090.1001 | 100 | 113.6364 | 100 | 100 | 94.1872 | 100
77 | DAKBEDEKKINGSTOEBEHOREN | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  |  | 6767.8202 |  |  | 6767.8202 |  | 36d | [5 empty] | 6374.4202 |  | 100% |  | 6767.8202 | 6767.8202
78 | Dakrandprofielen | 2012-04-06 08:00 | 2012-04-27 17:00 | 15d |  | 0 | 4834.1602 | 0 | 0 | 4834.1602 | 2012-04-24 08:00 | 15d | 4834.1602 | 0 | 0 | -281 | 0 | 4553.1602 | 0 | 100% | Finished | 4834.1602 | 4834.1602 | 100 | 100 | 100 | 100 | 94.1872 | 100
79 | Valbeveiliging | 2012-04-20 08:00 | 2012-04-27 17:00 | 6d |  | 0 | 1933.66 | 0 | 0 | 1933.66 | 2012-03-23 08:00 | 6d | 1933.66 | 0 | 0 | -112.4 | 0 | 1821.26 | 0 | 100% | Finished | 1933.66 | 1933.66 | 100 | 100 | 100 | 100 | 94.1872 | 100
89 | BINNENSCHRIJNWERK | 2012-05-16 08:00 | 2012-06-29 17:00 | 31d |  |  | 39567.9688 |  |  | 39567.9688 |  | 30d | [5 empty] | 39603.4387 |  | 100% |  | 39567.9688 | 39567.9688
90 | Binnenschrijnwerk (deuren,…) | 2012-05-16 08:00 | 2012-06-14 17:00 | 20d |  | 0 | 35453.8789 | 0 | 0 | 35453.8789 | 2012-08-01 08:00 | 30d | 35453.8789 | 0 | 0 | 18.67 | 0 | 35472.5489 | 0 | 100% | Finished | 35453.8789 | 35453.8789 | 100 | 150 | 100 | 100 | 100.0527 | 100
91 | Akoestische voorzetwand | 2012-06-06 08:00 | 2012-06-29 17:00 | 18d |  | 0 | 4114.0898 | 0 | 0 | 4114.0898 | 2012-08-01 08:00 | 25d | 4114.0898 | 0 | 0 | 16.8 | 0 | 4130.8898 | 0 | 100% | Finished | 4114.0898 | 4114.0898 | 100 | 138.8889 | 100 | 100 | 100.4084 | 100
92 | BEGLAZING EN SPIEGELS | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  |  | 26881.5098 |  |  | 26881.5098 |  | 10d | [5 empty] | 25566.2998 |  | 100% |  | 26881.5098 | 26881.5098
93 | Spiegelwand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 26881.5098 | 0 | 0 | 26881.5098 | 2012-06-19 08:00 | 10d | 26881.5098 | 0 | 0 | -1315.21 | 0 | 25566.2998 | 0 | 100% | Finished | 26881.5098 | 26881.5098 | 100 | 100 | 100 | 100 | 95.1074 | 100
94 | IJZERWERK | 2012-06-12 08:00 | 2012-08-01 17:00 | 22d |  |  | 4571.21 |  |  | 4571.21 |  | 20d | [5 empty] | 4582.41 |  | 100% |  | 4571.21 | 4571.21
95 | Roosters / RVS gaasvulling | 2012-07-02 08:00 | 2012-08-01 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-09-05 08:00 | 8d | 1828.48 | 0 | 0 | 0 | 0 | 1828.48 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100 | 100
96 | Borstweringen en handgrepen | 2012-06-12 08:00 | 2012-06-27 17:00 | 12d |  | 0 | 2742.73 | 0 | 0 | 2742.73 | 2012-08-20 08:00 | 12d | 2742.73 | 0 | 0 | 11.2 | 0 | 2753.93 | 0 | 100% | Finished | 2742.73 | 2742.73 | 100 | 100 | 100 | 100 | 100.4084 | 100
97 | DEMONTEERBARE WANDEN | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  |  | 11507.1699 |  |  | 11507.1699 |  | 19d | [5 empty] | 11459.6499 |  | 100% |  | 11507.1699 | 11507.1699
98 | Beglaasde wand | 2012-06-15 08:00 | 2012-06-18 17:00 | 2d |  | 0 | 5376.2998 | 0 | 0 | 5376.2998 | 2012-09-12 08:00 | 2d | 5376.2998 | 0 | 0 | 0 | 0 | 5376.2998 | 0 | 100% | Finished | 5376.2998 | 5376.2998 | 100 | 100 | 100 | 100 | 100 | 100
99 | Sanitaire wanden | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 6130.8701 | 0 | 0 | 6130.8701 | 2012-08-20 08:00 | 12d | 6130.8701 | 0 | 0 | -47.52 | 0 | 6083.3501 | 0 | 100% | Finished | 6130.8701 | 6130.8701 | 100 | 240 | 100 | 100 | 99.2249 | 100
100 | BEPLEISTERINGEN EN GIPSKARTONPLATEN | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  |  | 55882.5703 |  |  | 55882.5703 |  | 26d | [5 empty] | 43167.8701 |  | 100% |  | 55882.5703 | 55882.5703
101 | Cementering / bepleistering | 2012-03-13 08:00 | 2012-04-18 17:00 | 26d |  | 0 | 55882.5703 | 0 | 0 | 55882.5703 | 2012-04-02 08:00 | 26d | 55882.5703 | 0 | 0 | -12714.7002 | 0 | 43167.8701 | 0 | 100% | Finished | 55882.5703 | 55882.5703 | 100 | 100 | 100 | 100 | 77.2475 | 100
102 | VERLAAGDE PLAFONDS | 2012-04-17 08:00 | 2012-07-02 17:00 | 52d |  |  | 24596.2197 |  |  | 24596.2197 |  | 52d | [5 empty] | 24536.7697 |  | 100% |  | 24596.2197 | 24596.2197
103 | Structuur verlaagde plafonds | 2012-04-17 08:00 | 2012-05-07 17:00 | 14d |  | 0 | 10760.8496 | 0 | 0 | 10760.8496 | 2012-06-18 08:00 | 14d | 10760.8496 | 0 | 0 | -26.01 | 0 | 10734.8396 | 0 | 100% | Finished | 10760.8496 | 10760.8496 | 100 | 100 | 100 | 100 | 99.7583 | 100
104 | Afwerken verlaagde plafonds | 2012-06-07 08:00 | 2012-07-02 17:00 | 18d |  | 0 | 13835.3701 | 0 | 0 | 13835.3701 | 2012-08-24 08:00 | 18d | 13835.3701 | 0 | 0 | -33.44 | 0 | 13801.9301 | 0 | 100% | Finished | 13835.3701 | 13835.3701 | 100 | 100 | 100 | 100 | 99.7583 | 100
105 | DEKVLOEREN EN TOEBEHOREN | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  |  | 26429.0898 |  |  | 26429.0898 |  | 25d | [5 empty] | 27569.3699 |  | 100% |  | 26429.0898 | 26429.0898
106 | Dekvloeren | 2012-03-28 08:00 | 2012-05-03 17:00 | 25d |  | 0 | 26429.0898 | 0 | 0 | 26429.0898 | 2012-05-10 08:00 | 25d | 26429.0898 | 0 | 0 | 1140.28 | 0 | 27569.3699 | 0 | 100% | Finished | 26429.0898 | 26429.0898 | 100 | 100 | 100 | 100 | 104.3145 | 100
107 | TEGELWERKEN | 2012-06-05 08:00 | 2012-06-18 17:00 | 10d |  |  | 10571.6396 |  |  | 10571.6396 |  | 10d | [5 empty] | 11027.7596 |  | 100% |  | 10571.6396 | 10571.6396
108 | Buiten | 2012-06-12 08:00 | 2012-06-18 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 2012-08-20 08:00 | 5d | 5285.8198 | 0 | 0 | 228.06 | 0 | 5513.8798 | 0 | 100% | Finished | 5285.8198 | 5285.8198 | 100 | 100 | 100 | 100 | 104.3146 | 100
109 | Binnen | 2012-06-05 08:00 | 2012-06-11 17:00 | 5d |  | 0 | 5285.8198 | 0 | 0 | 5285.8198 | 2012-08-13 08:00 | 5d | 5285.8198 | 0 | 0 | 228.06 | 0 | 5513.8798 | 0 | 100% | Finished | 5285.8198 | 5285.8198 | 100 | 100 | 100 | 100 | 104.3146 | 100
110 | VLOERBEKLEDINGEN | 2012-04-26 08:00 | 2012-06-19 17:00 | 36d |  |  | 82765.0089 |  |  | 82765.0089 |  | 62d | [5 empty] | 32030.2609 |  | 100% |  | 82765.0089 | 82765.0089
111 | Gietvloeren | 2012-04-26 08:00 | 2012-05-25 17:00 | 20d |  | 0 | 21143.2695 | 0 | 0 | 21143.2695 | 2012-06-11 08:00 | 25d | 21143.2695 | 0 | 0 | 912.22 | 0 | 22055.4895 | 0 | 100% | Finished | 21143.2695 | 21143.2695 | 100 | 125 | 100 | 100 | 104.3145 | 100
112 | Dansvloer | 2012-05-11 08:00 | 2012-05-18 17:00 | 5d |  | 0 | 10003.6396 | 0 | 0 | 10003.6396 | 2012-06-25 08:00 | 5d | 10003.6396 | 0 | 0 | -8856.1699 | 0 | 1147.4697 | 0 | 100% | Finished | 10003.6396 | 10003.6396 | 100 | 100 | 100 | 100 | 11.4705 | 100
264 | Plaatsen isolatie sporthal | 2012-06-04 08:00 | 2012-06-12 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-07-02 08:00 | 7d | 1599.92 | 0 | 0 | 1490.03 | 0 | 3089.9501 | 0 | 100% | Finished | 1599.92 | 1599.92 | 100 | 100 | 100 | 100 | 193.1315 | 100
113 | Sportvloer | 2012-05-14 08:00 | 2012-06-19 17:00 | 25d |  | 0 | 50018.1797 | 0 | 0 | 50018.1797 | 2012-08-22 08:00 | 25d | 50018.1797 | 0 | 0 | -44280.8281 | 0 | 5737.3516 | 0 | 100% | Finished | 50018.1797 | 50018.1797 | 100 | 100 | 100 | 100 | 11.4705 | 100
114 | MEUBILAIR | 2012-05-07 08:00 | 2012-06-26 17:00 | 35d |  |  | 3656.9601 |  |  | 3656.9601 |  | 10d | [5 empty] | 3671.8901 |  | 100% |  | 3656.9601 | 3656.9601
115 | Ophijsbare scheidingswand | 2012-05-07 08:00 | 2012-05-21 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-08-22 08:00 | 10d | 2285.6001 | 0 | 0 | 9.33 | 0 | 2294.9301 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 100.4082 | 100
116 | Meubilair | 2012-06-19 08:00 | 2012-06-26 17:00 | 6d |  | 0 | 1371.36 | 0 | 0 | 1371.36 | 2012-08-27 08:00 | 6d | 1371.36 | 0 | 0 | 5.6 | 0 | 1376.96 | 0 | 100% | Finished | 1371.36 | 1371.36 | 100 | 100 | 100 | 100 | 100.4084 | 100
117 | SCHILDERWERKEN | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  |  | 13634.25 |  |  | 13634.25 |  | 19d | [5 empty] | 13655.32 |  | 100% |  | 13634.25 | 13634.25
118 | Schilderwerk | 2012-06-01 08:00 | 2012-08-01 17:00 | 29d |  | 0 | 13634.25 | 0 | 0 | 13634.25 | 2012-08-22 08:00 | 19d | 13634.25 | 0 | 0 | 21.07 | 0 | 13655.32 | 0 | 100% | Finished | 13634.25 | 13634.25 | 100 | 65.5172 | 100 | 100 | 100.1545 | 100
119 | DIVERSE TOEBEHOREN | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  |  | 14488.25 |  |  | 14488.25 |  | 3d | [5 empty] | 14488.25 |  | 100% |  | 14488.25 | 14488.25
120 | Signalisatie | 2012-07-05 08:00 | 2012-07-30 17:00 | 3d |  | 0 | 14488.25 | 0 | 0 | 14488.25 | 2012-09-18 08:00 | 3d | 14488.25 | 0 | 0 | 0 | 0 | 14488.25 | 0 | 100% | Finished | 14488.25 | 14488.25 | 100 | 100 | 100 | 100 | 100 | 100
121 | OMGEVINGSWERKEN | 2011-04-29 08:00 | 2012-11-21 17:00 | 359d |  |  | 899608.939 |  |  | 899608.939 |  | 175d | [5 empty] | 915758.9489 |  | 100% |  | 899608.939 | 811201.2708
122 | Aanleg toegangsweg naar zwembad | 2012-01-10 08:00 | 2012-02-01 17:00 | 17d |  | 0 | 24822.4199 | 0 | 0 | 24822.4199 | 2011-12-01 08:00 | 17d | 24822.4199 | 0 | 0 | -1573 | 0 | 23249.4199 | 0 | 100% | Finished | 24822.4199 | 24822.4199 | 100 | 100 | 100 | 100 | 93.663 | 100
123 | Aanleg finse piste tussen parking en zwembad | 2012-02-10 08:00 | 2012-03-05 17:00 | 17d |  | 0 | 3885.53 | 0 | 0 | 3885.53 | 2011-12-01 08:00 | 17d | 3885.53 | 0 | 0 | 15.87 | 0 | 3901.4 | 0 | 100% | Finished | 3885.53 | 3885.53 | 100 | 100 | 100 | 100 | 100.4084 | 100
124 | Aanleg finse piste in bos | 2012-03-23 08:00 | 2012-04-05 17:00 | 10d |  | 0 | 2285.6001 | 0 | 0 | 2285.6001 | 2012-01-09 08:00 | 10d | 2285.6001 | 0 | 0 | 9.33 | 0 | 2294.9301 | 0 | 100% | Finished | 2285.6001 | 2285.6001 | 100 | 100 | 100 | 100 | 100.4082 | 100
125 | Aanleg finse piste rond voetbaldveld | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
126 | Drainageleiding rond nieuwe sporthal | 2012-05-24 08:00 | 2012-06-05 17:00 | 8d |  | 0 | 5185.0098 | 0 | 0 | 5185.0098 | 2011-12-01 08:00 | 8d | 5185.0098 | 0 | 0 | -3066.97 | 0 | 2118.0398 | 0 | 100% | Finished | 5185.0098 | 5185.0098 | 100 | 100 | 100 | 100 | 40.8493 | 100
127 | Planten bomen / haag rond parking | 2012-04-30 08:00 | 2012-05-10 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
243 | Afwerken teelaarde | 2012-06-06 08:00 | 2012-06-15 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-01-23 08:00 | 8d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 100 | 100 | 100 | 100.4085 | 100
244 | Opbraak scheidingsmuur met buren + funderingssleuf + metsen muur | 2011-04-29 08:00 | 2011-05-11 17:00 | 8d |  | 0 | 38626.6719 | 0 | 0 | 38626.6719 | 2012-02-13 08:00 | 20d | 38626.6719 | 0 | 0 | -3355.99 | 0 | 35270.6819 | 0 | 100% | Finished | 38626.6719 | 38626.6719 | 100 | 250 | 100 | 100 | 91.3117 | 100
245 | Uitvoering omnisportveld, plaatsen prefabstukken, fundering,… | 2012-11-08 08:00 | 2012-11-21 17:00 | 10d |  | 0 | 85207.8281 | 0 | 0 | 85207.8281 | 2012-03-12 08:00 | 10d | 85207.8281 | 0 | 0 | 8332.1104 | 0 | 93539.9385 | 0 | 100% | Finished | 85207.8281 | 0 | 100 | 100 | 100 | 100 | 109.7786 | 100
246 | Riolering voor kolken achter nieuwe sporthal | 2012-02-10 08:00 | 2012-02-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2011-12-01 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
247 | Riolering rond nieuwe sporthal + aansluiting vijver | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-03-26 08:00 | 15d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 187.5 | 100 | 100 | 100.4085 | 100
248 | Grondwerk rond sporthal | 2012-06-18 08:00 | 2012-06-27 17:00 | 8d |  | 0 | 214498.8438 | 0 | 0 | 214498.8438 | 2012-03-26 08:00 | 12d | 214498.8438 | 0 | 0 | -3890.1699 | 0 | 210608.6738 | 0 | 100% | Finished | 214498.8438 | 214498.8438 | 100 | 150 | 100 | 100 | 98.1864 | 100
249 | Plaatsen keerwanden (na akkoord), sleufgoot | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 112.5 | 100 | 100 | 100.4085 | 100
250 | Wegeniskoffer aan nieuwe sporthal kant zwembad | 2012-06-28 08:00 | 2012-07-30 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-12 08:00 | 6d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 75 | 100 | 100 | 100.4085 | 100
251 | Plaatsen boordstenen en afwerking wegkoffer achter nieuwe sporthal | 2011-05-12 08:00 | 2011-05-23 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-04-20 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
252 | Opbraak bestaande verharding van nieuwe sporthal nr ingang | 2012-07-31 08:00 | 2012-08-09 17:00 | 8d |  | 0 | 2880.76 | 0 | 0 | 2880.76 | 2012-04-20 08:00 | 8d | 2880.76 | 0 | 0 | 413.66 | 0 | 3294.42 | 0 | 100% | Finished | 2880.76 | 2880.76 | 100 | 100 | 100 | 100 | 114.3594 | 100
253 | Grondwerk uitgraving wegenis van nieuwe sporthal nr ingang | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 214560.4219 | 0 | 0 | 214560.4219 | 2012-05-03 08:00 | 9d | 214560.4219 | 0 | 0 | -3951.75 | 0 | 210608.6719 | 0 | 100% | Finished | 214560.4219 | 214560.4219 | 100 | 112.5 | 100 | 100 | 98.1582 | 100
254 | Pl riolering voor waterafvoer | 2012-08-10 08:00 | 2012-08-21 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-03 08:00 | 9d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 112.5 | 100 | 100 | 100.4085 | 100
255 | Fundering wegenis van sporthal nr ingang | 2012-08-22 08:00 | 2012-08-31 17:00 | 8d |  | 0 | 1828.48 | 0 | 0 | 1828.48 | 2012-05-16 08:00 | 10d | 1828.48 | 0 | 0 | 7.47 | 0 | 1835.95 | 0 | 100% | Finished | 1828.48 | 1828.48 | 100 | 125 | 100 | 100 | 100.4085 | 100
256 | Pl boordstenen voor paadje langs scheidingsmuur | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-01 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 1599.92 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
257 | Aanleg finse piste tussen nieuwe sporthal en zwembad | 2012-09-12 08:00 | 2012-09-20 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-06-15 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 1599.92 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
258 | Plaatsen betonstraatstenen | 2012-09-21 08:00 | 2012-11-01 17:00 | 30d |  | 0 | 58330.2695 | 0 | 0 | 58330.2695 | 2012-06-29 08:00 | 30d | 58330.2695 | 0 | 0 | 6671.98 | 0 | 65002.2495 | 0 | 100% | Finished | 58330.2695 | 58330.2695 | 100 | 100 | 100 | 100 | 111.4383 | 100
259 | Plaatsen betontegels | 2011-05-24 08:00 | 2011-06-01 17:00 | 7d |  | 0 | 6831.02 | 0 | 0 | 6831.02 | 2012-05-07 08:00 | 15d | 6831.02 | 0 | 0 | 21343.1895 | 0 | 28174.2095 | 0 | 100% | Finished | 6831.02 | 6831.02 | 100 | 214.2857 | 100 | 100 | 412.4451 | 100
260 | Opbraak wegenis zijkant bestaande sporthal/grondwerk/fundering | 2012-09-03 08:00 | 2012-09-11 17:00 | 7d |  | 0 | 188607.2344 | 0 | 0 | 188607.2344 | 2012-06-01 08:00 | 10d | 188607.2344 | 0 | 0 | -3048.48 | 0 | 185558.7544 | 0 | 100% | Finished | 188607.2344 | 188607.2344 | 100 | 142.8571 | 100 | 100 | 98.3837 | 100
261 | Plaatsen asfalt | 2012-09-21 08:00 | 2012-10-18 17:00 | 20d |  | 0 | 29202.8496 | 0 | 0 | 29202.8496 | 2012-06-29 08:00 | 20d | 29202.8496 | 0 | 0 | -1850.59 | 0 | 27352.2596 | 0 | 100% | Finished | 29202.8496 | 29202.8496 | 100 | 100 | 100 | 100 | 93.663 | 100
262 | Boomspiegels | 2012-10-19 08:00 | 2012-10-29 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-08-17 08:00 | 3d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 42.8571 | 100 | 100 | 100.4081 | 100
263 | Diverse acodrains plaatsen ( bij akkoord ) | 2012-10-30 08:00 | 2012-11-07 17:00 | 7d |  | 0 | 1599.92 | 0 | 0 | 1599.92 | 2012-08-22 08:00 | 10d | 1599.92 | 0 | 0 | 6.53 | 0 | 1606.45 | 0 | 100% | Finished | 1599.92 | 0 | 100 | 142.8571 | 100 | 100 | 100.4081 | 100
130 | WERKEN THV TECHNISCH LOKAAL ZWEMBAD | 2012-02-29 08:00 | 2012-04-18 17:00 | 35d |  |  | 386283.059 |  |  | 386283.059 |  | 35d | [5 empty] | 383185.069 |  | 100% |  | 386283.059 | 386283.059
131 | Afbraakwerken thv technisch lokaal | 2012-02-29 08:00 | 2012-03-06 17:00 | 5d |  | 0 | 1761.99 | 0 | 0 | 1761.99 | 2012-03-01 08:00 | 5d | 1761.99 | 0 | 0 | 297.02 | 0 | 2059.01 | 0 | 100% | Finished | 1761.99 | 1761.99 | 100 | 100 | 100 | 100 | 116.8571 | 100
132 | Structuurwerken technisch lokaal | 2012-03-09 08:00 | 2012-03-15 17:00 | 5d |  | 0 | 1142.8 | 0 | 0 | 1142.8 | 2012-03-12 08:00 | 5d | 1142.8 | 0 | 0 | 4.67 | 0 | 1147.47 | 0 | 100% | Finished | 1142.8 | 1142.8 | 100 | 100 | 100 | 100 | 100.4086 | 100
133 | Technische uitrusting technisch lokaal | 2012-03-16 08:00 | 2012-03-29 17:00 | 10d |  | 0 | 34647.6914 | 0 | 0 | 34647.6914 | 2012-03-19 08:00 | 10d | 34647.6914 | 0 | 0 | 17.69 | 0 | 34665.3814 | 0 | 100% | Finished | 34647.6914 | 34647.6914 | 100 | 100 | 100 | 100 | 100.0511 | 100
134 | Dakwerken thv technisch lokaal | 2012-03-30 08:00 | 2012-04-05 17:00 | 5d |  | 0 | 1611.39 | 0 | 0 | 1611.39 | 2012-04-02 08:00 | 5d | 1611.39 | 0 | 0 | -93.67 | 0 | 1517.72 | 0 | 100% | Finished | 1611.39 | 1611.39 | 100 | 100 | 100 | 100 | 94.187 | 100
135 | Ventilatieroosters | 2012-04-16 08:00 | 2012-04-18 17:00 | 3d |  | 0 | 347119.1875 | 0 | 0 | 347119.1875 | 2012-04-17 08:00 | 3d | 347119.1875 | 0 | 0 | -3323.7 | 0 | 343795.4875 | 0 | 100% | Finished | 347119.1875 | 347119.1875 | 100 | 100 | 100 | 100 | 99.0425 | 100
136 | TECHNIEKEN | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 594749.1602 |  |  | 594749.1602 |  | 109d | [5 empty] | 593362.8701 |  | 100% |  | 594749.1602 | 594749.1602
137 | SANITAIR / BRANDBESTRIJDING | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 270794.9531 |  |  | 270794.9531 |  | 109d | [5 empty] | 269455.4231 |  | 100% |  | 270794.9531 | 270794.9531
138 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 79701.2578 | 0 | 0 | 79701.2578 | 2012-03-01 08:00 | 65d | 79701.2578 | 0 | 0 | -617.71 | 0 | 79083.5478 | 0 | 100% | Finished | 79701.2578 | 79701.2578 | 100 | 100 | 100 | 100 | 99.225 | 100
139 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 74182.2734 | 0 | 0 | 74182.2734 | 2012-05-07 08:00 | 42d | 74182.2734 | 0 | 0 | -516.37 | 0 | 73665.9034 | 0 | 100% | Finished | 74182.2734 | 74182.2734 | 100 | 100 | 100 | 100 | 99.3039 | 100
140 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 116911.4219 | 0 | 0 | 116911.4219 | 2012-06-26 08:00 | 30d | 116911.4219 | 0 | 0 | -205.45 | 0 | 116705.9719 | 0 | 100% | Finished | 116911.4219 | 116911.4219 | 100 | 120 | 100 | 100 | 99.8243 | 100
141 | HVAC | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 109d | [5 empty] | 139148.1781 |  | 100% |  | 139110.0781 | 139110.0781
142 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 100.4084 | 100
143 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 100% | Finished | 32282.5391 | 32282.5391 | 100 | 100 | 100 | 100 | 99.7583 | 100
144 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 30d | 91971.1094 | 0 | 0 | 55.46 | 0 | 92026.5694 | 0 | 100% | Finished | 91971.1094 | 91971.1094 | 100 | 120 | 100 | 100 | 100.0603 | 100
145 | ELEKTRICITEIT | 2012-02-08 08:00 | 2012-07-06 17:00 | 104d |  |  | 139110.0781 |  |  | 139110.0781 |  | 109d | [5 empty] | 139148.1781 |  | 100% |  | 139110.0781 | 139110.0781
146 | Werken in ruwbouwfase | 2012-02-08 08:00 | 2012-05-10 17:00 | 65d |  | 0 | 14856.4297 | 0 | 0 | 14856.4297 | 2012-03-01 08:00 | 65d | 14856.4297 | 0 | 0 | 60.67 | 0 | 14917.0997 | 0 | 100% | Finished | 14856.4297 | 14856.4297 | 100 | 100 | 100 | 100 | 100.4084 | 100
147 | Opbouw en inbouw in lichte wanden en plafonds | 2012-04-12 08:00 | 2012-06-13 17:00 | 42d |  | 0 | 32282.5391 | 0 | 0 | 32282.5391 | 2012-05-07 08:00 | 42d | 32282.5391 | 0 | 0 | -78.03 | 0 | 32204.5091 | 0 | 100% | Finished | 32282.5391 | 32282.5391 | 100 | 100 | 100 | 100 | 99.7583 | 100
148 | Plaatsen toestellen en afwerking | 2012-06-04 08:00 | 2012-07-06 17:00 | 25d |  | 0 | 91971.1094 | 0 | 0 | 91971.1094 | 2012-06-26 08:00 | 30d | 91971.1094 | 0 | 0 | 55.46 | 0 | 92026.5694 | 0 | 100% | Finished | 91971.1094 | 91971.1094 | 100 | 120 | 100 | 100 | 100.0603 | 100
149 | LIFTEN | 2012-05-10 08:00 | 2012-06-15 17:00 | 25d |  |  | 45734.0508 |  |  | 45734.0508 |  | 25d | [5 empty] | 45611.0908 |  | 100% |  | 45734.0508 | 45734.0508
150 | Werken in de schachten en machinekamers | 2012-05-10 08:00 | 2012-06-01 17:00 | 15d |  | 0 | 18175.6309 | 0 | 0 | 18175.6309 | 2012-05-29 08:00 | 15d | 18175.6309 | 0 | 0 | -73.78 | 0 | 18101.8509 | 0 | 100% | Finished | 18175.6309 | 18175.6309 | 100 | 100 | 100 | 100 | 99.5941 | 100
151 | Afwerken liftkooien en deuren | 2012-06-04 08:00 | 2012-06-15 17:00 | 10d |  | 0 | 27558.4199 | 0 | 0 | 27558.4199 | 2012-06-19 08:00 | 10d | 27558.4199 | 0 | 0 | -49.18 | 0 | 27509.2399 | 0 | 100% | Finished | 27558.4199 | 27558.4199 | 100 | 100 | 100 | 100 | 99.8215 | 100
152 | TESTEN | 2012-03-29 08:00 | 2012-08-22 17:00 | 86d |  |  | 1142.8 |  |  | 1142.8 |  | 88d | [5 empty] | 2657.07 |  | 100% |  | 1142.8 | 1142.8
153 | Indicatieve blowerdoortest | 2012-03-29 08:00 | 2012-03-30 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-04-19 08:00 | 2d | 457.12 | 0 | 0 | 1514.27 | 0 | 1971.39 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 431.2631 | 100
154 | Finale blowerdoortest | 2012-08-21 08:00 | 2012-08-22 17:00 | 2d |  | 0 | 457.12 | 0 | 0 | 457.12 | 2012-09-12 08:00 | 2d | 457.12 | 0 | 0 | 0 | 0 | 457.12 | 0 | 100% | Finished | 457.12 | 457.12 | 100 | 100 | 100 | 100 | 100 | 100
155 | Thermografische onderzoek | 2012-08-21 08:00 | 2012-08-21 17:00 | 1d |  | 0 | 228.56 | 0 | 0 | 228.56 | 2012-09-12 08:00 | 1d | 228.56 | 0 | 0 | 0 | 0 | 228.56 | 0 | 100% | Finished | 228.56 | 228.56 | 100 | 100 | 100 | 100 | 100 | 100
156 | EINDE VAN DE WERKEN EN OPLEVERING | 2012-07-30 08:00 | 2012-09-03 17:00 | 26d |  |  | 17500.3502 |  |  | 17500.3502 |  | 21d | [5 empty] | 20951.5502 |  | 100% |  | 17500.3502 | 17500.3502
157 | Opmaak van de plaatsbeschrijving na de werken | 2012-08-30 08:00 | 2012-08-31 17:00 | 2d |  | 0 | 450.5 | 0 | 0 | 450.5 | 2012-09-21 08:00 | 2d | 450.5 | 0 | 0 | 0 | 0 | 450.5 | 0 | 100% | Finished | 450.5 | 450.5 | 100 | 100 | 100 | 100 | 100 | 100
158 | Opbraak van werfuitrustingen | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 735.65 | 0 | 0 | 735.65 | 2012-09-18 08:00 | 3d | 735.65 | 0 | 0 | 0 | 0 | 735.65 | 0 | 100% | Finished | 735.65 | 735.65 | 100 | 100 | 100 | 100 | 100 | 100
159 | Voorbereiding oplevering | 2012-08-27 08:00 | 2012-08-29 17:00 | 3d |  | 0 | 675.75 | 0 | 0 | 675.75 | 2012-09-07 08:00 | 10d | 675.75 | 0 | 0 | 0 | 0 | 675.75 | 0 | 100% | Finished | 675.75 | 675.75 | 100 | 333.3333 | 100 | 100 | 100 | 100
160 | Eindopkuis | 2012-07-30 08:00 | 2012-08-31 17:00 | 25d |  | 0 | 15413.2002 | 0 | 0 | 15413.2002 | 2012-08-28 08:00 | 20d | 15413.2002 | 0 | 0 | 3451.2 | 0 | 18864.4001 | 0 | 100% | Finished | 15413.2002 | 15413.2002 | 100 | 80 | 100 | 100 | 122.3912 | 100
161 | Oplevering | 2012-09-03 08:00 | 2012-09-03 17:00 | 1d |  | 0 | 225.25 | 0 | 0 | 225.25 | 2012-09-25 08:00 | 1d | 225.25 | 0 | 0 | 0 | 0 | 225.25 | 0 | 100% | Finished | 225.25 | 225.25 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2011-08-15
1:00 - 2:00 | No | Tuesday | Yes | 2011-10-31
2:00 - 3:00 | No | Wednesday | Yes | 2011-11-01
3:00 - 4:00 | No | Thursday | Yes | 2011-11-11
4:00 - 5:00 | No | Friday | Yes | 2011-11-28
5:00 - 6:00 | No | Saturday | No | 2011-11-29
6:00 - 7:00 | No | Sunday | No | 2011-11-30
7:00 - 8:00 | No |  |  | 2011-12-26
8:00 - 9:00 | Yes |  |  | 2011-12-27
9:00 - 10:00 | Yes |  |  | 2011-12-28
10:00 - 11:00 | Yes |  |  | 2011-12-29
11:00 - 12:00 | Yes |  |  | 2011-12-30
12:00 - 13:00 | No |  |  | 2012-04-09
13:00 - 14:00 | Yes |  |  | 2012-05-01
14:00 - 15:00 | Yes |  |  | 2012-05-17
15:00 - 16:00 | Yes |  |  | 2012-05-28
16:00 - 17:00 | Yes |  |  | 2012-07-09
17:00 - 18:00 | No |  |  | 2012-07-10
18:00 - 19:00 | No |  |  | 2012-07-11
19:00 - 20:00 | No |  |  | 2012-07-12
20:00 - 21:00 | No |  |  | 2012-07-13
21:00 - 22:00 | No |  |  | 2012-07-16
22:00 - 23:00 | No |  |  | 2012-07-17
23:00 - 0:00 | No |  |  | 2012-07-18
2012-07-19
2012-07-20
Generated by PMConverter v1.1.3 |  |  |  | 2012-07-23
2012-07-24
2012-07-25
2012-07-26
2012-07-27
2011-05-02
2011-06-02
2011-06-03
2011-06-13
2011-07-11
2011-07-12
2011-07-13
2011-07-14
2011-07-15
2011-07-18
2011-07-19
2011-07-20
2011-07-21
2011-07-22
2011-07-25
2011-07-26
2011-07-27
2011-07-28
2011-07-29

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
11/08, 2011 | 2011-04-29 08:00 | 2011-08-11 17:00 | 222522.9083 | 433762.439 | 433762.439 | 2011-08-12 09:00 | 211239.5308 | 194.9% | 0 | 100% | 1h | 100.2% | 89.18% | 2012-11-02 09:00 | 2012-02-24 09:00 | 2012-02-24 09:00 | 2012-09-07 16:00 | 2012-02-24 09:00 | 2012-02-24 09:00 | 2012-11-21 16:00 | 2012-11-21 10:00 | 2012-11-21 10:00 | 5480518.9127 | 5480518.9127 | 3022780.8205 | 5469278.9205 | 3022780.8205 | 5469278.9205 | 4675237.9592 | 5478266.9017 | 1.0022 | 1 | 1.9493 | 0.89185 | 0.125 | 1 | 1 | 1.0022 | 1
31/08, 2011 | 2011-08-11 17:00 | 2011-08-31 17:00 | 556096.5084 | 500660.0409 | 477009.2202 | 2011-08-30 17:00 | -55436.4675 | 90.03% | 23650.8207 | 105% | -1d | 98.55% | 90.05% | 2012-11-27 14:00 | 2013-01-16 15:00 | 2012-12-20 16:00 | 2012-11-30 16:00 | 2013-01-16 15:00 | 2012-12-26 09:00 | 2012-11-22 17:00 | 2012-11-29 10:00 | 2012-11-09 11:00 | 5456868.092 | 5221623.1362 | 6008271.7627 | 5530101.3107 | 5746978.8937 | 5291396.8703 | 5360528.6323 | 5280268.4413 | 0.98551 | 1.0496 | 0.90031 | 0.90049 | -1 | 1.0496 | 1 | 0.98551 | 1
02/09, 2011 | 2011-08-31 17:00 | 2011-09-02 17:00 | 556801.3083 | 547862.8495 | 524326.9788 | 2011-08-30 17:00 | -8938.4589 | 98.39% | 23535.8707 | 104.5% | -3d | 95.77% | 90.05% | 2012-11-22 14:00 | 2012-11-29 16:00 | 2012-11-08 09:00 | 2012-11-23 09:00 | 2012-11-29 16:00 | 2012-11-13 10:00 | 2012-11-26 17:00 | 2012-12-13 16:00 | 2012-11-26 15:00 | 5456983.042 | 5245078.9946 | 5537460.0142 | 5674600.2212 | 5322098.7227 | 5453347.4659 | 5300794.5904 | 5325154.6446 | 0.95775 | 1.0449 | 0.98395 | 0.90049 | -3 | 1.0449 | 1 | 0.95775 | 1
30/09, 2011 | 2011-09-02 17:00 | 2011-09-30 17:00 | 716853.7901 | 935376.1057 | 929878.4556 | 2011-10-25 09:00 | 218522.3156 | 130.5% | 5497.65 | 100.6% | 16d 1h | 117.7% | 92.59% | 2012-11-01 14:00 | 2012-07-06 09:00 | 2012-07-04 12:00 | 2012-10-15 10:00 | 2012-07-06 09:00 | 2012-07-04 17:00 | 2012-10-30 16:00 | 2012-09-06 17:00 | 2012-09-05 15:00 | 5475021.2626 | 5448307.2976 | 4413186.2161 | 4790863.2438 | 4392713.1604 | 4768170.4007 | 5194827.6118 | 5299496.5866 | 1.1772 | 1.0059 | 1.3048 | 0.92593 | 16.125 | 1.0059 | 1 | 1.1772 | 1
31/10, 2011 | 2011-09-30 17:00 | 2011-10-31 17:00 | 1010196.707 | 1017323.6837 | 1016558.1937 | 2011-11-09 09:00 | 7126.9767 | 100.7% | 765.4901 | 100.1% | 5d 1h | 104.6% | 95.11% | 2012-11-21 12:00 | 2012-11-19 12:00 | 2012-11-19 10:00 | 2012-11-21 10:00 | 2012-11-19 12:00 | 2012-11-19 10:00 | 2012-11-14 16:00 | 2012-10-31 09:00 | 2012-10-30 17:00 | 5479753.4226 | 5476395.0701 | 5448486.0009 | 5282777.0993 | 5445151.1757 | 5279566.9625 | 5470785.1714 | 5436278.1781 | 1.0462 | 1.0008 | 1.0071 | 0.95106 | 5.125 | 1.0008 | 1 | 1.0462 | 1
30/11, 2011 | 2011-10-31 17:00 | 2011-11-30 17:00 | 1225065.2655 | 1243036.0615 | 1233100.8019 | 2011-12-05 09:00 | 17970.796 | 101.5% | 9935.2596 | 100.8% | 2d 1h | 101.7% | 96.08% | 2012-11-20 16:00 | 2012-11-14 15:00 | 2012-11-09 17:00 | 2012-11-20 09:00 | 2012-11-14 15:00 | 2012-11-12 17:00 | 2012-11-19 16:00 | 2012-11-14 09:00 | 2012-11-12 11:00 | 5470583.6531 | 5436714.5696 | 5409321.601 | 5401383.6449 | 5375942.1689 | 5368067.6589 | 5431207.2651 | 5429600.5506 | 1.0166 | 1.0081 | 1.0147 | 0.9608 | 2.125 | 1.0081 | 1 | 1.0166 | 1
08/12, 2011 | 2011-11-30 17:00 | 2011-12-08 17:00 | 1293750.6433 | 1278757.5012 | 1267876.4316 | 2011-12-02 17:00 | -14993.1421 | 98.84% | 10881.0696 | 100.9% | -4d | 97.01% | 95.86% | 2012-11-22 17:00 | 2012-11-28 10:00 | 2012-11-23 09:00 | 2012-11-23 12:00 | 2012-11-28 10:00 | 2012-11-26 10:00 | 2012-11-27 17:00 | 2012-12-06 17:00 | 2012-12-04 17:00 | 5469637.8431 | 5433884.6543 | 5518902.544 | 5598922.8096 | 5482730.1572 | 5562069.5227 | 5450615.0909 | 5465878.331 | 0.97015 | 1.0086 | 0.98841 | 0.95862 | -4 | 1.0086 | 1 | 0.97015 | 1
09/12, 2011 | 2011-12-08 17:00 | 2011-12-09 17:00 | 1383558.1199 | 1278757.5012 | 1267876.4316 | 2011-12-02 17:00 | -104800.6187 | 92.43% | 10881.0696 | 100.9% | -5d | 96.3% | 95.86% | 2012-11-30 16:00 | 2013-01-02 11:00 | 2012-12-28 09:00 | 2012-12-06 10:00 | 2013-01-02 11:00 | 2012-12-31 10:00 | 2012-11-28 17:00 | 2012-12-11 15:00 | 2012-12-07 15:00 | 5469637.8431 | 5433884.6543 | 5813993.3561 | 5631244.0512 | 5775310.0134 | 5594115.7398 | 5504734.8672 | 5471915.2137 | 0.96296 | 1.0086 | 0.92425 | 0.95862 | -5 | 1.0086 | 1 | 0.96296 | 1
16/12, 2011 | 2011-12-09 17:00 | 2011-12-16 17:00 | 1383558.1199 | 1368564.9778 | 1357684.7982 | 2011-12-08 17:00 | -14993.1421 | 98.92% | 10880.1796 | 100.8% | -6d | 95.71% | 96.08% | 2012-11-22 17:00 | 2012-11-27 16:00 | 2012-11-22 17:00 | 2012-11-23 12:00 | 2012-11-27 16:00 | 2012-11-26 09:00 | 2012-11-29 17:00 | 2012-12-14 09:00 | 2012-12-12 10:00 | 5469638.7331 | 5436948.4348 | 5514686.729 | 5653756.0734 | 5481638.2963 | 5619602.0305 | 5452262.6204 | 5478541.4693 | 0.95714 | 1.008 | 0.98916 | 0.9608 | -6 | 1.008 | 1 | 0.95714 | 1
31/12, 2011 | 2011-12-16 17:00 | 2011-12-31 17:00 | 1473365.5964 | 1458372.4543 | 1443590.0747 | 2011-12-20 17:00 | -14993.1421 | 98.98% | 14782.3796 | 101% | -3d | 97.93% | 96.33% | 2012-11-22 17:00 | 2012-11-27 15:00 | 2012-11-21 17:00 | 2012-11-23 12:00 | 2012-11-27 15:00 | 2012-11-23 12:00 | 2012-11-26 17:00 | 2012-12-03 14:00 | 2012-11-29 11:00 | 5465736.533 | 5424967.1839 | 5507087.1587 | 5550711.4582 | 5465898.6706 | 5509080.7848 | 5441124.5688 | 5449496.2748 | 0.97931 | 1.0102 | 0.98982 | 0.96334 | -3 | 1.0102 | 1 | 0.97931 | 1
31/01, 2012 | 2011-12-31 17:00 | 2012-01-31 17:00 | 1672259.4431 | 1944309.5203 | 1896956.5809 | 2012-02-15 09:00 | 272050.0771 | 116.3% | 47352.9394 | 102.5% | 10d 1h | 106.1% | 91.93% | 2012-10-29 09:00 | 2012-09-12 15:00 | 2012-09-03 10:00 | 2012-10-15 16:00 | 2012-09-12 15:00 | 2012-09-07 11:00 | 2012-11-07 16:00 | 2012-10-24 12:00 | 2012-10-18 10:00 | 5433165.9733 | 5347042.9011 | 4938375.3918 | 5231025.5634 | 4864302.7614 | 5149825.5462 | 5256753.4729 | 5323197.9594 | 1.0606 | 1.025 | 1.1627 | 0.91935 | 10.125 | 1.025 | 1 | 1.0606 | 1
29/02, 2012 | 2012-01-31 17:00 | 2012-02-29 17:00 | 2206828.5316 | 2144138.2937 | 2124144.4423 | 2012-02-22 17:00 | -62690.2379 | 97.16% | 19993.8514 | 100.9% | -5d | 97.34% | 93.71% | 2012-11-28 09:00 | 2012-12-06 12:00 | 2012-11-30 17:00 | 2012-11-29 11:00 | 2012-12-06 12:00 | 2012-12-04 15:00 | 2012-11-28 17:00 | 2012-12-05 15:00 | 2012-12-04 09:00 | 5460525.0613 | 5429413.6827 | 5558074.0371 | 5551683.0017 | 5526053.0252 | 5519721.5855 | 5454368.6396 | 5453164.6649 | 0.9734 | 1.0094 | 0.97159 | 0.93714 | -5 | 1.0094 | 1 | 0.9734 | 1
15/03, 2012 | 2012-02-29 17:00 | 2012-03-15 17:00 | 2444846.728 | 3052817.2978 | 3028512.459 | 2012-04-05 09:00 | 607970.5698 | 124.9% | 24304.8388 | 100.8% | 14d 1h | 107.1% | 88.69% | 2012-09-27 09:00 | 2012-08-14 12:00 | 2012-08-10 10:00 | 2012-09-13 12:00 | 2012-08-14 12:00 | 2012-08-13 15:00 | 2012-11-01 16:00 | 2012-10-19 10:00 | 2012-10-18 09:00 | 5456214.0739 | 5436886.0596 | 4972735.7029 | 5295316.5475 | 4957256.8754 | 5277269.5101 | 5327134.64 | 5407174.9705 | 1.071 | 1.008 | 1.2487 | 0.88691 | 14.125 | 1.008 | 1 | 1.071 | 1
31/03, 2012 | 2012-03-15 17:00 | 2012-03-31 17:00 | 3043593.2877 | 3538728.7148 | 3494943.7461 | 2012-04-12 09:00 | 495135.4271 | 116.3% | 43784.9688 | 101.3% | 7d 1h | 103.4% | 87.3% | 2012-10-08 14:00 | 2012-09-12 15:00 | 2012-09-06 17:00 | 2012-10-04 16:00 | 2012-09-12 15:00 | 2012-09-11 12:00 | 2012-11-12 16:00 | 2012-11-06 10:00 | 2012-11-02 12:00 | 5436733.9439 | 5412708.021 | 5165040.577 | 5373013.7129 | 5144376.3375 | 5349776.2054 | 5357467.3369 | 5404635.4898 | 1.0339 | 1.0125 | 1.1627 | 0.87297 | 7.125 | 1.0125 | 1 | 1.0339 | 1
30/04, 2012 | 2012-03-31 17:00 | 2012-04-30 17:00 | 3964948.002 | 4207920.9474 | 4329939.7159 | 2012-05-16 09:00 | 242972.9454 | 106.1% | -122018.7685 | 97.18% | 10d 1h | 104.4% | 91.76% | 2012-10-31 09:00 | 2012-10-24 10:00 | 2012-11-07 09:00 | 2012-11-01 16:00 | 2012-10-24 10:00 | 2012-10-29 11:00 | 2012-11-07 16:00 | 2012-10-31 16:00 | 2012-11-06 09:00 | 5602537.6811 | 5639439.7139 | 5529055.5792 | 5548877.9023 | 5563826.822 | 5584223.9409 | 5615766.4598 | 5620266.5778 | 1.044 | 0.97182 | 1.0613 | 0.91761 | 10.125 | 0.97182 | 1 | 1.044 | 1
31/05, 2012 | 2012-04-30 17:00 | 2012-05-31 17:00 | 4247568.795 | 4619140.6014 | 4695563.0519 | 2012-06-12 09:00 | 371571.8064 | 108.7% | -76422.4505 | 98.37% | 7d 1h | 102.8% | 88.39% | 2012-10-18 14:00 | 2012-10-12 09:00 | 2012-10-19 14:00 | 2012-10-23 09:00 | 2012-10-12 09:00 | 2012-10-15 12:00 | 2012-11-12 16:00 | 2012-11-07 17:00 | 2012-11-09 15:00 | 5556941.3632 | 5571192.6378 | 5487650.5745 | 5533072.3482 | 5500755.4515 | 5546928.7164 | 5553103.5503 | 5563293.4694 | 1.0285 | 0.98372 | 1.0875 | 0.8839 | 7.125 | 0.98372 | 1 | 1.0285 | 1
30/06, 2012 | 2012-05-31 17:00 | 2012-06-30 17:00 | 4857170.1488 | 5295682.1241 | 5343006.7048 | 2012-09-03 09:00 | 438511.9753 | 109% | -47324.5806 | 99.11% | 30d 1h | 111.1% | 96.57% | 2012-10-12 10:00 | 2012-10-11 10:00 | 2012-10-16 10:00 | 2012-10-18 12:00 | 2012-10-11 10:00 | 2012-10-11 15:00 | 2012-10-10 16:00 | 2012-10-03 09:00 | 2012-10-03 12:00 | 5527843.4933 | 5529495.2774 | 5512537.9777 | 5509352.1417 | 5514052.9849 | 5510838.6788 | 5525837.7564 | 5525085.6101 | 1.1112 | 0.99114 | 1.0903 | 0.96575 | 30.125 | 0.99114 | 1 | 1.1112 | 1
31/07, 2012 | 2012-06-30 17:00 | 2012-07-31 17:00 | 4891780.839 | 5297282.0442 | 5308149.8729 | 2012-09-03 09:00 | 405501.2052 | 108.3% | -10867.8287 | 99.8% | 23d 1h | 108.3% | 96.6% | 2012-10-16 12:00 | 2012-10-15 12:00 | 2012-10-16 10:00 | 2012-10-19 17:00 | 2012-10-15 12:00 | 2012-10-15 14:00 | 2012-10-19 16:00 | 2012-10-15 11:00 | 2012-10-15 12:00 | 5491386.7414 | 5491762.6675 | 5477360.1575 | 5477315.0018 | 5477707.3069 | 5477662.0586 | 5488689.307 | 5488679.0239 | 1.0832 | 0.99795 | 1.0829 | 0.96605 | 23.125 | 0.99795 | 1 | 1.0832 | 1
31/08, 2012 | 2012-07-31 17:00 | 2012-08-31 17:00 | 5112545.8008 | 5456053.0529 | 5426562.1434 | 2012-11-08 09:00 | 343507.252 | 106.7% | 29490.9095 | 100.5% | 48d 1h | 116% | 99.55% | 2012-10-22 12:00 | 2012-10-22 11:00 | 2012-10-18 14:00 | 2012-10-24 15:00 | 2012-10-22 11:00 | 2012-10-22 10:00 | 2012-09-14 16:00 | 2012-09-13 12:00 | 2012-09-13 12:00 | 5451028.0032 | 5450895.761 | 5449487.6589 | 5447655.5163 | 5449363.7425 | 5447541.5029 | 5450600.4706 | 5450170.4462 | 1.1599 | 1.0054 | 1.0672 | 0.99554 | 48.125 | 1.0054 | 1 | 1.1599 | 1
30/09, 2012 | 2012-08-31 17:00 | 2012-09-30 17:00 | 5392111.2444 | 5480518.9127 | 5451028.0032 | 2012-11-08 09:00 | 88407.6682 | 101.6% | 29490.9095 | 100.5% | 28d 1h | 108.8% | 100% | 2012-11-14 10:00 | 2012-11-14 10:00 | 2012-11-12 10:00 | 2012-11-14 15:00 | 2012-11-14 10:00 | 2012-11-13 17:00 | 2012-10-12 16:00 | 2012-10-12 09:00 | 2012-10-11 17:00 | 5451028.0032 | 5451028.0032 | 5451028.0032 | 5451028.0032 | 5451028.0032 | 5451028.0032 | 5451028.0032 | 5451028.0032 | 1.0876 | 1.0054 | 1.0164 | 1 | 28.125 | 1.0054 | 1 | 1.0876 | 1