## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Office Finishing Works (5) | 1 |  |  | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 | 224.375
1 | Vaste plafonds | 1.1 |  | FS17;SS4;SS6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 | 122.375
2 | Metalen plafonds | 1.2 |  | FS17;SS4;SS6 | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 | 122.375
4 | Verplaatsbare wanden (1) | 1.3 | 1SS;2SS |  | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 | 210.375
6 | Gipswanden | 1.4 | 1SS;2SS | FF9;FS10 | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 29.375
9 | Zuivere OA (1) | 1.5 | 6FF |  | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 | 0.375
10 | Démontage plafonds | 1.6 | 6FS | FS12 | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 8.375
12 | Uitregelen verhoogde vloer | 1.7 | 10FS | FS11;FS21;FS3 | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2.375
11 | Plaatsen tapijt | 1.8 | 12FS | FS13 | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 | 6.375
21 | Zuivere OA (2) | 1.9 | 12FS |  | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 | 92.375
13 | Plaatsen meubilair | 1.10 | 11FS | FS14;FS16 | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 | 4.375
14 | Leveren en plaatsen glas | 1.11 | 13FS | FS17 | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 | 0.375
3 | Akoestische dammen | 1.12 | 12FS | FS20;FS5;FS7;FS8 | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 1.375
20 | Verplaatsbare wanden (2) | 1.13 | 3FS | FS17;FS15;FS22 | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 | 10.375
5 | Verplaatsbare wanden (3) | 1.14 | 3FS | FS17;FS15;FS22 | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 | 10.375
7 | Deuren | 1.15 | 3FS | FS17;FS15;FS22 | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 4.375
8 | Schrijnwerk diversen | 1.16 | 3FS | FS17;FS15;FS22 | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 | 4.375
17 | Schilderwerken | 1.17 | 14FS;1FS;2FS;20FS;5FS;7FS;8FS | SS19 | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 | 56.375
19 | Bijkomende werken | 1.18 | 17SS |  | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 | 2.375
15 | Afwerkingen | 1.19 | 20FS;5FS;7FS;8FS | SS18 | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 98.375
22 | Diversen | 1.20 | 20FS;5FS;7FS;8FS |  | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 | 106.375
16 | Aanpassingswerken meubilair | 1.21 | 13FS |  | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 | 84.375
18 | Verplaatsen versteviging schermen | 1.22 | 15SS |  | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 | 4.375
23 | MEERWERKEN | 1.23 |  |  | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 0.041667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Office Finishing Works (5) | 1288h |  |  |  |  | 99 | 100 | 101
1 | Vaste plafonds | 712h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Metalen plafonds | 712h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Verplaatsbare wanden (1) | 1208h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Gipswanden | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Zuivere OA (1) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Démontage plafonds | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Uitregelen verhoogde vloer | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Plaatsen tapijt | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Zuivere OA (2) | 536h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Plaatsen meubilair | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Leveren en plaatsen glas | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Akoestische dammen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Verplaatsbare wanden (2) | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Verplaatsbare wanden (3) | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Deuren | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Schrijnwerk diversen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Schilderwerken | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Bijkomende werken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Afwerkingen | 568h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Diversen | 616h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Aanpassingswerken meubilair | 488h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Verplaatsen versteviging schermen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | MEERWERKEN | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-06-30 18:00 |  | TP Name | periode 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (5) | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 |  | 21d | [5 empty] | 27993.2196 |  | 8% |  | 19535.4351 | 58945.7991
1 | Vaste plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 |  | 0 | 0 | 2128.88 | 89d | 0 | 0 | 0 | 2128.88 | 0% | Not Started | 0 | 1052.48 | 100 |  | 0 | 100 |  | 0
2 | Metalen plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 |  | 0 | 0 | 19508.7997 | 89d | 0 | 0 | 0 | 19508.7997 | 0% | Not Started | 0 | 9644.7999 | 100 |  | 0 | 100 |  | 0
4 | Verplaatsbare wanden (1) | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 |  | 0 | 0 | 37641.2798 | 151d | 0 | 0 | 0 | 37641.2798 | 0% | Not Started | 0 | 8475.52 | 100 |  | 0 | 100 |  | 0
6 | Gipswanden | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 2012-06-01 08:00 | 21d | 34539.1194 | 98683.1982 | 60d | -19386.0098 | 0 | 15153.1096 | 98683.1982 | 25.93% | Started | 9380.9952 | 36183.8394 | 100 | 95.4545 | 25.9259 | 100 | 41.8781 | 25.9259
9 | Zuivere OA (1) | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 |  | 0 | 0 | 1079.36 | 1d | 0 | 0 | 0 | 1079.36 | 0% | Not Started | 0 | 1079.36 | 100 |  | 0 | 100 |  | 0
10 | Démontage plafonds | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 2012-06-14 08:00 | 7d | 2508.8 | 0 | 0 | -231.93 | 0 | 2276.87 | 0 | 100% | Finished | 2508.8 | 2508.8 | 100 | 100 | 100 | 100 | 90.7553 | 100
12 | Uitregelen verhoogde vloer | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 |  | 0 | 0 | 1800 | 3d | 0 | 0 | 0 | 1800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Plaatsen tapijt | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 |  | 0 | 0 | 27162.3999 | 5d | 0 | 0 | 0 | 27162.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Zuivere OA (2) | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 |  | 0 | 0 | 20067.8393 | 67d | 0 | 0 | 0 | 20067.8393 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Plaatsen meubilair | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 |  | 0 | 0 | 36023.0391 | 3d | 0 | 0 | 0 | 36023.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Leveren en plaatsen glas | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 |  | 0 | 0 | 180 | 1d | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Akoestische dammen | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 2012-06-28 08:00 | 2d | 1674.08 | 0 | 0 | -154.58 | 0 | 1519.5 | 0 | 100% | Finished | 1674.08 | 0 | 100 | 100 | 100 | 100 | 90.7663 | 100
20 | Verplaatsbare wanden (2) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 |  | 0 | 0 | 4926.2399 | 9d | 0 | 0 | 0 | 4926.2399 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Verplaatsbare wanden (3) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 |  | 0 | 0 | 619.2 | 9d | 0 | 0 | 0 | 619.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Deuren | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 2012-06-29 08:00 | 1d | 2086.3999 | 4172.7998 | 2d | -662.52 | 0 | 1423.8799 | 4172.7998 | 33.33% | Started | 2086.4 | 0 | 100 | 33.3333 | 33.3333 | 100 | 22.7486 | 33.3333
8 | Schrijnwerk diversen | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 |  | 0 | 0 | 1963.92 | 3d | 0 | 0 | 0 | 1963.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Schilderwerken | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 |  | 0 | 0 | 8537.8402 | 41d | 0 | 0 | 0 | 8537.8402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Bijkomende werken | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 |  | 0 | 0 | 16618.5601 | 3d | 0 | 0 | 0 | 16618.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Afwerkingen | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 2012-06-01 08:00 | 21d | 3884.1601 | 9248.0003 | 50d | 2019.92 | 0 | 5904.0802 | 9248.0003 | 29.58% | Started | 3884.16 | 0 | 100 | 29.5775 | 29.5775 | 100 | 44.9589 | 29.5775
22 | Diversen | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 |  | 0 | 0 | 997.92 | 77d | 0 | 0 | 0 | 997.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Aanpassingswerken meubilair | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 |  | 0 | 0 | 312.32 | 61d | 0 | 0 | 0 | 312.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verplaatsen versteviging schermen | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 |  | 0 | 0 | 4878.72 | 3d | 0 | 0 | 0 | 4878.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | MEERWERKEN | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2012-06-01 08:00 | 20d | 1 | 0 | 0 | 1714.78 | 0 | 1715.78 | 0 | 100% | Finished | 1 | 1 | 100 | 16000 | 100 | 100 | 171578.0029 | 100

## TP2
| TP Status Date | 2012-07-31 18:00 |  | TP Name | periode 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (5) | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 |  | 43d | [5 empty] | 139833.1987 |  | 60.71% |  | 148260.5923 | 77310.599
1 | Vaste plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 | 2012-07-02 08:00 | 22d | 526.24 | 0 | 0 | 1402.63 | 0 | 1928.87 | 0 | 100% | Finished | 2128.88 | 1578.72 | 100 | 24.7191 | 100 | 100 | 90.6049 | 100
2 | Metalen plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 | 2012-07-02 08:00 | 22d | 4822.3999 | 8767.9999 | 40d | 1044.0699 | 0 | 5866.4699 | 8767.9999 | 35.48% | Started | 6922.4771 | 14467.1998 | 100 | 24.7191 | 35.4839 | 100 | 30.0709 | 35.4839
4 | Verplaatsbare wanden (1) | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 | 2012-07-02 08:00 | 22d | 5484.16 | 0 | 0 | 28120.4902 | 0 | 33604.6502 | 0 | 100% | Finished | 37641.2798 | 13959.6799 | 100 | 14.5695 | 100 | 100 | 89.2761 | 100
6 | Gipswanden | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 2012-06-01 08:00 | 41d | 67433.5188 | 65788.7988 | 40d | -45908.1797 | 0 | 21525.3391 | 65788.7988 | 50.62% | Started | 18315.2766 | 36183.8394 | 100 | 186.3636 | 50.6173 | 100 | 59.4888 | 50.6173
9 | Zuivere OA (1) | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 | 2012-07-31 08:00 | 1d | 1079.36 | 0 | 0 | -232.71 | 0 | 846.65 | 0 | 100% | Finished | 1079.36 | 1079.36 | 100 | 100 | 100 | 100 | 78.44 | 100
10 | Démontage plafonds | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 2012-06-14 08:00 | 7d | 2508.8 | 0 | 0 | -231.93 | 0 | 2276.87 | 0 | 100% | Finished | 2508.8 | 2508.8 | 100 | 100 | 100 | 100 | 90.7553 | 100
12 | Uitregelen verhoogde vloer | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2012-07-23 08:00 | 3d | 1800 | 0 | 0 | -341.48 | 0 | 1458.52 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 81.0289 | 100
11 | Plaatsen tapijt | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 | 2012-07-25 08:00 | 5d | 27162.3999 | 0 | 0 | -5705.3301 | 0 | 21457.0698 | 0 | 100% | Finished | 27162.3999 | 5432.48 | 100 | 100 | 100 | 100 | 78.9955 | 100
21 | Zuivere OA (2) | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 | 2012-07-02 08:00 | 22d | 6589.4398 | 0 | 0 | 9105.04 | 0 | 15694.4798 | 0 | 100% | Finished | 20067.8393 | 299.52 | 100 | 32.8358 | 100 | 100 | 78.2071 | 100
13 | Plaatsen meubilair | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 |  | 0 | 0 | 36023.0391 | 3d | 0 | 0 | 0 | 36023.0391 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Leveren en plaatsen glas | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 |  | 0 | 0 | 180 | 1d | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Akoestische dammen | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 2012-06-28 08:00 | 2d | 1674.08 | 0 | 0 | -154.58 | 0 | 1519.5 | 0 | 100% | Finished | 1674.08 | 0 | 100 | 100 | 100 | 100 | 90.7663 | 100
20 | Verplaatsbare wanden (2) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 | 2012-07-19 08:00 | 9d | 4926.2399 | 0 | 0 | -1681.49 | 0 | 3244.7499 | 0 | 100% | Finished | 4926.2399 | 0 | 100 | 100 | 100 | 100 | 65.8667 | 100
5 | Verplaatsbare wanden (3) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 |  | 0 | 0 | 619.2 | 9d | 0 | 0 | 0 | 619.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Deuren | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 2012-06-29 08:00 | 3d | 6259.1997 | 0 | 0 | -730.47 | 0 | 5528.7297 | 0 | 100% | Finished | 6259.1997 | 0 | 100 | 100 | 100 | 100 | 88.3297 | 100
8 | Schrijnwerk diversen | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 | 2012-07-31 08:00 | 1d | 654.64 | 1309.28 | 2d | 180.78 | 0 | 835.42 | 1309.28 | 33.33% | Started | 654.64 | 0 | 100 | 33.3333 | 33.3333 | 100 | 42.5384 | 33.3333
17 | Schilderwerken | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 | 2012-07-02 08:00 | 22d | 4581.2801 | 0 | 0 | 1604.1801 | 0 | 6185.4602 | 0 | 100% | Finished | 8537.8402 | 0 | 100 | 53.6585 | 100 | 100 | 72.4476 | 100
19 | Bijkomende werken | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 |  | 0 | 0 | 16618.5601 | 3d | 0 | 0 | 0 | 16618.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Afwerkingen | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 2012-06-01 08:00 | 41d | 7583.3603 | 5548.8002 | 30d | 2508.1201 | 0 | 10091.4804 | 5548.8002 | 57.75% | Started | 7583.3599 | 0 | 100 | 57.7465 | 57.7465 | 100 | 76.8455 | 57.7465
22 | Diversen | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 | 2012-07-02 08:00 | 22d | 285.12 | 0 | 0 | 620.73 | 0 | 905.85 | 0 | 100% | Finished | 997.92 | 0 | 100 | 28.5714 | 100 | 100 | 90.7738 | 100
16 | Aanpassingswerken meubilair | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 |  | 0 | 0 | 312.32 | 61d | 0 | 0 | 0 | 312.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verplaatsen versteviging schermen | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 |  | 0 | 0 | 4878.72 | 3d | 0 | 0 | 0 | 4878.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | MEERWERKEN | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2012-06-01 08:00 | 40d | 1 | 0 | 0 | 6862.0898 | 0 | 6863.0898 | 0 | 100% | Finished | 1 | 1 | 100 | 32000 | 100 | 100 | 686308.9844 | 100

## TP3
| TP Status Date | 2012-08-31 18:00 |  | TP Name | periode 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (5) | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 |  | 66d | [5 empty] | 175005.51 |  | 91.31% |  | 222987.7161 | 169889.9573
1 | Vaste plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 | 2012-07-02 08:00 | 22d | 526.24 | 0 | 0 | 1402.63 | 0 | 1928.87 | 0 | 100% | Finished | 2128.88 | 2128.88 | 100 | 24.7191 | 100 | 100 | 90.6049 | 100
2 | Metalen plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 | 2012-07-02 08:00 | 42d | 9206.3999 | 4383.9999 | 20d | -3339.9299 | 0 | 5866.4699 | 4383.9999 | 67.74% | Started | 13215.6387 | 19508.7997 | 100 | 47.191 | 67.7419 | 100 | 30.0709 | 67.7419
4 | Verplaatsbare wanden (1) | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 | 2012-07-02 08:00 | 22d | 5484.16 | 0 | 0 | 28120.4902 | 0 | 33604.6502 | 0 | 100% | Finished | 37641.2798 | 19693.1199 | 100 | 14.5695 | 100 | 100 | 89.2761 | 100
6 | Gipswanden | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 2012-06-01 08:00 | 61d | 100327.9182 | 32894.3994 | 20d | -78802.5781 | 0 | 21525.3401 | 32894.3994 | 75.31% | Started | 27249.559 | 36183.8394 | 100 | 277.2727 | 75.3086 | 100 | 59.4888 | 75.3086
9 | Zuivere OA (1) | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 | 2012-07-31 08:00 | 1d | 1079.36 | 0 | 0 | -232.71 | 0 | 846.65 | 0 | 100% | Finished | 1079.36 | 1079.36 | 100 | 100 | 100 | 100 | 78.44 | 100
10 | Démontage plafonds | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 2012-06-14 08:00 | 7d | 2508.8 | 0 | 0 | -231.93 | 0 | 2276.87 | 0 | 100% | Finished | 2508.8 | 2508.8 | 100 | 100 | 100 | 100 | 90.7553 | 100
12 | Uitregelen verhoogde vloer | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2012-07-23 08:00 | 3d | 1800 | 0 | 0 | -341.48 | 0 | 1458.52 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 81.0289 | 100
11 | Plaatsen tapijt | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 | 2012-07-25 08:00 | 5d | 27162.3999 | 0 | 0 | -5705.3301 | 0 | 21457.0698 | 0 | 100% | Finished | 27162.3999 | 27162.3999 | 100 | 100 | 100 | 100 | 78.9955 | 100
21 | Zuivere OA (2) | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 | 2012-07-02 08:00 | 22d | 6589.4398 | 0 | 0 | 9105.04 | 0 | 15694.4798 | 0 | 100% | Finished | 20067.8393 | 7188.4797 | 100 | 32.8358 | 100 | 100 | 78.2071 | 100
13 | Plaatsen meubilair | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 | 2012-08-16 08:00 | 3d | 36023.0391 | 0 | 0 | -6831.98 | 0 | 29191.0591 | 0 | 100% | Finished | 36023.0391 | 36023.0391 | 100 | 100 | 100 | 100 | 81.0344 | 100
14 | Leveren en plaatsen glas | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 |  | 0 | 0 | 180 | 1d | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 180 | 100 |  | 0 | 100 |  | 0
3 | Akoestische dammen | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 2012-06-28 08:00 | 2d | 1674.08 | 0 | 0 | -154.58 | 0 | 1519.5 | 0 | 100% | Finished | 1674.08 | 1674.08 | 100 | 100 | 100 | 100 | 90.7663 | 100
20 | Verplaatsbare wanden (2) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 | 2012-07-19 08:00 | 9d | 4926.2399 | 0 | 0 | -1681.49 | 0 | 3244.7499 | 0 | 100% | Finished | 4926.2399 | 4926.2399 | 100 | 100 | 100 | 100 | 65.8667 | 100
5 | Verplaatsbare wanden (3) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 |  | 0 | 0 | 619.2 | 9d | 0 | 0 | 0 | 619.2 | 0% | Not Started | 0 | 619.2 | 100 |  | 0 | 100 |  | 0
7 | Deuren | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 2012-06-29 08:00 | 3d | 6259.1997 | 0 | 0 | -730.47 | 0 | 5528.7297 | 0 | 100% | Finished | 6259.1997 | 6259.1997 | 100 | 100 | 100 | 100 | 88.3297 | 100
8 | Schrijnwerk diversen | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 | 2012-07-31 08:00 | 3d | 1963.92 | 0 | 0 | -181.27 | 0 | 1782.65 | 0 | 100% | Finished | 1963.92 | 1963.92 | 100 | 100 | 100 | 100 | 90.77 | 100
17 | Schilderwerken | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 | 2012-07-02 08:00 | 22d | 4581.2801 | 0 | 0 | 1604.1801 | 0 | 6185.4602 | 0 | 100% | Finished | 8537.8402 | 0 | 100 | 53.6585 | 100 | 100 | 72.4476 | 100
19 | Bijkomende werken | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 | 2012-08-29 08:00 | 3d | 16618.5601 | 0 | 0 | -15245.0195 | 0 | 1373.5405 | 0 | 100% | Finished | 16618.5601 | 0 | 100 | 100 | 100 | 100 | 8.2651 | 100
15 | Afwerkingen | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 2012-06-01 08:00 | 65d | 12022.4004 | 0 | 0 | -102.5 | 0 | 11919.9004 | 0 | 100% | Finished | 13132.1605 | 924.8 | 100 | 91.5493 | 100 | 100 | 90.7688 | 100
22 | Diversen | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 | 2012-07-02 08:00 | 22d | 285.12 | 0 | 0 | 620.73 | 0 | 905.85 | 0 | 100% | Finished | 997.92 | 64.8 | 100 | 28.5714 | 100 | 100 | 90.7738 | 100
16 | Aanpassingswerken meubilair | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 |  | 0 | 0 | 312.32 | 61d | 0 | 0 | 0 | 312.32 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Verplaatsen versteviging schermen | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 |  | 0 | 0 | 4878.72 | 3d | 0 | 0 | 0 | 4878.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | MEERWERKEN | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2012-06-01 08:00 | 65d | 1 | 0 | 0 | 8694.1504 | 0 | 8695.1504 | 0 | 100% | Finished | 1 | 1 | 100 | 52000 | 100 | 100 | 869515.0391 | 100

## TP4
| TP Status Date | 2012-09-30 18:00 |  | TP Name | periode 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (5) | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 |  | 86d | [5 empty] | 202522.5397 |  | 97.8% |  | 238834.3574 | 184870.4372
1 | Vaste plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 | 2012-07-02 08:00 | 22d | 526.24 | 0 | 0 | 1402.63 | 0 | 1928.87 | 0 | 100% | Finished | 2128.88 | 2128.88 | 100 | 24.7191 | 100 | 100 | 90.6049 | 100
2 | Metalen plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 | 2012-07-02 08:00 | 62d | 13590.3998 | 0 | 0 | 6600.04 | 0 | 20190.4398 | 0 | 100% | Finished | 19508.7997 | 19508.7997 | 100 | 69.6629 | 100 | 100 | 103.494 | 100
4 | Verplaatsbare wanden (1) | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 | 2012-07-02 08:00 | 22d | 5484.16 | 0 | 0 | 28120.4902 | 0 | 33604.6502 | 0 | 100% | Finished | 37641.2798 | 24678.7199 | 100 | 14.5695 | 100 | 100 | 89.2761 | 100
6 | Gipswanden | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 2012-06-01 08:00 | 81d | 133222.3176 | 0 | 0 | -99119.0078 | 0 | 34103.3098 | 0 | 100% | Finished | 36183.8394 | 36183.8394 | 100 | 368.1818 | 100 | 100 | 94.2501 | 100
9 | Zuivere OA (1) | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 | 2012-07-31 08:00 | 1d | 1079.36 | 0 | 0 | -232.71 | 0 | 846.65 | 0 | 100% | Finished | 1079.36 | 1079.36 | 100 | 100 | 100 | 100 | 78.44 | 100
10 | Démontage plafonds | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 2012-06-14 08:00 | 7d | 2508.8 | 0 | 0 | -231.93 | 0 | 2276.87 | 0 | 100% | Finished | 2508.8 | 2508.8 | 100 | 100 | 100 | 100 | 90.7553 | 100
12 | Uitregelen verhoogde vloer | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2012-07-23 08:00 | 3d | 1800 | 0 | 0 | -341.48 | 0 | 1458.52 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 81.0289 | 100
11 | Plaatsen tapijt | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 | 2012-07-25 08:00 | 5d | 27162.3999 | 0 | 0 | -5705.3301 | 0 | 21457.0698 | 0 | 100% | Finished | 27162.3999 | 27162.3999 | 100 | 100 | 100 | 100 | 78.9955 | 100
21 | Zuivere OA (2) | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 | 2012-07-02 08:00 | 22d | 6589.4398 | 0 | 0 | 9105.04 | 0 | 15694.4798 | 0 | 100% | Finished | 20067.8393 | 13178.8795 | 100 | 32.8358 | 100 | 100 | 78.2071 | 100
13 | Plaatsen meubilair | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 | 2012-08-16 08:00 | 3d | 36023.0391 | 0 | 0 | -6831.98 | 0 | 29191.0591 | 0 | 100% | Finished | 36023.0391 | 36023.0391 | 100 | 100 | 100 | 100 | 81.0344 | 100
14 | Leveren en plaatsen glas | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 |  | 0 | 0 | 180 | 1d | 0 | 0 | 0 | 180 | 0% | Not Started | 0 | 180 | 100 |  | 0 | 100 |  | 0
3 | Akoestische dammen | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 2012-06-28 08:00 | 2d | 1674.08 | 0 | 0 | -154.58 | 0 | 1519.5 | 0 | 100% | Finished | 1674.08 | 1674.08 | 100 | 100 | 100 | 100 | 90.7663 | 100
20 | Verplaatsbare wanden (2) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 | 2012-07-19 08:00 | 9d | 4926.2399 | 0 | 0 | -1681.49 | 0 | 3244.7499 | 0 | 100% | Finished | 4926.2399 | 4926.2399 | 100 | 100 | 100 | 100 | 65.8667 | 100
5 | Verplaatsbare wanden (3) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 | 2012-09-03 08:00 | 9d | 619.2 | 0 | 0 | -4.11 | 0 | 615.09 | 0 | 100% | Finished | 619.2 | 619.2 | 100 | 100 | 100 | 100 | 99.3362 | 100
7 | Deuren | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 2012-06-29 08:00 | 3d | 6259.1997 | 0 | 0 | -730.47 | 0 | 5528.7297 | 0 | 100% | Finished | 6259.1997 | 6259.1997 | 100 | 100 | 100 | 100 | 88.3297 | 100
8 | Schrijnwerk diversen | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 | 2012-07-31 08:00 | 3d | 1963.92 | 0 | 0 | -181.27 | 0 | 1782.65 | 0 | 100% | Finished | 1963.92 | 1963.92 | 100 | 100 | 100 | 100 | 90.77 | 100
17 | Schilderwerken | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 | 2012-07-02 08:00 | 22d | 4581.2801 | 0 | 0 | 1604.1801 | 0 | 6185.4602 | 0 | 100% | Finished | 8537.8402 | 0 | 100 | 53.6585 | 100 | 100 | 72.4476 | 100
19 | Bijkomende werken | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 | 2012-08-29 08:00 | 3d | 16618.5601 | 0 | 0 | -15245.0195 | 0 | 1373.5405 | 0 | 100% | Finished | 16618.5601 | 0 | 100 | 100 | 100 | 100 | 8.2651 | 100
15 | Afwerkingen | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 2012-06-01 08:00 | 65d | 12022.4004 | 0 | 0 | -102.5 | 0 | 11919.9004 | 0 | 100% | Finished | 13132.1605 | 4624.0002 | 100 | 91.5493 | 100 | 100 | 90.7688 | 100
22 | Diversen | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 | 2012-07-02 08:00 | 22d | 285.12 | 0 | 0 | 620.73 | 0 | 905.85 | 0 | 100% | Finished | 997.92 | 324 | 100 | 28.5714 | 100 | 100 | 90.7738 | 100
16 | Aanpassingswerken meubilair | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 |  | 0 | 0 | 312.32 | 61d | 0 | 0 | 0 | 312.32 | 0% | Not Started | 0 | 46.08 | 100 |  | 0 | 100 |  | 0
18 | Verplaatsen versteviging schermen | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 |  | 0 | 0 | 4878.72 | 3d | 0 | 0 | 0 | 4878.72 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | MEERWERKEN | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2012-06-01 08:00 | 85d | 1 | 0 | 0 | 8694.1504 | 0 | 8695.1504 | 0 | 100% | Finished | 1 | 1 | 100 | 68000 | 100 | 100 | 869515.0391 | 100

## TP5
| TP Status Date | 2012-10-31 18:00 |  | TP Name | periode 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Office Finishing Works (5) | 2012-05-01 08:00 | 2012-12-11 17:00 | 161d |  |  | 1 |  |  | 244205.3974 |  | 107d | [5 empty] | 203605.9696 |  | 100% |  | 244205.3974 | 226158.9171
1 | Vaste plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 2.99 | 2128.88 | 2128.88 | 2012-07-02 08:00 | 22d | 526.24 | 0 | 0 | 1402.63 | 0 | 1928.87 | 0 | 100% | Finished | 2128.88 | 2128.88 | 100 | 24.7191 | 100 | 100 | 90.6049 | 100
2 | Metalen plafonds | 2012-05-01 08:00 | 2012-08-31 17:00 | 89d |  | 0 | 0 | 27.4 | 19508.7997 | 19508.7997 | 2012-07-02 08:00 | 62d | 13590.3998 | 0 | 0 | 6600.04 | 0 | 20190.4398 | 0 | 100% | Finished | 19508.7997 | 19508.7997 | 100 | 69.6629 | 100 | 100 | 103.494 | 100
4 | Verplaatsbare wanden (1) | 2012-05-15 08:00 | 2012-12-11 17:00 | 151d |  | 0 | 0 | 31.16 | 37641.2798 | 37641.2798 | 2012-07-02 08:00 | 22d | 5484.16 | 0 | 0 | 28120.4902 | 0 | 33604.6502 | 0 | 100% | Finished | 37641.2798 | 30412.1599 | 100 | 14.5695 | 100 | 100 | 89.2761 | 100
6 | Gipswanden | 2012-05-15 08:00 | 2012-06-13 17:00 | 22d |  | 0 | 0 | 205.59 | 36183.8394 | 36183.8394 | 2012-06-01 08:00 | 81d | 133222.3176 | 0 | 0 | -99119.0078 | 0 | 34103.3098 | 0 | 100% | Finished | 36183.8394 | 36183.8394 | 100 | 368.1818 | 100 | 100 | 94.2501 | 100
9 | Zuivere OA (1) | 2012-06-13 08:00 | 2012-06-13 17:00 | 1d |  | 0 | 0 | 134.92 | 1079.36 | 1079.36 | 2012-07-31 08:00 | 1d | 1079.36 | 0 | 0 | -232.71 | 0 | 846.65 | 0 | 100% | Finished | 1079.36 | 1079.36 | 100 | 100 | 100 | 100 | 78.44 | 100
10 | Démontage plafonds | 2012-06-14 08:00 | 2012-06-22 17:00 | 7d |  | 0 | 0 | 44.8 | 2508.8 | 2508.8 | 2012-06-14 08:00 | 7d | 2508.8 | 0 | 0 | -231.93 | 0 | 2276.87 | 0 | 100% | Finished | 2508.8 | 2508.8 | 100 | 100 | 100 | 100 | 90.7553 | 100
12 | Uitregelen verhoogde vloer | 2012-07-23 08:00 | 2012-07-25 17:00 | 3d |  | 0 | 0 | 75 | 1800 | 1800 | 2012-07-23 08:00 | 3d | 1800 | 0 | 0 | -341.48 | 0 | 1458.52 | 0 | 100% | Finished | 1800 | 1800 | 100 | 100 | 100 | 100 | 81.0289 | 100
11 | Plaatsen tapijt | 2012-07-31 08:00 | 2012-08-06 17:00 | 5d |  | 0 | 0 | 679.06 | 27162.3999 | 27162.3999 | 2012-07-25 08:00 | 5d | 27162.3999 | 0 | 0 | -5705.3301 | 0 | 21457.0698 | 0 | 100% | Finished | 27162.3999 | 27162.3999 | 100 | 100 | 100 | 100 | 78.9955 | 100
21 | Zuivere OA (2) | 2012-07-31 08:00 | 2012-10-31 17:00 | 67d |  | 0 | 0 | 37.44 | 20067.8393 | 20067.8393 | 2012-07-02 08:00 | 22d | 6589.4398 | 0 | 0 | 9105.04 | 0 | 15694.4798 | 0 | 100% | Finished | 20067.8393 | 20067.8393 | 100 | 32.8358 | 100 | 100 | 78.2071 | 100
13 | Plaatsen meubilair | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 1500.96 | 36023.0391 | 36023.0391 | 2012-08-16 08:00 | 3d | 36023.0391 | 0 | 0 | -6831.98 | 0 | 29191.0591 | 0 | 100% | Finished | 36023.0391 | 36023.0391 | 100 | 100 | 100 | 100 | 81.0344 | 100
14 | Leveren en plaatsen glas | 2012-08-30 08:00 | 2012-08-30 17:00 | 1d |  | 0 | 0 | 22.5 | 180 | 180 | 2012-10-01 08:00 | 1d | 180 | 0 | 0 | -2.04 | 0 | 177.96 | 0 | 100% | Finished | 180 | 180 | 100 | 100 | 100 | 100 | 98.8667 | 100
3 | Akoestische dammen | 2012-08-06 08:00 | 2012-08-07 17:00 | 2d |  | 0 | 0 | 104.63 | 1674.08 | 1674.08 | 2012-06-28 08:00 | 2d | 1674.08 | 0 | 0 | -154.58 | 0 | 1519.5 | 0 | 100% | Finished | 1674.08 | 1674.08 | 100 | 100 | 100 | 100 | 90.7663 | 100
20 | Verplaatsbare wanden (2) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 68.42 | 4926.2399 | 4926.2399 | 2012-07-19 08:00 | 9d | 4926.2399 | 0 | 0 | -1681.49 | 0 | 3244.7499 | 0 | 100% | Finished | 4926.2399 | 4926.2399 | 100 | 100 | 100 | 100 | 65.8667 | 100
5 | Verplaatsbare wanden (3) | 2012-08-13 08:00 | 2012-08-23 17:00 | 9d |  | 0 | 0 | 8.6 | 619.2 | 619.2 | 2012-09-03 08:00 | 9d | 619.2 | 0 | 0 | -4.11 | 0 | 615.09 | 0 | 100% | Finished | 619.2 | 619.2 | 100 | 100 | 100 | 100 | 99.3362 | 100
7 | Deuren | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 260.8 | 6259.1997 | 6259.1997 | 2012-06-29 08:00 | 3d | 6259.1997 | 0 | 0 | -730.47 | 0 | 5528.7297 | 0 | 100% | Finished | 6259.1997 | 6259.1997 | 100 | 100 | 100 | 100 | 88.3297 | 100
8 | Schrijnwerk diversen | 2012-08-16 08:00 | 2012-08-20 17:00 | 3d |  | 0 | 0 | 81.83 | 1963.92 | 1963.92 | 2012-07-31 08:00 | 3d | 1963.92 | 0 | 0 | -181.27 | 0 | 1782.65 | 0 | 100% | Finished | 1963.92 | 1963.92 | 100 | 100 | 100 | 100 | 90.77 | 100
17 | Schilderwerken | 2012-10-16 08:00 | 2012-12-11 17:00 | 41d |  | 0 | 0 | 26.03 | 8537.8402 | 8537.8402 | 2012-07-02 08:00 | 22d | 4581.2801 | 0 | 0 | 1604.1801 | 0 | 6185.4602 | 0 | 100% | Finished | 8537.8402 | 2498.8801 | 100 | 53.6585 | 100 | 100 | 72.4476 | 100
19 | Bijkomende werken | 2012-10-29 08:00 | 2012-10-31 17:00 | 3d |  | 0 | 0 | 692.44 | 16618.5601 | 16618.5601 | 2012-08-29 08:00 | 3d | 16618.5601 | 0 | 0 | -15245.0195 | 0 | 1373.5405 | 0 | 100% | Finished | 16618.5601 | 16618.5601 | 100 | 100 | 100 | 100 | 8.2651 | 100
15 | Afwerkingen | 2012-08-27 08:00 | 2012-12-03 17:00 | 71d |  | 0 | 0 | 23.12 | 13132.1605 | 13132.1605 | 2012-06-01 08:00 | 65d | 12022.4004 | 0 | 0 | -102.5 | 0 | 11919.9004 | 0 | 100% | Finished | 13132.1605 | 8878.0803 | 100 | 91.5493 | 100 | 100 | 90.7688 | 100
22 | Diversen | 2012-08-27 08:00 | 2012-12-11 17:00 | 77d |  | 0 | 0 | 1.62 | 997.92 | 997.92 | 2012-07-02 08:00 | 22d | 285.12 | 0 | 0 | 620.73 | 0 | 905.85 | 0 | 100% | Finished | 997.92 | 622.08 | 100 | 28.5714 | 100 | 100 | 90.7738 | 100
16 | Aanpassingswerken meubilair | 2012-09-18 08:00 | 2012-12-11 17:00 | 61d |  | 0 | 0 | 0.64 | 312.32 | 312.32 | 2012-10-01 08:00 | 1h | 0.64 | 0 | 0 | -0.64 | 0 | 0 | 0 | 100% | Finished | 312.32 | 163.84 | 100 | 0.20492 | 100 | 100 |  | 100
18 | Verplaatsen versteviging schermen | 2012-10-25 08:00 | 2012-10-29 17:00 | 3d |  | 0 | 0 | 203.28 | 4878.72 | 4878.72 | 2012-10-25 08:00 | 3d | 4878.72 | 0 | 0 | -3973.25 | 0 | 905.47 | 0 | 100% | Finished | 4878.72 | 4878.72 | 100 | 100 | 100 | 100 | 18.5596 | 100
23 | MEERWERKEN | 2012-05-01 08:00 | 2012-05-01 09:00 | 1h |  | 0 | 1 | 0 | 0 | 1 | 2012-06-01 08:00 | 85d | 1 | 0 | 0 | 8694.1504 | 0 | 8695.1504 | 0 | 100% | Finished | 1 | 1 | 100 | 68000 | 100 | 100 | 869515.0391 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
periode 1 | 2012-05-01 08:00 | 2012-06-30 18:00 | 58945.7991 | 19535.4351 | 27993.2196 | 2012-05-24 17:00 | -39410.364 | 33.14% | -8457.7845 | 69.79% | -26d | 40.91% | 48.04% | 2013-01-16 17:00 | 2014-03-11 15:00 | 2014-12-31 09:00 | 2013-01-22 11:00 | 2014-03-11 15:00 | 2014-12-04 09:00 | 2013-01-16 17:00 | 2013-11-01 12:00 | 2014-06-02 16:00 | 252663.182 | 349933.0983 | 705907.5026 | 577186.4609 | 999407.6433 | 814957.3674 | 387710.811 | 378980.4429 | 0.40909 | 0.69786 | 0.33141 | 0.48041 | -26 | 0.69786 | 1 | 0.40909 | 1
periode 2 | 2012-06-30 18:00 | 2012-07-31 18:00 | 77310.599 | 148260.5923 | 139833.1987 | 2012-08-20 11:00 | 70949.9933 | 191.8% | 8427.3936 | 106% | 13d 3h | 120.3% | 61.15% | 2012-10-08 10:00 | 2012-08-24 17:00 | 2012-08-20 09:00 | 2012-09-18 11:00 | 2012-08-24 17:00 | 2012-08-23 16:00 | 2012-11-22 14:00 | 2012-11-02 16:00 | 2012-10-29 17:00 | 235778.0038 | 230324.3319 | 189863.6906 | 219610.9264 | 187019.8692 | 215076.2197 | 217725.6938 | 227957.478 | 1.2027 | 1.0603 | 1.9177 | 0.61153 | 13.375 | 1.0603 | 1 | 1.2027 | 1
periode 3 | 2012-07-31 18:00 | 2012-08-31 18:00 | 169889.9573 | 222987.7161 | 175005.51 | 2012-10-31 14:00 | 53097.7588 | 131.3% | 47982.2061 | 127.4% | 42d 5h | 147.9% | 90.58% | 2012-10-23 17:00 | 2012-10-18 14:00 | 2012-09-12 10:00 | 2012-11-02 09:00 | 2012-10-18 14:00 | 2012-10-09 11:00 | 2012-10-12 11:00 | 2012-09-28 16:00 | 2012-09-24 14:00 | 196223.1913 | 191657.5983 | 191170.8443 | 189352.1283 | 187692.4087 | 186265.0417 | 191557.9165 | 191139.0727 | 1.4789 | 1.2742 | 1.3125 | 0.90583 | 42.625 | 1.2742 | 1 | 1.4789 | 1
periode 4 | 2012-08-31 18:00 | 2012-09-30 18:00 | 184870.4372 | 238834.3574 | 202522.5397 | 2012-11-28 10:00 | 53963.9203 | 129.2% | 36311.8178 | 117.9% | 42d 2h | 138.8% | 97.77% | 2012-10-23 11:00 | 2012-10-22 14:00 | 2012-09-25 14:00 | 2012-10-29 09:00 | 2012-10-22 14:00 | 2012-10-18 10:00 | 2012-10-12 15:00 | 2012-10-09 17:00 | 2012-10-08 17:00 | 207893.5796 | 207076.9793 | 206680.0089 | 206393.2395 | 206047.917 | 205804.7474 | 206991.6342 | 206921.5661 | 1.3876 | 1.1793 | 1.2919 | 0.97772 | 42.25 | 1.1793 | 1 | 1.3876 | 1
periode 5 | 2012-09-30 18:00 | 2012-10-31 18:00 | 226158.9171 | 244205.3974 | 203605.9696 | 2012-12-11 17:00 | 18046.4803 | 108% | 40599.4278 | 119.9% | 29d | 122% | 100% | 2012-11-26 09:00 | 2012-11-26 09:00 | 2012-10-22 11:00 | 2012-11-27 12:00 | 2012-11-26 09:00 | 2012-11-21 10:00 | 2012-10-31 17:00 | 2012-10-31 17:00 | 2012-10-31 17:00 | 203605.9696 | 203605.9696 | 203605.9696 | 203605.9696 | 203605.9696 | 203605.9696 | 203605.9696 | 203605.9696 | 1.2197 | 1.1994 | 1.0798 | 1 | 29 | 1.1994 | 1 | 1.2197 | 1