## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Mixed-used Building | 1 |  |  | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 | 745.375
1 | Mixed-use Building | 1.1 |  |  | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
6 | Dates clés contractuelles | 1.2 |  |  | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 | 414
2 | Date clé 1 | 1.2.1 |  |  | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
3 | Date clé 2 | 1.2.2 |  |  | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
4 | Date clé 3 | 1.2.3 |  |  | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
5 | Date clé 4 | 1.2.4 |  |  | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
11 | Dates clés suivant planning | 1.3 |  |  | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 | 436
7 | Date clé 1 | 1.3.1 | 24FS |  | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
8 | Date clé 2 | 1.3.2 | 37FS |  | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
9 | Date clé 3 | 1.3.3 | 47FS;51FS |  | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
10 | Date clé 4 | 1.3.4 | 64FS |  | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
12 | Notification de la commande | 1.4 |  | FS13;FS14 | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
13 | Préparation du chantier | 1.5 | 12FS | FS15 | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 56.375
66 | Délais contractuel | 1.6 |  |  | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 | 745.375
14 | Début des travaux | 1.6.1 | 12FS | FS15;FS16 | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
15 | Installation de chantier | 1.6.2 | 14FS;13FS |  | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 13.375
16 | Démolitions et etançonnages | 1.6.3 | 14FS | FS20-4w;FS17-6w | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 159.375
19 | Grue | 1.6.4 |  |  | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 | 456.375
17 | Montage | 1.6.4.1 | 16FS-6w | FS18 | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 22.375
18 | Démontage | 1.6.4.2 | 17FS;52FS |  | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 6.375
65 | Batiment | 1.6.5 |  |  | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 | 611.375
39 | Gros oeuvre | 1.6.5.1 |  |  | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 | 398.375
25 | Sous-sols | 1.6.5.1.1 |  |  | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 | 147.375
20 | Radier sciences | 1.6.5.1.1.1 | 16FS-4w | FS21 | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 29.375
21 | Radier industries | 1.6.5.1.1.2 | 20FS | FS22-4w | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 17.375
22 | Sous-sol -3 | 1.6.5.1.1.3 | 21FS-4w | FS23-1w 2d | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 37.375
23 | Sous-sol -2 | 1.6.5.1.1.4 | 22FS-1w 2d | FS24-1w 1d | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 63.375
24 | Sous-sol -1 | 1.6.5.1.1.5 | 23FS-1w 1d | FS26-1w 1d;FS7 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 42.375
38 | Hors sol | 1.6.5.1.2 |  |  | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 | 258.375
26 | Rez | 1.6.5.1.2.1 | 24FS-1w 1d | FS40;FS27-1w 1d | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 27.375
27 | Etage +1 | 1.6.5.1.2.2 | 26FS-1w 1d | FS28-1w 1d | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 27.375
28 | Etage +2 | 1.6.5.1.2.3 | 27FS-1w 1d | FS51;FS29-1w 2d | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 30.375
29 | Etage +3 | 1.6.5.1.2.4 | 28FS-1w 2d | FS30-1w 1d;FS41 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 28.375
30 | Etage +4 | 1.6.5.1.2.5 | 29FS-1w 1d | FS31-3w | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 41.375
31 | Etage +5 | 1.6.5.1.2.6 | 30FS-3w | FS32-1w 1d;FS55 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 39.375
32 | Etage +6 | 1.6.5.1.2.7 | 31FS-1w 1d | FS33-1w 1d | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 27.375
33 | Etage +7 | 1.6.5.1.2.8 | 32FS-1w 1d | FS34-1w 1d | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 27.375
34 | Etage +8 | 1.6.5.1.2.9 | 33FS-1w 1d | FS35-1w 1d | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 27.375
35 | Etage +9 | 1.6.5.1.2.10 | 34FS-1w 1d | FS56;FS36-1w 1d | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 29.375
36 | Etage +10 | 1.6.5.1.2.11 | 35FS-1w 1d | FS37-1w 1d;FS47-1w;FS48 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 28.375
37 | Etage +11 Toiture | 1.6.5.1.2.12 | 36FS-1w 1d | FS8;FS41-20w 2d;FS48-1w 4d | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 27.375
42 | Maçonneries intérieures | 1.6.5.2 |  |  | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 | 268.375
40 | Maçonneries sous-sols | 1.6.5.2.1 | 26FS | FS43-8w 3d | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 72.375
41 | Maçonneries hors sol | 1.6.5.2.2 | 29FS;37FS-20w 2d | FS44-27w 4d | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 193.375
46 | Techniques | 1.6.5.3 |  |  | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 | 369.375
43 | Techniques sous-sols | 1.6.5.3.1 | 40FS-8w 3d | FS57-12w | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 142.375
44 | Techniques hors sol | 1.6.5.3.2 | 41FS-27w 4d | FS58-32w 2d;FS45-12w 1d;FS55-23w 4d | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 283.375
45 | Unités terminales | 1.6.5.3.3 | 44FS-12w 1d | FS59 | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 | 140.375
50 | Toitures | 1.6.5.4 |  |  | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 | 148.375
47 | Etanchéités 1ère phase (hors eau) | 1.6.5.4.1 | 36FS-1w | FS9;FS48-6w | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 49.375
48 | Etanchéités | 1.6.5.4.2 | 36FS;37FS-1w 4d;47FS-6w | FS49-1w | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 115.375
49 | Finitions | 1.6.5.4.3 | 48FS-1w | FS62 | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 25.375
54 | Façades | 1.6.5.5 |  |  | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 | 295.375
51 | Menuiseries extérieures | 1.6.5.5.1 | 28FS | FS52-26w 1d;FS9 | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 210.375
52 | Parements | 1.6.5.5.2 | 51FS-26w 1d | FS53;FS18 | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 210.375
53 | Finitions | 1.6.5.5.3 | 52FS | FS61-6w 1d;FS62 | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 70.375
60 | Parachèvements | 1.6.5.6 |  |  | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 | 346.375
55 | Etanchéité provisoire +4 | 1.6.5.6.1 | 31FS;44FS-23w 4d |  | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 6.375
56 | Etanchéité provisoire +8 | 1.6.5.6.2 | 35FS |  | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 6.375
57 | Parachèvements sous-sols | 1.6.5.6.3 | 43FS-12w | FS62 | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 141.375
58 | Parachèvements hors sol | 1.6.5.6.4 | 44FS-32w 2d | FS59-1w 2d | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 299.375
59 | Finitions | 1.6.5.6.5 | 45FS;58FS-1w 2d | FS62-4w 3d | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 | 16.375
61 | Abords | 1.6.5.7 | 53FS-6w 1d | FS62 | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 84.375
62 | Mise en état de réception | 1.6.5.8 | 61FS;53FS;49FS;57FS;59FS-4w 3d | FS63 | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 | 38.375
63 | Réserve pour intempéries et aléas | 1.6.5.9 | 62FS | FS64 | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 | 25.375
64 | Fin des travaux prêt pour RP | 1.6.5.10 | 63FS | FS10 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Mixed-used Building | 3792h |  |  |  |  | 99 | 100 | 101
1 | Mixed-use Building | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Dates clés contractuelles | 2128h |  |  |  |  | 99 | 100 | 101
2 | Date clé 1 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Date clé 2 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Date clé 3 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Date clé 4 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Dates clés suivant planning | 2256h |  |  |  |  | 99 | 100 | 101
7 | Date clé 1 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Date clé 2 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Date clé 3 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Date clé 4 | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Notification de la commande | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Préparation du chantier | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Délais contractuel | 3792h |  |  |  |  | 99 | 100 | 101
14 | Début des travaux | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Installation de chantier | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Démolitions et etançonnages | 832h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Grue | 2376h |  |  |  |  | 99 | 100 | 101
17 | Montage | 136h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Démontage | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Batiment | 3104h |  |  |  |  | 99 | 100 | 101
39 | Gros oeuvre | 2040h |  |  |  |  | 99 | 100 | 101
25 | Sous-sols | 688h |  |  |  |  | 99 | 100 | 101
20 | Radier sciences | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Radier industries | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Sous-sol -3 | 224h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Sous-sol -2 | 208h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Sous-sol -1 | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Hors sol | 1400h |  |  |  |  | 99 | 100 | 101
26 | Rez | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Etage +1 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Etage +2 | 184h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Etage +3 | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Etage +4 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Etage +5 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Etage +6 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Etage +7 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Etage +8 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Etage +9 | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Etage +10 | 168h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Etage +11 Toiture | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Maçonneries intérieures | 1464h |  |  |  |  | 99 | 100 | 101
40 | Maçonneries sous-sols | 424h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Maçonneries hors sol | 1040h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Techniques | 1872h |  |  |  |  | 99 | 100 | 101
43 | Techniques sous-sols | 744h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Techniques hors sol | 1376h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Unités terminales | 648h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Toitures | 696h |  |  |  |  | 99 | 100 | 101
47 | Etanchéités 1ère phase (hors eau) | 288h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Etanchéités | 512h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Finitions | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Façades | 1456h |  |  |  |  | 99 | 100 | 101
51 | Menuiseries extérieures | 1128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Parements | 1128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Finitions | 248h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Parachèvements | 1752h |  |  |  |  | 99 | 100 | 101
55 | Etanchéité provisoire +4 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Etanchéité provisoire +8 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Parachèvements sous-sols | 736h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Parachèvements hors sol | 1552h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Finitions | 104h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Abords | 328h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Mise en état de réception | 232h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Réserve pour intempéries et aléas | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Fin des travaux prêt pour RP | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2010-12-31 17:00 |  | TP Name | 31/12, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 14d | [5 empty] | 1695199.1548 |  | 4.205% |  | 1627216.125 | 1627216.125
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 9d | 139677 | 0 | 22d | 5835.5298 | 0 | 145512.5298 | 0 | 29.03% | Started | 139677 | 139677 | 100 | 29.0323 | 29.0323 | 100 | 104.1779 | 29.0323
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 14d | [5 empty] | 1549686.625 |  | 3.858% |  | 1487539.125 | 1487539.125
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 |  | 0 | 0 | 2974378.75 | 10d | 0 | 0 | 0 | 2974378.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 12d | 1487539.125 | 0 | 95d | 62147.5 | 0 | 1549686.625 | 0 | 11.21% | Started | 1487539.125 | 1487539.125 | 100 | 11.5385 | 11.215 | 100 | 104.1779 | 11.215
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 |  | 0 | 0 | 67607.1094 | 17d | 0 | 0 | 0 | 67607.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 |  | 0 | 0 | 539823.8125 | 22d | 0 | 0 | 0 | 539823.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 |  | 0 | 0 | 284117.7812 | 12d | 0 | 0 | 0 | 284117.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 28d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2011-01-31 17:00 |  | TP Name | 31/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 30d | [5 empty] | 1695199.1548 |  | 4.205% |  | 1627216.125 | 1627216.125
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 25d | 139677 | 0 | 6d | 5835.5298 | 0 | 145512.5298 | 0 | 80.65% | Started | 139677 | 139677 | 100 | 80.6452 | 80.6452 | 100 | 104.1779 | 80.6452
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 30d | [5 empty] | 1549686.625 |  | 3.858% |  | 1487539.125 | 1487539.125
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 |  | 0 | 0 | 2974378.75 | 10d | 0 | 0 | 0 | 2974378.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 28d | 1487539.125 | 0 | 79d | 62147.5 | 0 | 1549686.625 | 0 | 26.17% | Started | 1487539.125 | 1487539.125 | 100 | 26.9231 | 26.1682 | 100 | 104.1779 | 26.1682
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 |  | 0 | 0 | 67607.1094 | 17d | 0 | 0 | 0 | 67607.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 |  | 0 | 0 | 539823.8125 | 22d | 0 | 0 | 0 | 539823.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 |  | 0 | 0 | 284117.7812 | 12d | 0 | 0 | 0 | 284117.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 28d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2011-02-28 17:00 |  | TP Name | 28/02, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 50d | [5 empty] | 4793843.7642 |  | 11.89% |  | 4601594.875 | 4601594.875
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 50d | [5 empty] | 4648331.2344 |  | 11.57% |  | 4461917.875 | 4461917.875
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 48d | 1487539.125 | 0 | 59d | 62147.5 | 0 | 1549686.625 | 0 | 44.86% | Started | 1487539.125 | 1487539.125 | 100 | 46.1538 | 44.8598 | 100 | 104.1779 | 44.8598
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 |  | 0 | 0 | 67607.1094 | 17d | 0 | 0 | 0 | 67607.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 |  | 0 | 0 | 539823.8125 | 22d | 0 | 0 | 0 | 539823.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 |  | 0 | 0 | 284117.7812 | 12d | 0 | 0 | 0 | 284117.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 28d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2011-03-31 17:00 |  | TP Name | 31/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 73d | [5 empty] | 4793843.7642 |  | 11.89% |  | 4601594.875 | 4601594.875
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 73d | [5 empty] | 4648331.2344 |  | 11.57% |  | 4461917.875 | 4461917.875
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 71d | 1487539.125 | 0 | 36d | 62147.5 | 0 | 1549686.625 | 0 | 66.36% | Started | 1487539.125 | 1487539.125 | 100 | 68.2692 | 66.3551 | 100 | 104.1779 | 66.3551
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 |  | 0 | 0 | 67607.1094 | 17d | 0 | 0 | 0 | 67607.1094 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 |  | 0 | 0 | 539823.8125 | 22d | 0 | 0 | 0 | 539823.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 |  | 0 | 0 | 284117.7812 | 12d | 0 | 0 | 0 | 284117.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 28d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2011-04-30 17:00 |  | TP Name | 30/04, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 94d | [5 empty] | 4864275.4136 |  | 12.07% |  | 4669201.9844 | 5209025.7969
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 94d | [5 empty] | 4718762.8838 |  | 11.75% |  | 4529524.9844 | 5069348.7969
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 92d | 1487539.125 | 0 | 15d | 62147.5 | 0 | 1549686.625 | 0 | 85.98% | Started | 1487539.125 | 1487539.125 | 100 | 88.4615 | 85.9813 | 100 | 104.1779 | 85.9813
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 1d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 1d | 67607.1094 | 0 | 15d | 2824.54 | 0 | 70431.6494 | 0 | 6.25% | Started | 67607.1094 | 67607.1094 | 100 | 5.8824 | 6.25 | 100 | 104.1779 | 6.25
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 539823.8125
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 539823.8125
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 539823.8125
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 |  | 0 | 0 | 539823.8125 | 22d | 0 | 0 | 0 | 539823.8125 | 0% | Not Started | 0 | 539823.8125 | 100 |  | 0 | 100 |  | 0
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 |  | 0 | 0 | 284117.7812 | 12d | 0 | 0 | 0 | 284117.7812 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 28d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2011-05-31 17:00 |  | TP Name | 31/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 116d | [5 empty] | 6166622.1167 |  | 15.3% |  | 5919320.2969 | 6203438.0781
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 116d | [5 empty] | 6021109.5869 |  | 14.99% |  | 5779643.2969 | 6063761.0781
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 23d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 12d | [5 empty] | 1302346.7031 |  | 3.676% |  | 1250118.3125 | 1534236.0938
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 12d | [5 empty] | 1302346.7031 |  | 12.72% |  | 1250118.3125 | 1534236.0938
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 12d | [5 empty] | 1302346.7031 |  | 40.37% |  | 1250118.3125 | 1534236.0938
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 12d | 539823.8125 | 0 | 10d | 22553.1699 | 0 | 562376.9824 | 0 | 54.55% | Started | 539823.8125 | 539823.8125 | 100 | 54.5455 | 54.5455 | 100 | 104.1779 | 54.5455
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 |  | 0 | 0 | 284117.7812 | 12d | 0 | 0 | 0 | 284117.7812 | 0% | Not Started | 0 | 284117.7812 | 100 |  | 0 | 100 |  | 0
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 2d | 710294.5 | 0 | 30d | 29675.2207 | 0 | 739969.7207 | 0 | 6.25% | Started | 710294.5 | 710294.5 | 100 | 7.1429 | 6.25 | 100 | 104.1779 | 6.25
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2011-06-30 17:00 |  | TP Name | 30/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 138d | [5 empty] | 6462609.9878 |  | 16.03% |  | 6203438.0781 | 6913732.5781
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 138d | [5 empty] | 6317097.458 |  | 15.73% |  | 6063761.0781 | 6774055.5781
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 45d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 34d | [5 empty] | 1598334.5742 |  | 4.512% |  | 1534236.0938 | 2244530.5938
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 34d | [5 empty] | 1598334.5742 |  | 15.61% |  | 1534236.0938 | 2244530.5938
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 34d | [5 empty] | 1598334.5742 |  | 49.54% |  | 1534236.0938 | 2244530.5938
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 24d | 710294.5 | 0 | 8d | 29675.2207 | 0 | 739969.7207 | 0 | 75% | Started | 710294.5 | 710294.5 | 100 | 85.7143 | 75 | 100 | 104.1779 | 75
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 710294.5 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2011-07-31 17:00 |  | TP Name | 31/07, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 139d | [5 empty] | 6462609.9878 |  | 16.03% |  | 6203438.0781 | 6913732.5781
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 139d | [5 empty] | 6317097.458 |  | 15.73% |  | 6063761.0781 | 6774055.5781
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 46d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 35d | [5 empty] | 1598334.5742 |  | 4.512% |  | 1534236.0938 | 2244530.5938
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 35d | [5 empty] | 1598334.5742 |  | 15.61% |  | 1534236.0938 | 2244530.5938
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 35d | [5 empty] | 1598334.5742 |  | 49.54% |  | 1534236.0938 | 2244530.5938
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 25d | 710294.5 | 0 | 7d | 29675.2207 | 0 | 739969.7207 | 0 | 78.12% | Started | 710294.5 | 710294.5 | 100 | 89.2857 | 78.125 | 100 | 104.1779 | 78.125
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 |  | 0 | 0 | 710294.5 | 26d | 0 | 0 | 0 | 710294.5 | 0% | Not Started | 0 | 710294.5 | 100 |  | 0 | 100 |  | 0
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 |  | 0 | 0 | 852353.375 | 31d | 0 | 0 | 0 | 852353.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2011-08-31 17:00 |  | TP Name | 31/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 162d | [5 empty] | 8090543.2827 |  | 20.07% |  | 7766085.9531 | 7766085.9531
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 162d | [5 empty] | 7945030.7529 |  | 19.78% |  | 7626408.9531 | 7626408.9531
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 69d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 58d | [5 empty] | 3226267.8691 |  | 9.107% |  | 3096883.9688 | 3096883.9688
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 58d | [5 empty] | 3226267.8691 |  | 31.5% |  | 3096883.9688 | 3096883.9688
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 58d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 7d | 852353.375 | 0 | 13d | 35610.1992 | 0 | 887963.5742 | 0 | 35% | Started | 852353.375 | 852353.375 | 100 | 22.5806 | 35 | 100 | 104.1779 | 35
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 |  | 0 | 0 | 157496.7969 | 53d | 0 | 0 | 0 | 157496.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 |  | 0 | 0 | 3319967.25 | 93d | 0 | 0 | 0 | 3319967.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2011-09-30 17:00 |  | TP Name | 30/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 184d | [5 empty] | 12758538.8145 |  | 31.99% |  | 12380021.125 | 8902557.0781
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 184d | [5 empty] | 12613026.2847 |  | 31.75% |  | 12240344.125 | 8762880.0781
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 91d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 80d | [5 empty] | 7894263.4009 |  | 22.67% |  | 7710819.1406 | 4233355.0938
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 80d | [5 empty] | 4410219.334 |  | 43.06% |  | 4233355.0938 | 4233355.0938
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 15d | [5 empty] | 1183951.4648 |  | 16.88% |  | 1136471.125 | 1136471.125
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 15d | 568235.5625 | 0 | 1d | 23740.1699 | 0 | 591975.7324 | 0 | 93.75% | Started | 568235.5625 | 568235.5625 | 100 | 75 | 93.75 | 100 | 104.1779 | 93.75
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 5d | 568235.5625 | 0 | 11d | 23740.1699 | 0 | 591975.7324 | 0 | 31.25% | Started | 568235.5625 | 568235.5625 | 100 | 25 | 31.25 | 100 | 104.1779 | 31.25
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 23d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 9d | [5 empty] | 164076.8169 |  | 28.74% |  | 157496.7969 | 0
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 9d | 157496.7969 | 0 | 26d | 6580.02 | 0 | 164076.8169 | 0 | 25.71% | Started | 157496.7969 | 0 | 100 | 16.9811 | 25.7143 | 100 | 104.1779 | 25.7143
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 |  | 0 | 0 | 390592.0625 | 130d | 0 | 0 | 0 | 390592.0625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 4d | [5 empty] | 3319967.25 |  | 26.87% |  | 3319967.25 | 0
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 4d | 3319967.25 | 0 | 165d | 0 | 0 | 3319967.25 | 0 | 2.367% | Started | 3319967.25 | 0 | 100 | 4.3011 | 2.3669 | 100 | 100 | 2.3669
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 |  | 0 | 0 | 6086606.5 | 172d | 0 | 0 | 0 | 6086606.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2011-10-31 17:00 |  | TP Name | 31/10, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 205d | [5 empty] | 23473919.6516 |  | 51.88% |  | 20077038.9922 | 12948256.6875
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 11d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 205d | [5 empty] | 23328407.1218 |  | 51.71% |  | 19937361.9922 | 12808579.6875
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 112d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 101d | [5 empty] | 18609644.238 |  | 45.31% |  | 15407837.0078 | 8279054.7031
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 101d | [5 empty] | 5594170.7988 |  | 54.62% |  | 5369826.2188 | 4801590.6562
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 36d | [5 empty] | 2367902.9297 |  | 33.76% |  | 2272942.25 | 1704706.6875
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 7d | 568235.5625 | 0 | 11d | 23740.1699 | 0 | 591975.7324 | 0 | 38.89% | Started | 568235.5625 | 0 | 100 | 33.3333 | 38.8889 | 100 | 104.1779 | 38.8889
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 30d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 157496.7969
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 30d | 157496.7969 | 0 | 5d | 6580.02 | 0 | 164076.8169 | 0 | 85.71% | Started | 157496.7969 | 157496.7969 | 100 | 56.6038 | 85.7143 | 100 | 104.1779 | 85.7143
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 7d | 390592.0625 | 0 | 117d | 16318.4502 | 0 | 406910.5127 | 0 | 5.645% | Started | 390592.0625 | 0 | 100 | 5.3846 | 5.6452 | 100 | 104.1779 | 5.6452
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 25d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 3319967.25
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 25d | 3319967.25 | 0 | 144d | 0 | 0 | 3319967.25 | 0 | 14.79% | Started | 3319967.25 | 3319967.25 | 100 | 26.8817 | 14.7929 | 100 | 100 | 14.7929
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 10d | 6086606.5 | 0 | 202d | 2951082 | 0 | 9037688.5 | 0 | 4.717% | Started | 6086606.5 | 0 | 100 | 5.814 | 4.717 | 100 | 148.4848 | 4.717
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 |  | 0 | 0 | 2356061.25 | 141d | 0 | 0 | 0 | 2356061.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 18d | [5 empty] | 86830.3596 |  | 1.695% |  | 83348.1797 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 |  | 0 | 0 | 83348.1797 | 5d | 0 | 0 | 0 | 83348.1797 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2011-11-30 17:00 |  | TP Name | 30/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 227d | [5 empty] | 29653690.5698 |  | 67.21% |  | 26008980.7969 | 16440789.0625
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 20d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 33d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 227d | [5 empty] | 29508178.04 |  | 67.09% |  | 25869303.7969 | 16301112.0625
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 134d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 123d | [5 empty] | 24789415.1562 |  | 62.75% |  | 21339778.8125 | 11771587.0781
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 123d | [5 empty] | 6778122.2637 |  | 66.18% |  | 6506297.3438 | 5938061.7812
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 58d | [5 empty] | 3551854.3945 |  | 50.63% |  | 3409413.375 | 2841177.8125
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 8d | 568235.5625 | 0 | 7d | 23740.1699 | 0 | 591975.7324 | 0 | 53.33% | Started | 568235.5625 | 0 | 100 | 40 | 53.3333 | 100 | 104.1779 | 53.3333
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 52d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 157496.7969
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 29d | 390592.0625 | 0 | 95d | 16318.4502 | 0 | 406910.5127 | 0 | 23.39% | Started | 390592.0625 | 0 | 100 | 22.3077 | 23.3871 | 100 | 104.1779 | 23.3871
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 47d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 3319967.25
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 47d | 3319967.25 | 0 | 122d | 0 | 0 | 3319967.25 | 0 | 27.81% | Started | 3319967.25 | 3319967.25 | 100 | 50.5376 | 27.8107 | 100 | 100 | 27.8107
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 32d | 6086606.5 | 0 | 180d | 2951082 | 0 | 9037688.5 | 0 | 15.09% | Started | 6086606.5 | 0 | 100 | 18.6047 | 15.0943 | 100 | 148.4848 | 15.0943
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 21d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 2356061.25
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 21d | 2356061.25 | 0 | 97d | 98433.2969 | 0 | 2454494.5469 | 0 | 17.8% | Started | 2356061.25 | 2356061.25 | 100 | 14.8936 | 17.7966 | 100 | 104.1779 | 17.7966
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 16d | 2356061.25 | 0 | 121d | 98433.2969 | 0 | 2454494.5469 | 0 | 11.68% | Started | 2356061.25 | 0 | 100 | 11.3475 | 11.6788 | 100 | 104.1779 | 11.6788
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 40d | [5 empty] | 173660.7192 |  | 3.39% |  | 166696.3594 | 0
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 2d | 83348.1797 | 0 | 3d | 3482.1799 | 0 | 86830.3596 | 0 | 40% | Started | 83348.1797 | 0 | 100 | 40 | 40 | 100 | 104.1779 | 40
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 |  | 0 | 0 | 3083882.5 | 194d | 0 | 0 | 0 | 3083882.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2011-12-31 17:00 |  | TP Name | 31/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 244d | [5 empty] | 34050365.3315 |  | 78.12% |  | 30229334.4219 | 27342551.5625
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 37d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 50d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 244d | [5 empty] | 33904852.8018 |  | 78.04% |  | 30089657.4219 | 27202874.5625
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 151d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 140d | [5 empty] | 29186089.918 |  | 75.16% |  | 25560132.4375 | 22673349.5781
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 140d | [5 empty] | 7962073.7285 |  | 77.75% |  | 7642768.4688 | 6506297.3438
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 75d | [5 empty] | 4735805.8594 |  | 67.51% |  | 4545884.5 | 3409413.375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 16d | 568235.5625 | 0 | 8d | 23740.1699 | 0 | 591975.7324 | 0 | 66.67% | Started | 568235.5625 | 0 | 100 | 80 | 66.6667 | 100 | 104.1779 | 66.6667
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 3d | 568235.5625 | 0 | 16d | 23740.1699 | 0 | 591975.7324 | 0 | 15.79% | Started | 568235.5625 | 0 | 100 | 15 | 15.7895 | 100 | 104.1779 | 15.7895
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 20d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 69d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 46d | 390592.0625 | 0 | 78d | 16318.4502 | 0 | 406910.5127 | 0 | 37.1% | Started | 390592.0625 | 390592.0625 | 100 | 35.3846 | 37.0968 | 100 | 104.1779 | 37.0968
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 64d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 9406573.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 64d | 3319967.25 | 0 | 105d | 0 | 0 | 3319967.25 | 0 | 37.87% | Started | 3319967.25 | 3319967.25 | 100 | 68.8172 | 37.8698 | 100 | 100 | 37.8698
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 49d | 6086606.5 | 0 | 163d | 2951082 | 0 | 9037688.5 | 0 | 23.11% | Started | 6086606.5 | 6086606.5 | 100 | 28.4884 | 23.1132 | 100 | 148.4848 | 23.1132
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 38d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 4712122.5
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 38d | 2356061.25 | 0 | 80d | 98433.2969 | 0 | 2454494.5469 | 0 | 32.2% | Started | 2356061.25 | 2356061.25 | 100 | 26.9504 | 32.2034 | 100 | 104.1779 | 32.2034
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 33d | 2356061.25 | 0 | 104d | 98433.2969 | 0 | 2454494.5469 | 0 | 24.09% | Started | 2356061.25 | 2356061.25 | 100 | 23.4043 | 24.0876 | 100 | 104.1779 | 24.0876
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 57d | [5 empty] | 3386384.0161 |  | 66.1% |  | 3250578.8594 | 1500267.125
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 |  | 0 | 0 | 1500267.125 | 92d | 0 | 0 | 0 | 1500267.125 | 0% | Not Started | 0 | 1500267.125 | 100 |  | 0 | 100 |  | 0
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 11d | 3083882.5 | 0 | 166d | 128840.7969 | 0 | 3212723.2969 | 0 | 6.215% | Started | 3083882.5 | 0 | 100 | 5.6701 | 6.2147 | 100 | 104.1779 | 6.2147
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2012-01-31 17:00 |  | TP Name | 31/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 261d | [5 empty] | 36205287.4897 |  | 83.46% |  | 32297837.1094 | 30994669.625
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 54d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 67d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 261d | [5 empty] | 36059774.96 |  | 83.4% |  | 32158160.1094 | 30854992.625
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 168d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 157d | [5 empty] | 31341012.0762 |  | 81.25% |  | 27628635.125 | 26325467.6406
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 157d | [5 empty] | 8554049.4609 |  | 83.53% |  | 8211004.0312 | 7074532.9062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 92d | [5 empty] | 5327781.5918 |  | 75.95% |  | 5114120.0625 | 3977648.9375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 0 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 7d | 568235.5625 | 0 | 12d | 23740.1699 | 0 | 591975.7324 | 0 | 36.84% | Started | 568235.5625 | 0 | 100 | 35 | 36.8421 | 100 | 104.1779 | 36.8421
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 22d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 |  | 0 | 0 | 568235.5625 | 21d | 0 | 0 | 0 | 568235.5625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 86d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 63d | 390592.0625 | 0 | 61d | 16318.4502 | 0 | 406910.5127 | 0 | 50.81% | Started | 390592.0625 | 390592.0625 | 100 | 48.4615 | 50.8065 | 100 | 104.1779 | 50.8065
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 81d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 9406573.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 81d | 3319967.25 | 0 | 88d | 0 | 0 | 3319967.25 | 0 | 47.93% | Started | 3319967.25 | 3319967.25 | 100 | 87.0968 | 47.929 | 100 | 100 | 47.929
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 66d | 6086606.5 | 0 | 146d | 2951082 | 0 | 9037688.5 | 0 | 31.13% | Started | 6086606.5 | 6086606.5 | 100 | 38.3721 | 31.1321 | 100 | 148.4848 | 31.1321
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 55d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 4712122.5
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 55d | 2356061.25 | 0 | 63d | 98433.2969 | 0 | 2454494.5469 | 0 | 46.61% | Started | 2356061.25 | 2356061.25 | 100 | 39.0071 | 46.6102 | 100 | 104.1779 | 46.6102
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 50d | 2356061.25 | 0 | 87d | 98433.2969 | 0 | 2454494.5469 | 0 | 36.5% | Started | 2356061.25 | 2356061.25 | 100 | 35.461 | 36.4964 | 100 | 104.1779 | 36.4964
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 74d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4584149.625
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 8d | 1500267.125 | 0 | 88d | 62679.3008 | 0 | 1562946.4258 | 0 | 8.333% | Started | 1500267.125 | 1500267.125 | 100 | 8.6957 | 8.3333 | 100 | 104.1779 | 8.3333
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 28d | 3083882.5 | 0 | 149d | 128840.7969 | 0 | 3212723.2969 | 0 | 15.82% | Started | 3083882.5 | 3083882.5 | 100 | 14.433 | 15.8192 | 100 | 104.1779 | 15.8192
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2012-02-29 17:00 |  | TP Name | 29/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 282d | [5 empty] | 37389238.9546 |  | 86.4% |  | 33434308.2344 | 32131140.75
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 75d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 88d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 282d | [5 empty] | 37243726.4248 |  | 86.35% |  | 33294631.2344 | 31991463.75
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 189d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 178d | [5 empty] | 32524963.541 |  | 84.59% |  | 28765106.25 | 27461938.7656
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 178d | [5 empty] | 9738000.9258 |  | 95.09% |  | 9347475.1562 | 8211004.0312
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 113d | [5 empty] | 6511733.0566 |  | 92.83% |  | 6250591.1875 | 5114120.0625
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 15d | 568235.5625 | 0 | 4d | 23740.1699 | 0 | 591975.7324 | 0 | 78.95% | Started | 568235.5625 | 0 | 100 | 68.1818 | 78.9474 | 100 | 104.1779 | 78.9474
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 2d | 568235.5625 | 0 | 17d | 23740.1699 | 0 | 591975.7324 | 0 | 10.53% | Started | 568235.5625 | 0 | 100 | 9.5238 | 10.5263 | 100 | 104.1779 | 10.5263
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 |  | 0 | 0 | 483000.25 | 20d | 0 | 0 | 0 | 483000.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 107d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 84d | 390592.0625 | 0 | 40d | 16318.4502 | 0 | 406910.5127 | 0 | 67.74% | Started | 390592.0625 | 390592.0625 | 100 | 64.6154 | 67.7419 | 100 | 104.1779 | 67.7419
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 102d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 9406573.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 102d | 3319967.25 | 0 | 67d | 0 | 0 | 3319967.25 | 0 | 60.36% | Started | 3319967.25 | 3319967.25 | 100 | 109.6774 | 60.355 | 100 | 100 | 60.355
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 87d | 6086606.5 | 0 | 125d | 2951082 | 0 | 9037688.5 | 0 | 41.04% | Started | 6086606.5 | 6086606.5 | 100 | 50.5814 | 41.0377 | 100 | 148.4848 | 41.0377
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 |  | 0 | 0 | 227095.7969 | 36d | 0 | 0 | 0 | 227095.7969 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 76d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 4712122.5
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 76d | 2356061.25 | 0 | 42d | 98433.2969 | 0 | 2454494.5469 | 0 | 64.41% | Started | 2356061.25 | 2356061.25 | 100 | 53.9007 | 64.4068 | 100 | 104.1779 | 64.4068
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 71d | 2356061.25 | 0 | 66d | 98433.2969 | 0 | 2454494.5469 | 0 | 51.82% | Started | 2356061.25 | 2356061.25 | 100 | 50.3546 | 51.8248 | 100 | 104.1779 | 51.8248
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 95d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4584149.625
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 29d | 1500267.125 | 0 | 67d | 62679.3008 | 0 | 1562946.4258 | 0 | 30.21% | Started | 1500267.125 | 1500267.125 | 100 | 31.5217 | 30.2083 | 100 | 104.1779 | 30.2083
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 49d | 3083882.5 | 0 | 128d | 128840.7969 | 0 | 3212723.2969 | 0 | 27.68% | Started | 3083882.5 | 3083882.5 | 100 | 25.2577 | 27.6836 | 100 | 104.1779 | 27.6836
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2012-03-31 17:00 |  | TP Name | 31/03, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 304d | [5 empty] | 38108822.7817 |  | 88.23% |  | 34144404.2812 | 32782724.4922
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 97d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 110d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 304d | [5 empty] | 37963310.252 |  | 88.19% |  | 34004727.2812 | 32643047.4922
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 211d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 200d | [5 empty] | 33244547.3682 |  | 86.68% |  | 29475202.2969 | 28113522.5078
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 200d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 8779239.5938
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 135d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 5682355.625
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 0 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 11d | 483000.25 | 0 | 8d | 0 | 0 | 483000.25 | 0 | 57.89% | Started | 483000.25 | 0 | 100 | 55 | 57.8947 | 100 | 100 | 57.8947
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 129d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 106d | 390592.0625 | 0 | 18d | 16318.4502 | 0 | 406910.5127 | 0 | 85.48% | Started | 390592.0625 | 390592.0625 | 100 | 81.5385 | 85.4839 | 100 | 104.1779 | 85.4839
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 124d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 9406573.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 124d | 3319967.25 | 0 | 45d | 0 | 0 | 3319967.25 | 0 | 73.37% | Started | 3319967.25 | 3319967.25 | 100 | 133.3333 | 73.3728 | 100 | 100 | 73.3728
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 109d | 6086606.5 | 0 | 103d | 2951082 | 0 | 9037688.5 | 0 | 51.42% | Started | 6086606.5 | 6086606.5 | 100 | 63.3721 | 51.4151 | 100 | 148.4848 | 51.4151
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 8d | [5 empty] | 236583.5771 |  | 29.2% |  | 227095.7969 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 8d | 227095.7969 | 0 | 25d | 9487.7803 | 0 | 236583.5771 | 0 | 24.24% | Started | 227095.7969 | 0 | 100 | 22.2222 | 24.2424 | 100 | 104.1779 | 24.2424
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 |  | 0 | 0 | 412901.4375 | 64d | 0 | 0 | 0 | 412901.4375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 98d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 4712122.5
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 98d | 2356061.25 | 0 | 20d | 98433.2969 | 0 | 2454494.5469 | 0 | 83.05% | Started | 2356061.25 | 2356061.25 | 100 | 69.5035 | 83.0508 | 100 | 104.1779 | 83.0508
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 93d | 2356061.25 | 0 | 44d | 98433.2969 | 0 | 2454494.5469 | 0 | 67.88% | Started | 2356061.25 | 2356061.25 | 100 | 65.9574 | 67.8832 | 100 | 104.1779 | 67.8832
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 117d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4667497.8047
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 51d | 1500267.125 | 0 | 45d | 62679.3008 | 0 | 1562946.4258 | 0 | 53.12% | Started | 1500267.125 | 1500267.125 | 100 | 55.4348 | 53.125 | 100 | 104.1779 | 53.125
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 71d | 3083882.5 | 0 | 106d | 128840.7969 | 0 | 3212723.2969 | 0 | 40.11% | Started | 3083882.5 | 3083882.5 | 100 | 36.5979 | 40.113 | 100 | 104.1779 | 40.113
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2012-04-30 17:00 |  | TP Name | 30/04, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 325d | [5 empty] | 38538974.729 |  | 89.3% |  | 34557305.7188 | 33917308.4844
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 118d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 131d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 325d | [5 empty] | 38393462.1992 |  | 89.26% |  | 34417628.7188 | 33777631.4844
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 232d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 221d | [5 empty] | 33674699.3154 |  | 87.89% |  | 29888103.7344 | 29248106.5
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 145d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 9406573.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 145d | 3319967.25 | 0 | 24d | 0 | 0 | 3319967.25 | 0 | 85.8% | Started | 3319967.25 | 3319967.25 | 100 | 155.914 | 85.7988 | 100 | 100 | 85.7988
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 130d | 6086606.5 | 0 | 82d | 2951082 | 0 | 9037688.5 | 0 | 61.32% | Started | 6086606.5 | 6086606.5 | 100 | 75.5814 | 61.3208 | 100 | 148.4848 | 61.3208
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 29d | [5 empty] | 666735.5244 |  | 82.3% |  | 639997.2344 | 0
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 29d | 227095.7969 | 0 | 4d | 9487.7803 | 0 | 236583.5771 | 0 | 87.88% | Started | 227095.7969 | 0 | 100 | 80.5556 | 87.8788 | 100 | 104.1779 | 87.8788
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 20d | 412901.4375 | 0 | 36d | 17250.5098 | 0 | 430151.9473 | 0 | 35.71% | Started | 412901.4375 | 0 | 100 | 31.25 | 35.7143 | 100 | 104.1779 | 35.7143
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 119d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 4712122.5
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 114d | 2356061.25 | 0 | 23d | 98433.2969 | 0 | 2454494.5469 | 0 | 83.21% | Started | 2356061.25 | 2356061.25 | 100 | 80.8511 | 83.2117 | 100 | 104.1779 | 83.2117
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 138d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4750845.9844
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 72d | 1500267.125 | 0 | 24d | 62679.3008 | 0 | 1562946.4258 | 0 | 75% | Started | 1500267.125 | 1500267.125 | 100 | 78.2609 | 75 | 100 | 104.1779 | 75
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 92d | 3083882.5 | 0 | 85d | 128840.7969 | 0 | 3212723.2969 | 0 | 51.98% | Started | 3083882.5 | 3083882.5 | 100 | 47.4227 | 51.9774 | 100 | 104.1779 | 51.9774
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2012-05-31 17:00 |  | TP Name | 31/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 348d | [5 empty] | 38538974.729 |  | 89.3% |  | 34557305.7188 | 34557305.7188
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 141d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 154d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 348d | [5 empty] | 38393462.1992 |  | 89.26% |  | 34417628.7188 | 34417628.7188
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 255d | [5 empty] | 70431.6494 |  | 75% |  | 67607.1094 | 67607.1094
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 |  | 0 | 0 | 22535.6992 | 5d | 0 | 0 | 0 | 22535.6992 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 244d | [5 empty] | 33674699.3154 |  | 87.89% |  | 29888103.7344 | 29888103.7344
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 168d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 9406573.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 168d | 3319967.25 | 0 | 1d | 0 | 0 | 3319967.25 | 0 | 99.41% | Started | 3319967.25 | 3319967.25 | 100 | 180.6452 | 99.4083 | 100 | 100 | 99.4083
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 153d | 6086606.5 | 0 | 59d | 2951082 | 0 | 9037688.5 | 0 | 72.17% | Started | 6086606.5 | 6086606.5 | 100 | 88.9535 | 72.1698 | 100 | 148.4848 | 72.1698
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 52d | [5 empty] | 666735.5244 |  | 82.3% |  | 639997.2344 | 639997.2344
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 43d | 412901.4375 | 0 | 18d | 17250.5098 | 0 | 430151.9473 | 0 | 70.49% | Started | 412901.4375 | 412901.4375 | 100 | 67.1875 | 70.4918 | 100 | 104.1779 | 70.4918
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 |  | 0 | 0 | 137633.8125 | 20d | 0 | 0 | 0 | 137633.8125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 142d | [5 empty] | 4908989.0938 |  | 90% |  | 4712122.5 | 4712122.5
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 |  | 0 | 0 | 523569.1562 | 31d | 0 | 0 | 0 | 523569.1562 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 161d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4750845.9844
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 95d | 1500267.125 | 0 | 1d | 62679.3008 | 0 | 1562946.4258 | 0 | 98.96% | Started | 1500267.125 | 1500267.125 | 100 | 103.2609 | 98.9583 | 100 | 104.1779 | 98.9583
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 115d | 3083882.5 | 0 | 62d | 128840.7969 | 0 | 3212723.2969 | 0 | 64.97% | Started | 3083882.5 | 3083882.5 | 100 | 59.2784 | 64.9718 | 100 | 104.1779 | 64.9718
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 |  | 0 | 0 | 328000 | 41d | 0 | 0 | 0 | 328000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2012-06-30 17:00 |  | TP Name | 30/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 369d | [5 empty] | 39592982.5869 |  | 91.91% |  | 35569044.3867 | 38382492.5742
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 162d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 175d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 369d | [5 empty] | 39447470.0571 |  | 91.89% |  | 35429367.3867 | 38242815.5742
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 100% |  | 90142.8086 | 90142.8086
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 100% | Finished | 22535.6992 | 22535.6992 | 100 | 100 | 100 | 100 | 104.1779 | 100
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 265d | [5 empty] | 34705229.9541 |  | 90.8% |  | 30877306.7031 | 33690754.8906
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 189d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 12357655.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 100% | Finished | 3319967.25 | 3319967.25 | 100 | 181.7204 | 100 | 100 | 100 | 100
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 174d | 6086606.5 | 0 | 38d | 2951082 | 0 | 9037688.5 | 0 | 82.08% | Started | 6086606.5 | 6086606.5 | 100 | 101.1628 | 82.0755 | 100 | 148.4848 | 82.0755
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 2951082 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 73d | [5 empty] | 810119.5068 |  | 100% |  | 777631.0469 | 639997.2344
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 100% | Finished | 412901.4375 | 412901.4375 | 100 | 95.3125 | 100 | 100 | 104.1779 | 100
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 13d | 137633.8125 | 0 | 7d | 5750.1699 | 0 | 143383.9824 | 0 | 65% | Started | 137633.8125 | 0 | 100 | 65 | 65 | 100 | 104.1779 | 65
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 163d | [5 empty] | 5454432.3203 |  | 100% |  | 5235691.6562 | 5235691.6562
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 21d | 523569.1562 | 0 | 9d | 21874.0703 | 0 | 545443.2266 | 0 | 70% | Started | 523569.1562 | 523569.1562 | 100 | 67.7419 | 70 | 100 | 104.1779 | 70
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 182d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4750845.9844
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 100% | Finished | 1500267.125 | 1500267.125 | 100 | 104.3478 | 100 | 100 | 104.1779 | 100
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 136d | 3083882.5 | 0 | 41d | 128840.7969 | 0 | 3212723.2969 | 0 | 76.84% | Started | 3083882.5 | 3083882.5 | 100 | 70.1031 | 76.8362 | 100 | 104.1779 | 76.8362
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 21d | 328000 | 0 | 20d | 13703.4297 | 0 | 341703.4297 | 0 | 51.22% | Started | 328000 | 328000 | 100 | 51.2195 | 51.2195 | 100 | 104.1779 | 51.2195
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2012-07-31 17:00 |  | TP Name | 31/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 374d | [5 empty] | 39592982.5869 |  | 91.91% |  | 35569044.3867 | 38382492.5742
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 167d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 180d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 374d | [5 empty] | 39447470.0571 |  | 91.89% |  | 35429367.3867 | 38242815.5742
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 100% |  | 90142.8086 | 90142.8086
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 100% | Finished | 22535.6992 | 22535.6992 | 100 | 100 | 100 | 100 | 104.1779 | 100
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 270d | [5 empty] | 34705229.9541 |  | 90.8% |  | 30877306.7031 | 33690754.8906
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 194d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 12357655.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 100% | Finished | 3319967.25 | 3319967.25 | 100 | 181.7204 | 100 | 100 | 100 | 100
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 179d | 6086606.5 | 0 | 32d | 2951082 | 0 | 9037688.5 | 0 | 84.83% | Started | 6086606.5 | 6086606.5 | 100 | 104.0698 | 84.8341 | 100 | 148.4848 | 84.8341
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 2951082 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 78d | [5 empty] | 810119.5068 |  | 100% |  | 777631.0469 | 639997.2344
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 100% | Finished | 412901.4375 | 412901.4375 | 100 | 95.3125 | 100 | 100 | 104.1779 | 100
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 18d | 137633.8125 | 0 | 2d | 5750.1699 | 0 | 143383.9824 | 0 | 90% | Started | 137633.8125 | 0 | 100 | 90 | 90 | 100 | 104.1779 | 90
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 168d | [5 empty] | 5454432.3203 |  | 100% |  | 5235691.6562 | 5235691.6562
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 26d | 523569.1562 | 0 | 4d | 21874.0703 | 0 | 545443.2266 | 0 | 86.67% | Started | 523569.1562 | 523569.1562 | 100 | 83.871 | 86.6667 | 100 | 104.1779 | 86.6667
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 187d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4750845.9844
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 100% | Finished | 1500267.125 | 1500267.125 | 100 | 104.3478 | 100 | 100 | 104.1779 | 100
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 141d | 3083882.5 | 0 | 36d | 128840.7969 | 0 | 3212723.2969 | 0 | 79.66% | Started | 3083882.5 | 3083882.5 | 100 | 72.6804 | 79.661 | 100 | 104.1779 | 79.661
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 26d | 328000 | 0 | 15d | 13703.4297 | 0 | 341703.4297 | 0 | 63.41% | Started | 328000 | 328000 | 100 | 63.4146 | 63.4146 | 100 | 104.1779 | 63.4146
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2012-08-31 17:00 |  | TP Name | 31/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 394d | [5 empty] | 39592982.5869 |  | 91.91% |  | 35569044.3867 | 38382492.5742
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 187d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 200d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 394d | [5 empty] | 39447470.0571 |  | 91.89% |  | 35429367.3867 | 38242815.5742
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 100% |  | 90142.8086 | 90142.8086
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 100% | Finished | 22535.6992 | 22535.6992 | 100 | 100 | 100 | 100 | 104.1779 | 100
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 290d | [5 empty] | 34705229.9541 |  | 90.8% |  | 30877306.7031 | 33690754.8906
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 214d | [5 empty] | 12357655.75 |  | 76.12% |  | 9406573.75 | 12357655.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 100% | Finished | 3319967.25 | 3319967.25 | 100 | 181.7204 | 100 | 100 | 100 | 100
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 199d | 6086606.5 | 0 | 12d | 2951082 | 0 | 9037688.5 | 0 | 94.31% | Started | 6086606.5 | 6086606.5 | 100 | 115.6977 | 94.3128 | 100 | 148.4848 | 94.3128
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 |  | 0 | 0 | 2951082 | 81d | 0 | 0 | 0 | 2951082 | 0% | Not Started | 0 | 2951082 | 100 |  | 0 | 100 |  | 0
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 80d | [5 empty] | 810119.5068 |  | 100% |  | 777631.0469 | 639997.2344
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 100% | Finished | 412901.4375 | 412901.4375 | 100 | 95.3125 | 100 | 100 | 104.1779 | 100
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 20d | 137633.8125 | 0 | 0 | 5750.1699 | 0 | 143383.9824 | 0 | 100% | Finished | 137633.8125 | 0 | 100 | 100 | 100 | 100 | 104.1779 | 100
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 172d | [5 empty] | 5454432.3203 |  | 100% |  | 5235691.6562 | 5235691.6562
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 30d | 523569.1562 | 0 | 0 | 21874.0703 | 0 | 545443.2266 | 0 | 100% | Finished | 523569.1562 | 523569.1562 | 100 | 96.7742 | 100 | 100 | 104.1779 | 100
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 207d | [5 empty] | 4949330.4419 |  | 96.61% |  | 4750845.9844 | 4750845.9844
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 100% | Finished | 1500267.125 | 1500267.125 | 100 | 104.3478 | 100 | 100 | 104.1779 | 100
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 161d | 3083882.5 | 0 | 16d | 128840.7969 | 0 | 3212723.2969 | 0 | 90.96% | Started | 3083882.5 | 3083882.5 | 100 | 82.9897 | 90.9605 | 100 | 104.1779 | 90.9605
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 |  | 0 | 0 | 166696.3438 | 13d | 0 | 0 | 0 | 166696.3438 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 41d | 328000 | 0 | 0 | 13703.4297 | 0 | 341703.4297 | 0 | 100% | Finished | 328000 | 328000 | 100 | 100 | 100 | 100 | 104.1779 | 100
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 |  | 0 | 0 | 10000 | 29d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2012-09-30 17:00 |  | TP Name | 30/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 414d | [5 empty] | 39776643.3008 |  | 100% |  | 38696822.7305 | 38520126.3867
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 207d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 220d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 414d | [5 empty] | 39631130.771 |  | 100% |  | 38557145.7305 | 38380449.3867
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 100% |  | 90142.8086 | 90142.8086
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 100% | Finished | 22535.6992 | 22535.6992 | 100 | 100 | 100 | 100 | 104.1779 | 100
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 310d | [5 empty] | 34888890.668 |  | 100% |  | 34005085.0469 | 33828388.7031
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 227d 1h | [5 empty] | 12357655.75 |  | 100% |  | 12357655.75 | 12357655.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 100% | Finished | 3319967.25 | 3319967.25 | 100 | 181.7204 | 100 | 100 | 100 | 100
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 211d | 6086606.5 | 0 | 0 | 2951082 | 0 | 9037688.5 | 0 | 100% | Finished | 6086606.5 | 6086606.5 | 100 | 122.6744 | 100 | 100 | 148.4848 | 100
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 | 2012-09-20 08:00 | 1h | 2951082 | 0 | 0 | -2951082 | 0 | 0 | 0 | 100% | Finished | 2951082 | 2951082 | 100 | 0.15432 | 100 | 100 |  | 100
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 80d | [5 empty] | 810119.5068 |  | 100% |  | 777631.0469 | 777631.0469
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 100% | Finished | 412901.4375 | 412901.4375 | 100 | 95.3125 | 100 | 100 | 104.1779 | 100
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 20d | 137633.8125 | 0 | 0 | 5750.1699 | 0 | 143383.9824 | 0 | 100% | Finished | 137633.8125 | 137633.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 172d | [5 empty] | 5454432.3203 |  | 100% |  | 5235691.6562 | 5235691.6562
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 30d | 523569.1562 | 0 | 0 | 21874.0703 | 0 | 545443.2266 | 0 | 100% | Finished | 523569.1562 | 523569.1562 | 100 | 96.7742 | 100 | 100 | 104.1779 | 100
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 227d | [5 empty] | 5122991.1558 |  | 100% |  | 4917542.3281 | 4750845.9844
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 100% | Finished | 1500267.125 | 1500267.125 | 100 | 104.3478 | 100 | 100 | 104.1779 | 100
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 177d | 3083882.5 | 0 | 0 | 128840.7969 | 0 | 3212723.2969 | 0 | 100% | Finished | 3083882.5 | 3083882.5 | 100 | 91.2371 | 100 | 100 | 104.1779 | 100
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 | 2012-09-25 08:00 | 4d | 166696.3438 | 0 | 6d | 6964.3701 | 0 | 173660.7139 | 0 | 40% | Started | 166696.3438 | 0 | 100 | 30.7692 | 40 | 100 | 104.1779 | 40
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 41d | 328000 | 0 | 0 | 13703.4297 | 0 | 341703.4297 | 0 | 100% | Finished | 328000 | 328000 | 100 | 100 | 100 | 100 | 104.1779 | 100
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 | 2012-09-13 08:00 | 12d | 10000 | 0 | 11d | 0 | 0 | 10000 | 0 | 52.17% | Started | 10000 | 0 | 100 | 41.3793 | 52.1739 | 100 | 100 | 52.1739
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 20d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2012-10-31 18:00 |  | TP Name | 31/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 437d | [5 empty] | 39777643.3008 |  | 100% |  | 38697822.7305 | 38696822.7305
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 230d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 243d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 437d | [5 empty] | 39632130.771 |  | 100% |  | 38558145.7305 | 38557145.7305
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 100% |  | 90142.8086 | 90142.8086
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 100% | Finished | 22535.6992 | 22535.6992 | 100 | 100 | 100 | 100 | 104.1779 | 100
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 333d | [5 empty] | 34889890.668 |  | 100% |  | 34006085.0469 | 34005085.0469
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 227d 1h | [5 empty] | 12357655.75 |  | 100% |  | 12357655.75 | 12357655.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 100% | Finished | 3319967.25 | 3319967.25 | 100 | 181.7204 | 100 | 100 | 100 | 100
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 211d | 6086606.5 | 0 | 0 | 2951082 | 0 | 9037688.5 | 0 | 100% | Finished | 6086606.5 | 6086606.5 | 100 | 122.6744 | 100 | 100 | 148.4848 | 100
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 | 2012-09-20 08:00 | 1h | 2951082 | 0 | 0 | -2951082 | 0 | 0 | 0 | 100% | Finished | 2951082 | 2951082 | 100 | 0.15432 | 100 | 100 |  | 100
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 80d | [5 empty] | 810119.5068 |  | 100% |  | 777631.0469 | 777631.0469
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 100% | Finished | 412901.4375 | 412901.4375 | 100 | 95.3125 | 100 | 100 | 104.1779 | 100
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 20d | 137633.8125 | 0 | 0 | 5750.1699 | 0 | 143383.9824 | 0 | 100% | Finished | 137633.8125 | 137633.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 172d | [5 empty] | 5454432.3203 |  | 100% |  | 5235691.6562 | 5235691.6562
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 30d | 523569.1562 | 0 | 0 | 21874.0703 | 0 | 545443.2266 | 0 | 100% | Finished | 523569.1562 | 523569.1562 | 100 | 96.7742 | 100 | 100 | 104.1779 | 100
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 233d | [5 empty] | 5122991.1558 |  | 100% |  | 4917542.3281 | 4917542.3281
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 100% | Finished | 1500267.125 | 1500267.125 | 100 | 104.3478 | 100 | 100 | 104.1779 | 100
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 177d | 3083882.5 | 0 | 0 | 128840.7969 | 0 | 3212723.2969 | 0 | 100% | Finished | 3083882.5 | 3083882.5 | 100 | 91.2371 | 100 | 100 | 104.1779 | 100
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 | 2012-09-25 08:00 | 10d | 166696.3438 | 0 | 0 | 6964.3701 | 0 | 173660.7139 | 0 | 100% | Finished | 166696.3438 | 166696.3438 | 100 | 76.9231 | 100 | 100 | 104.1779 | 100
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 41d | 328000 | 0 | 0 | 13703.4297 | 0 | 341703.4297 | 0 | 100% | Finished | 328000 | 328000 | 100 | 100 | 100 | 100 | 104.1779 | 100
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 | 2012-09-13 08:00 | 23d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 79.3103 | 100 | 100 | 100 | 100
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 | 2012-10-16 08:00 | 12d | 1000 | 0 | 11d | 0 | 0 | 1000 | 0 | 52.17% | Started | 1000 | 0 | 100 | 60 | 52.1739 | 100 | 100 | 52.1739
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2012-11-30 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Mixed-used Building | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38697822.7305 |  |  | 38697822.7305 |  | 448d | [5 empty] | 39777643.3008 |  | 100% |  | 38697822.7305 | 38697822.7305
1 | Mixed-use Building | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
6 | Dates clés contractuelles | 2011-11-03 17:00 | 2012-12-21 17:00 | 266d |  |  | 0 |  |  | 0 |  | 240d | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Date clé 1 | 2011-11-03 17:00 | 2011-11-03 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-11-03 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Date clé 2 | 2012-07-04 17:00 | 2012-07-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-07-04 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Date clé 3 | 2012-08-22 17:00 | 2012-08-22 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-08-22 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
5 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
11 | Dates clés suivant planning | 2011-10-12 17:00 | 2012-12-21 17:00 | 282d |  |  | 0 |  |  | 0 |  | 253d | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Date clé 1 | 2011-10-12 17:00 | 2011-10-12 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2011-10-17 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
8 | Date clé 2 | 2012-06-26 17:00 | 2012-06-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-05-29 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
9 | Date clé 3 | 2012-08-17 17:00 | 2012-08-17 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-06-20 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
10 | Date clé 4 | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
12 | Notification de la commande | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
13 | Préparation du chantier | 2010-12-14 08:00 | 2011-02-08 17:00 | 31d |  | 0 | 139677 | 0 | 0 | 139677 | 2010-12-14 08:00 | 31d | 139677 | 0 | 0 | 5835.5298 | 0 | 145512.5298 | 0 | 100% | Finished | 139677 | 139677 | 100 | 100 | 100 | 100 | 104.1779 | 100
66 | Délais contractuel | 2010-12-07 08:00 | 2012-12-21 17:00 | 474d |  |  | 38558145.7305 |  |  | 38558145.7305 |  | 448d | [5 empty] | 39632130.771 |  | 100% |  | 38558145.7305 | 38558145.7305
14 | Début des travaux | 2010-12-07 08:00 | 2010-12-06 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2010-12-07 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
15 | Installation de chantier | 2011-02-09 08:00 | 2011-02-22 17:00 | 10d |  | 0 | 2974378.75 | 0 | 0 | 2974378.75 | 2011-02-09 08:00 | 10d | 2974378.75 | 0 | 0 | 124265.8594 | 0 | 3098644.6094 | 0 | 100% | Finished | 2974378.75 | 2974378.75 | 100 | 100 | 100 | 100 | 104.1779 | 100
16 | Démolitions et etançonnages | 2010-12-09 08:00 | 2011-05-17 17:00 | 104d |  | 0 | 1487539.125 | 0 | 0 | 1487539.125 | 2010-12-09 08:00 | 107d | 1487539.125 | 0 | 0 | 62147.5 | 0 | 1549686.625 | 0 | 100% | Finished | 1487539.125 | 1487539.125 | 100 | 102.8846 | 100 | 100 | 104.1779 | 100
19 | Grue | 2011-04-06 08:00 | 2012-07-05 17:00 | 297d |  |  | 90142.8086 |  |  | 90142.8086 |  | 260d | [5 empty] | 93908.8687 |  | 100% |  | 90142.8086 | 90142.8086
17 | Montage | 2011-04-06 08:00 | 2011-04-28 17:00 | 17d |  | 0 | 67607.1094 | 0 | 0 | 67607.1094 | 2011-04-29 08:00 | 16d | 67607.1094 | 0 | 0 | 2824.54 | 0 | 70431.6494 | 0 | 100% | Finished | 67607.1094 | 67607.1094 | 100 | 94.1176 | 100 | 100 | 104.1779 | 100
18 | Démontage | 2012-06-29 08:00 | 2012-07-05 17:00 | 5d |  | 0 | 22535.6992 | 0 | 0 | 22535.6992 | 2012-06-01 08:00 | 5d | 22535.6992 | 0 | 0 | 941.52 | 0 | 23477.2192 | 0 | 100% | Finished | 22535.6992 | 22535.6992 | 100 | 100 | 100 | 100 | 104.1779 | 100
65 | Batiment | 2011-04-20 08:00 | 2012-12-21 17:00 | 388d |  |  | 34006085.0469 |  |  | 34006085.0469 |  | 344d | [5 empty] | 34889890.668 |  | 100% |  | 34006085.0469 | 34006085.0469
39 | Gros oeuvre | 2011-04-20 08:00 | 2012-05-22 17:00 | 255d |  |  | 9830475.4062 |  |  | 9830475.4062 |  | 208d | [5 empty] | 10221001.1758 |  | 100% |  | 9830475.4062 | 9830475.4062
25 | Sous-sols | 2011-04-20 08:00 | 2011-09-14 17:00 | 86d |  |  | 3096883.9688 |  |  | 3096883.9688 |  | 71d | [5 empty] | 3226267.8691 |  | 100% |  | 3096883.9688 | 3096883.9688
20 | Radier sciences | 2011-04-20 08:00 | 2011-05-19 17:00 | 22d |  | 0 | 539823.8125 | 0 | 0 | 539823.8125 | 2011-05-16 08:00 | 22d | 539823.8125 | 0 | 0 | 22553.1699 | 0 | 562376.9824 | 0 | 100% | Finished | 539823.8125 | 539823.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
21 | Radier industries | 2011-05-20 08:00 | 2011-06-06 17:00 | 12d |  | 0 | 284117.7812 | 0 | 0 | 284117.7812 | 2011-06-15 08:00 | 10d | 284117.7812 | 0 | 0 | 11870.0898 | 0 | 295987.8711 | 0 | 100% | Finished | 284117.7812 | 284117.7812 | 100 | 83.3333 | 100 | 100 | 104.1779 | 100
22 | Sous-sol -3 | 2011-05-10 08:00 | 2011-06-16 17:00 | 28d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-05-30 08:00 | 32d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 114.2857 | 100 | 100 | 104.1779 | 100
23 | Sous-sol -2 | 2011-06-08 08:00 | 2011-08-10 17:00 | 26d |  | 0 | 710294.5 | 0 | 0 | 710294.5 | 2011-08-01 08:00 | 21d | 710294.5 | 0 | 0 | 29675.2207 | 0 | 739969.7207 | 0 | 100% | Finished | 710294.5 | 710294.5 | 100 | 80.7692 | 100 | 100 | 104.1779 | 100
24 | Sous-sol -1 | 2011-08-03 08:00 | 2011-09-14 17:00 | 31d |  | 0 | 852353.375 | 0 | 0 | 852353.375 | 2011-08-23 08:00 | 20d | 852353.375 | 0 | 0 | 35610.1992 | 0 | 887963.5742 | 0 | 100% | Finished | 852353.375 | 852353.375 | 100 | 64.5161 | 100 | 100 | 104.1779 | 100
38 | Hors sol | 2011-09-07 08:00 | 2012-05-22 17:00 | 175d |  |  | 6733591.4375 |  |  | 6733591.4375 |  | 143d | [5 empty] | 6994733.3066 |  | 100% |  | 6733591.4375 | 6733591.4375
26 | Rez | 2011-09-07 08:00 | 2011-10-04 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-12 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
27 | Etage +1 | 2011-09-27 08:00 | 2011-10-24 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-09-26 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
28 | Etage +2 | 2011-10-17 08:00 | 2011-11-16 17:00 | 23d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-10 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 65.2174 | 100 | 100 | 104.1779 | 100
29 | Etage +3 | 2011-11-08 08:00 | 2011-12-06 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-10-21 08:00 | 18d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 85.7143 | 100 | 100 | 104.1779 | 100
30 | Etage +4 | 2011-11-29 08:00 | 2012-01-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-07 08:00 | 16d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 80 | 100 | 100 | 104.1779 | 100
31 | Etage +5 | 2011-12-12 08:00 | 2012-01-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-11-21 08:00 | 15d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 75 | 100 | 100 | 104.1779 | 100
32 | Etage +6 | 2012-01-13 08:00 | 2012-02-09 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-02 08:00 | 24d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 120 | 100 | 100 | 104.1779 | 100
33 | Etage +7 | 2012-02-02 08:00 | 2012-02-29 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2011-12-21 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
34 | Etage +8 | 2012-02-22 08:00 | 2012-03-20 17:00 | 20d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-01-23 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 95 | 100 | 100 | 104.1779 | 100
35 | Etage +9 | 2012-03-13 08:00 | 2012-04-11 17:00 | 22d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-09 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 86.3636 | 100 | 100 | 104.1779 | 100
36 | Etage +10 | 2012-04-04 08:00 | 2012-05-02 17:00 | 21d |  | 0 | 568235.5625 | 0 | 0 | 568235.5625 | 2012-02-28 08:00 | 19d | 568235.5625 | 0 | 0 | 23740.1699 | 0 | 591975.7324 | 0 | 100% | Finished | 568235.5625 | 568235.5625 | 100 | 90.4762 | 100 | 100 | 104.1779 | 100
37 | Etage +11 Toiture | 2012-04-25 08:00 | 2012-05-22 17:00 | 20d |  | 0 | 483000.25 | 0 | 0 | 483000.25 | 2012-03-16 08:00 | 19d | 483000.25 | 0 | 0 | 0 | 0 | 483000.25 | 0 | 100% | Finished | 483000.25 | 483000.25 | 100 | 95 | 100 | 100 | 100 | 100
42 | Maçonneries intérieures | 2011-10-05 08:00 | 2012-06-29 17:00 | 183d |  |  | 548088.8594 |  |  | 548088.8594 |  | 147d | [5 empty] | 570987.3296 |  | 100% |  | 548088.8594 | 548088.8594
40 | Maçonneries sous-sols | 2011-10-05 08:00 | 2011-12-16 17:00 | 53d |  | 0 | 157496.7969 | 0 | 0 | 157496.7969 | 2011-09-20 08:00 | 35d | 157496.7969 | 0 | 0 | 6580.02 | 0 | 164076.8169 | 0 | 100% | Finished | 157496.7969 | 157496.7969 | 100 | 66.0377 | 100 | 100 | 104.1779 | 100
41 | Maçonneries hors sol | 2011-12-19 08:00 | 2012-06-29 17:00 | 130d |  | 0 | 390592.0625 | 0 | 0 | 390592.0625 | 2011-10-21 08:00 | 124d | 390592.0625 | 0 | 0 | 16318.4502 | 0 | 406910.5127 | 0 | 100% | Finished | 390592.0625 | 390592.0625 | 100 | 95.3846 | 100 | 100 | 104.1779 | 100
46 | Techniques | 2011-10-19 08:00 | 2012-10-22 17:00 | 234d |  |  | 12357655.75 |  |  | 12357655.75 |  | 227d 1h | [5 empty] | 12357655.75 |  | 100% |  | 12357655.75 | 12357655.75
43 | Techniques sous-sols | 2011-10-19 08:00 | 2012-03-09 17:00 | 93d |  | 0 | 3319967.25 | 0 | 0 | 3319967.25 | 2011-09-27 08:00 | 169d | 3319967.25 | 0 | 0 | 0 | 0 | 3319967.25 | 0 | 100% | Finished | 3319967.25 | 3319967.25 | 100 | 181.7204 | 100 | 100 | 100 | 100
44 | Techniques hors sol | 2011-12-16 08:00 | 2012-09-24 17:00 | 172d |  | 0 | 6086606.5 | 0 | 0 | 6086606.5 | 2011-10-18 08:00 | 211d | 6086606.5 | 0 | 0 | 2951082 | 0 | 9037688.5 | 0 | 100% | Finished | 6086606.5 | 6086606.5 | 100 | 122.6744 | 100 | 100 | 148.4848 | 100
45 | Unités terminales | 2012-06-04 08:00 | 2012-10-22 17:00 | 81d |  | 0 | 2951082 | 0 | 0 | 2951082 | 2012-09-20 08:00 | 1h | 2951082 | 0 | 0 | -2951082 | 0 | 0 | 0 | 100% | Finished | 2951082 | 2951082 | 100 | 0.15432 | 100 | 100 |  | 100
50 | Toitures | 2012-05-03 08:00 | 2012-09-28 17:00 | 87d |  |  | 777631.0469 |  |  | 777631.0469 |  | 80d | [5 empty] | 810119.5068 |  | 100% |  | 777631.0469 | 777631.0469
47 | Etanchéités 1ère phase (hors eau) | 2012-05-03 08:00 | 2012-06-21 17:00 | 36d |  | 0 | 227095.7969 | 0 | 0 | 227095.7969 | 2012-03-21 08:00 | 33d | 227095.7969 | 0 | 0 | 9487.7803 | 0 | 236583.5771 | 0 | 100% | Finished | 227095.7969 | 227095.7969 | 100 | 91.6667 | 100 | 100 | 104.1779 | 100
48 | Etanchéités | 2012-05-15 08:00 | 2012-09-07 17:00 | 64d |  | 0 | 412901.4375 | 0 | 0 | 412901.4375 | 2012-04-03 08:00 | 61d | 412901.4375 | 0 | 0 | 17250.5098 | 0 | 430151.9473 | 0 | 100% | Finished | 412901.4375 | 412901.4375 | 100 | 95.3125 | 100 | 100 | 104.1779 | 100
49 | Finitions | 2012-09-03 08:00 | 2012-09-28 17:00 | 20d |  | 0 | 137633.8125 | 0 | 0 | 137633.8125 | 2012-06-13 08:00 | 20d | 137633.8125 | 0 | 0 | 5750.1699 | 0 | 143383.9824 | 0 | 100% | Finished | 137633.8125 | 137633.8125 | 100 | 100 | 100 | 100 | 104.1779 | 100
54 | Façades | 2011-11-17 08:00 | 2012-09-07 17:00 | 182d |  |  | 5235691.6562 |  |  | 5235691.6562 |  | 172d | [5 empty] | 5454432.3203 |  | 100% |  | 5235691.6562 | 5235691.6562
51 | Menuiseries extérieures | 2011-11-17 08:00 | 2012-06-14 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-02 08:00 | 118d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 83.6879 | 100 | 100 | 104.1779 | 100
52 | Parements | 2011-12-01 08:00 | 2012-06-28 17:00 | 141d |  | 0 | 2356061.25 | 0 | 0 | 2356061.25 | 2011-11-09 08:00 | 137d | 2356061.25 | 0 | 0 | 98433.2969 | 0 | 2454494.5469 | 0 | 100% | Finished | 2356061.25 | 2356061.25 | 100 | 97.1631 | 100 | 100 | 104.1779 | 100
53 | Finitions | 2012-06-29 08:00 | 2012-09-07 17:00 | 31d |  | 0 | 523569.1562 | 0 | 0 | 523569.1562 | 2012-06-01 08:00 | 30d | 523569.1562 | 0 | 0 | 21874.0703 | 0 | 545443.2266 | 0 | 100% | Finished | 523569.1562 | 523569.1562 | 100 | 96.7742 | 100 | 100 | 104.1779 | 100
60 | Parachèvements | 2011-12-05 08:00 | 2012-11-15 17:00 | 219d |  |  | 4917542.3281 |  |  | 4917542.3281 |  | 233d | [5 empty] | 5122991.1558 |  | 100% |  | 4917542.3281 | 4917542.3281
55 | Etanchéité provisoire +4 | 2012-03-16 08:00 | 2012-03-22 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-10-06 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
56 | Etanchéité provisoire +8 | 2012-04-19 08:00 | 2012-04-25 17:00 | 5d |  | 0 | 83348.1797 | 0 | 0 | 83348.1797 | 2011-11-29 08:00 | 5d | 83348.1797 | 0 | 0 | 3482.1799 | 0 | 86830.3596 | 0 | 100% | Finished | 83348.1797 | 83348.1797 | 100 | 100 | 100 | 100 | 104.1779 | 100
57 | Parachèvements sous-sols | 2011-12-05 08:00 | 2012-04-24 17:00 | 92d |  | 0 | 1500267.125 | 0 | 0 | 1500267.125 | 2012-01-20 08:00 | 96d | 1500267.125 | 0 | 0 | 62679.3008 | 0 | 1562946.4258 | 0 | 100% | Finished | 1500267.125 | 1500267.125 | 100 | 104.3478 | 100 | 100 | 104.1779 | 100
58 | Parachèvements hors sol | 2012-01-13 08:00 | 2012-11-07 17:00 | 194d |  | 0 | 3083882.5 | 0 | 0 | 3083882.5 | 2011-12-09 08:00 | 177d | 3083882.5 | 0 | 0 | 128840.7969 | 0 | 3212723.2969 | 0 | 100% | Finished | 3083882.5 | 3083882.5 | 100 | 91.2371 | 100 | 100 | 104.1779 | 100
59 | Finitions | 2012-10-30 08:00 | 2012-11-15 17:00 | 13d |  | 0 | 166696.3438 | 0 | 0 | 166696.3438 | 2012-09-25 08:00 | 10d | 166696.3438 | 0 | 0 | 6964.3701 | 0 | 173660.7139 | 0 | 100% | Finished | 166696.3438 | 166696.3438 | 100 | 76.9231 | 100 | 100 | 104.1779 | 100
61 | Abords | 2012-06-29 08:00 | 2012-09-21 17:00 | 41d |  | 0 | 328000 | 0 | 0 | 328000 | 2012-06-01 08:00 | 41d | 328000 | 0 | 0 | 13703.4297 | 0 | 341703.4297 | 0 | 100% | Finished | 328000 | 328000 | 100 | 100 | 100 | 100 | 104.1779 | 100
62 | Mise en état de réception | 2012-10-16 08:00 | 2012-11-23 17:00 | 29d |  | 0 | 10000 | 0 | 0 | 10000 | 2012-09-13 08:00 | 23d | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 100% | Finished | 10000 | 10000 | 100 | 79.3103 | 100 | 100 | 100 | 100
63 | Réserve pour intempéries et aléas | 2012-11-26 08:00 | 2012-12-21 17:00 | 20d |  | 0 | 1000 | 0 | 0 | 1000 | 2012-10-16 08:00 | 23d | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000 | 100 | 115 | 100 | 100 | 100 | 100
64 | Fin des travaux prêt pour RP | 2012-12-21 17:00 | 2012-12-21 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-15 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2011-07-04
1:00 - 2:00 | No | Tuesday | Yes | 2011-07-05
2:00 - 3:00 | No | Wednesday | Yes | 2011-07-06
3:00 - 4:00 | No | Thursday | Yes | 2011-07-07
4:00 - 5:00 | No | Friday | Yes | 2011-07-08
5:00 - 6:00 | No | Saturday | No | 2011-07-11
6:00 - 7:00 | No | Sunday | No | 2011-07-12
7:00 - 8:00 | No |  |  | 2011-07-13
8:00 - 9:00 | Yes |  |  | 2011-07-14
9:00 - 10:00 | Yes |  |  | 2011-07-15
10:00 - 11:00 | Yes |  |  | 2011-07-18
11:00 - 12:00 | Yes |  |  | 2011-07-19
12:00 - 13:00 | No |  |  | 2011-07-20
13:00 - 14:00 | Yes |  |  | 2011-07-21
14:00 - 15:00 | Yes |  |  | 2011-07-22
15:00 - 16:00 | Yes |  |  | 2011-07-25
16:00 - 17:00 | Yes |  |  | 2011-07-26
17:00 - 18:00 | No |  |  | 2011-07-27
18:00 - 19:00 | No |  |  | 2011-07-28
19:00 - 20:00 | No |  |  | 2011-07-29
20:00 - 21:00 | No |  |  | 2010-12-27
21:00 - 22:00 | No |  |  | 2010-12-28
22:00 - 23:00 | No |  |  | 2010-12-29
23:00 - 0:00 | No |  |  | 2010-12-30
2010-12-31
2011-01-03
Generated by PMConverter v1.1.3 |  |  |  | 2011-01-04
2011-01-05
2011-01-06
2011-01-07
2011-12-26
2011-12-27
2011-12-28
2011-12-29
2011-12-30
2012-01-02
2012-01-03
2012-01-04
2012-01-05
2012-01-06
2012-07-09
2012-07-10
2012-07-11
2012-07-12
2012-07-13
2012-07-16
2012-07-17
2012-07-18
2012-07-19
2012-07-20
2012-07-23
2012-07-24
2012-07-25
2012-07-26
2012-07-27
2012-07-30
2012-07-31
2012-08-01
2012-08-02
2012-08-03
2012-12-24
2012-12-25
2012-12-26
2012-12-27
2012-12-28
2012-12-31
2013-01-01
2013-01-02
2013-01-03
2013-01-04

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
31/12, 2010 | 2010-12-07 08:00 | 2010-12-31 17:00 | 1627216.125 | 1627216.125 | 1695199.1548 | 2010-12-24 17:00 | 0 | 100% | -67983.0298 | 95.99% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 10:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 10:00 | 38765805.7603 | 40314568.776 | 38765805.7603 | 38765805.7603 | 40314568.776 | 40314568.776 | 39994549.1046 | 39994549.1046 | 1 | 0.9599 | 1 | 1 | 0 | 0.9599 | 1 | 1 | 1
31/01, 2011 | 2010-12-31 17:00 | 2011-01-31 17:00 | 1627216.125 | 1627216.125 | 1695199.1548 | 2011-01-31 17:00 | 0 | 100% | -67983.0298 | 95.99% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-31 12:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-31 12:00 | 38765805.7603 | 40314568.776 | 38765805.7603 | 38765805.7603 | 40314568.776 | 40314568.776 | 39994549.1046 | 39994549.1046 | 1 | 0.9599 | 1 | 1 | 0 | 0.9599 | 1 | 1 | 1
28/02, 2011 | 2011-01-31 17:00 | 2011-02-28 17:00 | 4601594.875 | 4601594.875 | 4793843.7642 | 2011-02-28 17:00 | 0 | 100% | -192248.8892 | 95.99% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-30 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-30 15:00 | 38890071.6196 | 40314569.4531 | 38890071.6196 | 38890071.6196 | 40314569.4531 | 40314569.4531 | 40020226.5936 | 40020226.5936 | 1 | 0.9599 | 1 | 1 | 0 | 0.9599 | 1 | 1 | 1
31/03, 2011 | 2011-02-28 17:00 | 2011-03-31 17:00 | 4601594.875 | 4601594.875 | 4793843.7642 | 2011-03-31 17:00 | 0 | 100% | -192248.8892 | 95.99% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-29 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-29 15:00 | 38890071.6196 | 40314569.4531 | 38890071.6196 | 38890071.6196 | 40314569.4531 | 40314569.4531 | 40020226.5936 | 40020226.5936 | 1 | 0.9599 | 1 | 1 | 0 | 0.9599 | 1 | 1 | 1
30/04, 2011 | 2011-03-31 17:00 | 2011-04-30 17:00 | 5209025.7969 | 4669201.9844 | 4864275.4136 | 2011-04-19 17:00 | -539823.8125 | 89.64% | -195073.4292 | 95.99% | -8d | 91.49% | 100% | 2013-01-15 14:00 | 2013-03-22 15:00 | 2013-04-23 16:00 | 2013-01-18 15:00 | 2013-03-22 15:00 | 2013-04-17 17:00 | 2013-01-16 17:00 | 2013-03-08 09:00 | 2013-04-02 15:00 | 38892896.1597 | 40314569.4482 | 42827071.6027 | 42058349.2523 | 44413109.8292 | 43612271.2188 | 40790107.2854 | 40650120.9394 | 0.91489 | 0.9599 | 0.89637 | 1 | -8 | 0.9599 | 1 | 0.91489 | 1
31/05, 2011 | 2011-04-30 17:00 | 2011-05-31 17:00 | 6203438.0781 | 5919320.2969 | 6166622.1167 | 2011-05-19 17:00 | -284117.7812 | 95.42% | -247301.8198 | 95.99% | -8d | 93.1% | 100% | 2013-01-10 12:00 | 2013-02-06 15:00 | 2013-03-07 12:00 | 2013-01-14 11:00 | 2013-02-06 15:00 | 2013-02-28 14:00 | 2013-01-16 17:00 | 2013-02-25 09:00 | 2013-03-19 12:00 | 38945124.5503 | 40314569.5028 | 40518439.5454 | 41373161.7676 | 41953615.6363 | 42844047.087 | 40355149.6939 | 40521164.3744 | 0.93103 | 0.9599 | 0.9542 | 1 | -8 | 0.9599 | 1 | 0.93103 | 1
30/06, 2011 | 2011-05-31 17:00 | 2011-06-30 17:00 | 6913732.5781 | 6203438.0781 | 6462609.9878 | 2011-06-07 17:00 | -710294.5 | 89.73% | -259171.9097 | 95.99% | -17d | 87.68% | 100% | 2013-01-17 15:00 | 2013-03-22 10:00 | 2013-04-23 11:00 | 2013-01-25 09:00 | 2013-03-22 10:00 | 2013-04-15 14:00 | 2013-01-29 17:00 | 2013-04-09 14:00 | 2013-05-02 11:00 | 38956994.6401 | 40314569.5233 | 42677606.0831 | 43522321.4095 | 44190623.4742 | 45070629.9539 | 40762180.4453 | 40910913.1273 | 0.87681 | 0.9599 | 0.89726 | 1 | -17 | 0.9599 | 1 | 0.87681 | 1
31/07, 2011 | 2011-06-30 17:00 | 2011-07-31 17:00 | 6913732.5781 | 6203438.0781 | 6462609.9878 | 2011-06-07 17:00 | -710294.5 | 89.73% | -259171.9097 | 95.99% | -18d | 87.05% | 100% | 2013-01-17 15:00 | 2013-03-22 10:00 | 2013-04-23 11:00 | 2013-01-25 10:00 | 2013-03-22 10:00 | 2013-04-15 12:00 | 2013-01-30 17:00 | 2013-04-15 12:00 | 2013-05-08 12:00 | 38956994.6401 | 40314569.5233 | 42677606.0831 | 43790870.043 | 44190623.4742 | 45350398.2145 | 40762180.4453 | 40957048.0791 | 0.8705 | 0.9599 | 0.89726 | 1 | -18 | 0.9599 | 1 | 0.8705 | 1
31/08, 2011 | 2011-07-31 17:00 | 2011-08-31 17:00 | 7766085.9531 | 7766085.9531 | 8090543.2827 | 2011-08-31 17:00 | 0 | 100% | -324457.3296 | 95.99% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-02-01 15:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-23 17:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-23 17:00 | 39022280.0601 | 40314569.2228 | 39022280.0601 | 39022280.0601 | 40314569.2228 | 40314569.2228 | 40047544.5375 | 40047544.5375 | 1 | 0.9599 | 1 | 1 | 0 | 0.9599 | 1 | 1 | 1
30/09, 2011 | 2011-08-31 17:00 | 2011-09-30 17:00 | 8902557.0781 | 12380021.125 | 12758538.8145 | 2011-10-19 09:00 | 3477464.0469 | 139.1% | -378517.6895 | 97.03% | 12d 1h | 106.6% | 95.61% | 2012-10-24 11:00 | 2012-05-22 16:00 | 2012-06-06 10:00 | 2012-09-13 09:00 | 2012-05-22 16:00 | 2012-05-29 14:00 | 2012-12-05 16:00 | 2012-11-12 15:00 | 2012-11-22 14:00 | 39076340.4199 | 39881004.1079 | 31683848.2786 | 37449299.7853 | 32262487.389 | 38204216.8972 | 37718787.9294 | 39357085.0601 | 1.0659 | 0.97033 | 1.3906 | 0.95611 | 12.125 | 0.97033 | 1 | 1.0659 | 1
31/10, 2011 | 2011-09-30 17:00 | 2011-10-31 17:00 | 12948256.6875 | 20077038.9922 | 23473919.6516 | 2011-12-05 09:00 | 7128782.3047 | 155.1% | -3396880.6594 | 85.53% | 24d 1h | 111.8% | 66.59% | 2012-08-22 14:00 | 2012-04-03 15:00 | 2012-06-14 11:00 | 2012-06-20 09:00 | 2012-04-03 15:00 | 2012-04-26 15:00 | 2012-11-19 16:00 | 2012-10-15 09:00 | 2012-12-05 09:00 | 42094703.3899 | 45245196.855 | 35482995.6742 | 40134086.226 | 37514839.02 | 42952858.3388 | 42200605.0774 | 43986595.3368 | 1.1177 | 0.85529 | 1.5506 | 0.66593 | 24.125 | 0.85529 | 1 | 1.1177 | 1
30/11, 2011 | 2011-10-31 17:00 | 2011-11-30 17:00 | 16440789.0625 | 26008980.7969 | 29653690.5698 | 2011-12-16 09:00 | 9568191.7344 | 158.2% | -3644709.7729 | 87.71% | 11d 1h | 104.9% | 94.43% | 2012-06-13 15:00 | 2012-03-26 14:00 | 2012-05-23 14:00 | 2012-05-23 16:00 | 2012-03-26 14:00 | 2012-04-09 15:00 | 2012-12-06 16:00 | 2012-11-21 16:00 | 2013-01-18 11:00 | 42342532.5034 | 44120654.7053 | 37674557.4891 | 41749720.4656 | 38798543.5567 | 43444770.2916 | 42117333.7132 | 43574916.7707 | 1.049 | 0.87709 | 1.582 | 0.94434 | 11.125 | 0.87709 | 1 | 1.049 | 1
31/12, 2011 | 2011-11-30 17:00 | 2011-12-31 17:00 | 27342551.5625 | 30229334.4219 | 34050365.3315 | 2012-01-13 09:00 | 2886782.8594 | 110.6% | -3821030.9097 | 88.78% | 4d 1h | 101.7% | 95.16% | 2012-11-02 14:00 | 2012-10-19 15:00 | 2013-01-17 16:00 | 2012-11-16 10:00 | 2012-10-19 15:00 | 2012-11-22 09:00 | 2012-12-17 16:00 | 2012-12-12 09:00 | 2013-02-04 10:00 | 42518853.6401 | 43589282.6193 | 41710146.2252 | 42378067.6884 | 42678353.4358 | 43430701.1228 | 43143145.2206 | 43319650.1168 | 1.0169 | 0.88778 | 1.1056 | 0.9516 | 4.125 | 0.88778 | 1 | 1.0169 | 1
31/01, 2012 | 2011-12-31 17:00 | 2012-01-31 17:00 | 30994669.625 | 32297837.1094 | 36205287.4897 | 2012-03-13 09:00 | 1303167.4844 | 104.2% | -3907450.3804 | 89.21% | 29d 1h | 111.2% | 98.26% | 2012-11-29 17:00 | 2012-11-26 16:00 | 2013-02-25 16:00 | 2012-12-06 17:00 | 2012-11-26 16:00 | 2013-01-11 11:00 | 2012-11-12 16:00 | 2012-10-17 11:00 | 2012-11-14 11:00 | 42605273.1108 | 43379554.8736 | 42347043.6469 | 41962792.8654 | 43090084.345 | 42659346.2133 | 43146183.4149 | 43043038.7747 | 1.1116 | 0.89208 | 1.042 | 0.98262 | 29.125 | 0.89208 | 1 | 1.1116 | 1
29/02, 2012 | 2012-01-31 17:00 | 2012-02-29 17:00 | 32131140.75 | 33434308.2344 | 37389238.9546 | 2012-04-19 09:00 | 1303167.4844 | 104.1% | -3954930.7202 | 89.42% | 35d 1h | 112.5% | 100% | 2012-11-29 17:00 | 2012-11-27 12:00 | 2013-02-25 11:00 | 2012-12-06 14:00 | 2012-11-27 12:00 | 2013-01-08 17:00 | 2012-11-02 16:00 | 2012-10-10 12:00 | 2012-11-01 17:00 | 42652753.4507 | 43275372.4393 | 42447597.6898 | 42069762.6847 | 43045948.8869 | 42623419.9327 | 43088830.5872 | 42986998.1675 | 1.1246 | 0.89422 | 1.0406 | 1 | 35.125 | 0.89422 | 1 | 1.1246 | 1
31/03, 2012 | 2012-02-29 17:00 | 2012-03-31 17:00 | 32782724.4922 | 34144404.2812 | 38108822.7817 | 2012-05-03 09:00 | 1361679.7891 | 104.2% | -3964418.5005 | 89.6% | 23d 1h | 107.6% | 100% | 2012-11-29 11:00 | 2012-11-27 09:00 | 2013-02-21 16:00 | 2012-12-05 11:00 | 2012-11-27 09:00 | 2012-12-20 14:00 | 2012-11-20 16:00 | 2012-11-06 12:00 | 2012-11-28 11:00 | 42662241.231 | 43190926.8742 | 42480650.777 | 42340352.6512 | 42988252.4221 | 42831664.6437 | 43030989.3265 | 42994513.6232 | 1.0761 | 0.89597 | 1.0415 | 1 | 23.125 | 0.89597 | 1 | 1.0761 | 1
30/04, 2012 | 2012-03-31 17:00 | 2012-04-30 17:00 | 33917308.4844 | 34557305.7188 | 38538974.729 | 2012-05-15 09:00 | 639997.2344 | 101.9% | -3981669.0103 | 89.67% | 10d 1h | 103.1% | 100% | 2012-12-12 09:00 | 2012-12-11 10:00 | 2013-03-08 16:00 | 2012-12-13 16:00 | 2012-12-11 10:00 | 2013-01-16 11:00 | 2012-12-07 16:00 | 2012-12-03 14:00 | 2013-01-08 10:00 | 42679491.7407 | 43156559.2646 | 42602809.853 | 42554395.9265 | 43071042.1425 | 43017049.9967 | 43034056.8019 | 43022098.9955 | 1.0312 | 0.89668 | 1.0189 | 1 | 10.125 | 0.89668 | 1 | 1.0312 | 1
31/05, 2012 | 2012-04-30 17:00 | 2012-05-31 17:00 | 34557305.7188 | 34557305.7188 | 38538974.729 | 2012-05-31 17:00 | 0 | 100% | -3981669.0103 | 89.67% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-03-22 14:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-25 12:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-25 12:00 | 42679491.7407 | 43156559.2646 | 42679491.7407 | 42679491.7407 | 43156559.2646 | 43156559.2646 | 43052549.0779 | 43052549.0779 | 1 | 0.89668 | 1 | 1 | 0 | 0.89668 | 1 | 1 | 1
30/06, 2012 | 2012-05-31 17:00 | 2012-06-30 17:00 | 38382492.5742 | 35569044.3867 | 39592982.5869 | 2012-06-01 17:00 | -2813448.1875 | 92.67% | -4023938.2002 | 89.84% | -20d | 94.58% | 100% | 2013-02-22 12:00 | 2013-02-27 12:00 | 2013-05-20 11:00 | 2013-02-12 17:00 | 2013-02-27 12:00 | 2013-03-21 14:00 | 2013-02-01 17:00 | 2013-02-13 09:00 | 2013-03-06 09:00 | 42721760.9307 | 43075720.6986 | 42969241.7363 | 42901060.5492 | 43351199.0927 | 43275304.5446 | 43053890.9801 | 43039328.6112 | 0.9458 | 0.89837 | 0.9267 | 1 | -20 | 0.89837 | 1 | 0.9458 | 1
31/07, 2012 | 2012-06-30 17:00 | 2012-07-31 17:00 | 38382492.5742 | 35569044.3867 | 39592982.5869 | 2012-06-01 17:00 | -2813448.1875 | 92.67% | -4023938.2002 | 89.84% | -25d | 93.32% | 100% | 2013-02-22 12:00 | 2013-02-27 12:00 | 2013-05-20 11:00 | 2013-02-13 11:00 | 2013-02-27 12:00 | 2013-03-20 17:00 | 2013-02-08 17:00 | 2013-02-21 17:00 | 2013-03-15 09:00 | 42721760.9307 | 43075720.6986 | 42969241.7363 | 42945885.4539 | 43351199.0927 | 43325200.506 | 43053890.9801 | 43048955.4092 | 0.93316 | 0.89837 | 0.9267 | 1 | -25 | 0.89837 | 1 | 0.93316 | 1
31/08, 2012 | 2012-07-31 17:00 | 2012-08-31 17:00 | 38382492.5742 | 35569044.3867 | 39592982.5869 | 2012-06-01 17:00 | -2813448.1875 | 92.67% | -4023938.2002 | 89.84% | -45d | 88.58% | 100% | 2013-02-22 12:00 | 2013-02-27 12:00 | 2013-05-20 11:00 | 2013-02-14 16:00 | 2013-02-27 12:00 | 2013-03-18 15:00 | 2013-03-08 17:00 | 2013-04-02 09:00 | 2013-04-24 09:00 | 42721760.9307 | 43075720.6986 | 42969241.7363 | 43125185.0724 | 43351199.0927 | 43524784.352 | 43053890.9801 | 43085502.4316 | 0.88579 | 0.89837 | 0.9267 | 1 | -45 | 0.89837 | 1 | 0.88579 | 1
30/09, 2012 | 2012-08-31 17:00 | 2012-09-30 17:00 | 38520126.3867 | 38696822.7305 | 39776643.3008 | 2012-10-30 09:00 | 176696.3438 | 100.5% | -1079820.5703 | 97.29% | 21d 1h | 105.1% | 100% | 2012-12-19 16:00 | 2012-12-19 16:00 | 2013-01-21 17:00 | 2012-12-20 09:00 | 2012-12-19 16:00 | 2012-12-21 12:00 | 2012-11-22 16:00 | 2012-11-20 17:00 | 2012-11-21 17:00 | 39777643.3008 | 39777671.2054 | 39777638.7346 | 39777594.7515 | 39777666.5118 | 39777621.3014 | 39777664.5429 | 39777654.9472 | 1.051 | 0.97285 | 1.0046 | 1 | 21.125 | 0.97285 | 1 | 1.051 | 1
31/10, 2012 | 2012-09-30 17:00 | 2012-10-31 18:00 | 38696822.7305 | 38697822.7305 | 39777643.3008 | 2012-11-26 09:00 | 1000 | 100% | -1079820.5703 | 97.29% | 17d 1h | 103.9% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-24 10:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-07 17:00 | 2012-11-28 16:00 | 2012-11-28 09:00 | 2012-11-28 14:00 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 1.0392 | 0.97285 | 1 | 1 | 17.125 | 0.97285 | 1 | 1.0392 | 1
Actual Schedule | 2012-10-31 18:00 | 2012-11-30 17:00 | 38697822.7305 | 38697822.7305 | 39777643.3008 | 2012-11-30 17:00 | 0 | 100% | -1079820.5703 | 97.29% | 0 | 100% | 100% | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-24 10:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-07 11:00 | 2012-12-21 17:00 | 2012-12-21 17:00 | 2013-01-07 11:00 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 39777643.3008 | 1 | 0.97285 | 1 | 1 | 0 | 0.97285 | 1 | 1 | 1