## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Playing Cards | 1 |  |  | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 | 173.375
2 | Engineering | 1.1 |  | FS3;FS5;FS7 | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 6.375
3 | Bestellen aandrijfsysteem | 1.2 | 2FS | FS4 | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 4.375
4 | Levering aandrijfsysteem | 1.3 | 3FS | FS11 | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 55.375
5 | Bestellen machinebesturing | 1.4 | 2FS | FS6 | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 4.375
6 | Levering kast machinebesturing | 1.5 | 5FS | FS12 | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 69.375
7 | Werkvoorbereiding | 1.6 | 2FS | FS8 | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 13.375
8 | Productie onderdelen | 1.7 | 7FS | FS9 | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 41.375
9 | Toelevering spellenverzamelaar 1 | 1.8 | 8FS | FS10 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 0.375
10 | Montage M machine 1+2 | 1.9 | 9FS | FS11 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 11.375
11 | Montage spindel | 1.10 | 4FS;10FS | FS12 | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 4.375
12 | Montage E machine 1 | 1.11 | 6FS;11FS | FS13 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 11.375
13 | Inbedrijfname machine 1 mevi | 1.12 | 12FS | FS14 | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 4.375
14 | Transport naar cm | 1.13 | 13FS | FS15 | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 0.375
15 | Inbedrijfname machine 1 cm | 1.14 | 14FS | FS16 | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 6.375
16 | Machine 1 gereed | 1.15 | 15FS | FS17 | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
17 | Toelevering spellenverzamelaar 2 | 1.16 | 16FS | FS18 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 0.375
18 | Aanpassen onderdelen spv 2 | 1.17 | 17FS | FS19 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 13.375
19 | Montage M machine 2 | 1.18 | 18FS | FS20 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 13.375
20 | Montage E machine 2 | 1.19 | 19FS | FS21 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 13.375
21 | Inbedrijfname machine 2 mevi | 1.20 | 20FS | FS22 | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 6.375
22 | Transport naar cm | 1.21 | 21FS | FS23 | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 0.375
23 | Inbedrijfname machine 2 cm | 1.22 | 22FS | FS24 | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 6.375
24 | Machine 2 gereed | 1.23 | 23FS |  | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Playing Cards | 992h |  |  |  |  | 99 | 100 | 101
2 | Engineering | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Bestellen aandrijfsysteem | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Levering aandrijfsysteem | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Bestellen machinebesturing | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Levering kast machinebesturing | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Werkvoorbereiding | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Productie onderdelen | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Toelevering spellenverzamelaar 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Montage M machine 1+2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Montage spindel | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Montage E machine 1 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Inbedrijfname machine 1 mevi | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Transport naar cm | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Inbedrijfname machine 1 cm | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Machine 1 gereed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Toelevering spellenverzamelaar 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Aanpassen onderdelen spv 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Montage M machine 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Montage E machine 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Inbedrijfname machine 2 mevi | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Transport naar cm | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Inbedrijfname machine 2 cm | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Machine 2 gereed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-05-13 17:00 |  | TP Name | 13/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 6d | [5 empty] | 5771.7 |  | 3.014% |  | 5771.7 | 5771.7
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 1d | 520 | 0 | 2d | 0 | 0 | 520 | 0 | 33.33% | Started | 520 | 520 | 100 | 33.3333 | 33.3333 | 100 | 100 | 33.3333
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 |  | 0 | 0 | 6926.7998 | 40d | 0 | 0 | 0 | 6926.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 1d | 520 | 0 | 2d | 0 | 0 | 520 | 0 | 33.33% | Started | 520 | 520 | 100 | 33.3333 | 33.3333 | 100 | 100 | 33.3333
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 |  | 0 | 0 | 8658.5 | 50d | 0 | 0 | 0 | 8658.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 1d | 1731.7 | 0 | 9d | 0 | 0 | 1731.7 | 0 | 10% | Started | 1731.7 | 1731.7 | 100 | 10 | 10 | 100 | 100 | 10
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 |  | 0 | 0 | 51629 | 30d | 0 | 0 | 0 | 51629 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-05-20 17:00 |  | TP Name | 20/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 11d | [5 empty] | 21356.9998 |  | 11.15% |  | 21356.9998 | 21356.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 3d | 6926.7998 | 0 | 47d | 0 | 0 | 6926.7998 | 0 | 6% | Started | 6926.7998 | 6926.7998 | 100 | 7.5 | 6 | 100 | 100 | 6
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 3d | 8658.5 | 0 | 47d | 0 | 0 | 8658.5 | 0 | 6% | Started | 8658.5 | 8658.5 | 100 | 6 | 6 | 100 | 100 | 6
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 6d | 1731.7 | 0 | 4d | 0 | 0 | 1731.7 | 0 | 60% | Started | 1731.7 | 1731.7 | 100 | 60 | 60 | 100 | 100 | 60
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 |  | 0 | 0 | 51629 | 30d | 0 | 0 | 0 | 51629 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-05-27 17:00 |  | TP Name | 27/05, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 16d | [5 empty] | 72985.9998 |  | 38.11% |  | 72985.9998 | 72985.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 8d | 6926.7998 | 0 | 42d | 0 | 0 | 6926.7998 | 0 | 16% | Started | 6926.7998 | 6926.7998 | 100 | 20 | 16 | 100 | 100 | 16
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 8d | 8658.5 | 0 | 42d | 0 | 0 | 8658.5 | 0 | 16% | Started | 8658.5 | 8658.5 | 100 | 16 | 16 | 100 | 100 | 16
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 1d | 51629 | 0 | 29d | 0 | 0 | 51629 | 0 | 3.333% | Started | 51629 | 51629 | 100 | 3.3333 | 3.3333 | 100 | 100 | 3.3333
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-06-03 17:00 |  | TP Name | 03/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 21d | [5 empty] | 72985.9998 |  | 38.11% |  | 72985.9998 | 72985.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 13d | 6926.7998 | 0 | 37d | 0 | 0 | 6926.7998 | 0 | 26% | Started | 6926.7998 | 6926.7998 | 100 | 32.5 | 26 | 100 | 100 | 26
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 13d | 8658.5 | 0 | 37d | 0 | 0 | 8658.5 | 0 | 26% | Started | 8658.5 | 8658.5 | 100 | 26 | 26 | 100 | 100 | 26
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 6d | 51629 | 0 | 24d | 0 | 0 | 51629 | 0 | 20% | Started | 51629 | 51629 | 100 | 20 | 20 | 100 | 100 | 20
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-06-10 17:00 |  | TP Name | 10/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 26d | [5 empty] | 72985.9998 |  | 38.11% |  | 72985.9998 | 72985.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 18d | 6926.7998 | 0 | 32d | 0 | 0 | 6926.7998 | 0 | 36% | Started | 6926.7998 | 6926.7998 | 100 | 45 | 36 | 100 | 100 | 36
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 18d | 8658.5 | 0 | 32d | 0 | 0 | 8658.5 | 0 | 36% | Started | 8658.5 | 8658.5 | 100 | 36 | 36 | 100 | 100 | 36
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 11d | 51629 | 0 | 19d | 0 | 0 | 51629 | 0 | 36.67% | Started | 51629 | 51629 | 100 | 36.6667 | 36.6667 | 100 | 100 | 36.6667
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-06-17 17:00 |  | TP Name | 17/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 31d | [5 empty] | 72985.9998 |  | 38.11% |  | 72985.9998 | 72985.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 23d | 6926.7998 | 0 | 27d | 0 | 0 | 6926.7998 | 0 | 46% | Started | 6926.7998 | 6926.7998 | 100 | 57.5 | 46 | 100 | 100 | 46
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 23d | 8658.5 | 0 | 27d | 0 | 0 | 8658.5 | 0 | 46% | Started | 8658.5 | 8658.5 | 100 | 46 | 46 | 100 | 100 | 46
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 16d | 51629 | 0 | 14d | 0 | 0 | 51629 | 0 | 53.33% | Started | 51629 | 51629 | 100 | 53.3333 | 53.3333 | 100 | 100 | 53.3333
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2012-06-24 17:00 |  | TP Name | 24/06, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 36d | [5 empty] | 72985.9998 |  | 38.11% |  | 72985.9998 | 72985.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 28d | 6926.7998 | 0 | 22d | 0 | 0 | 6926.7998 | 0 | 56% | Started | 6926.7998 | 6926.7998 | 100 | 70 | 56 | 100 | 100 | 56
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 28d | 8658.5 | 0 | 22d | 0 | 0 | 8658.5 | 0 | 56% | Started | 8658.5 | 8658.5 | 100 | 56 | 56 | 100 | 100 | 56
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 21d | 51629 | 0 | 9d | 0 | 0 | 51629 | 0 | 70% | Started | 51629 | 51629 | 100 | 70 | 70 | 100 | 100 | 70
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2012-07-01 17:00 |  | TP Name | 01/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 41d | [5 empty] | 72985.9998 |  | 38.11% |  | 72985.9998 | 72985.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 33d | 6926.7998 | 0 | 17d | 0 | 0 | 6926.7998 | 0 | 66% | Started | 6926.7998 | 6926.7998 | 100 | 82.5 | 66 | 100 | 100 | 66
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 33d | 8658.5 | 0 | 17d | 0 | 0 | 8658.5 | 0 | 66% | Started | 8658.5 | 8658.5 | 100 | 66 | 66 | 100 | 100 | 66
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 26d | 51629 | 0 | 4d | 0 | 0 | 51629 | 0 | 86.67% | Started | 51629 | 51629 | 100 | 86.6667 | 86.6667 | 100 | 100 | 86.6667
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2012-07-08 17:00 |  | TP Name | 08/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 46d | [5 empty] | 74706.9998 |  | 39.01% |  | 74706.9998 | 74706.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 38d | 6926.7998 | 0 | 12d | 0 | 0 | 6926.7998 | 0 | 76% | Started | 6926.7998 | 6926.7998 | 100 | 95 | 76 | 100 | 100 | 76
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 38d | 8658.5 | 0 | 12d | 0 | 0 | 8658.5 | 0 | 76% | Started | 8658.5 | 8658.5 | 100 | 76 | 76 | 100 | 100 | 76
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2012-07-15 17:00 |  | TP Name | 15/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 51d | [5 empty] | 86944.9998 |  | 45.4% |  | 86944.9998 | 86944.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 43d | 6926.7998 | 0 | 7d | 0 | 0 | 6926.7998 | 0 | 86% | Started | 6926.7998 | 6926.7998 | 100 | 107.5 | 86 | 100 | 100 | 86
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 43d | 8658.5 | 0 | 7d | 0 | 0 | 8658.5 | 0 | 86% | Started | 8658.5 | 8658.5 | 100 | 86 | 86 | 100 | 100 | 86
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 5d | 12238 | 0 | 20d | 0 | 0 | 12238 | 0 | 20% | Started | 12238 | 12238 | 100 | 50 | 20 | 100 | 100 | 20
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2012-07-22 17:00 |  | TP Name | 22/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 56d | [5 empty] | 86944.9998 |  | 45.4% |  | 86944.9998 | 86944.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 48d | 6926.7998 | 0 | 2d | 0 | 0 | 6926.7998 | 0 | 96% | Started | 6926.7998 | 6926.7998 | 100 | 120 | 96 | 100 | 100 | 96
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 48d | 8658.5 | 0 | 2d | 0 | 0 | 8658.5 | 0 | 96% | Started | 8658.5 | 8658.5 | 100 | 96 | 96 | 100 | 100 | 96
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 10d | 12238 | 0 | 15d | 0 | 0 | 12238 | 0 | 40% | Started | 12238 | 12238 | 100 | 100 | 40 | 100 | 100 | 40
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2012-07-29 17:00 |  | TP Name | 29/07, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 61d | [5 empty] | 86944.9998 |  | 45.4% |  | 86944.9998 | 93063.9998
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 15d | 12238 | 0 | 10d | 0 | 0 | 12238 | 0 | 60% | Started | 12238 | 12238 | 100 | 150 | 60 | 100 | 100 | 60
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 6119 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2012-08-05 17:00 |  | TP Name | 05/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 66d | [5 empty] | 86944.9998 |  | 45.4% |  | 86944.9998 | 106915.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 20d | 12238 | 0 | 5d | 0 | 0 | 12238 | 0 | 80% | Started | 12238 | 12238 | 100 | 200 | 80 | 100 | 100 | 80
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 6119 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2012-08-12 17:00 |  | TP Name | 12/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 71d | [5 empty] | 86944.9998 |  | 45.4% |  | 86944.9998 | 106915.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 |  | 0 | 0 | 6119 | 5d | 0 | 0 | 0 | 6119 | 0% | Not Started | 0 | 6119 | 100 |  | 0 | 100 |  | 0
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2012-08-19 17:00 |  | TP Name | 19/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 76d | [5 empty] | 93063.9998 |  | 48.6% |  | 93063.9998 | 125272.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2012-08-26 17:00 |  | TP Name | 26/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 81d | [5 empty] | 105301.9994 |  | 55.83% |  | 106915.0994 | 134450.5994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 5d | 13851.0996 | 0 | 5d | -1613.1 | 0 | 12237.9996 | 0 | 50% | Started | 13851.0996 | 13851.0996 | 100 | 50 | 50 | 100 | 88.354 | 50
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2012-09-02 17:00 |  | TP Name | 02/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 86d | [5 empty] | 105301.9994 |  | 55.83% |  | 106915.0994 | 137868.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 1721 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 1696.5 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2012-09-09 17:00 |  | TP Name | 09/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 91d | [5 empty] | 124658.9994 |  | 65.42% |  | 125272.0994 | 137868.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 1721 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 1696.5 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2012-09-16 17:00 |  | TP Name | 16/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 96d | [5 empty] | 124658.9994 |  | 65.42% |  | 125272.0994 | 150106.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 1721 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 1696.5 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 12238 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2012-09-23 17:00 |  | TP Name | 23/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 101d | [5 empty] | 133837.4994 |  | 70.21% |  | 134450.5994 | 150106.0994
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 2d | 7648.75 | 0 | 3d | 0 | 0 | 7648.75 | 0 | 40% | Started | 7648.75 | 7648.75 | 100 | 40 | 40 | 100 | 100 | 40
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 |  | 0 | 0 | 1721 | 1d | 0 | 0 | 0 | 1721 | 0% | Not Started | 0 | 1721 | 100 |  | 0 | 100 |  | 0
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 |  | 0 | 0 | 1696.5 | 10d | 0 | 0 | 0 | 1696.5 | 0% | Not Started | 0 | 1696.5 | 100 |  | 0 | 100 |  | 0
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 12238 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2012-09-30 17:00 |  | TP Name | 30/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 106d | [5 empty] | 137254.9994 |  | 72% |  | 137868.0994 | 163957.199
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 1d | 1696.5 | 0 | 9d | 0 | 0 | 1696.5 | 0 | 10% | Started | 1696.5 | 1696.5 | 100 | 10 | 10 | 100 | 100 | 10
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 12238 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2012-10-07 17:00 |  | TP Name | 07/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 111d | [5 empty] | 137254.9994 |  | 72% |  | 137868.0994 | 163957.199
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 6d | 1696.5 | 0 | 4d | 0 | 0 | 1696.5 | 0 | 60% | Started | 1696.5 | 1696.5 | 100 | 60 | 60 | 100 | 100 | 60
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 |  | 0 | 0 | 12238 | 10d | 0 | 0 | 0 | 12238 | 0% | Not Started | 0 | 12238 | 100 |  | 0 | 100 |  | 0
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2012-10-14 17:00 |  | TP Name | 14/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 116d | [5 empty] | 149492.9994 |  | 78.39% |  | 150106.0994 | 182314.199
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 1d | 12238 | 0 | 9d | 0 | 0 | 12238 | 0 | 10% | Started | 12238 | 12238 | 100 | 10 | 10 | 100 | 100 | 10
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2012-10-21 17:00 |  | TP Name | 21/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 121d | [5 empty] | 149492.9994 |  | 78.39% |  | 150106.0994 | 191492.699
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 6d | 12238 | 0 | 4d | 0 | 0 | 12238 | 0 | 60% | Started | 12238 | 12238 | 100 | 60 | 60 | 100 | 100 | 60
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 |  | 0 | 0 | 13851.0996 | 10d | 0 | 0 | 0 | 13851.0996 | 0% | Not Started | 0 | 13851.0996 | 100 |  | 0 | 100 |  | 0
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2012-10-28 17:00 |  | TP Name | 28/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 126d | [5 empty] | 161730.999 |  | 85.62% |  | 163957.199 | 191492.699
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 10d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 100 | 100 | 100 | 100 | 100
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-10-26 08:00 | 1d | 13851.0996 | 0 | 9d | -1613.1 | 0 | 12237.9996 | 0 | 10% | Started | 13851.0996 | 13851.0996 | 100 | 10 | 10 | 100 | 88.354 | 10
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2012-11-04 17:00 |  | TP Name | 04/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 131d | [5 empty] | 161730.999 |  | 85.62% |  | 163957.199 | 191492.699
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 10d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 100 | 100 | 100 | 100 | 100
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-10-26 08:00 | 6d | 13851.0996 | 0 | 4d | -1613.1 | 0 | 12237.9996 | 0 | 60% | Started | 13851.0996 | 13851.0996 | 100 | 60 | 60 | 100 | 88.354 | 60
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 |  | 0 | 0 | 18357 | 5d | 0 | 0 | 0 | 18357 | 0% | Not Started | 0 | 18357 | 100 |  | 0 | 100 |  | 0
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2012-11-11 17:00 |  | TP Name | 11/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 136d | [5 empty] | 181087.999 |  | 95.21% |  | 182314.199 | 191492.699
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 10d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 100 | 100 | 100 | 100 | 100
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-10-26 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-11-09 08:00 | 1d | 18357 | 0 | 4d | 1000 | 0 | 19357 | 0 | 20% | Started | 18357 | 18357 | 100 | 20 | 20 | 100 | 105.4475 | 20
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 |  | 0 | 0 | 1529.75 | 1d | 0 | 0 | 0 | 1529.75 | 0% | Not Started | 0 | 1529.75 | 100 |  | 0 | 100 |  | 0
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2012-11-18 17:00 |  | TP Name | 18/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 141d | [5 empty] | 182617.749 |  | 96.01% |  | 183843.949 | 191492.699
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 10d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 100 | 100 | 100 | 100 | 100
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-10-26 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-11-09 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-11-16 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 |  | 0 | 0 | 7648.75 | 5d | 0 | 0 | 0 | 7648.75 | 0% | Not Started | 0 | 7648.75 | 100 |  | 0 | 100 |  | 0
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2012-11-25 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Playing Cards | 2012-05-04 08:00 | 2012-10-24 17:00 | 124d |  |  | 191492.699 |  |  | 191492.699 |  | 146d | [5 empty] | 190266.499 |  | 100% |  | 191492.699 | 191492.699
2 | Engineering | 2012-05-04 08:00 | 2012-05-10 17:00 | 5d |  | 0 | 3000 | 0 | 0 | 3000 | 2012-05-04 08:00 | 5d | 3000 | 0 | 0 | 0 | 0 | 3000 | 0 | 100% | Finished | 3000 | 3000 | 100 | 100 | 100 | 100 | 100 | 100
3 | Bestellen aandrijfsysteem | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
4 | Levering aandrijfsysteem | 2012-05-16 08:00 | 2012-07-10 17:00 | 40d |  | 0 | 6926.7998 | 0 | 0 | 6926.7998 | 2012-05-16 08:00 | 50d | 6926.7998 | 0 | 0 | 0 | 0 | 6926.7998 | 0 | 100% | Finished | 6926.7998 | 6926.7998 | 100 | 125 | 100 | 100 | 100 | 100
5 | Bestellen machinebesturing | 2012-05-11 08:00 | 2012-05-15 17:00 | 3d |  | 0 | 520 | 0 | 0 | 520 | 2012-05-11 08:00 | 3d | 520 | 0 | 0 | 0 | 0 | 520 | 0 | 100% | Finished | 520 | 520 | 100 | 100 | 100 | 100 | 100 | 100
6 | Levering kast machinebesturing | 2012-05-16 08:00 | 2012-07-24 17:00 | 50d |  | 0 | 8658.5 | 0 | 0 | 8658.5 | 2012-05-16 08:00 | 50d | 8658.5 | 0 | 0 | 0 | 0 | 8658.5 | 0 | 100% | Finished | 8658.5 | 8658.5 | 100 | 100 | 100 | 100 | 100 | 100
7 | Werkvoorbereiding | 2012-05-11 08:00 | 2012-05-24 17:00 | 10d |  | 0 | 1731.7 | 0 | 0 | 1731.7 | 2012-05-11 08:00 | 10d | 1731.7 | 0 | 0 | 0 | 0 | 1731.7 | 0 | 100% | Finished | 1731.7 | 1731.7 | 100 | 100 | 100 | 100 | 100 | 100
8 | Productie onderdelen | 2012-05-25 08:00 | 2012-07-05 17:00 | 30d |  | 0 | 51629 | 0 | 0 | 51629 | 2012-05-25 08:00 | 30d | 51629 | 0 | 0 | 0 | 0 | 51629 | 0 | 100% | Finished | 51629 | 51629 | 100 | 100 | 100 | 100 | 100 | 100
9 | Toelevering spellenverzamelaar 1 | 2012-07-06 08:00 | 2012-07-06 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-07-06 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
10 | Montage M machine 1+2 | 2012-07-09 08:00 | 2012-07-20 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-07-09 08:00 | 25d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 250 | 100 | 100 | 100 | 100
11 | Montage spindel | 2012-07-23 08:00 | 2012-07-27 17:00 | 5d |  | 0 | 6119 | 0 | 0 | 6119 | 2012-08-13 08:00 | 5d | 6119 | 0 | 0 | 0 | 0 | 6119 | 0 | 100% | Finished | 6119 | 6119 | 100 | 100 | 100 | 100 | 100 | 100
12 | Montage E machine 1 | 2012-07-30 08:00 | 2012-08-10 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-08-20 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
13 | Inbedrijfname machine 1 mevi | 2012-08-13 08:00 | 2012-08-17 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-09-03 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
14 | Transport naar cm | 2012-08-20 08:00 | 2012-08-20 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-09-19 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
15 | Inbedrijfname machine 1 cm | 2012-08-21 08:00 | 2012-08-27 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-09-20 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Machine 1 gereed | 2012-08-27 17:00 | 2012-08-27 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-09-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
17 | Toelevering spellenverzamelaar 2 | 2012-08-28 08:00 | 2012-08-28 17:00 | 1d |  | 0 | 1721 | 0 | 0 | 1721 | 2012-09-27 08:00 | 1d | 1721 | 0 | 0 | 0 | 0 | 1721 | 0 | 100% | Finished | 1721 | 1721 | 100 | 100 | 100 | 100 | 100 | 100
18 | Aanpassen onderdelen spv 2 | 2012-08-29 08:00 | 2012-09-11 17:00 | 10d |  | 0 | 1696.5 | 0 | 0 | 1696.5 | 2012-09-28 08:00 | 10d | 1696.5 | 0 | 0 | 0 | 0 | 1696.5 | 0 | 100% | Finished | 1696.5 | 1696.5 | 100 | 100 | 100 | 100 | 100 | 100
19 | Montage M machine 2 | 2012-09-12 08:00 | 2012-09-25 17:00 | 10d |  | 0 | 12238 | 0 | 0 | 12238 | 2012-10-12 08:00 | 10d | 12238 | 0 | 0 | 0 | 0 | 12238 | 0 | 100% | Finished | 12238 | 12238 | 100 | 100 | 100 | 100 | 100 | 100
20 | Montage E machine 2 | 2012-09-26 08:00 | 2012-10-09 17:00 | 10d |  | 0 | 13851.0996 | 0 | 0 | 13851.0996 | 2012-10-26 08:00 | 10d | 13851.0996 | 0 | 0 | -1613.1 | 0 | 12237.9996 | 0 | 100% | Finished | 13851.0996 | 13851.0996 | 100 | 100 | 100 | 100 | 88.354 | 100
21 | Inbedrijfname machine 2 mevi | 2012-10-10 08:00 | 2012-10-16 17:00 | 5d |  | 0 | 18357 | 0 | 0 | 18357 | 2012-11-09 08:00 | 5d | 18357 | 0 | 0 | 1000 | 0 | 19357 | 0 | 100% | Finished | 18357 | 18357 | 100 | 100 | 100 | 100 | 105.4475 | 100
22 | Transport naar cm | 2012-10-17 08:00 | 2012-10-17 17:00 | 1d |  | 0 | 1529.75 | 0 | 0 | 1529.75 | 2012-11-16 08:00 | 1d | 1529.75 | 0 | 0 | 0 | 0 | 1529.75 | 0 | 100% | Finished | 1529.75 | 1529.75 | 100 | 100 | 100 | 100 | 100 | 100
23 | Inbedrijfname machine 2 cm | 2012-10-18 08:00 | 2012-10-24 17:00 | 5d |  | 0 | 7648.75 | 0 | 0 | 7648.75 | 2012-11-19 08:00 | 5d | 7648.75 | 0 | 0 | 0 | 0 | 7648.75 | 0 | 100% | Finished | 7648.75 | 7648.75 | 100 | 100 | 100 | 100 | 100 | 100
24 | Machine 2 gereed | 2012-10-24 17:00 | 2012-10-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-23 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
13/05, 2012 | 2012-05-04 08:00 | 2012-05-13 17:00 | 5771.7 | 5771.7 | 5771.7 | 2012-05-11 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
20/05, 2012 | 2012-05-13 17:00 | 2012-05-20 17:00 | 21356.9998 | 21356.9998 | 21356.9998 | 2012-05-18 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
27/05, 2012 | 2012-05-20 17:00 | 2012-05-27 17:00 | 72985.9998 | 72985.9998 | 72985.9998 | 2012-05-25 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
03/06, 2012 | 2012-05-27 17:00 | 2012-06-03 17:00 | 72985.9998 | 72985.9998 | 72985.9998 | 2012-06-01 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
10/06, 2012 | 2012-06-03 17:00 | 2012-06-10 17:00 | 72985.9998 | 72985.9998 | 72985.9998 | 2012-06-08 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
17/06, 2012 | 2012-06-10 17:00 | 2012-06-17 17:00 | 72985.9998 | 72985.9998 | 72985.9998 | 2012-06-15 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
24/06, 2012 | 2012-06-17 17:00 | 2012-06-24 17:00 | 72985.9998 | 72985.9998 | 72985.9998 | 2012-06-22 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
01/07, 2012 | 2012-06-24 17:00 | 2012-07-01 17:00 | 72985.9998 | 72985.9998 | 72985.9998 | 2012-06-29 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
08/07, 2012 | 2012-07-01 17:00 | 2012-07-08 17:00 | 74706.9998 | 74706.9998 | 74706.9998 | 2012-07-06 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
15/07, 2012 | 2012-07-08 17:00 | 2012-07-15 17:00 | 86944.9998 | 86944.9998 | 86944.9998 | 2012-07-13 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
22/07, 2012 | 2012-07-15 17:00 | 2012-07-22 17:00 | 86944.9998 | 86944.9998 | 86944.9998 | 2012-07-20 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 17:00 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 191492.699 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
29/07, 2012 | 2012-07-22 17:00 | 2012-07-29 17:00 | 93063.9998 | 86944.9998 | 86944.9998 | 2012-07-20 17:00 | -6119 | 93.42% | 0 | 100% | -5d | 91.8% | 100% | 2012-10-30 17:00 | 2012-11-06 15:00 | 2012-11-06 15:00 | 2012-10-30 17:00 | 2012-11-06 15:00 | 2012-11-06 15:00 | 2012-10-31 17:00 | 2012-11-09 09:00 | 2012-11-09 09:00 | 191492.699 | 191492.699 | 198850.5387 | 200827.315 | 198850.5387 | 200827.315 | 192885.8305 | 193235.1606 | 0.91803 | 1 | 0.93425 | 1 | -5 | 1 | 1 | 0.91803 | 1
05/08, 2012 | 2012-07-29 17:00 | 2012-08-05 17:00 | 106915.0994 | 86944.9998 | 86944.9998 | 2012-07-20 17:00 | -19970.0996 | 81.32% | 0 | 100% | -10d | 84.85% | 100% | 2012-11-12 16:00 | 2012-12-04 12:00 | 2012-12-04 12:00 | 2012-11-12 11:00 | 2012-12-04 12:00 | 2012-12-04 12:00 | 2012-11-07 17:00 | 2012-11-26 09:00 | 2012-11-26 09:00 | 191492.699 | 191492.699 | 215505.9024 | 210161.931 | 215505.9024 | 210161.931 | 195549.8425 | 194759.8146 | 0.84848 | 1 | 0.81322 | 1 | -10 | 1 | 1 | 0.84848 | 1
12/08, 2012 | 2012-08-05 17:00 | 2012-08-12 17:00 | 106915.0994 | 86944.9998 | 86944.9998 | 2012-07-20 17:00 | -19970.0996 | 81.32% | 0 | 100% | -15d | 78.87% | 100% | 2012-11-12 16:00 | 2012-12-04 12:00 | 2012-12-04 12:00 | 2012-11-13 10:00 | 2012-12-04 12:00 | 2012-12-04 12:00 | 2012-11-14 17:00 | 2012-12-11 10:00 | 2012-12-11 10:00 | 191492.699 | 191492.699 | 215505.9024 | 219496.547 | 215505.9024 | 219496.547 | 195549.8425 | 196105.0975 | 0.78873 | 1 | 0.81322 | 1 | -15 | 1 | 1 | 0.78873 | 1
19/08, 2012 | 2012-08-12 17:00 | 2012-08-19 17:00 | 125272.0994 | 93063.9998 | 93063.9998 | 2012-07-27 17:00 | -32208.0996 | 74.29% | 0 | 100% | -15d | 80.26% | 100% | 2012-11-22 16:00 | 2012-12-24 16:00 | 2012-12-24 16:00 | 2012-11-21 12:00 | 2012-12-24 16:00 | 2012-12-24 16:00 | 2012-11-14 17:00 | 2012-12-06 12:00 | 2012-12-06 12:00 | 191492.699 | 191492.699 | 225557.4432 | 215696.4775 | 225557.4432 | 215696.4775 | 196828.3694 | 195537.714 | 0.80263 | 1 | 0.74289 | 1 | -15 | 1 | 1 | 0.80263 | 1
26/08, 2012 | 2012-08-19 17:00 | 2012-08-26 17:00 | 134450.5994 | 106915.0994 | 105301.9994 | 2012-08-10 17:00 | -27535.5 | 79.52% | 1613.1 | 101.5% | -10d | 87.65% | 100% | 2012-11-19 16:00 | 2012-12-07 16:00 | 2012-12-05 14:00 | 2012-11-16 14:00 | 2012-12-07 16:00 | 2012-12-06 15:00 | 2012-11-07 17:00 | 2012-11-19 12:00 | 2012-11-16 12:00 | 189879.599 | 188603.5199 | 211662.177 | 201791.937 | 210057.4495 | 200336.1284 | 192379.1475 | 190944.6788 | 0.87654 | 1.0153 | 0.7952 | 1 | -10 | 1.0153 | 1 | 0.87654 | 1
02/09, 2012 | 2012-08-26 17:00 | 2012-09-02 17:00 | 137868.0994 | 106915.0994 | 105301.9994 | 2012-08-10 17:00 | -30953 | 77.55% | 1613.1 | 101.5% | -15d | 82.56% | 100% | 2012-11-21 17:00 | 2012-12-13 16:00 | 2012-12-11 12:00 | 2012-11-21 10:00 | 2012-12-13 16:00 | 2012-12-12 15:00 | 2012-11-14 17:00 | 2012-11-30 10:00 | 2012-11-29 10:00 | 189879.599 | 188603.5199 | 214365.6674 | 207748.106 | 212720.1506 | 206202.4327 | 192734.0184 | 191837.79 | 0.82558 | 1.0153 | 0.77549 | 1 | -15 | 1.0153 | 1 | 0.82558 | 1
09/09, 2012 | 2012-09-02 17:00 | 2012-09-09 17:00 | 137868.0994 | 125272.0994 | 124658.9994 | 2012-08-17 17:00 | -12596 | 90.86% | 613.1 | 100.5% | -15d | 83.52% | 100% | 2012-11-06 09:00 | 2012-11-12 12:00 | 2012-11-09 15:00 | 2012-11-06 11:00 | 2012-11-12 12:00 | 2012-11-12 10:00 | 2012-11-14 17:00 | 2012-11-28 12:00 | 2012-11-28 10:00 | 190879.599 | 190555.5057 | 197538.0224 | 203949.4542 | 197181.3418 | 203561.3951 | 191842.879 | 192859.6311 | 0.83516 | 1.0049 | 0.90864 | 1 | -15 | 1.0049 | 1 | 0.83516 | 1
16/09, 2012 | 2012-09-09 17:00 | 2012-09-16 17:00 | 150106.0994 | 125272.0994 | 124658.9994 | 2012-08-17 17:00 | -24834 | 83.46% | 613.1 | 100.5% | -20d | 79.17% | 100% | 2012-11-16 09:00 | 2012-11-28 14:00 | 2012-11-27 16:00 | 2012-11-15 16:00 | 2012-11-28 14:00 | 2012-11-28 11:00 | 2012-11-21 17:00 | 2012-12-10 14:00 | 2012-12-10 11:00 | 190879.599 | 190555.5057 | 204007.2019 | 208306.0726 | 203618.8602 | 207896.6916 | 192868.1707 | 193476.2167 | 0.79167 | 1.0049 | 0.83456 | 1 | -20 | 1.0049 | 1 | 0.79167 | 1
23/09, 2012 | 2012-09-16 17:00 | 2012-09-23 17:00 | 150106.0994 | 134450.5994 | 133837.4994 | 2012-08-27 17:00 | -15655.5 | 89.57% | 613.1 | 100.5% | -19d | 81.19% | 100% | 2012-11-08 09:00 | 2012-11-14 12:00 | 2012-11-13 15:00 | 2012-11-08 12:00 | 2012-11-14 12:00 | 2012-11-14 10:00 | 2012-11-20 17:00 | 2012-12-04 15:00 | 2012-12-04 12:00 | 190879.599 | 190619.4848 | 197521.6117 | 204096.6709 | 197231.2097 | 203776.2863 | 191877.5692 | 192884.787 | 0.81188 | 1.0046 | 0.8957 | 1 | -19 | 1.0046 | 1 | 0.81188 | 1
30/09, 2012 | 2012-09-23 17:00 | 2012-09-30 17:00 | 163957.199 | 137868.0994 | 137254.9994 | 2012-09-11 17:00 | -26089.0996 | 84.09% | 613.1 | 100.4% | -13d | 87.74% | 100% | 2012-11-16 16:00 | 2012-11-27 12:00 | 2012-11-26 15:00 | 2012-11-16 16:00 | 2012-11-27 12:00 | 2012-11-27 10:00 | 2012-11-12 17:00 | 2012-11-19 11:00 | 2012-11-19 09:00 | 190879.599 | 190641.1302 | 201027.1061 | 198375.5108 | 200743.5113 | 198103.7076 | 192438.5785 | 192027.3429 | 0.87736 | 1.0045 | 0.84088 | 1 | -13 | 1.0045 | 1 | 0.87736 | 1
07/10, 2012 | 2012-09-30 17:00 | 2012-10-07 17:00 | 163957.199 | 137868.0994 | 137254.9994 | 2012-09-11 17:00 | -26089.0996 | 84.09% | 613.1 | 100.4% | -18d | 83.78% | 100% | 2012-11-16 16:00 | 2012-11-27 12:00 | 2012-11-26 15:00 | 2012-11-19 14:00 | 2012-11-27 12:00 | 2012-11-27 10:00 | 2012-11-19 17:00 | 2012-11-27 17:00 | 2012-11-27 16:00 | 190879.599 | 190641.1302 | 201027.1061 | 201258.5538 | 200743.5113 | 200973.9297 | 192438.5785 | 192473.1358 | 0.83784 | 1.0045 | 0.84088 | 1 | -18 | 1.0045 | 1 | 0.83784 | 1
14/10, 2012 | 2012-10-07 17:00 | 2012-10-14 17:00 | 182314.199 | 150106.0994 | 149492.9994 | 2012-09-25 17:00 | -32208.0996 | 82.33% | 613.1 | 100.4% | -13d | 88.79% | 100% | 2012-11-22 16:00 | 2012-11-30 14:00 | 2012-11-29 17:00 | 2012-11-22 12:00 | 2012-11-30 14:00 | 2012-11-30 12:00 | 2012-11-12 17:00 | 2012-11-15 14:00 | 2012-11-15 12:00 | 190879.599 | 190710.5577 | 199759.8759 | 196103.1504 | 199554.5636 | 195912.7738 | 192250.0286 | 191686.8878 | 0.88793 | 1.0041 | 0.82334 | 1 | -13 | 1.0041 | 1 | 0.88793 | 1
21/10, 2012 | 2012-10-14 17:00 | 2012-10-21 17:00 | 191492.699 | 150106.0994 | 149492.9994 | 2012-09-25 17:00 | -41386.5996 | 78.39% | 613.1 | 100.4% | -18d | 85.12% | 100% | 2012-11-30 15:00 | 2012-12-12 10:00 | 2012-12-11 12:00 | 2012-11-30 09:00 | 2012-12-12 10:00 | 2012-12-11 17:00 | 2012-11-19 17:00 | 2012-11-23 14:00 | 2012-11-23 14:00 | 190879.599 | 190710.5577 | 202290.5319 | 198112.2086 | 202074.8833 | 197913.6262 | 192601.5392 | 192004.9372 | 0.85124 | 1.0041 | 0.78387 | 1 | -18 | 1.0041 | 1 | 0.85124 | 1
28/10, 2012 | 2012-10-21 17:00 | 2012-10-28 17:00 | 191492.699 | 163957.199 | 161730.999 | 2012-10-09 17:00 | -27535.5 | 85.62% | 2226.2 | 101.4% | -13d | 89.68% | 100% | 2012-11-19 16:00 | 2012-11-22 16:00 | 2012-11-20 16:00 | 2012-11-22 09:00 | 2012-11-27 09:00 | 2012-11-26 16:00 | 2012-11-12 17:00 | 2012-11-14 10:00 | 2012-11-14 09:00 | 189266.499 | 188892.6238 | 193890.8996 | 192434.2999 | 193454.2346 | 192017.4125 | 189763.9988 | 189534.0493 | 0.89683 | 1.0138 | 0.85621 | 1 | -13 | 1.0138 | 1 | 0.89683 | 1
04/11, 2012 | 2012-10-28 17:00 | 2012-11-04 17:00 | 191492.699 | 163957.199 | 161730.999 | 2012-10-09 17:00 | -27535.5 | 85.62% | 2226.2 | 101.4% | -18d | 86.26% | 100% | 2012-11-19 16:00 | 2012-11-22 16:00 | 2012-11-20 16:00 | 2012-11-29 16:00 | 2012-12-04 17:00 | 2012-12-04 15:00 | 2012-11-19 17:00 | 2012-11-21 15:00 | 2012-11-21 14:00 | 189266.499 | 188892.6238 | 193890.8996 | 193652.6849 | 193454.2346 | 193219.2543 | 189763.9988 | 189727.5761 | 0.8626 | 1.0138 | 0.85621 | 1 | -18 | 1.0138 | 1 | 0.8626 | 1
11/11, 2012 | 2012-11-04 17:00 | 2012-11-11 17:00 | 191492.699 | 182314.199 | 181087.999 | 2012-10-16 17:00 | -9178.5 | 95.21% | 1226.2 | 100.7% | -18d | 86.76% | 100% | 2012-11-01 17:00 | 2012-11-02 10:00 | 2012-11-01 11:00 | 2012-11-20 12:00 | 2012-11-20 16:00 | 2012-11-20 15:00 | 2012-11-19 17:00 | 2012-11-20 16:00 | 2012-11-20 16:00 | 190266.499 | 190204.7667 | 190728.5852 | 191666.6092 | 190663.745 | 191595.4601 | 190304.9265 | 190463.895 | 0.86765 | 1.0068 | 0.95207 | 1 | -18 | 1.0068 | 1 | 0.86765 | 1
18/11, 2012 | 2012-11-11 17:00 | 2012-11-18 17:00 | 191492.699 | 183843.949 | 182617.749 | 2012-10-17 17:00 | -7648.75 | 96.01% | 1226.2 | 100.7% | -22d | 84.4% | 100% | 2012-10-31 17:00 | 2012-11-01 09:00 | 2012-10-31 10:00 | 2012-11-26 14:00 | 2012-11-26 16:00 | 2012-11-26 16:00 | 2012-11-23 17:00 | 2012-11-26 16:00 | 2012-11-26 16:00 | 190266.499 | 190215.4835 | 190584.722 | 191680.5536 | 190531.584 | 191620.1067 | 190286.5675 | 190469.3371 | 0.84397 | 1.0067 | 0.96006 | 1 | -22 | 1.0067 | 1 | 0.84397 | 1
Actual Schedule | 2012-11-18 17:00 | 2012-11-25 17:00 | 191492.699 | 191492.699 | 190266.499 | 2012-10-24 17:00 | 0 | 100% | 1226.2 | 100.6% | -22d | 84.93% | 100% | 2012-10-24 17:00 | 2012-10-24 17:00 | 2012-10-24 10:00 | 2012-11-23 17:00 | 2012-11-23 17:00 | 2012-11-23 17:00 | 2012-11-23 17:00 | 2012-11-23 17:00 | 2012-11-23 17:00 | 190266.499 | 190266.499 | 190266.499 | 190266.499 | 190266.499 | 190266.499 | 190266.499 | 190266.499 | 0.84932 | 1.0064 | 1 | 1 | -22 | 1.0064 | 1 | 0.84932 | 1