## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Organizational Development | 1 |  |  | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 | 318.2917
85 | Department A | 1.1 |  |  | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 | 115.375
1 | Directieteam | 1.1.1 |  | FS107 | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
107 | Directieteam extra | 1.1.2 | 1FS | FS2 | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 0.041667
2 | Organisatorische oefening | 1.1.3 | 107FS | FS3 | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
3 | Opleiding | 1.1.4 | 2FS | FS108 | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
108 | Opleiding extra | 1.1.5 | 3FS | FS4 | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
4 | Testfase | 1.1.6 | 108FS | FS5 | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
5 | Live | 1.1.7 | 4FS | FS109 | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
109 | Live extra | 1.1.8 | 5FS | FS6 | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 0.041667
6 | Optimalisatie/standaardisatie | 1.1.9 | 109FS |  | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
86 | Department B | 1.2 |  |  | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 | 115.375
7 | Directieteam | 1.2.1 |  | FS110 | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
110 | Directieteam extra | 1.2.2 | 7FS | FS8 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
8 | Organisatorische oefening | 1.2.3 | 110FS | FS111 | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
111 | Organisatorische oefening extra | 1.2.4 | 8FS | FS9 | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
9 | Opleiding | 1.2.5 | 111FS | FS112 | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
112 | Opleiding extra | 1.2.6 | 9FS | FS10 | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
10 | Testfase | 1.2.7 | 112FS | FS11 | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
11 | Live | 1.2.8 | 10FS | FS12 | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
12 | Live extra | 1.2.9 | 11FS |  | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
87 | Department C | 1.3 |  |  | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 | 113.1667
13 | Directieteam | 1.3.1 |  | FS14 | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
14 | Organisatorische oefening | 1.3.2 | 13FS | FS113 | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
113 | Organisatorische oefening extra | 1.3.3 | 14FS | FS15 | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
15 | Opleiding | 1.3.4 | 113FS | FS16 | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
16 | Testfase | 1.3.5 | 15FS | FS17 | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
17 | Live | 1.3.6 | 16FS | FS18 | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
18 | Optimalisatie/standaardisatie | 1.3.7 | 17FS |  | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
88 | Department D | 1.4 |  |  | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 | 114.2917
19 | Directieteam | 1.4.1 |  | FS20 | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
20 | Organisatorische oefening | 1.4.2 | 19FS | FS114 | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
114 | Organisatorische oefening extra | 1.4.3 | 20FS | FS21 | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
21 | Opleiding | 1.4.4 | 114FS | FS115 | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
115 | Opleiding extra | 1.4.5 | 21FS | FS22 | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
22 | Testfase | 1.4.6 | 115FS | FS23 | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
23 | Live | 1.4.7 | 22FS | FS24 | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
24 | Optimalisatie/standaardisatie | 1.4.8 | 23FS |  | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
89 | Department E | 1.5 |  |  | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 | 141.125
25 | Directieteam | 1.5.1 |  | FS116 | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
116 | Directieteam extra | 1.5.2 | 25FS | FS26 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
26 | Organisatorische oefening | 1.5.3 | 116FS | FS117 | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 48.375
117 | Organisatorische oefening extra | 1.5.4 | 26FS | FS27 | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
27 | Opleiding | 1.5.5 | 117FS | FS28 | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
28 | Testfase | 1.5.6 | 27FS | FS29 | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
29 | Live | 1.5.7 | 28FS | FS30 | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
30 | Optimalisatie/standaardisatie | 1.5.8 | 29FS |  | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
90 | Department F | 1.6 |  |  | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 | 112.0833
31 | Directieteam | 1.6.1 |  | FS32 | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
32 | Organisatorische oefening | 1.6.2 | 31FS | FS33 | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
33 | Opleiding | 1.6.3 | 32FS | FS34 | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
34 | Testfase | 1.6.4 | 33FS | FS35 | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
35 | Live | 1.6.5 | 34FS | FS36 | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
36 | Optimalisatie/standaardisatie | 1.6.6 | 35FS |  | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
91 | Department G | 1.7 |  |  | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 | 114.2917
37 | Directieteam | 1.7.1 |  | FS118 | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
118 | Directieteam extra | 1.7.2 | 37FS | FS38 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
38 | Organisatorische oefening | 1.7.3 | 118FS | FS119 | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
119 | Organisatorische oefening extra | 1.7.4 | 38FS | FS39 | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
39 | Opleiding | 1.7.5 | 119FS | FS40 | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
40 | Testfase | 1.7.6 | 39FS | FS41 | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
41 | Live | 1.7.7 | 40FS | FS42 | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
42 | Optimalisatie/standaardisatie | 1.7.8 | 41FS |  | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
92 | Department H | 1.8 |  |  | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 | 112.0417
43 | Directieteam | 1.8.1 |  | FS44 | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
44 | Organisatorische oefening | 1.8.2 | 43FS | FS45 | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 7
45 | Opleiding | 1.8.3 | 44FS | FS46 | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
46 | Testfase | 1.8.4 | 45FS | FS47 | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 27.375
47 | Live | 1.8.5 | 46FS | FS48 | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 6.375
48 | Optimalisatie/standaardisatie | 1.8.6 | 47FS |  | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
93 | Department I | 1.9 |  |  | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 | 115.375
49 | Directieteam | 1.9.1 |  | FS120 | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
120 | Directieteam extra | 1.9.2 | 49FS | FS50 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
50 | Organisatorische oefening | 1.9.3 | 120FS | FS121 | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
121 | Organisatorische oefening extra | 1.9.4 | 50FS | FS51 | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
51 | Opleiding | 1.9.5 | 121FS | FS122 | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
122 | Opleiding extra | 1.9.6 | 51FS | FS52 | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
52 | Testfase | 1.9.7 | 122FS | FS53 | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
53 | Live | 1.9.8 | 52FS | FS54 | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
54 | Optimalisatie/standaardisatie | 1.9.9 | 53FS |  | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
106 | Department J | 1.10 |  |  | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 | 42.125
100 | Directieteam | 1.10.1 |  | FS101 | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
101 | Organisatorische oefening | 1.10.2 | 100FS | FS102 | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 7
102 | Opleiding | 1.10.3 | 101FS | FS103 | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
103 | Testfase | 1.10.4 | 102FS | FS104 | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 28
104 | Live | 1.10.5 | 103FS | FS105 | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
105 | Optimalisatie/standaardisatie | 1.10.6 | 104FS |  | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
94 | Department K | 1.11 |  |  | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 | 112.0833
55 | Directieteam | 1.11.1 |  | FS56 | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
56 | Organisatorische oefening | 1.11.2 | 55FS | FS57 | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
57 | Opleiding | 1.11.3 | 56FS | FS58 | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
58 | Testfase | 1.11.4 | 57FS | FS59 | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
59 | Live | 1.11.5 | 58FS | FS60 | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
60 | Optimalisatie/standaardisatie | 1.11.6 | 59FS |  | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
95 | Department L | 1.12 |  |  | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 | 112.0833
61 | Directieteam | 1.12.1 |  | FS62 | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
62 | Organisatorische oefening | 1.12.2 | 61FS | FS63 | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
63 | Opleiding | 1.12.3 | 62FS | FS64 | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
64 | Testfase | 1.12.4 | 63FS | FS65 | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
65 | Live | 1.12.5 | 64FS | FS66 | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
66 | Optimalisatie/standaardisatie | 1.12.6 | 65FS |  | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
96 | Department M | 1.13 |  |  | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 | 112.0833
67 | Directieteam | 1.13.1 |  | FS68 | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
68 | Organisatorische oefening | 1.13.2 | 67FS | FS69 | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
69 | Opleiding | 1.13.3 | 68FS | FS70 | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
70 | Testfase | 1.13.4 | 69FS | FS71 | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
71 | Live | 1.13.5 | 70FS | FS72 | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
72 | Optimalisatie/standaardisatie | 1.13.6 | 71FS |  | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
97 | Department N | 1.14 |  |  | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 | 120.1667
73 | Directieteam | 1.14.1 |  | FS123 | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
123 | Directieteam extra 1 | 1.14.2 | 73FS | FS124 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
124 | Directieteam extra 2 | 1.14.3 | 123FS | FS74 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
74 | Organisatorische oefening | 1.14.4 | 124FS | FS125 | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 49
125 | Organisatorische oefening extra | 1.14.5 | 74FS | FS75 | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
75 | Opleiding | 1.14.6 | 125FS | FS126 | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 21
126 | Opleiding extra 1 | 1.14.7 | 75FS | FS127 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
127 | Opleiding extra 2 | 1.14.8 | 126FS | FS76 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
76 | Testfase | 1.14.9 | 127FS | FS77 | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 35
77 | Live | 1.14.10 | 76FS | FS78 | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 7
78 | Optimalisatie/standaardisatie | 1.14.11 | 77FS |  | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
98 | Department O | 1.15 |  |  | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 | 112.0833
79 | Directieteam | 1.15.1 |  | FS80 | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667
80 | Organisatorische oefening | 1.15.2 | 79FS | FS81 | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 7
81 | Opleiding | 1.15.3 | 80FS | FS82 | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 0.041667
82 | Testfase | 1.15.4 | 81FS | FS83 | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 27.375
83 | Live | 1.15.5 | 82FS | FS84 | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 6.375
84 | Optimalisatie/standaardisatie | 1.15.6 | 83FS | FS128 | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 0.041667
128 | Hiatus | 1.15.7 | 84FS |  | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 0.041667

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Personeel | Renewable | 10 | 0 | 15 | 1[0.80 Personeel];107[0.80 Personeel];2[0.40 Personeel];3[0.60 Personeel];108[0.60 Personeel];4[0.20 Personeel];5[0.01 Personeel];109[0.01 Personeel];6[0.40 Personeel];7[0.80 Personeel];110[0.80 Personeel];8[0.40 Personeel];111[0.40 Personeel];9[0.60 Personeel];112[0.60 Personeel];10[0.20 Personeel];11[0.01 Personeel];12[0.40 Personeel];13[0.80 Personeel];14[0.40 Personeel];113[0.40 Personeel];15[0.60 Personeel];16[0.20 Personeel];17[0.01 Personeel];18[0.40 Personeel];19[0.80 Personeel];20[0.40 Personeel];114[0.40 Personeel];21[0.60 Personeel];115[0.60 Personeel];22[0.20 Personeel];23[0.01 Personeel];24[0.40 Personeel];25[0.80 Personeel];116[0.80 Personeel];26[0.40 Personeel];117[0.40 Personeel];27[0.60 Personeel];28[0.20 Personeel];29[0.01 Personeel];30[0.40 Personeel];31[0.80 Personeel];32[0.40 Personeel];33[0.60 Personeel];34[0.20 Personeel];35[0.01 Personeel];36[0.40 Personeel];37[0.80 Personeel];118[0.80 Personeel];38[0.40 Personeel];119[0.40 Personeel];39[0.60 Personeel];40[0.20 Personeel];41[0.01 Personeel];42[0.40 Personeel];43[0.80 Personeel];44[0.40 Personeel];45[0.60 Personeel];46[0.20 Personeel];47[0.01 Personeel];48[0.40 Personeel];49[0.80 Personeel];120[0.80 Personeel];50[0.40 Personeel];121[0.40 Personeel];51[0.60 Personeel];122[0.60 Personeel];52[0.20 Personeel];53[0.01 Personeel];54[0.40 Personeel];100[0.80 Personeel];101[0.40 Personeel];102[0.60 Personeel];103[0.20 Personeel];104[0.01 Personeel];105[0.40 Personeel];55[0.80 Personeel];56[0.40 Personeel];57[0.60 Personeel];58[0.20 Personeel];59[0.01 Personeel];60[0.40 Personeel];61[0.80 Personeel];62[0.40 Personeel];63[0.60 Personeel];64[0.20 Personeel];65[0.01 Personeel];66[0.40 Personeel];67[0.80 Personeel];68[0.40 Personeel];69[0.60 Personeel];70[0.20 Personeel];71[0.01 Personeel];72[0.40 Personeel];73[0.80 Personeel];123[0.80 Personeel];124[0.80 Personeel];74[0.40 Personeel];125[0.40 Personeel];75[0.60 Personeel];126[0.60 Personeel];127[0.60 Personeel];76[0.20 Personeel];77[0.01 Personeel];78[0.40 Personeel];79[0.80 Personeel];80[0.40 Personeel];81[0.60 Personeel];82[0.20 Personeel];83[0.01 Personeel];84[0.40 Personeel];128[0.80 Personeel]; | 43059.1484

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Organizational Development | 1830h |  |  |  |  | 99 | 100 | 101
85 | Department A | 672h |  |  |  |  | 99 | 100 | 101
1 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | Directieteam extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | Opleiding extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Live extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Department B | 672h |  |  |  |  | 99 | 100 | 101
7 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | Directieteam extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Opleiding extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Live extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Department C | 652h |  |  |  |  | 99 | 100 | 101
13 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Department D | 662h |  |  |  |  | 99 | 100 | 101
19 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Opleiding extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Department E | 811h |  |  |  |  | 99 | 100 | 101
25 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | Directieteam extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Department F | 642h |  |  |  |  | 99 | 100 | 101
31 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Department G | 662h |  |  |  |  | 99 | 100 | 101
37 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | Directieteam extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Department H | 641h |  |  |  |  | 99 | 100 | 101
43 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Organisatorische oefening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Opleiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Testfase | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Department I | 672h |  |  |  |  | 99 | 100 | 101
49 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | Directieteam extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | Opleiding extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | Department J | 243h |  |  |  |  | 99 | 100 | 101
100 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | Organisatorische oefening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | Opleiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | Testfase | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | Department K | 642h |  |  |  |  | 99 | 100 | 101
55 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Department L | 642h |  |  |  |  | 99 | 100 | 101
61 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Department M | 642h |  |  |  |  | 99 | 100 | 101
67 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Department N | 692h |  |  |  |  | 99 | 100 | 101
73 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | Directieteam extra 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | Directieteam extra 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Organisatorische oefening | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Organisatorische oefening extra | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Opleiding | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Opleiding extra 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | Opleiding extra 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Testfase | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | Department O | 642h |  |  |  |  | 99 | 100 | 101
79 | Directieteam | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Organisatorische oefening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | Opleiding | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | Testfase | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Live | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | Optimalisatie/standaardisatie | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | Hiatus | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-08-12 17:00 |  | TP Name | 12/08, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 20d | [5 empty] | 2400 |  | 3.947% |  | 1704 | 1995
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 20d | [5 empty] | 1200 |  | 24.23% |  | 852 | 1029
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 |  | 0 | 0 | 123 | 1h | 0 | 0 | 0 | 123 | 0% | Not Started | 0 | 123 | 100 |  | 0 | 100 |  | 0
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 15d | 720 | 720 | 15d | 0 | 0 | 720 | 720 | 50% | Started | 840 | 894 | 100 | 42.8571 | 50 | 100 | 42.8571 | 50
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 20d | [5 empty] | 1200 |  | 25.13% |  | 852 | 966
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 15d | 720 | 720 | 15d | 0 | 0 | 720 | 720 | 50% | Started | 840 | 954 | 100 | 42.8571 | 50 | 100 | 42.8571 | 50
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-09-09 17:00 |  | TP Name | 09/09, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 40d | [5 empty] | 9720 |  | 9.819% |  | 4239 | 4437
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 40d | [5 empty] | 6960 |  | 61.86% |  | 2175 | 2076
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 5d | 360 | 720 | 10d | 0 | 0 | 360 | 720 | 33.33% | Started | 360 | 261 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 150
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 126 | 100 |  | 0 | 100 |  | 0
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 40d | [5 empty] | 2280 |  | 60.53% |  | 2052 | 1959
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 5d | 360 | 720 | 10d | 0 | 0 | 360 | 720 | 33.33% | Started | 360 | 261 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 5d | [5 empty] | 480 |  | 0.3518% |  | 12 | 150
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 126 | 100 |  | 0 | 100 |  | 0
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 102
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2012-10-07 17:00 |  | TP Name | 07/10, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 60d | [5 empty] | 13362 |  | 16.91% |  | 7302.2308 | 10323
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 60d | [5 empty] | 7920 |  | 89.16% |  | 3135 | 3081
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 10d | 240 | 360 | 15d | 0 | 0 | 240 | 360 | 40% | Started | 240 | 177 | 100 | 40 | 40 | 100 | 40 | 40
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1110
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1086 | 100 |  | 0 | 100 |  | 0
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 60d | [5 empty] | 3240 |  | 88.85% |  | 3012 | 2985
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 10d | 240 | 360 | 15d | 0 | 0 | 240 | 360 | 40% | Started | 240 | 207 | 100 | 40 | 40 | 100 | 40 | 40
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 15d | [5 empty] | 501 |  | 66.53% |  | 501 | 252
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 0 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 10d | 240 | 240 | 10d | 0 | 0 | 240 | 240 | 50% | Started | 240 | 0 | 100 | 50 | 50 | 100 | 50 | 50
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 25d | [5 empty] | 720 |  | 4.14% |  | 141.2308 | 1110
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 5d | 240 | 2880 | 60d | 0 | 0 | 240 | 2880 | 7.692% | Started | 129.2308 | 1086 | 100 | 14.2857 | 7.6923 | 100 | 14.2857 | 7.6923
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 15d | [5 empty] | 501 |  | 66.53% |  | 501 | 471
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 10d | 240 | 240 | 10d | 0 | 0 | 240 | 240 | 50% | Started | 240 | 210 | 100 | 50 | 50 | 100 | 50 | 50
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1062
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1026 | 100 |  | 0 | 100 |  | 0
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 15d | [5 empty] | 480 |  | 1.569% |  | 12 | 252
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 |  | 0 | 0 | 240 | 5d | 0 | 0 | 0 | 240 | 0% | Not Started | 0 | 240 | 100 |  | 0 | 100 |  | 0
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 |  | 0 | 0 | 480 | 20d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2012-11-04 17:00 |  | TP Name | 04/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 80d | [5 empty] | 17697 |  | 22.99% |  | 9925.4286 | 15013.2
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 80d | [5 empty] | 8400 |  | 96.96% |  | 3409.2857 | 3506.85
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 30d | 720 | 120 | 5d | 0 | 0 | 720 | 120 | 85.71% | Started | 514.2857 | 600 | 100 | 120 | 85.7143 | 100 | 120 | 85.7143
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 2.85 | 100 |  | 0 | 100 |  | 0
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2169
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 459 | 100 |  | 0 | 100 |  | 0
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 80d | [5 empty] | 3720 |  | 96.94% |  | 3286.2857 | 3382.35
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 30d | 720 | 120 | 5d | 0 | 0 | 720 | 120 | 85.71% | Started | 514.2857 | 600 | 100 | 120 | 85.7143 | 100 | 120 | 85.7143
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 4.35 | 100 |  | 0 | 100 |  | 0
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 35d | [5 empty] | 981 |  | 89.3% |  | 672.4286 | 252
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 0 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 30d | 720 | 120 | 5d | 0 | 0 | 720 | 120 | 85.71% | Started | 411.4286 | 0 | 100 | 150 | 85.7143 | 100 | 150 | 85.7143
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 45d | [5 empty] | 1680 |  | 16.77% |  | 572 | 2169
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 25d | 1200 | 2400 | 50d | 0 | 0 | 1200 | 2400 | 33.33% | Started | 560 | 1680 | 100 | 71.4286 | 33.3333 | 100 | 71.4286 | 33.3333
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 459 | 100 |  | 0 | 100 |  | 0
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 35d | [5 empty] | 981 |  | 89.3% |  | 672.4286 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 30d | 720 | 120 | 5d | 0 | 0 | 720 | 120 | 85.71% | Started | 411.4286 | 480 | 100 | 150 | 85.7143 | 100 | 150 | 85.7143
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 438
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 426 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 20d | [5 empty] | 1200 |  | 21.33% |  | 732 | 2091
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 15d | 720 | 960 | 20d | 0 | 0 | 720 | 960 | 42.86% | Started | 720 | 1680 | 100 | 42.8571 | 42.8571 | 100 | 42.8571 | 42.8571
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 369 | 100 |  | 0 | 100 |  | 0
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 35d | [5 empty] | 735 |  | 75.95% |  | 581 | 252
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 0 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 10d | 240 | 120 | 5d | 0 | 0 | 240 | 120 | 66.67% | Started | 320 | 0 | 100 | 50 | 66.6667 | 100 | 50 | 66.6667
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2012-12-02 17:00 |  | TP Name | 02/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 100d | [5 empty] | 23667 |  | 28.12% |  | 12139.7 | 19272.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 100d | [5 empty] | 8538 |  | 99.46% |  | 3497.25 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 30 | 25d | 0 | 0 | 18 | 30 | 37.5% | Started | 2.25 | 6 | 100 | 300 | 37.5 | 100 | 300 | 37.5
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0.15 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 5d | [5 empty] | 480 |  | 0.3518% |  | 12 | 3042
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 243 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 100d | [5 empty] | 3858 |  | 99.58% |  | 3375.6 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 12 | 10d | 0 | 0 | 18 | 12 | 60% | Started | 3.6 | 6 | 100 | 300 | 60 | 100 | 300 | 60
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 5d | [5 empty] | 480 |  | 0.353% |  | 12 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 0 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 10d | [5 empty] | 720 |  | 7.407% |  | 252 | 24
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 5d | 240 | 1440 | 30d | 0 | 0 | 240 | 1440 | 14.29% | Started | 240 | 0 | 100 | 14.2857 | 14.2857 | 100 | 14.2857 | 14.2857
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 10d | [5 empty] | 720 |  | 7.447% |  | 252 | 0
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 0 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 5d | 240 | 1440 | 30d | 0 | 0 | 240 | 1440 | 14.29% | Started | 240 | 0 | 100 | 14.2857 | 14.2857 | 100 | 14.2857 | 14.2857
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 20d | [5 empty] | 960 |  | 14.46% |  | 492 | 390
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 10d | 480 | 1200 | 25d | 0 | 0 | 480 | 1200 | 28.57% | Started | 480 | 366 | 100 | 28.5714 | 28.5714 | 100 | 28.5714 | 28.5714
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 55d | [5 empty] | 1119 |  | 98.88% |  | 744.6 | 357
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 96 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 12 | 10d | 0 | 0 | 18 | 12 | 60% | Started | 3.6 | 0 | 100 | 300 | 60 | 100 | 300 | 60
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 65d | [5 empty] | 2640 |  | 29.9% |  | 1020 | 3042
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 45d | 2160 | 1440 | 30d | 0 | 0 | 2160 | 1440 | 60% | Started | 1008 | 1680 | 100 | 128.5714 | 60 | 100 | 128.5714 | 60
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 243 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d | [5 empty] | 1119 |  | 99.2% |  | 747 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1398
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1386 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 40d | [5 empty] | 2160 |  | 28.9% |  | 992 | 3003
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 35d | 1680 | 1200 | 25d | 0 | 0 | 1680 | 1200 | 58.33% | Started | 980 | 1680 | 100 | 100 | 58.3333 | 100 | 100 | 58.3333
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 183 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 55d | [5 empty] | 873 |  | 97.16% |  | 743.25 | 357
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 96 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 30 | 25d | 0 | 0 | 18 | 30 | 37.5% | Started | 2.25 | 0 | 100 | 300 | 37.5 | 100 | 300 | 37.5
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2012-12-30 17:00 |  | TP Name | 30/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 120d | [5 empty] | 30717 |  | 40.52% |  | 17491.9797 | 25239.3
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 120d | [5 empty] | 8562 |  | 99.53% |  | 3499.6667 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 35d | 42 | 12 | 10d | 0 | 0 | 42 | 12 | 77.78% | Started | 4.6667 | 6 | 100 | 700 | 77.7778 | 100 | 700 | 77.7778
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0.15 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 25d | [5 empty] | 1440 |  | 39.75% |  | 1356 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 20d | 960 | 240 | 5d | 0 | 0 | 960 | 240 | 80% | Started | 1344 | 1680 | 100 | 57.1429 | 80 | 100 | 57.1429 | 80
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 25d | [5 empty] | 1440 |  | 33.3% |  | 1132 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 0 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 20d | 960 | 480 | 10d | 0 | 0 | 960 | 480 | 66.67% | Started | 1120 | 0 | 100 | 57.1429 | 66.6667 | 100 | 57.1429 | 66.6667
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 30d | [5 empty] | 1680 |  | 41.5% |  | 1412 | 456
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 25d | 1200 | 240 | 5d | 0 | 0 | 1200 | 240 | 83.33% | Started | 1400 | 432 | 100 | 71.4286 | 83.3333 | 100 | 71.4286 | 83.3333
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 30d | [5 empty] | 1680 |  | 27.94% |  | 945.3334 | 438
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 25d | 1200 | 960 | 20d | 0 | 0 | 1200 | 960 | 55.56% | Started | 933.3334 | 426 | 100 | 71.4286 | 55.5556 | 100 | 71.4286 | 55.5556
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 40d | [5 empty] | 1920 |  | 17.78% |  | 604.9412 | 1350
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 30d | 1440 | 2640 | 55d | 0 | 0 | 1440 | 2640 | 35.29% | Started | 592.9412 | 1326 | 100 | 85.7143 | 35.2941 | 100 | 85.7143 | 35.2941
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 741
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 0 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 0 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 85d | [5 empty] | 3600 |  | 43.04% |  | 1468 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 65d | 3120 | 480 | 10d | 0 | 0 | 3120 | 480 | 86.67% | Started | 1456 | 1680 | 100 | 185.7143 | 86.6667 | 100 | 185.7143 | 86.6667
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2691
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 999 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 918
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 906 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 60d | [5 empty] | 3120 |  | 41.77% |  | 1433.5385 | 3423.15
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 55d | 2640 | 480 | 10d | 0 | 0 | 2640 | 480 | 84.62% | Started | 1421.5385 | 1680 | 100 | 157.1429 | 84.6154 | 100 | 157.1429 | 84.6154
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 3.15 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 75d | [5 empty] | 897 |  | 97.32% |  | 744.5 | 741
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 35d | 42 | 30 | 25d | 0 | 0 | 42 | 30 | 58.33% | Started | 3.5 | 0 | 100 | 700 | 58.3333 | 100 | 700 | 58.3333
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-01-27 17:00 |  | TP Name | 27/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 140d | [5 empty] | 41175 |  | 56.56% |  | 24416.6027 | 30408.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 140d | [5 empty] | 9294 |  | 99.74% |  | 3507 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 10d | 720 | 360 | 5d | 0 | 0 | 720 | 360 | 66.67% | Started | 6 | 9 | 100 | 8000 | 66.6667 | 100 | 8000 | 66.6667
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 |  | 0 | 0 | 0.15 | 1h | 0 | 0 | 0 | 0.15 | 0% | Not Started | 0 | 0.15 | 100 |  | 0 | 100 |  | 0
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 45d | [5 empty] | 2880 |  | 71.06% |  | 2424 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 10d | 720 | 360 | 5d | 0 | 0 | 720 | 360 | 66.67% | Started | 720 | 1080 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 45d | [5 empty] | 2520 |  | 81.57% |  | 2772.5455 | 0
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 0 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 0 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 5d | 240 | 2400 | 50d | 0 | 0 | 240 | 2400 | 9.091% | Started | 0.54545 | 0 | 100 | 4000 | 9.0909 | 100 | 4000 | 9.0909
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 0 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 50d | [5 empty] | 3120 |  | 71.25% |  | 2424 | 1416
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1392 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 10d | 720 | 360 | 5d | 0 | 0 | 720 | 360 | 66.67% | Started | 720 | 0 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 50d | [5 empty] | 2640 |  | 30.14% |  | 1020 | 1398
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 45d | 2160 | 1440 | 30d | 0 | 0 | 2160 | 1440 | 60% | Started | 1008 | 1386 | 100 | 128.5714 | 60 | 100 | 128.5714 | 60
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 60d | [5 empty] | 2880 |  | 31.22% |  | 1062 | 2529
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 50d | 2400 | 1440 | 30d | 0 | 0 | 2400 | 1440 | 62.5% | Started | 1050 | 1680 | 100 | 142.8571 | 62.5 | 100 | 142.8571 | 62.5
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 819 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 105d | [5 empty] | 4680 |  | 81.29% |  | 2772.8571 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 5d | 240 | 1440 | 30d | 0 | 0 | 240 | 1440 | 14.29% | Started | 0.85714 | 6 | 100 | 4000 | 14.2857 | 100 | 4000 | 14.2857
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3225
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 453 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 438
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 426 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1971
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 279 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 80d | [5 empty] | 4440 |  | 81.12% |  | 2784 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 95d | [5 empty] | 2343 |  | 98.59% |  | 754.2 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 15d | 1440 | 960 | 10d | 0 | 0 | 1440 | 960 | 60% | Started | 7.2 | 12 | 100 | 12000 | 60 | 100 | 12000 | 60

## TP8
| TP Status Date | 2013-02-24 17:00 |  | TP Name | 24/02, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 160d | [5 empty] | 49833 |  | 60.33% |  | 26046.063 | 36378.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 160d | [5 empty] | 9906 |  | 99.86% |  | 3511.35 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 9 | 9 | 100 | 12000 | 100 | 100 | 12000 | 100
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 0.15 | 0.15 | 100 | 8000 | 100 | 100 | 8000 | 100
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 5d | 240 | 960 | 20d | 0 | 0 | 240 | 960 | 20% | Started | 1.2 | 6 | 100 | 4000 | 20 | 100 | 4000 | 20
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 65d | [5 empty] | 3960 |  | 81.72% |  | 2787.6 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 15d | 720 | 480 | 10d | 0 | 0 | 720 | 480 | 60% | Started | 3.6 | 6 | 100 | 12000 | 60 | 100 | 12000 | 60
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 65d | [5 empty] | 3480 |  | 81.63% |  | 2774.7273 | 678
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 666 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 25d | 1200 | 1440 | 30d | 0 | 0 | 1200 | 1440 | 45.45% | Started | 2.7273 | 0 | 100 | 20000 | 45.4545 | 100 | 20000 | 45.4545
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 0 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 70d | [5 empty] | 4200 |  | 81.97% |  | 2788.5 | 2628
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 15d | 720 | 240 | 5d | 0 | 0 | 720 | 240 | 75% | Started | 4.5 | 6 | 100 | 12000 | 75 | 100 | 12000 | 75
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 918 | 100 | 100 | 100 | 100 | 100 | 100
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 70d | [5 empty] | 3600 |  | 43.38% |  | 1468 | 2691
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 65d | 3120 | 480 | 10d | 0 | 0 | 3120 | 480 | 86.67% | Started | 1456 | 1680 | 100 | 185.7143 | 86.6667 | 100 | 185.7143 | 86.6667
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 999 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 80d | [5 empty] | 3840 |  | 43.56% |  | 1482 | 3183
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 70d | 3360 | 480 | 10d | 0 | 0 | 3360 | 480 | 87.5% | Started | 1470 | 1680 | 100 | 200 | 87.5 | 100 | 200 | 87.5
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 393 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 125d | [5 empty] | 5640 |  | 81.39% |  | 2776.2857 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 25d | 1200 | 480 | 10d | 0 | 0 | 1200 | 480 | 71.43% | Started | 4.2857 | 6 | 100 | 20000 | 71.4286 | 100 | 20000 | 71.4286
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3384
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1398
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1386 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2985
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 213 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 100d | [5 empty] | 5520 |  | 81.49% |  | 2796.6 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 |  | 0 | 0 | 12 | 1h | 0 | 0 | 0 | 12 | 0% | Not Started | 0 | 12 | 100 |  | 0 | 100 |  | 0
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 15d | 720 | 480 | 10d | 0 | 0 | 720 | 480 | 60% | Started | 3.6 | 6 | 100 | 12000 | 60 | 100 | 12000 | 60
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 100% |  | 765 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 12 | 12 | 100 | 20000 | 100 | 100 | 20000 | 100

## TP9
| TP Status Date | 2013-03-24 17:00 |  | TP Name | 24/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 180d | [5 empty] | 60408 |  | 63.67% |  | 27485.3363 | 40363.8
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 180d | [5 empty] | 10866 |  | 99.91% |  | 3513.15 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 9 | 9 | 100 | 12000 | 100 | 100 | 12000 | 100
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 0.15 | 0.15 | 100 | 8000 | 100 | 100 | 8000 | 100
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 25d | 1200 | 1200 | 25d | 0 | 0 | 1200 | 1200 | 50% | Started | 3 | 6 | 100 | 20000 | 50 | 100 | 20000 | 50
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 85d | [5 empty] | 4920 |  | 81.76% |  | 2788.6667 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 35d | 1680 | 480 | 10d | 0 | 0 | 1680 | 480 | 77.78% | Started | 4.6667 | 6 | 100 | 28000 | 77.7778 | 100 | 28000 | 77.7778
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 85d | [5 empty] | 4440 |  | 81.66% |  | 2775.6 | 1638
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1626 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 45d | 2160 | 1440 | 30d | 0 | 0 | 2160 | 1440 | 60% | Started | 3.6 | 0 | 100 | 36000 | 60 | 100 | 36000 | 60
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 0 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 90d | [5 empty] | 4695 |  | 99.69% |  | 3391.5 | 3216
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-03-11 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 426 | 100 | 0.5 | 100 | 100 | 0.5 | 100
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-11 08:00 | 10d | 12 | 36 | 30d | 0 | 0 | 12 | 36 | 25% | Started | 1.5 | 0 | 100 | 200 | 25 | 100 | 200 | 25
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 90d | [5 empty] | 4560 |  | 43.38% |  | 1468 | 3225
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 85d | 4080 | 1200 | 25d | 0 | 0 | 4080 | 1200 | 86.67% | Started | 1456 | 1680 | 100 | 242.8571 | 86.6667 | 100 | 242.8571 | 86.6667
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 453 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 100d | [5 empty] | 5040 |  | 50.13% |  | 1705.5 | 3402
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 80d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 1680 | 1680 | 100 | 228.5714 | 100 | 100 | 228.5714 | 100
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-18 08:00 | 5d | 240 | 720 | 15d | 0 | 0 | 240 | 720 | 25% | Started | 1.5 | 6 | 100 | 4000 | 25 | 100 | 4000 | 25
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 145d | [5 empty] | 6960 |  | 81.86% |  | 2792.25 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 35d | 1680 | 0 | 0 | 0 | 0 | 1680 | 0 | 100% | Finished | 6 | 6 | 100 | 28000 | 100 | 100 | 28000 | 100
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 5d | 360 | 1080 | 15d | 0 | 0 | 360 | 1080 | 25% | Started | 2.25 | 9 | 100 | 4000 | 25 | 100 | 4000 | 25
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 20d | [5 empty] | 1200 |  | 11.81% |  | 399.6923 | 3384
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-04 08:00 | 15d | 720 | 2400 | 50d | 0 | 0 | 720 | 2400 | 23.08% | Started | 387.6923 | 1680 | 100 | 42.8571 | 23.0769 | 100 | 42.8571 | 23.0769
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 20d | [5 empty] | 480 |  | 0.3546% |  | 12 | 2691
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 999 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 10d | [5 empty] | 720 |  | 4.868% |  | 164.7273 | 3376.65
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-18 08:00 | 5d | 240 | 2400 | 50d | 0 | 0 | 240 | 2400 | 9.091% | Started | 152.7273 | 1680 | 100 | 14.2857 | 9.0909 | 100 | 14.2857 | 9.0909
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 4.65 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 120d | [5 empty] | 6840 |  | 81.97% |  | 2813.25 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 5d | 360 | 1080 | 15d | 0 | 0 | 360 | 1080 | 25% | Started | 2.25 | 9 | 100 | 4000 | 25 | 100 | 4000 | 25
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 100% |  | 765 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 12 | 12 | 100 | 20000 | 100 | 100 | 20000 | 100

## TP10
| TP Status Date | 2013-04-21 17:00 |  | TP Name | 21/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 200d | [5 empty] | 69336 |  | 69.12% |  | 29838.265 | 42432.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 200d | [5 empty] | 11826 |  | 99.98% |  | 3515.55 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 9 | 9 | 100 | 12000 | 100 | 100 | 12000 | 100
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 0.15 | 0.15 | 100 | 8000 | 100 | 100 | 8000 | 100
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 45d | 2160 | 240 | 5d | 0 | 0 | 2160 | 240 | 90% | Started | 5.4 | 6 | 100 | 36000 | 90 | 100 | 36000 | 90
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 105d | [5 empty] | 5415 |  | 99.42% |  | 3391.3333 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 45d | 2160 | 0 | 0 | 0 | 0 | 2160 | 0 | 100% | Finished | 6 | 6 | 100 | 36000 | 100 | 100 | 36000 | 100
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-08 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-08 08:00 | 10d | 12 | 42 | 35d | 0 | 0 | 12 | 42 | 22.22% | Started | 1.3333 | 6 | 100 | 200 | 22.2222 | 100 | 200 | 22.2222
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 105d | [5 empty] | 5400 |  | 81.71% |  | 2777.2 | 2820
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 65d | 3120 | 480 | 10d | 0 | 0 | 3120 | 480 | 86.67% | Started | 5.2 | 6 | 100 | 52000 | 86.6667 | 100 | 52000 | 86.6667
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 33 | 100 |  | 0 | 100 |  | 0
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 110d | [5 empty] | 4719 |  | 99.78% |  | 3394.5 | 3402
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-03-11 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-11 08:00 | 30d | 36 | 12 | 10d | 0 | 0 | 36 | 12 | 75% | Started | 4.5 | 6 | 100 | 600 | 75 | 100 | 600 | 75
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 110d | [5 empty] | 5520 |  | 47.74% |  | 1615.6363 | 3384
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 105d | 5040 | 240 | 5d | 0 | 0 | 5040 | 240 | 95.45% | Started | 1603.6363 | 1680 | 100 | 300 | 95.4545 | 100 | 300 | 95.4545
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 120d | [5 empty] | 6120 |  | 54.23% |  | 1845 | 3402
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 80d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 1680 | 1680 | 100 | 228.5714 | 100 | 100 | 228.5714 | 100
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-18 08:00 | 20d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 100% | Finished | 6 | 6 | 100 | 16000 | 100 | 100 | 16000 | 100
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-15 08:00 | 5d | 360 | 2520 | 35d | 0 | 0 | 360 | 2520 | 12.5% | Started | 135 | 1080 | 100 | 33.3333 | 12.5 | 100 | 33.3333 | 12.5
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 165d | [5 empty] | 8049 |  | 99.66% |  | 3399.4615 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 35d | 1680 | 0 | 0 | 0 | 0 | 1680 | 0 | 100% | Finished | 6 | 6 | 100 | 28000 | 100 | 100 | 28000 | 100
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 20d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 9 | 9 | 100 | 16000 | 100 | 100 | 16000 | 100
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-15 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-15 08:00 | 5d | 6 | 72 | 60d | 0 | 0 | 6 | 72 | 7.692% | Started | 0.46154 | 6 | 100 | 100 | 7.6923 | 100 | 100 | 7.6923
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 40d | [5 empty] | 2160 |  | 18.65% |  | 630.9474 | 3384
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-04 08:00 | 35d | 1680 | 2880 | 60d | 0 | 0 | 1680 | 2880 | 36.84% | Started | 618.9474 | 1680 | 100 | 100 | 36.8421 | 100 | 100 | 36.8421
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 40d | [5 empty] | 480 |  | 0.3546% |  | 12 | 3225
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 |  | 0 | 0 | 1680 | 35d | 0 | 0 | 0 | 1680 | 0% | Not Started | 0 | 1680 | 100 |  | 0 | 100 |  | 0
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 453 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 30d | [5 empty] | 1680 |  | 22.92% |  | 775.6364 | 3384
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-18 08:00 | 25d | 1200 | 1440 | 30d | 0 | 0 | 1200 | 1440 | 45.45% | Started | 763.6364 | 1680 | 100 | 71.4286 | 45.4545 | 100 | 71.4286 | 45.4545
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 140d | [5 empty] | 8280 |  | 82.17% |  | 2820 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 25d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 9 | 9 | 100 | 20000 | 100 | 100 | 20000 | 100
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 100% |  | 765 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 12 | 12 | 100 | 20000 | 100 | 100 | 20000 | 100

## TP11
| TP Status Date | 2013-05-19 17:00 |  | TP Name | 19/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 220d | [5 empty] | 75447 |  | 81.42% |  | 35149.4105 | 43071.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 205d | [5 empty] | 12066 |  | 100% |  | 3516.15 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 9 | 9 | 100 | 12000 | 100 | 100 | 12000 | 100
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 0.15 | 0.15 | 100 | 8000 | 100 | 100 | 8000 | 100
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 50d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 6 | 6 | 100 | 40000 | 100 | 100 | 40000 | 100
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 125d | [5 empty] | 5439 |  | 99.5% |  | 3394 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 45d | 2160 | 0 | 0 | 0 | 0 | 2160 | 0 | 100% | Finished | 6 | 6 | 100 | 36000 | 100 | 100 | 36000 | 100
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 |  | 0 | 0 | 9 | 1h | 0 | 0 | 0 | 9 | 0% | Not Started | 0 | 9 | 100 |  | 0 | 100 |  | 0
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-08 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-08 08:00 | 30d | 36 | 18 | 15d | 0 | 0 | 36 | 18 | 66.67% | Started | 4 | 6 | 100 | 600 | 66.6667 | 100 | 600 | 66.6667
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 125d | [5 empty] | 6249 |  | 99.67% |  | 3387.6667 | 3300
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 6 | 6 | 100 | 60000 | 100 | 100 | 60000 | 100
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-05-06 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-13 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 513 | 100 | 0.5 | 100 | 100 | 0.5 | 100
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-13 08:00 | 5d | 6 | 48 | 40d | 0 | 0 | 6 | 48 | 11.11% | Started | 0.66667 | 0 | 100 | 100 | 11.1111 | 100 | 100 | 11.1111
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 125d | [5 empty] | 4971 |  | 100% |  | 3402 | 3402
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-03-11 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-11 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 130d | [5 empty] | 6135 |  | 99.68% |  | 3373.2 | 3384
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 110d | 5280 | 0 | 0 | 0 | 0 | 5280 | 0 | 100% | Finished | 1680 | 1680 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-29 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-06 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 10d | 12 | 48 | 40d | 0 | 0 | 12 | 48 | 20% | Started | 1.2 | 6 | 100 | 200 | 20 | 100 | 200 | 20
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 140d | [5 empty] | 7560 |  | 64.69% |  | 2200.9091 | 3402
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 80d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 1680 | 1680 | 100 | 228.5714 | 100 | 100 | 228.5714 | 100
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-18 08:00 | 20d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 100% | Finished | 6 | 6 | 100 | 16000 | 100 | 100 | 16000 | 100
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-15 08:00 | 25d | 1800 | 2160 | 30d | 0 | 0 | 1800 | 2160 | 45.45% | Started | 490.9091 | 1080 | 100 | 166.6667 | 45.4545 | 100 | 166.6667 | 45.4545
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 185d | [5 empty] | 8073 |  | 99.72% |  | 3401.3077 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 35d | 1680 | 0 | 0 | 0 | 0 | 1680 | 0 | 100% | Finished | 6 | 6 | 100 | 28000 | 100 | 100 | 28000 | 100
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 20d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 9 | 9 | 100 | 16000 | 100 | 100 | 16000 | 100
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-15 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-15 08:00 | 25d | 30 | 48 | 40d | 0 | 0 | 30 | 48 | 38.46% | Started | 2.3077 | 6 | 100 | 500 | 38.4615 | 100 | 500 | 38.4615
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 60d | [5 empty] | 3120 |  | 29.1% |  | 984.6316 | 3384
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-04 08:00 | 55d | 2640 | 1920 | 40d | 0 | 0 | 2640 | 1920 | 57.89% | Started | 972.6316 | 1680 | 100 | 157.1429 | 57.8947 | 100 | 157.1429 | 57.8947
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 60d | [5 empty] | 1200 |  | 30.14% |  | 1020 | 3384
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-04-29 08:00 | 15d | 720 | 480 | 10d | 0 | 0 | 720 | 480 | 60% | Started | 1008 | 1680 | 100 | 42.8571 | 60 | 100 | 42.8571 | 60
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 50d | [5 empty] | 2640 |  | 40.97% |  | 1386.5454 | 3384
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-18 08:00 | 45d | 2160 | 480 | 10d | 0 | 0 | 2160 | 480 | 81.82% | Started | 1374.5454 | 1680 | 100 | 128.5714 | 81.8182 | 100 | 128.5714 | 81.8182
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 160d | [5 empty] | 8307 |  | 99.71% |  | 3422 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 25d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 9 | 9 | 100 | 20000 | 100 | 100 | 20000 | 100
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-22 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-22 08:00 | 20d | 24 | 48 | 40d | 0 | 0 | 24 | 48 | 33.33% | Started | 2 | 6 | 100 | 400 | 33.3333 | 100 | 400 | 33.3333
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 100% |  | 765 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 12 | 12 | 100 | 20000 | 100 | 100 | 20000 | 100

## TP12
| TP Status Date | 2013-06-16 17:00 |  | TP Name | 16/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 240d | [5 empty] | 80721 |  | 88.79% |  | 38328.6894 | 43170.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 205d | [5 empty] | 12066 |  | 100% |  | 3516.15 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 9 | 9 | 100 | 12000 | 100 | 100 | 12000 | 100
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 0.15 | 0.15 | 100 | 8000 | 100 | 100 | 8000 | 100
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 50d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 6 | 6 | 100 | 40000 | 100 | 100 | 40000 | 100
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 145d | [5 empty] | 5817 |  | 99.69% |  | 3400.5 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 45d | 2160 | 0 | 0 | 0 | 0 | 2160 | 0 | 100% | Finished | 6 | 6 | 100 | 36000 | 100 | 100 | 36000 | 100
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-06-10 08:00 | 5d | 360 | 360 | 5d | 0 | 0 | 360 | 360 | 50% | Started | 4.5 | 9 | 100 | 4000 | 50 | 100 | 4000 | 50
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-08 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-08 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 145d | [5 empty] | 6273 |  | 99.75% |  | 3390.3333 | 3399
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 6 | 6 | 100 | 60000 | 100 | 100 | 60000 | 100
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-05-06 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-13 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-13 08:00 | 25d | 30 | 24 | 20d | 0 | 0 | 30 | 24 | 55.56% | Started | 3.3333 | 6 | 100 | 500 | 55.5556 | 100 | 500 | 55.5556
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 125d | [5 empty] | 4971 |  | 100% |  | 3402 | 3402
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-03-11 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-11 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 150d | [5 empty] | 6159 |  | 99.75% |  | 3375.6 | 3384
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 110d | 5280 | 0 | 0 | 0 | 0 | 5280 | 0 | 100% | Finished | 1680 | 1680 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-29 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-06 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 30d | 36 | 24 | 20d | 0 | 0 | 36 | 24 | 60% | Started | 3.6 | 6 | 100 | 600 | 60 | 100 | 600 | 60
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 160d | [5 empty] | 9000 |  | 76.24% |  | 2593.6364 | 3402
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 80d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 1680 | 1680 | 100 | 228.5714 | 100 | 100 | 228.5714 | 100
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-18 08:00 | 20d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 100% | Finished | 6 | 6 | 100 | 16000 | 100 | 100 | 16000 | 100
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-15 08:00 | 45d | 3240 | 720 | 10d | 0 | 0 | 3240 | 720 | 81.82% | Started | 883.6364 | 1080 | 100 | 300 | 81.8182 | 100 | 300 | 81.8182
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 205d | [5 empty] | 8097 |  | 99.77% |  | 3403.1538 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 35d | 1680 | 0 | 0 | 0 | 0 | 1680 | 0 | 100% | Finished | 6 | 6 | 100 | 28000 | 100 | 100 | 28000 | 100
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 20d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 9 | 9 | 100 | 16000 | 100 | 100 | 16000 | 100
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-15 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-15 08:00 | 45d | 54 | 24 | 20d | 0 | 0 | 54 | 24 | 69.23% | Started | 4.1538 | 6 | 100 | 900 | 69.2308 | 100 | 900 | 69.2308
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 80d | [5 empty] | 4080 |  | 39.55% |  | 1338.3158 | 3384
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-04 08:00 | 75d | 3600 | 960 | 20d | 0 | 0 | 3600 | 960 | 78.95% | Started | 1326.3158 | 1680 | 100 | 214.2857 | 78.9474 | 100 | 214.2857 | 78.9474
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 |  | 0 | 0 | 1080 | 15d | 0 | 0 | 0 | 1080 | 0% | Not Started | 0 | 1080 | 100 |  | 0 | 100 |  | 0
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 80d | [5 empty] | 2400 |  | 71.28% |  | 2412 | 3384
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-04-29 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-06-03 08:00 | 10d | 720 | 360 | 5d | 0 | 0 | 720 | 360 | 66.67% | Started | 720 | 1080 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 70d | [5 empty] | 3840 |  | 71.28% |  | 2412 | 3384
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-18 08:00 | 55d | 2640 | 0 | 0 | 0 | 0 | 2640 | 0 | 100% | Finished | 1680 | 1680 | 100 | 157.1429 | 100 | 100 | 157.1429 | 100
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-06-03 08:00 | 10d | 720 | 360 | 5d | 0 | 0 | 720 | 360 | 66.67% | Started | 720 | 1080 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 25d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 600 | 100 |  | 0 | 100 |  | 0
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 5d | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 180d | [5 empty] | 8331 |  | 99.77% |  | 3424 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 25d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 9 | 9 | 100 | 20000 | 100 | 100 | 20000 | 100
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-22 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-22 08:00 | 40d | 48 | 24 | 20d | 0 | 0 | 48 | 24 | 66.67% | Started | 4 | 6 | 100 | 800 | 66.6667 | 100 | 800 | 66.6667
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 |  | 0 | 0 | 6 | 1h | 0 | 0 | 0 | 6 | 0% | Not Started | 0 | 6 | 100 |  | 0 | 100 |  | 0
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 100% |  | 765 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 12 | 12 | 100 | 20000 | 100 | 100 | 20000 | 100

## TP13
| TP Status Date | 2013-07-14 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Organizational Development | 2012-07-16 08:00 | 2013-05-30 15:00 | 228d 6h |  |  | 0 |  |  | 43170.15 |  | 260d | [5 empty] | 83712.15 |  | 100% |  | 43170.15 | 43170.15
85 | Department A | 2012-07-16 08:00 | 2012-11-08 17:00 | 84d |  |  | 0 |  |  | 3516.15 |  | 205d | [5 empty] | 12066 |  | 100% |  | 3516.15 | 3516.15
1 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
107 | Directieteam extra | 2012-07-16 09:00 | 2012-07-16 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 111 | 111 | 123 | 2012-08-27 08:00 | 5d | 4920 | 0 | 0 | 0 | 0 | 4920 | 0 | 100% | Finished | 123 | 123 | 100 | 4000 | 100 | 100 | 4000 | 100
2 | Organisatorische oefening | 2012-07-17 11:00 | 2012-09-04 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
3 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
108 | Opleiding extra | 2012-09-25 11:00 | 2012-09-25 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 9 | 9 | 100 | 12000 | 100 | 100 | 12000 | 100
4 | Testfase | 2012-09-26 14:00 | 2012-10-31 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
5 | Live | 2012-10-31 14:00 | 2012-11-07 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
109 | Live extra | 2012-11-07 14:00 | 2012-11-07 15:00 | 1h | Personeel[0.01 #10] | 0.15 | 0 | 0 | 0 | 0.15 | 2013-02-04 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 0.15 | 0.15 | 100 | 8000 | 100 | 100 | 8000 | 100
6 | Optimalisatie/standaardisatie | 2012-11-08 16:00 | 2012-11-08 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-18 08:00 | 50d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 6 | 6 | 100 | 40000 | 100 | 100 | 40000 | 100
86 | Department B | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 165d | [5 empty] | 6195 |  | 100% |  | 3411 | 3411
7 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
110 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
8 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
111 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 45d | 2160 | 0 | 0 | 0 | 0 | 2160 | 0 | 100% | Finished | 6 | 6 | 100 | 36000 | 100 | 100 | 36000 | 100
9 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
112 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-06-10 08:00 | 10d | 720 | 0 | 0 | 0 | 0 | 720 | 0 | 100% | Finished | 9 | 9 | 100 | 8000 | 100 | 100 | 8000 | 100
10 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-08 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
11 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-08 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
12 | Live extra | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-06-24 08:00 | 15d | 720 | 0 | 0 | -702 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 12000 | 100 | 100 | 300 | 100
87 | Department C | 2012-07-16 08:00 | 2012-11-06 12:00 | 81d 4h |  |  | 0 |  |  | 3390 |  | 115d 1h | [5 empty] | 4116 |  | 100% |  | 3390 | 3390
13 | Directieteam | 2012-07-16 08:00 | 2012-07-16 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-07-16 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
14 | Organisatorische oefening | 2012-07-16 09:00 | 2012-09-03 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-07-23 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
113 | Organisatorische oefening extra | 2012-09-03 09:00 | 2012-09-03 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
15 | Opleiding | 2012-09-04 11:00 | 2012-09-25 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2012-09-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
16 | Testfase | 2012-09-25 11:00 | 2012-10-30 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 600 | 600 | 100 | 140 | 100 | 100 | 140 | 100
17 | Live | 2012-10-30 11:00 | 2012-11-06 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
18 | Optimalisatie/standaardisatie | 2012-11-06 11:00 | 2012-11-06 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-24 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
88 | Department D | 2013-02-05 08:00 | 2013-05-30 15:00 | 82d 6h |  |  | 0 |  |  | 3399 |  | 165d | [5 empty] | 6303 |  | 100% |  | 3399 | 3399
19 | Directieteam | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-26 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
20 | Organisatorische oefening | 2013-02-05 09:00 | 2013-03-26 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-12-03 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
114 | Organisatorische oefening extra | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 6 | 6 | 100 | 60000 | 100 | 100 | 60000 | 100
21 | Opleiding | 2013-03-27 11:00 | 2013-04-17 11:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
115 | Opleiding extra | 2013-04-17 11:00 | 2013-04-17 12:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-05-06 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
22 | Testfase | 2013-04-18 14:00 | 2013-05-23 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-13 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
23 | Live | 2013-05-23 14:00 | 2013-05-30 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-13 08:00 | 45d | 54 | 0 | 0 | 0 | 0 | 54 | 0 | 100% | Finished | 6 | 6 | 100 | 900 | 100 | 100 | 900 | 100
24 | Optimalisatie/standaardisatie | 2013-05-30 14:00 | 2013-05-30 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
89 | Department E | 2012-11-20 08:00 | 2013-04-10 11:00 | 101d 3h |  |  | 0 |  |  | 3402 |  | 125d | [5 empty] | 4971 |  | 100% |  | 3402 | 3402
25 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
116 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
26 | Organisatorische oefening | 2012-12-18 08:00 | 2013-02-04 17:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 30d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 1680 | 1680 | 100 | 85.7143 | 100 | 100 | 85.7143 | 100
117 | Organisatorische oefening extra | 2013-02-05 08:00 | 2013-02-05 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
27 | Opleiding | 2013-02-06 10:00 | 2013-02-27 10:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
28 | Testfase | 2013-02-27 10:00 | 2013-04-03 10:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-03-11 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
29 | Live | 2013-04-03 10:00 | 2013-04-10 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-11 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
30 | Optimalisatie/standaardisatie | 2013-04-10 10:00 | 2013-04-10 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 6 | 6 | 100 | 4000 | 100 | 100 | 4000 | 100
90 | Department F | 2012-12-18 08:00 | 2013-04-09 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 170d | [5 empty] | 6189 |  | 100% |  | 3384 | 3384
31 | Directieteam | 2012-12-18 08:00 | 2012-12-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-19 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
32 | Organisatorische oefening | 2012-12-18 09:00 | 2013-02-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-26 08:00 | 110d | 5280 | 0 | 0 | 0 | 0 | 5280 | 0 | 100% | Finished | 1680 | 1680 | 100 | 314.2857 | 100 | 100 | 314.2857 | 100
33 | Opleiding | 2013-02-05 09:00 | 2013-02-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-29 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
34 | Testfase | 2013-02-26 09:00 | 2013-04-02 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-05-06 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
35 | Live | 2013-04-02 09:00 | 2013-04-09 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-05-06 08:00 | 50d | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 100% | Finished | 6 | 6 | 100 | 1000 | 100 | 100 | 1000 | 100
36 | Optimalisatie/standaardisatie | 2013-04-09 09:00 | 2013-04-09 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
91 | Department G | 2012-11-20 08:00 | 2013-03-14 15:00 | 82d 6h |  |  | 0 |  |  | 3402 |  | 180d | [5 empty] | 9741 |  | 100% |  | 3402 | 3402
37 | Directieteam | 2012-11-20 08:00 | 2012-11-20 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-11-05 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
118 | Directieteam extra | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
38 | Organisatorische oefening | 2012-11-21 11:00 | 2013-01-09 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-11-19 08:00 | 80d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 1680 | 1680 | 100 | 228.5714 | 100 | 100 | 228.5714 | 100
119 | Organisatorische oefening extra | 2013-01-09 11:00 | 2013-01-09 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-03-18 08:00 | 20d | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 100% | Finished | 6 | 6 | 100 | 16000 | 100 | 100 | 16000 | 100
39 | Opleiding | 2013-01-10 14:00 | 2013-01-31 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-04-15 08:00 | 55d | 3960 | 0 | 0 | 0 | 0 | 3960 | 0 | 100% | Finished | 1080 | 1080 | 100 | 366.6667 | 100 | 100 | 366.6667 | 100
40 | Testfase | 2013-01-31 14:00 | 2013-03-07 14:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-07-01 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
41 | Live | 2013-03-07 14:00 | 2013-03-14 14:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-01 08:00 | 10d | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 6 | 6 | 100 | 200 | 100 | 100 | 200 | 100
42 | Optimalisatie/standaardisatie | 2013-03-14 14:00 | 2013-03-14 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
92 | Department H | 2012-09-18 08:00 | 2013-01-08 09:00 | 80d 1h |  |  | 0 |  |  | 753 |  | 65d 1h | [5 empty] | 1137 |  | 100% |  | 753 | 753
43 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
44 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
45 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
46 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
47 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 25d | 30 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | Finished | 6 | 6 | 100 | 500 | 100 | 100 | 500 | 100
48 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-17 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
93 | Department I | 2012-09-04 08:00 | 2012-12-28 17:00 | 84d |  |  | 0 |  |  | 3411 |  | 225d | [5 empty] | 8127 |  | 100% |  | 3411 | 3411
49 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-03 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
120 | Directieteam extra | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
50 | Organisatorische oefening | 2012-09-05 11:00 | 2012-10-24 11:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-01 08:00 | 75d | 3600 | 0 | 0 | 0 | 0 | 3600 | 0 | 100% | Finished | 1680 | 1680 | 100 | 214.2857 | 100 | 100 | 214.2857 | 100
121 | Organisatorische oefening extra | 2012-10-24 11:00 | 2012-10-24 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-01-21 08:00 | 35d | 1680 | 0 | 0 | 0 | 0 | 1680 | 0 | 100% | Finished | 6 | 6 | 100 | 28000 | 100 | 100 | 28000 | 100
51 | Opleiding | 2012-10-25 14:00 | 2012-11-15 14:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
122 | Opleiding extra | 2012-11-15 14:00 | 2012-11-15 15:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 20d | 1440 | 0 | 0 | 0 | 0 | 1440 | 0 | 100% | Finished | 9 | 9 | 100 | 16000 | 100 | 100 | 16000 | 100
52 | Testfase | 2012-11-16 16:00 | 2012-12-21 16:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-15 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
53 | Live | 2012-12-21 16:00 | 2012-12-28 16:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-15 08:00 | 65d | 78 | 0 | 0 | 0 | 0 | 78 | 0 | 100% | Finished | 6 | 6 | 100 | 1300 | 100 | 100 | 1300 | 100
54 | Optimalisatie/standaardisatie | 2012-12-28 16:00 | 2012-12-28 17:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
106 | Department J | 2012-09-18 08:00 | 2012-10-30 11:00 | 30d 3h |  |  | 0 |  |  | 753 |  | 55d 1h | [5 empty] | 1125 |  | 100% |  | 753 | 753
100 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 1h | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 100% | Finished | 12 | 12 | 100 | 100 | 100 | 100 | 100 | 100
101 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-09-17 08:00 | 5d | 240 | 0 | 0 | 0 | 0 | 240 | 0 | 100% | Finished | 240 | 240 | 100 | 100 | 100 | 100 | 100 | 100
102 | Opleiding | 2012-09-25 09:00 | 2012-09-25 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-09-24 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
103 | Testfase | 2012-09-25 10:00 | 2012-10-23 10:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-09-24 08:00 | 35d | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 480 | 480 | 100 | 175 | 100 | 100 | 175 | 100
104 | Live | 2012-10-23 10:00 | 2012-10-30 10:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
105 | Optimalisatie/standaardisatie | 2012-10-30 10:00 | 2012-10-30 11:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2012-12-03 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
94 | Department K | 2012-10-23 08:00 | 2013-02-12 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 100d | [5 empty] | 5058.15 |  | 100% |  | 3384 | 3384
55 | Directieteam | 2012-10-23 08:00 | 2012-10-23 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
56 | Organisatorische oefening | 2012-10-23 09:00 | 2012-12-11 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-04 08:00 | 95d | 4560 | 0 | 0 | 0 | 0 | 4560 | 0 | 100% | Finished | 1680 | 1680 | 100 | 271.4286 | 100 | 100 | 271.4286 | 100
57 | Opleiding | 2012-12-11 09:00 | 2013-01-01 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-07-12 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 1080 | 1080 | 100 | 0.83333 | 100 | 100 | 0.83333 | 100
58 | Testfase | 2013-01-01 09:00 | 2013-02-05 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-07-12 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
59 | Live | 2013-02-05 09:00 | 2013-02-12 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 0.15 | 0 | 0 | 0 | 0 | 0.15 | 0 | 100% | Finished | 6 | 6 | 100 | 2.5 | 100 | 100 | 2.5 | 100
60 | Optimalisatie/standaardisatie | 2013-02-12 09:00 | 2013-02-12 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
95 | Department L | 2013-01-15 08:00 | 2013-05-07 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 100d | [5 empty] | 2787 |  | 100% |  | 3384 | 3384
61 | Directieteam | 2013-01-15 08:00 | 2013-01-15 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-02-25 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
62 | Organisatorische oefening | 2013-01-15 09:00 | 2013-03-05 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-04-29 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 1680 | 1680 | 100 | 71.4286 | 100 | 100 | 71.4286 | 100
63 | Opleiding | 2013-03-05 09:00 | 2013-03-26 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-06-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
64 | Testfase | 2013-03-26 09:00 | 2013-04-30 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-06-24 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
65 | Live | 2013-04-30 09:00 | 2013-05-07 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-06-24 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
66 | Optimalisatie/standaardisatie | 2013-05-07 09:00 | 2013-05-07 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
96 | Department M | 2012-12-04 08:00 | 2013-03-26 10:00 | 80d 2h |  |  | 0 |  |  | 3384 |  | 90d | [5 empty] | 4227 |  | 100% |  | 3384 | 3384
67 | Directieteam | 2012-12-04 08:00 | 2012-12-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
68 | Organisatorische oefening | 2012-12-04 09:00 | 2013-01-22 09:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2013-03-18 08:00 | 55d | 2640 | 0 | 0 | 0 | 0 | 2640 | 0 | 100% | Finished | 1680 | 1680 | 100 | 157.1429 | 100 | 100 | 157.1429 | 100
69 | Opleiding | 2013-01-22 09:00 | 2013-02-12 09:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-06-03 08:00 | 15d | 1080 | 0 | 0 | 0 | 0 | 1080 | 0 | 100% | Finished | 1080 | 1080 | 100 | 100 | 100 | 100 | 100 | 100
70 | Testfase | 2013-02-12 09:00 | 2013-03-19 09:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-06-24 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
71 | Live | 2013-03-19 09:00 | 2013-03-26 09:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-06-24 08:00 | 15d | 18 | 0 | 0 | 0 | 0 | 18 | 0 | 100% | Finished | 6 | 6 | 100 | 300 | 100 | 100 | 300 | 100
72 | Optimalisatie/standaardisatie | 2013-03-26 09:00 | 2013-03-26 10:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
97 | Department N | 2012-09-04 08:00 | 2013-01-02 12:00 | 86d 4h |  |  | 0 |  |  | 3432 |  | 200d | [5 empty] | 8361 |  | 100% |  | 3432 | 3432
73 | Directieteam | 2012-09-04 08:00 | 2012-09-04 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-10-08 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
123 | Directieteam extra 1 | 2012-09-04 09:00 | 2012-09-04 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-21 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
124 | Directieteam extra 2 | 2012-09-05 11:00 | 2012-09-05 12:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-03-11 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
74 | Organisatorische oefening | 2012-09-06 14:00 | 2012-10-25 14:00 | 35d | Personeel[0.40 #10] | 1680 | 0 | 0 | 0 | 1680 | 2012-10-15 08:00 | 65d | 3120 | 0 | 0 | 0 | 0 | 3120 | 0 | 100% | Finished | 1680 | 1680 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
125 | Organisatorische oefening extra | 2012-10-25 14:00 | 2012-10-25 15:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-04 08:00 | 25d | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 100% | Finished | 6 | 6 | 100 | 20000 | 100 | 100 | 20000 | 100
75 | Opleiding | 2012-10-26 16:00 | 2012-11-16 16:00 | 15d | Personeel[0.60 #10] | 1080 | 0 | 0 | 0 | 1080 | 2013-01-14 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 1080 | 1080 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
126 | Opleiding extra 1 | 2012-11-16 16:00 | 2012-11-16 17:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-01-28 08:00 | 5d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 9 | 9 | 100 | 4000 | 100 | 100 | 4000 | 100
127 | Opleiding extra 2 | 2012-11-20 09:00 | 2012-11-20 10:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2013-03-18 08:00 | 25d | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 100% | Finished | 9 | 9 | 100 | 20000 | 100 | 100 | 20000 | 100
76 | Testfase | 2012-11-21 11:00 | 2012-12-26 11:00 | 25d | Personeel[0.20 #10] | 600 | 0 | 0 | 0 | 600 | 2013-04-22 08:00 | 1h | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 100% | Finished | 600 | 600 | 100 | 0.5 | 100 | 100 | 0.5 | 100
77 | Live | 2012-12-26 11:00 | 2013-01-02 11:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2013-04-22 08:00 | 60d | 72 | 0 | 0 | 0 | 0 | 72 | 0 | 100% | Finished | 6 | 6 | 100 | 1200 | 100 | 100 | 1200 | 100
78 | Optimalisatie/standaardisatie | 2013-01-02 11:00 | 2013-01-02 12:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-07-12 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
98 | Department O | 2012-09-18 08:00 | 2013-01-08 10:00 | 80d 2h |  |  | 0 |  |  | 765 |  | 105d 1h | [5 empty] | 3309 |  | 100% |  | 765 | 765
79 | Directieteam | 2012-09-18 08:00 | 2012-09-18 09:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2012-09-17 08:00 | 5d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 12 | 12 | 100 | 4000 | 100 | 100 | 4000 | 100
80 | Organisatorische oefening | 2012-09-18 09:00 | 2012-09-25 09:00 | 5d | Personeel[0.40 #10] | 240 | 0 | 0 | 0 | 240 | 2012-10-22 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 240 | 240 | 100 | 2.5 | 100 | 100 | 2.5 | 100
81 | Opleiding | 2012-11-06 08:00 | 2012-11-06 09:00 | 1h | Personeel[0.60 #10] | 9 | 0 | 0 | 0 | 9 | 2012-10-22 08:00 | 1h | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 100% | Finished | 9 | 9 | 100 | 100 | 100 | 100 | 100 | 100
82 | Testfase | 2012-11-27 08:00 | 2012-12-24 17:00 | 20d | Personeel[0.20 #10] | 480 | 0 | 0 | 0 | 480 | 2012-10-22 08:00 | 15d | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 100% | Finished | 480 | 480 | 100 | 75 | 100 | 100 | 75 | 100
83 | Live | 2013-01-01 08:00 | 2013-01-07 17:00 | 5d | Personeel[0.01 #10] | 6 | 0 | 0 | 0 | 6 | 2012-11-12 08:00 | 40d | 48 | 0 | 0 | 0 | 0 | 48 | 0 | 100% | Finished | 6 | 6 | 100 | 800 | 100 | 100 | 800 | 100
84 | Optimalisatie/standaardisatie | 2013-01-08 08:00 | 2013-01-08 09:00 | 1h | Personeel[0.40 #10] | 6 | 0 | 0 | 0 | 6 | 2013-02-11 08:00 | 1h | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 100% | Finished | 6 | 6 | 100 | 100 | 100 | 100 | 100 | 100
128 | Hiatus | 2013-01-08 09:00 | 2013-01-08 10:00 | 1h | Personeel[0.80 #10] | 12 | 0 | 0 | 0 | 12 | 2013-01-07 08:00 | 25d | 2400 | 0 | 0 | 0 | 0 | 2400 | 0 | 100% | Finished | 12 | 12 | 100 | 20000 | 100 | 100 | 20000 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
12/08, 2012 | 2012-07-16 08:00 | 2012-08-12 17:00 | 1995 | 1704 | 2400 | 2012-08-07 16:00 | -291 | 85.41% | -696 | 71% | -3d 1h | 84.38% | 92.74% | 2013-06-03 10:00 | 2013-07-24 16:00 | 2013-12-25 10:00 | 2013-06-04 14:00 | 2013-07-24 16:00 | 2013-12-12 17:00 | 2013-06-04 16:00 | 2013-07-30 09:00 | 2013-12-19 14:00 | 43866.15 | 60803.0282 | 50947.5172 | 51545.0667 | 70776.7847 | 71618.4038 | 58524.2973 | 58682.5246 | 0.84375 | 0.71 | 0.85414 | 0.92743 | -3.125 | 0.71 | 1 | 0.84375 | 1
09/09, 2012 | 2012-08-12 17:00 | 2012-09-09 17:00 | 4437 | 4239 | 9720 | 2012-09-07 10:00 | -198 | 95.54% | -5481 | 43.61% | -6h | 98.12% | 93.18% | 2013-05-31 15:00 | 2013-06-14 11:00 | 2014-08-21 17:00 | 2013-06-03 12:00 | 2013-06-14 11:00 | 2014-06-11 10:00 | 2013-05-31 12:00 | 2013-06-06 09:00 | 2014-05-21 16:00 | 48651.15 | 98988.8785 | 50469.5899 | 49395.0573 | 103158.5496 | 100694.6532 | 81819.5365 | 81135.1029 | 0.98125 | 0.43611 | 0.95538 | 0.93177 | -0.75 | 0.43611 | 1 | 0.98125 | 1
07/10, 2012 | 2012-09-09 17:00 | 2012-10-07 17:00 | 10323 | 7302.2308 | 13362 | 2012-09-20 12:00 | -3020.7692 | 70.74% | -6059.7692 | 54.65% | -11d 4h | 80.83% | 77.9% | 2013-06-21 15:00 | 2013-10-10 11:00 | 2014-10-21 15:00 | 2013-06-25 10:00 | 2013-10-10 11:00 | 2014-08-12 17:00 | 2013-06-17 10:00 | 2013-08-14 17:00 | 2014-04-30 17:00 | 49229.9192 | 78994.9759 | 64067.6735 | 57734.6836 | 106145.867 | 94557.4341 | 75345.4971 | 73255.6086 | 0.80833 | 0.54649 | 0.70737 | 0.77905 | -11.5 | 0.54649 | 1 | 0.80833 | 1
04/11, 2012 | 2012-10-07 17:00 | 2012-11-04 17:00 | 15013.2 | 9925.4286 | 17697 | 2012-10-04 09:00 | -5087.7714 | 66.11% | -7771.5714 | 56.09% | -21d 7h | 72.66% | 82.63% | 2013-07-08 15:00 | 2013-11-11 17:00 | 2014-11-25 16:00 | 2013-07-08 16:00 | 2013-11-11 17:00 | 2014-08-29 10:00 | 2013-07-01 14:00 | 2013-09-27 16:00 | 2014-06-12 15:00 | 50941.7214 | 76972.2068 | 67982.9544 | 63453.1757 | 107356.6579 | 99280.0803 | 74926.1205 | 73664.9692 | 0.72656 | 0.56085 | 0.66111 | 0.82628 | -21.875 | 0.56085 | 1 | 0.72656 | 1
02/12, 2012 | 2012-11-04 17:00 | 2012-12-02 17:00 | 19272.15 | 12139.7 | 23667 | 2012-10-18 11:00 | -7132.45 | 62.99% | -11527.3 | 51.29% | -31d 5h | 68.38% | 79.57% | 2013-07-23 12:00 | 2013-12-05 09:00 | 2015-04-01 17:00 | 2013-07-22 15:00 | 2013-12-05 09:00 | 2014-11-19 17:00 | 2013-07-15 11:00 | 2013-10-25 12:00 | 2014-09-03 10:00 | 54697.45 | 84162.5358 | 72928.8008 | 69049.7422 | 119705.5376 | 112143.1035 | 81523.7861 | 80385.0299 | 0.68375 | 0.51294 | 0.62991 | 0.79566 | -31.625 | 0.51294 | 1 | 0.68375 | 1
30/12, 2012 | 2012-12-02 17:00 | 2012-12-30 17:00 | 25239.3 | 17491.9797 | 30717 | 2012-11-16 15:00 | -7747.3203 | 69.3% | -13225.0203 | 56.95% | -30d 2h | 74.79% | 71.07% | 2013-07-26 15:00 | 2013-10-21 09:00 | 2014-10-03 14:00 | 2013-07-22 14:00 | 2013-10-21 09:00 | 2014-05-29 16:00 | 2013-07-11 17:00 | 2013-09-16 16:00 | 2014-04-01 11:00 | 56395.1703 | 75809.4576 | 67768.2116 | 65049.9296 | 95781.2227 | 91007.7512 | 73933.5932 | 73149.8674 | 0.74792 | 0.56946 | 0.69305 | 0.71073 | -30.25 | 0.56946 | 1 | 0.74792 | 1
27/01, 2013 | 2012-12-30 17:00 | 2013-01-27 17:00 | 30408.15 | 24416.6027 | 41175 | 2012-12-25 17:00 | -5991.5473 | 80.3% | -16758.3973 | 59.3% | -23d | 83.57% | 76.92% | 2013-07-15 12:00 | 2013-08-16 16:00 | 2014-05-19 11:00 | 2013-07-09 11:00 | 2013-08-16 16:00 | 2014-01-03 11:00 | 2013-07-02 15:00 | 2013-08-01 15:00 | 2013-12-09 12:00 | 59928.5473 | 72800.0922 | 64530.4474 | 63615.1421 | 80560.5181 | 79016.9907 | 70708.6504 | 70407.1004 | 0.83571 | 0.593 | 0.80296 | 0.76919 | -23 | 0.593 | 1 | 0.83571 | 1
24/02, 2013 | 2013-01-27 17:00 | 2013-02-24 17:00 | 36378.15 | 26046.063 | 49833 | 2013-01-03 11:00 | -10332.087 | 71.6% | -23786.937 | 52.27% | -36d 5h | 77.11% | 77.59% | 2013-08-15 12:00 | 2013-10-04 12:00 | 2014-11-18 10:00 | 2013-08-02 10:00 | 2013-10-04 12:00 | 2014-04-28 09:00 | 2013-07-22 11:00 | 2013-09-03 14:00 | 2014-02-25 12:00 | 66957.087 | 82595.9027 | 73749.9584 | 72040.5292 | 95592.4604 | 92321.8708 | 80339.287 | 79751.7865 | 0.77109 | 0.52267 | 0.71598 | 0.77592 | -36.625 | 0.52267 | 1 | 0.77109 | 1
24/03, 2013 | 2013-02-24 17:00 | 2013-03-24 17:00 | 40363.8 | 27485.3363 | 60408 | 2013-01-11 17:00 | -12878.4637 | 68.09% | -32922.6637 | 45.5% | -50d | 72.22% | 78.95% | 2013-09-03 17:00 | 2013-10-28 16:00 | 2015-05-14 11:00 | 2013-08-20 09:00 | 2013-10-28 16:00 | 2014-07-16 15:00 | 2013-08-08 15:00 | 2013-10-01 15:00 | 2014-05-19 12:00 | 76092.8137 | 94880.499 | 83442.0527 | 82125.4344 | 111032.8511 | 108139.1525 | 91766.0859 | 91256.8725 | 0.72222 | 0.45499 | 0.68094 | 0.78946 | -50 | 0.45499 | 1 | 0.72222 | 1
21/04, 2013 | 2013-03-24 17:00 | 2013-04-21 17:00 | 42432.15 | 29838.265 | 69336 | 2013-01-24 09:00 | -12593.885 | 70.32% | -39497.735 | 43.03% | -61d 7h | 69.06% | 82.77% | 2013-09-02 12:00 | 2013-10-14 10:00 | 2015-06-08 16:00 | 2013-08-22 09:00 | 2013-10-14 10:00 | 2014-06-03 09:00 | 2013-08-26 14:00 | 2013-10-22 10:00 | 2014-06-20 16:00 | 82667.885 | 100315.6693 | 88294.8955 | 88640.0869 | 113391.3088 | 114193.4397 | 96829.2796 | 96972.6102 | 0.69063 | 0.43034 | 0.7032 | 0.82771 | -61.875 | 0.43034 | 1 | 0.69063 | 1
19/05, 2013 | 2013-04-21 17:00 | 2013-05-19 17:00 | 43071.15 | 35149.4105 | 75447 | 2013-02-18 14:00 | -7921.7395 | 81.61% | -40297.5895 | 46.59% | -64d 3h | 70.74% | 85.83% | 2013-07-29 15:00 | 2013-08-12 10:00 | 2014-11-04 14:00 | 2013-07-26 10:00 | 2013-08-12 10:00 | 2013-11-15 12:00 | 2013-08-29 09:00 | 2013-10-10 11:00 | 2014-03-25 16:00 | 83467.7395 | 92663.2412 | 85275.4002 | 86785.5554 | 96543.3228 | 99784.819 | 90413.2641 | 91045.998 | 0.70739 | 0.46588 | 0.81608 | 0.85835 | -64.375 | 0.46588 | 1 | 0.70739 | 1
16/06, 2013 | 2013-05-19 17:00 | 2013-06-16 17:00 | 43170.15 | 38328.6894 | 80721 | 2013-03-07 17:00 | -4841.4606 | 88.79% | -42392.3106 | 47.48% | -71d | 70.42% | 90.46% | 2013-07-05 11:00 | 2013-07-10 14:00 | 2014-08-13 14:00 | 2013-07-23 16:00 | 2013-07-29 11:00 | 2013-09-12 16:00 | 2013-09-06 15:00 | 2013-10-11 16:00 | 2014-02-20 15:00 | 85562.4606 | 90917.2145 | 86174.0062 | 87596.447 | 92205.142 | 95200.8313 | 89406.267 | 90019.0434 | 0.70417 | 0.47483 | 0.88785 | 0.90457 | -71 | 0.47483 | 1 | 0.70417 | 1
Actual Schedule | 2013-06-16 17:00 | 2013-07-14 17:00 | 43170.15 | 43170.15 | 83712.15 | 2013-05-30 15:00 | 0 | 100% | -40542 | 51.57% | -31d 2h | 87.98% | 100% | 2013-05-30 15:00 | 2013-05-30 15:00 | 2014-03-27 14:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 2013-07-12 17:00 | 83712.15 | 83712.15 | 83712.15 | 83712.15 | 83712.15 | 83712.15 | 83712.15 | 83712.15 | 0.87981 | 0.5157 | 1 | 1 | -31.25 | 0.5157 | 1 | 0.87981 | 1