## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building (5) | 1 |  |  | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 | 221.375
1 | Dakwerken | 1.1 |  | FS2 | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 4.375
2 | Schrijnwerk | 1.2 | 1FS | FS3 | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 4.375
3 | Ventilatie | 1.3 | 2FS | FS4 | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 4.375
4 | Sanitair | 1.4 | 3FS | FS5;FS7+1w | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 4.375
5 | Elektriciteit | 1.5 | 4FS |  | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 4.375
6 | Sanitair | 1.6 |  | FS14+2w | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 4.375
7 | Isolatie zolder | 1.7 | 4FS+1w | FS8 | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 4.375
8 | Elektriciteit | 1.8 | 7FS |  | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 4.375
9 | Sanitair | 1.9 |  | FS10 | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 4.375
10 | Elektriciteit | 1.10 | 9FS | SF15+3w | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 4.375
11 | Sanitair | 1.11 |  | FS12;FS18+1w | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 4.375
12 | Elektriciteit | 1.12 | 11FS |  | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 4.375
13 | Sanitair | 1.13 |  | FS16 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 4.375
14 | Isolatie zolder | 1.14 | 6FS+2w |  | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 4.375
15 | Isolatie chap/pure | 1.15 | 10SF+3w | FS19 | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 4.375
16 | Elektriciteit | 1.16 | 13FS |  | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 4.375
17 | Sanitair | 1.17 |  | FS20 | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 4.375
18 | Isolatie zolder | 1.18 | 11FS+1w |  | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 4.375
19 | Chap | 1.19 | 15FS | FS22 | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 4.375
20 | Elektriciteit | 1.20 | 17FS | SF26+3w | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 4.375
21 | Sanitair | 1.21 |  | FS23 | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 4.375
22 | Bevloering en faience | 1.22 | 19FS | FS25 | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 4.375
23 | Elektriciteit | 1.23 | 21FS |  | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 4.375
24 | Sanitair | 1.24 |  |  | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 4.375
25 | Elektriciteit | 1.25 | 22FS | SF31+3w;FS32+2w;FS27 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 4.375
26 | Isolatie chap/pure | 1.26 | 20SF+3w | FS28 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 4.375
27 | Sanitair | 1.27 | 25FS | FS29 | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 4.375
28 | Chape | 1.28 | 26FS | FS30 | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 4.375
29 | Parket | 1.29 | 27FS | FS36+1w | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 4.375
30 | Vloer | 1.30 | 28FS | FS33;FS34 | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 4.375
31 | Isolatie chape/pure | 1.31 | 25SF+3w | FS35 | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 4.375
32 | Ventilatie | 1.32 | 25FS+2w |  | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 4.375
33 | Elektriciteit | 1.33 | 30FS | FS37 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 | 4.375
34 | Vloer | 1.34 | 30FS | FS38 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 4.375
35 | Chape | 1.35 | 31FS | FS39 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 4.375
36 | Schrijnwerk | 1.36 | 29FS+1w | FS40 | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 | 4.375
37 | Sanitair | 1.37 | 33FS | FS41 | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 4.375
38 | Elektriciteit | 1.38 | 34FS | FS42;FS44+1w | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 4.375
39 | Vloer | 1.39 | 35FS | FS43 | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 4.375
40 | Keuken | 1.40 | 36FS |  | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 | 4.375
41 | Parket | 1.41 | 37FS | FS46+5w | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 4.375
42 | Sanitair | 1.42 | 38FS | FS47+5w | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 | 4.375
43 | Elektriciteit | 1.43 | 39FS | FS45;FS48+5w | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 4.375
44 | Ventilatie | 1.44 | 38FS+1w |  | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 | 4.375
45 | Sanitair | 1.45 | 43FS | FS51+5w | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 4.375
46 | Schrijnwerk | 1.46 | 41FS+5w | FS49 | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 4.375
47 | Parket | 1.47 | 42FS+5w | FS50 | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 4.375
48 | Ventilatie | 1.48 | 43FS+5w |  | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 4.375
49 | Keuken | 1.49 | 46FS |  | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 4.375
50 | Schrijnwerk | 1.50 | 47FS | FS52 | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 | 4.375
51 | Parket | 1.51 | 45FS+5w | FS53 | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 4.375
52 | Keuken | 1.52 | 50FS |  | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 | 4.375
53 | Schrijnwerk | 1.53 | 51FS | FS54 | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 4.375
54 | Keuken | 1.54 | 53FS | FS55 | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 4.375
55 | Plakwerken | 1.55 | 54FS | FS56 | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 | 4.375
56 | Plakwerken deel 2 | 1.56 | 55FS |  | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 | 25.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building (5) | 1280h |  |  |  |  | 99 | 100 | 101
1 | Dakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Ventilatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Chap | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Bevloering en faience | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Parket | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Isolatie chape/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Ventilatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Vloer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Parket | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Ventilatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Parket | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Ventilatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Parket | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Plakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Plakwerken deel 2 | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-03-01 17:00 |  | TP Name | 01/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 5d | [5 empty] | 200000 |  | 7.27% |  | 200000 | 200000
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 |  | 0 | 0 | 410156.4062 | 5d | 0 | 0 | 0 | 410156.4062 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 |  | 0 | 0 | 175000 | 5d | 0 | 0 | 0 | 175000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 |  | 0 | 0 | 170731.6016 | 5d | 0 | 0 | 0 | 170731.6016 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 |  | 0 | 0 | 72066.8018 | 5d | 0 | 0 | 0 | 72066.8018 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 |  | 0 | 0 | 143414.8047 | 5d | 0 | 0 | 0 | 143414.8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 |  | 0 | 0 | 3571.6 | 5d | 0 | 0 | 0 | 3571.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 |  | 0 | 0 | 27316.7993 | 5d | 0 | 0 | 0 | 27316.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 |  | 0 | 0 | 47804.7998 | 5d | 0 | 0 | 0 | 47804.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 |  | 0 | 0 | 54633.999 | 5d | 0 | 0 | 0 | 54633.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 |  | 0 | 0 | 3571.6 | 5d | 0 | 0 | 0 | 3571.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 |  | 0 | 0 | 14285.6006 | 5d | 0 | 0 | 0 | 14285.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 |  | 0 | 0 | 27316.7993 | 5d | 0 | 0 | 0 | 27316.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 |  | 0 | 0 | 3571.6 | 5d | 0 | 0 | 0 | 3571.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 |  | 0 | 0 | 14285.6006 | 5d | 0 | 0 | 0 | 14285.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 |  | 0 | 0 | 27316.7993 | 5d | 0 | 0 | 0 | 27316.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 |  | 0 | 0 | 6829.1998 | 5d | 0 | 0 | 0 | 6829.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 |  | 0 | 0 | 56000 | 5d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 |  | 0 | 0 | 6829.1998 | 5d | 0 | 0 | 0 | 6829.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 |  | 0 | 0 | 15666.8005 | 5d | 0 | 0 | 0 | 15666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 |  | 0 | 0 | 16406.4001 | 5d | 0 | 0 | 0 | 16406.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 |  | 0 | 0 | 13658.3997 | 5d | 0 | 0 | 0 | 13658.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 |  | 0 | 0 | 20488.0005 | 5d | 0 | 0 | 0 | 20488.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 |  | 0 | 0 | 70000 | 5d | 0 | 0 | 0 | 70000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 |  | 0 | 0 | 13658.3997 | 5d | 0 | 0 | 0 | 13658.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 |  | 0 | 0 | 49218.7988 | 5d | 0 | 0 | 0 | 49218.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 |  | 0 | 0 | 65625.2002 | 5d | 0 | 0 | 0 | 65625.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-04-12 16:00 |  | TP Name | 12/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 35d | [5 empty] | 1273343.4123 |  | 46.35% |  | 1275129.2123 | 1213794.9631
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12219.8695 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 26633.8793 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 0 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 0 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 |  | 0 | 0 | 54633.999 | 5d | 0 | 0 | 0 | 54633.999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 |  | 0 | 0 | 3571.6 | 5d | 0 | 0 | 0 | 3571.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 |  | 0 | 0 | 14285.6006 | 5d | 0 | 0 | 0 | 14285.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 |  | 0 | 0 | 27316.7993 | 5d | 0 | 0 | 0 | 27316.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 |  | 0 | 0 | 3571.6 | 5d | 0 | 0 | 0 | 3571.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 |  | 0 | 0 | 14285.6006 | 5d | 0 | 0 | 0 | 14285.6006 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 |  | 0 | 0 | 27316.7993 | 5d | 0 | 0 | 0 | 27316.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 |  | 0 | 0 | 12533.1995 | 5d | 0 | 0 | 0 | 12533.1995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 |  | 0 | 0 | 6829.1998 | 5d | 0 | 0 | 0 | 6829.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 |  | 0 | 0 | 56000 | 5d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 |  | 0 | 0 | 6829.1998 | 5d | 0 | 0 | 0 | 6829.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 |  | 0 | 0 | 15666.8005 | 5d | 0 | 0 | 0 | 15666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 |  | 0 | 0 | 16406.4001 | 5d | 0 | 0 | 0 | 16406.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 |  | 0 | 0 | 13658.3997 | 5d | 0 | 0 | 0 | 13658.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 |  | 0 | 0 | 20488.0005 | 5d | 0 | 0 | 0 | 20488.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 |  | 0 | 0 | 70000 | 5d | 0 | 0 | 0 | 70000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 |  | 0 | 0 | 13658.3997 | 5d | 0 | 0 | 0 | 13658.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 |  | 0 | 0 | 49218.7988 | 5d | 0 | 0 | 0 | 49218.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 |  | 0 | 0 | 65625.2002 | 5d | 0 | 0 | 0 | 65625.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-05-24 17:00 |  | TP Name | 24/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 65d | [5 empty] | 1586644.6086 |  | 57.06% |  | 1569680.4086 | 1569680.4086
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 47804.7998 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 100% | Finished | 54633.999 | 54633.999 | 100 | 100 | 100 | 100 | 100 | 100
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 |  | 0 | 0 | 6829.1998 | 5d | 0 | 0 | 0 | 6829.1998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 |  | 0 | 0 | 15666.8005 | 5d | 0 | 0 | 0 | 15666.8005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 |  | 0 | 0 | 16406.4001 | 5d | 0 | 0 | 0 | 16406.4001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 |  | 0 | 0 | 13658.3997 | 5d | 0 | 0 | 0 | 13658.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 |  | 0 | 0 | 20488.0005 | 5d | 0 | 0 | 0 | 20488.0005 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 |  | 0 | 0 | 70000 | 5d | 0 | 0 | 0 | 70000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 |  | 0 | 0 | 13658.3997 | 5d | 0 | 0 | 0 | 13658.3997 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 |  | 0 | 0 | 49218.7988 | 5d | 0 | 0 | 0 | 49218.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 |  | 0 | 0 | 65625.2002 | 5d | 0 | 0 | 0 | 65625.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-07-05 17:00 |  | TP Name | 05/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 95d | [5 empty] | 1653249.0081 |  | 58.74% |  | 1615797.2079 | 2065219.6085
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 47804.7998 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 100% | Finished | 54633.999 | 54633.999 | 100 | 100 | 100 | 100 | 100 | 100
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-06-10 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 17857.1997 | 100 |  | 0 | 100 |  | 0
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 18750 | 100 |  | 0 | 100 |  | 0
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 12500 | 100 |  | 0 | 100 |  | 0
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 49000 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 |  | 0 | 0 | 15666.8005 | 5d | 0 | 0 | 0 | 15666.8005 | 0% | Not Started | 0 | 15666.8005 | 100 |  | 0 | 100 |  | 0
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 56250 | 100 |  | 0 | 100 |  | 0
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 12500 | 100 |  | 0 | 100 |  | 0
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 |  | 0 | 0 | 16406.4001 | 5d | 0 | 0 | 0 | 16406.4001 | 0% | Not Started | 0 | 16406.4001 | 100 |  | 0 | 100 |  | 0
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-06-10 08:00 | 5d | 13658.3997 | 0 | 0 | 13658.4004 | 0 | 27316.8 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 100 | 100 | 100 | 200 | 100
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 18800 | 100 |  | 0 | 100 |  | 0
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 21874.7998 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 |  | 0 | 0 | 20488.0005 | 5d | 0 | 0 | 0 | 20488.0005 | 0% | Not Started | 0 | 20488.0005 | 100 |  | 0 | 100 |  | 0
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-06-10 08:00 | 20d | 75200 | 0 | 0 | -56400 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 400 | 100 | 100 | 100 | 100
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 |  | 0 | 0 | 70000 | 5d | 0 | 0 | 0 | 70000 | 0% | Not Started | 0 | 70000 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-07-01 08:00 | 5d | 13658.3997 | 13658.3997 | 5d | 0 | 0 | 13658.3997 | 13658.3997 | 50% | Started | 6829.1998 | 13658.3997 | 100 | 100 | 50 | 100 | 100 | 50
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 |  | 0 | 0 | 49218.7988 | 5d | 0 | 0 | 0 | 49218.7988 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 |  | 0 | 0 | 65625.2002 | 5d | 0 | 0 | 0 | 65625.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-08-16 17:00 |  | TP Name | 16/08, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 125d | [5 empty] | 1653249.0081 |  | 58.74% |  | 1615797.2079 | 2333750.8072
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 47804.7998 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 100% | Finished | 54633.999 | 54633.999 | 100 | 100 | 100 | 100 | 100 | 100
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-06-10 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 |  | 0 | 0 | 17857.1997 | 5d | 0 | 0 | 0 | 17857.1997 | 0% | Not Started | 0 | 17857.1997 | 100 |  | 0 | 100 |  | 0
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 18750 | 100 |  | 0 | 100 |  | 0
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 12500 | 100 |  | 0 | 100 |  | 0
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 49000 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 |  | 0 | 0 | 15666.8005 | 5d | 0 | 0 | 0 | 15666.8005 | 0% | Not Started | 0 | 15666.8005 | 100 |  | 0 | 100 |  | 0
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 56250 | 100 |  | 0 | 100 |  | 0
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 |  | 0 | 0 | 12500 | 5d | 0 | 0 | 0 | 12500 | 0% | Not Started | 0 | 12500 | 100 |  | 0 | 100 |  | 0
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 |  | 0 | 0 | 16406.4001 | 5d | 0 | 0 | 0 | 16406.4001 | 0% | Not Started | 0 | 16406.4001 | 100 |  | 0 | 100 |  | 0
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-06-10 08:00 | 5d | 13658.3997 | 0 | 0 | 13658.4004 | 0 | 27316.8 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 100 | 100 | 100 | 200 | 100
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 |  | 0 | 0 | 18800 | 5d | 0 | 0 | 0 | 18800 | 0% | Not Started | 0 | 18800 | 100 |  | 0 | 100 |  | 0
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 21874.7998 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 |  | 0 | 0 | 20488.0005 | 5d | 0 | 0 | 0 | 20488.0005 | 0% | Not Started | 0 | 20488.0005 | 100 |  | 0 | 100 |  | 0
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-06-10 08:00 | 20d | 75200 | 0 | 0 | -56400 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 400 | 100 | 100 | 100 | 100
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 |  | 0 | 0 | 70000 | 5d | 0 | 0 | 0 | 70000 | 0% | Not Started | 0 | 70000 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-07-01 08:00 | 5d | 13658.3997 | 13658.3997 | 5d | 0 | 0 | 13658.3997 | 13658.3997 | 50% | Started | 6829.1998 | 13658.3997 | 100 | 100 | 50 | 100 | 100 | 50
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 32812.3999 | 100 |  | 0 | 100 |  | 0
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 56250 | 100 |  | 0 | 100 |  | 0
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 49000 | 100 |  | 0 | 100 |  | 0
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 43750 | 100 |  | 0 | 100 |  | 0
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 |  | 0 | 0 | 49218.7988 | 5d | 0 | 0 | 0 | 49218.7988 | 0% | Not Started | 0 | 49218.7988 | 100 |  | 0 | 100 |  | 0
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 |  | 0 | 0 | 65625.2002 | 5d | 0 | 0 | 0 | 65625.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-09-27 09:00 |  | TP Name | 27/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 155d | [5 empty] | 2010887.8082 |  | 68.51% |  | 1884706.8082 | 2680927.7416
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 47804.7998 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 100% | Finished | 54633.999 | 54633.999 | 100 | 100 | 100 | 100 | 100 | 100
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-06-10 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-08-19 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 |  | 0 | 0 | 18750 | 5d | 0 | 0 | 0 | 18750 | 0% | Not Started | 0 | 18750 | 100 |  | 0 | 100 |  | 0
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-08-26 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 100% | Finished | 12500 | 12500 | 100 | 100 | 100 | 100 | 100 | 100
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-08-19 08:00 | 5d | 49000 | 0 | 0 | 0 | 0 | 49000 | 0 | 100% | Finished | 49000 | 49000 | 100 | 100 | 100 | 100 | 100 | 100
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 | 2013-09-16 08:00 | 5d | 15666.8005 | 0 | 0 | 0 | 0 | 15666.8005 | 0 | 100% | Finished | 15666.8005 | 15666.8005 | 100 | 100 | 100 | 100 | 100 | 100
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 |  | 0 | 0 | 56250 | 5d | 0 | 0 | 0 | 56250 | 0% | Not Started | 0 | 56250 | 100 |  | 0 | 100 |  | 0
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-09-02 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 100% | Finished | 12500 | 12500 | 100 | 100 | 100 | 100 | 100 | 100
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 | 2013-08-19 08:00 | 5d | 16406.4001 | 0 | 0 | 0 | 0 | 16406.4001 | 0 | 100% | Finished | 16406.4001 | 16406.4001 | 100 | 100 | 100 | 100 | 100 | 100
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-06-10 08:00 | 5d | 13658.3997 | 0 | 0 | 13658.4004 | 0 | 27316.8 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 100 | 100 | 100 | 200 | 100
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-09-09 08:00 | 15d | 56400 | 56400 | 15d | -37600 | 0 | 18800 | 56400 | 50% | Started | 9400 | 18800 | 100 | 300 | 50 | 100 | 100 | 50
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 21874.7998 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-09-09 08:00 | 5d | 37500 | 0 | 0 | 56250 | 0 | 93750 | 0 | 100% | Finished | 37500 | 37500 | 100 | 100 | 100 | 100 | 250 | 100
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 |  | 0 | 0 | 20488.0005 | 5d | 0 | 0 | 0 | 20488.0005 | 0% | Not Started | 0 | 20488.0005 | 100 |  | 0 | 100 |  | 0
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-06-10 08:00 | 20d | 75200 | 0 | 0 | -56400 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 400 | 100 | 100 | 100 | 100
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 | 2013-09-16 08:00 | 10d | 140000 | 140000 | 10d | -70000 | 0 | 70000 | 140000 | 50% | Started | 35000 | 70000 | 100 | 200 | 50 | 100 | 100 | 50
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-07-01 08:00 | 10d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 200 | 100 | 100 | 200 | 100
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 32812.3999 | 100 |  | 0 | 100 |  | 0
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-09-23 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 100% | Finished | 56250 | 56250 | 100 | 100 | 100 | 100 | 66.6667 | 100
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 |  | 0 | 0 | 49000 | 5d | 0 | 0 | 0 | 49000 | 0% | Not Started | 0 | 49000 | 100 |  | 0 | 100 |  | 0
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 43750 | 100 |  | 0 | 100 |  | 0
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 |  | 0 | 0 | 49218.7988 | 5d | 0 | 0 | 0 | 49218.7988 | 0% | Not Started | 0 | 49218.7988 | 100 |  | 0 | 100 |  | 0
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 |  | 0 | 0 | 65625.2002 | 5d | 0 | 0 | 0 | 65625.2002 | 0% | Not Started | 0 | 65625.2002 | 100 |  | 0 | 100 |  | 0
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 32812.3999 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 43750 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 36666.7993 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 168322.535 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-11-08 17:00 |  | TP Name | 08/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 185d | [5 empty] | 2395422.0772 |  | 85.06% |  | 2340001.2076 | 2750937.9996
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 47804.7998 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 100% | Finished | 54633.999 | 54633.999 | 100 | 100 | 100 | 100 | 100 | 100
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-06-10 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-08-19 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-10-07 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-10-07 08:00 | 10d | 75000 | 0 | 0 | -37500 | 0 | 37500 | 0 | 100% | Finished | 37500 | 37500 | 100 | 200 | 100 | 100 | 100 | 100
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-08-26 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 100% | Finished | 12500 | 12500 | 100 | 100 | 100 | 100 | 100 | 100
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-08-19 08:00 | 5d | 49000 | 0 | 0 | 0 | 0 | 49000 | 0 | 100% | Finished | 49000 | 49000 | 100 | 100 | 100 | 100 | 100 | 100
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 | 2013-09-16 08:00 | 5d | 15666.8005 | 0 | 0 | 0 | 0 | 15666.8005 | 0 | 100% | Finished | 15666.8005 | 15666.8005 | 100 | 100 | 100 | 100 | 100 | 100
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-10-07 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 100% | Finished | 56250 | 56250 | 100 | 100 | 100 | 100 | 66.6667 | 100
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-09-02 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 100% | Finished | 12500 | 12500 | 100 | 100 | 100 | 100 | 100 | 100
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 | 2013-08-19 08:00 | 5d | 16406.4001 | 0 | 0 | 0 | 0 | 16406.4001 | 0 | 100% | Finished | 16406.4001 | 16406.4001 | 100 | 100 | 100 | 100 | 100 | 100
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-06-10 08:00 | 5d | 13658.3997 | 0 | 0 | 13658.4004 | 0 | 27316.8 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 100 | 100 | 100 | 200 | 100
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-09-09 08:00 | 30d | 112800 | 0 | 0 | -94000 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 600 | 100 | 100 | 100 | 100
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 |  | 0 | 0 | 37500 | 5d | 0 | 0 | 0 | 37500 | 0% | Not Started | 0 | 37500 | 100 |  | 0 | 100 |  | 0
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 |  | 0 | 0 | 21874.7998 | 5d | 0 | 0 | 0 | 21874.7998 | 0% | Not Started | 0 | 21874.7998 | 100 |  | 0 | 100 |  | 0
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-09-09 08:00 | 5d | 37500 | 0 | 0 | 56250 | 0 | 93750 | 0 | 100% | Finished | 37500 | 37500 | 100 | 100 | 100 | 100 | 250 | 100
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 | 2013-10-21 08:00 | 5d | 20488.0005 | 0 | 0 | -6829.3301 | 0 | 13658.6704 | 0 | 100% | Finished | 20488.0005 | 20488.0005 | 100 | 100 | 100 | 100 | 66.6667 | 100
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-06-10 08:00 | 20d | 75200 | 0 | 0 | -56400 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 400 | 100 | 100 | 100 | 100
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 | 2013-09-16 08:00 | 20d | 280000 | 0 | 0 | -210000 | 0 | 70000 | 0 | 100% | Finished | 70000 | 70000 | 100 | 400 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-07-01 08:00 | 10d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 200 | 100 | 100 | 200 | 100
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 2013-09-30 08:00 | 20d | 131249.5996 | 0 | 0 | -98437 | 0 | 32812.5996 | 0 | 100% | Finished | 32812.3999 | 32812.3999 | 100 | 400 | 100 | 100 | 100.0006 | 100
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-09-23 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 100% | Finished | 56250 | 56250 | 100 | 100 | 100 | 100 | 66.6667 | 100
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-10-07 08:00 | 10d | 98000 | 0 | 0 | -49000 | 0 | 49000 | 0 | 100% | Finished | 49000 | 49000 | 100 | 200 | 100 | 100 | 100 | 100
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-10-07 08:00 | 10d | 87500 | 0 | 0 | -43750 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 200 | 100 | 100 | 100 | 100
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 | 2013-09-30 08:00 | 5d | 49218.7988 | 0 | 0 | -16406 | 0 | 32812.7988 | 0 | 100% | Finished | 49218.7988 | 49218.7988 | 100 | 100 | 100 | 100 | 66.6672 | 100
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-10-28 08:00 | 10d | 75000 | 0 | 0 | -18750 | 0 | 56250 | 0 | 100% | Finished | 37500 | 37500 | 100 | 200 | 100 | 100 | 150 | 100
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 | 2013-10-14 08:00 | 5d | 65625.2002 | 0 | 0 | -21875 | 0 | 43750.2002 | 0 | 100% | Finished | 65625.2002 | 65625.2002 | 100 | 100 | 100 | 100 | 66.6668 | 100
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 |  | 0 | 0 | 32812.3999 | 5d | 0 | 0 | 0 | 32812.3999 | 0% | Not Started | 0 | 32812.3999 | 100 |  | 0 | 100 |  | 0
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 |  | 0 | 0 | 43750 | 5d | 0 | 0 | 0 | 43750 | 0% | Not Started | 0 | 43750 | 100 |  | 0 | 100 |  | 0
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 |  | 0 | 0 | 36666.7993 | 5d | 0 | 0 | 0 | 36666.7993 | 0% | Not Started | 0 | 36666.7993 | 100 |  | 0 | 100 |  | 0
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 |  | 0 | 0 | 238332.793 | 20d | 0 | 0 | 0 | 238332.793 | 0% | Not Started | 0 | 238332.793 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-12-20 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building (5) | 2013-02-25 08:00 | 2013-10-04 17:00 | 160d |  |  | 0 |  |  | 2750937.9996 |  | 205d | [5 empty] | 2590796.7261 |  | 100% |  | 2750937.9996 | 2750937.9996
1 | Dakwerken | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 5000 | 200000 | 200000 | 2013-02-25 08:00 | 5d | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | 100% | Finished | 200000 | 200000 | 100 | 100 | 100 | 100 | 100 | 100
2 | Schrijnwerk | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 10253.9102 | 410156.4062 | 410156.4062 | 2013-03-04 08:00 | 5d | 410156.4062 | 0 | 0 | 0 | 0 | 410156.4062 | 0 | 100% | Finished | 410156.4062 | 410156.4062 | 100 | 100 | 100 | 100 | 100 | 100
3 | Ventilatie | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 4375 | 175000 | 175000 | 2013-03-11 08:00 | 5d | 175000 | 0 | 0 | 0 | 0 | 175000 | 0 | 100% | Finished | 175000 | 175000 | 100 | 100 | 100 | 100 | 100 | 100
4 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 4268.29 | 170731.6016 | 170731.6016 | 2013-03-18 08:00 | 5d | 170731.6016 | 0 | 0 | 0 | 0 | 170731.6016 | 0 | 100% | Finished | 170731.6016 | 170731.6016 | 100 | 100 | 100 | 100 | 100 | 100
5 | Elektriciteit | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1801.67 | 72066.8018 | 72066.8018 | 2013-03-25 08:00 | 5d | 72066.8018 | 0 | 0 | 0 | 0 | 72066.8018 | 0 | 100% | Finished | 72066.8018 | 72066.8018 | 100 | 100 | 100 | 100 | 100 | 100
6 | Sanitair | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 3585.3701 | 143414.8047 | 143414.8047 | 2013-04-01 08:00 | 5d | 143414.8047 | 0 | 0 | 0 | 0 | 143414.8047 | 0 | 100% | Finished | 143414.8047 | 143414.8047 | 100 | 100 | 100 | 100 | 100 | 100
7 | Isolatie zolder | 2013-04-01 08:00 | 2013-04-05 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-01 08:00 | 5d | 3571.6 | 0 | 0 | -1785.8 | 0 | 1785.8 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 50 | 100
8 | Elektriciteit | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
9 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-08 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
10 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-08 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
11 | Sanitair | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1195.12 | 47804.7998 | 47804.7998 | 2013-04-08 08:00 | 5d | 47804.7998 | 0 | 0 | 0 | 0 | 47804.7998 | 0 | 100% | Finished | 47804.7998 | 47804.7998 | 100 | 100 | 100 | 100 | 100 | 100
12 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-22 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
13 | Sanitair | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1365.85 | 54633.999 | 54633.999 | 2013-04-22 08:00 | 5d | 54633.999 | 0 | 0 | 0 | 0 | 54633.999 | 0 | 100% | Finished | 54633.999 | 54633.999 | 100 | 100 | 100 | 100 | 100 | 100
14 | Isolatie zolder | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-22 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
15 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-04-29 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
16 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-04-29 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
17 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-04-29 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
18 | Isolatie zolder | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 89.29 | 3571.6 | 3571.6 | 2013-04-29 08:00 | 5d | 3571.6 | 0 | 0 | 0 | 0 | 3571.6 | 0 | 100% | Finished | 3571.6 | 3571.6 | 100 | 100 | 100 | 100 | 100 | 100
19 | Chap | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 357.14 | 14285.6006 | 14285.6006 | 2013-05-06 08:00 | 5d | 14285.6006 | 0 | 0 | 0 | 0 | 14285.6006 | 0 | 100% | Finished | 14285.6006 | 14285.6006 | 100 | 100 | 100 | 100 | 100 | 100
20 | Elektriciteit | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-06 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
21 | Sanitair | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 682.92 | 27316.7993 | 27316.7993 | 2013-05-06 08:00 | 5d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 27316.7993 | 27316.7993 | 100 | 100 | 100 | 100 | 100 | 100
22 | Bevloering en faience | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-05-13 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
23 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 313.33 | 12533.1995 | 12533.1995 | 2013-05-13 08:00 | 5d | 12533.1995 | 0 | 0 | 0 | 0 | 12533.1995 | 0 | 100% | Finished | 12533.1995 | 12533.1995 | 100 | 100 | 100 | 100 | 100 | 100
24 | Sanitair | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-05-13 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
25 | Elektriciteit | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1400 | 56000 | 56000 | 2013-05-20 08:00 | 5d | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 100% | Finished | 56000 | 56000 | 100 | 100 | 100 | 100 | 100 | 100
26 | Isolatie chap/pure | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-05-20 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
27 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 170.73 | 6829.1998 | 6829.1998 | 2013-06-10 08:00 | 5d | 6829.1998 | 0 | 0 | 0 | 0 | 6829.1998 | 0 | 100% | Finished | 6829.1998 | 6829.1998 | 100 | 100 | 100 | 100 | 100 | 100
28 | Chape | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 446.43 | 17857.1997 | 17857.1997 | 2013-08-19 08:00 | 5d | 17857.1997 | 0 | 0 | 0 | 0 | 17857.1997 | 0 | 100% | Finished | 17857.1997 | 17857.1997 | 100 | 100 | 100 | 100 | 100 | 100
29 | Parket | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 468.75 | 18750 | 18750 | 2013-10-07 08:00 | 5d | 18750 | 0 | 0 | 18750 | 0 | 37500 | 0 | 100% | Finished | 18750 | 18750 | 100 | 100 | 100 | 100 | 200 | 100
30 | Vloer | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-10-07 08:00 | 10d | 75000 | 0 | 0 | -37500 | 0 | 37500 | 0 | 100% | Finished | 37500 | 37500 | 100 | 200 | 100 | 100 | 100 | 100
31 | Isolatie chape/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-08-26 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 100% | Finished | 12500 | 12500 | 100 | 100 | 100 | 100 | 100 | 100
32 | Ventilatie | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-08-19 08:00 | 5d | 49000 | 0 | 0 | 0 | 0 | 49000 | 0 | 100% | Finished | 49000 | 49000 | 100 | 100 | 100 | 100 | 100 | 100
33 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 391.67 | 15666.8005 | 15666.8005 | 2013-09-16 08:00 | 5d | 15666.8005 | 0 | 0 | 0 | 0 | 15666.8005 | 0 | 100% | Finished | 15666.8005 | 15666.8005 | 100 | 100 | 100 | 100 | 100 | 100
34 | Vloer | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-10-07 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 100% | Finished | 56250 | 56250 | 100 | 100 | 100 | 100 | 66.6667 | 100
35 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 312.5 | 12500 | 12500 | 2013-09-02 08:00 | 5d | 12500 | 0 | 0 | 0 | 0 | 12500 | 0 | 100% | Finished | 12500 | 12500 | 100 | 100 | 100 | 100 | 100 | 100
36 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 410.16 | 16406.4001 | 16406.4001 | 2013-08-19 08:00 | 5d | 16406.4001 | 0 | 0 | 0 | 0 | 16406.4001 | 0 | 100% | Finished | 16406.4001 | 16406.4001 | 100 | 100 | 100 | 100 | 100 | 100
37 | Sanitair | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-06-10 08:00 | 5d | 13658.3997 | 0 | 0 | 13658.4004 | 0 | 27316.8 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 100 | 100 | 100 | 200 | 100
38 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-09-09 08:00 | 30d | 112800 | 0 | 0 | -94000 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 600 | 100 | 100 | 100 | 100
39 | Vloer | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-11-25 08:00 | 5d | 37500 | 0 | 0 | 18750 | 0 | 56250 | 0 | 100% | Finished | 37500 | 37500 | 100 | 100 | 100 | 100 | 150 | 100
40 | Keuken | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 546.87 | 21874.7998 | 21874.7998 | 2013-11-18 08:00 | 5d | 21874.7998 | 0 | 0 | 0 | 0 | 21874.7998 | 0 | 100% | Finished | 21874.7998 | 21874.7998 | 100 | 100 | 100 | 100 | 100 | 100
41 | Parket | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-09-09 08:00 | 5d | 37500 | 0 | 0 | 56250 | 0 | 93750 | 0 | 100% | Finished | 37500 | 37500 | 100 | 100 | 100 | 100 | 250 | 100
42 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 512.2 | 20488.0005 | 20488.0005 | 2013-10-21 08:00 | 5d | 20488.0005 | 0 | 0 | -6829.3301 | 0 | 13658.6704 | 0 | 100% | Finished | 20488.0005 | 20488.0005 | 100 | 100 | 100 | 100 | 66.6667 | 100
43 | Elektriciteit | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 470 | 18800 | 18800 | 2013-06-10 08:00 | 20d | 75200 | 0 | 0 | -56400 | 0 | 18800 | 0 | 100% | Finished | 18800 | 18800 | 100 | 400 | 100 | 100 | 100 | 100
44 | Ventilatie | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 1750 | 70000 | 70000 | 2013-09-16 08:00 | 20d | 280000 | 0 | 0 | -210000 | 0 | 70000 | 0 | 100% | Finished | 70000 | 70000 | 100 | 400 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 341.46 | 13658.3997 | 13658.3997 | 2013-07-01 08:00 | 10d | 27316.7993 | 0 | 0 | 0 | 0 | 27316.7993 | 0 | 100% | Finished | 13658.3997 | 13658.3997 | 100 | 200 | 100 | 100 | 200 | 100
46 | Schrijnwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 2013-09-30 08:00 | 20d | 131249.5996 | 0 | 0 | -98437 | 0 | 32812.5996 | 0 | 100% | Finished | 32812.3999 | 32812.3999 | 100 | 400 | 100 | 100 | 100.0006 | 100
47 | Parket | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1406.25 | 56250 | 56250 | 2013-09-23 08:00 | 5d | 56250 | 0 | 0 | -18750 | 0 | 37500 | 0 | 100% | Finished | 56250 | 56250 | 100 | 100 | 100 | 100 | 66.6667 | 100
48 | Ventilatie | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1225 | 49000 | 49000 | 2013-10-07 08:00 | 10d | 98000 | 0 | 0 | -49000 | 0 | 49000 | 0 | 100% | Finished | 49000 | 49000 | 100 | 200 | 100 | 100 | 100 | 100
49 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-10-07 08:00 | 10d | 87500 | 0 | 0 | -43750 | 0 | 43750 | 0 | 100% | Finished | 43750 | 43750 | 100 | 200 | 100 | 100 | 100 | 100
50 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 1230.47 | 49218.7988 | 49218.7988 | 2013-09-30 08:00 | 5d | 49218.7988 | 0 | 0 | -16406 | 0 | 32812.7988 | 0 | 100% | Finished | 49218.7988 | 49218.7988 | 100 | 100 | 100 | 100 | 66.6672 | 100
51 | Parket | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 937.5 | 37500 | 37500 | 2013-10-28 08:00 | 10d | 75000 | 0 | 0 | -18750 | 0 | 56250 | 0 | 100% | Finished | 37500 | 37500 | 100 | 200 | 100 | 100 | 150 | 100
52 | Keuken | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 1640.63 | 65625.2002 | 65625.2002 | 2013-10-14 08:00 | 5d | 65625.2002 | 0 | 0 | -21875 | 0 | 43750.2002 | 0 | 100% | Finished | 65625.2002 | 65625.2002 | 100 | 100 | 100 | 100 | 66.6668 | 100
53 | Schrijnwerk | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 820.31 | 32812.3999 | 32812.3999 | 2013-11-18 08:00 | 5d | 32812.3999 | 0 | 0 | 16406.1992 | 0 | 49218.5991 | 0 | 100% | Finished | 32812.3999 | 32812.3999 | 100 | 100 | 100 | 100 | 150 | 100
54 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1093.75 | 43750 | 43750 | 2013-12-02 08:00 | 5d | 43750 | 0 | 0 | 21875 | 0 | 65625 | 0 | 100% | Finished | 43750 | 43750 | 100 | 100 | 100 | 100 | 150 | 100
55 | Plakwerken | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 916.67 | 36666.7993 | 36666.7993 | 2013-12-02 08:00 | 1h | 916.67 | 0 | 0 | 0 | 0 | 916.67 | 0 | 100% | Finished | 36666.7993 | 36666.7993 | 100 | 2.5 | 100 | 100 | 2.5 | 100
56 | Plakwerken deel 2 | 2013-09-09 08:00 | 2013-10-04 17:00 | 20d |  | 0 | 0 | 1489.58 | 238332.793 | 238332.793 | 2013-12-02 08:00 | 1h | 1489.58 | 0 | 0 | 0 | 0 | 1489.58 | 0 | 100% | Finished | 238332.793 | 238332.793 | 100 | 0.625 | 100 | 100 | 0.625 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
01/03, 2013 | 2013-02-25 08:00 | 2013-03-01 17:00 | 200000 | 200000 | 200000 | 2013-03-01 17:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2750937.9996 | 2750937.9996 | 2750937.9996 | 2750937.9996 | 2750937.9996 | 2750937.9996 | 2750937.9996 | 2750937.9996 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
12/04, 2013 | 2013-03-01 17:00 | 2013-04-12 16:00 | 1213794.9631 | 1275129.2123 | 1273343.4123 | 2013-04-19 17:00 | 61334.2492 | 105.1% | 1785.8 | 100.1% | 5d 1h | 114.7% | 100% | 2013-10-01 11:00 | 2013-09-25 10:00 | 2013-09-25 09:00 | 2013-10-03 10:00 | 2013-09-25 10:00 | 2013-09-25 09:00 | 2013-09-27 16:00 | 2013-09-06 12:00 | 2013-09-06 11:00 | 2749152.1995 | 2747085.3506 | 2678165.1787 | 2560064.1987 | 2676197.7461 | 2558262.1648 | 2732765.5801 | 2705454.7022 | 1.147 | 1.0014 | 1.0505 | 1 | 5.125 | 1.0014 | 1 | 1.147 | 1
24/05, 2013 | 2013-04-12 16:00 | 2013-05-24 17:00 | 1569680.4086 | 1569680.4086 | 1586644.6086 | 2013-05-24 17:00 | 0 | 100% | -16964.2 | 98.93% | 0 | 100% | 100% | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-08 15:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-07 17:00 | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-10-07 17:00 | 2767902.1995 | 2780668.5498 | 2767902.1995 | 2767902.1995 | 2780668.5498 | 2780668.5498 | 2778093.252 | 2778093.252 | 1 | 0.98931 | 1 | 1 | 0 | 0.98931 | 1 | 1 | 1
05/07, 2013 | 2013-05-24 17:00 | 2013-07-05 17:00 | 2065219.6085 | 1615797.2079 | 1653249.0081 | 2013-06-04 12:00 | -449422.4005 | 78.24% | -37451.8002 | 97.73% | -23d 4h | 75.26% | 97.62% | 2013-11-12 09:00 | 2013-12-06 12:00 | 2013-12-13 10:00 | 2013-11-04 14:00 | 2013-12-06 12:00 | 2013-12-10 17:00 | 2013-11-07 12:00 | 2013-12-18 14:00 | 2013-12-23 11:00 | 2788389.7997 | 2814700.6919 | 3104121.0666 | 3161478.032 | 3137750.1447 | 3196436.56 | 2862963.532 | 2870684.0858 | 0.75263 | 0.97735 | 0.78239 | 0.97617 | -23.5 | 0.97735 | 1 | 0.75263 | 1
16/08, 2013 | 2013-07-05 17:00 | 2013-08-16 17:00 | 2333750.8072 | 1615797.2079 | 1653249.0081 | 2013-06-04 12:00 | -717953.5992 | 69.24% | -37451.8002 | 97.73% | -53d 4h | 57.2% | 97.62% | 2013-12-03 15:00 | 2014-01-14 09:00 | 2014-01-21 12:00 | 2013-11-28 12:00 | 2014-01-14 09:00 | 2014-01-16 12:00 | 2013-12-19 12:00 | 2014-03-21 15:00 | 2014-03-27 10:00 | 2788389.7997 | 2814700.6919 | 3292771.422 | 3637760.8816 | 3330773.1375 | 3683758.9448 | 2886629.3247 | 2919755.3355 | 0.572 | 0.97735 | 0.69236 | 0.97617 | -53.5 | 0.97735 | 1 | 0.572 | 1
27/09, 2013 | 2013-08-16 17:00 | 2013-09-27 09:00 | 2680927.7416 | 1884706.8082 | 2010887.8082 | 2013-06-21 17:00 | -796220.9335 | 70.3% | -126181 | 93.73% | -69d 1h | 55.15% | 91.53% | 2013-12-10 10:00 | 2014-01-08 14:00 | 2014-01-29 16:00 | 2013-12-09 15:00 | 2014-01-08 14:00 | 2014-01-15 12:00 | 2014-01-10 09:00 | 2014-04-07 09:00 | 2014-04-18 10:00 | 2877118.9996 | 2935113.1223 | 3243070.5655 | 3581568.7773 | 3325565.1222 | 3686725.7675 | 2983741.8918 | 3018015.1472 | 0.5515 | 0.93725 | 0.70301 | 0.91534 | -69.125 | 0.93725 | 1 | 0.5515 | 1
08/11, 2013 | 2013-09-27 09:00 | 2013-11-08 17:00 | 2750937.9996 | 2340001.2076 | 2395422.0772 | 2013-08-19 10:00 | -410936.792 | 85.06% | -55420.8696 | 97.69% | -59d 6h | 67.7% | 97.39% | 2013-11-07 16:00 | 2013-11-14 09:00 | 2013-11-20 12:00 | 2013-12-18 14:00 | 2013-12-25 12:00 | 2013-12-26 10:00 | 2013-12-27 15:00 | 2014-01-21 11:00 | 2014-01-22 12:00 | 2806358.8692 | 2816091.5455 | 2878525.0914 | 3002394.5843 | 2889966.9612 | 3016770.1941 | 2827253.0315 | 2843604.3991 | 0.67703 | 0.97686 | 0.85062 | 0.97391 | -59.75 | 0.97686 | 1 | 0.67703 | 1
Actual Schedule | 2013-11-08 17:00 | 2013-12-20 17:00 | 2750937.9996 | 2750937.9996 | 2590796.7261 | 2013-10-04 17:00 | 0 | 100% | 160141.2735 | 106.2% | -55d | 74.42% | 100% | 2013-10-04 17:00 | 2013-10-04 17:00 | 2013-09-23 14:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2013-12-20 17:00 | 2590796.7261 | 2590796.7261 | 2590796.7261 | 2590796.7261 | 2590796.7261 | 2590796.7261 | 2590796.7261 | 2590796.7261 | 0.74419 | 1.0618 | 1 | 1 | -55 | 1.0618 | 1 | 0.74419 | 1