## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Family Residence (2) | 1 |  |  | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 | 361.375
1 | Spanten | 1.1 |  | FS9;FS10 | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 11.375
2 | Isolatie chap/pure | 1.2 |  | FS6 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
3 | Plakwerken | 1.3 |  | FS7 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 4.375
4 | Schrijnwerk | 1.4 |  | FS13 | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 11.375
5 | Schrijnwerk deel 2 | 1.5 |  | FS8 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 4.375
6 | Chape | 1.6 | 2FS | FS19+2w | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
7 | Sanitair | 1.7 | 3FS | FS11;FS13 | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 11.375
8 | Elektriciteit | 1.8 | 5FS | FS15 | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 4.375
9 | Spanten | 1.9 | 1FS | FS17 | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 11.375
10 | Dakconstructie | 1.10 | 1FS | FS18 | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 11.375
11 | Isolatie chap/pure | 1.11 | 7FS | FS12-2w | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
12 | Chape | 1.12 | 11FS-2w | FS20-1w;FS25 | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
13 | Elektriciteit | 1.13 | 4FS;7FS | FS21;FS22 | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 4.375
14 | Ruwbouw | 1.14 |  | SS16;FS51;FS54 | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 60.375
15 | Sanitair | 1.15 | 8FS | FS23-1w;FS24 | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 11.375
16 | Ruwbouw deel 2 | 1.16 | 14SS | FS61 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 67.375
17 | Dakconstructie | 1.17 | 9FS | FS28;FS32 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 11.375
18 | Schrijnwerk | 1.18 | 10FS;19FS-1w | FS24-1w;FS29 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 11.375
19 | Elektriciteit | 1.19 | 6FS+2w | FS18-1w | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
20 | Vloer | 1.20 | 12FS-1w | FS30 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
21 | Isolatie zolder | 1.21 | 13FS | FS26 | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
22 | Sanitair | 1.22 | 13FS |  | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
23 | Elektriciteit deel 2 | 1.23 | 15FS-1w | FS27-1w | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 11.375
24 | Elektriciteit | 1.24 | 18FS-1w;15FS | FS29;FS31 | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 4.375
25 | Vloer | 1.25 | 12FS | FS30-1w | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
26 | Plakwerken | 1.26 | 21FS | FS36+1w | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 4.375
27 | Isolatie zolder | 1.27 | 23FS-1w | SS41+3w | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
28 | Schrijnwerk | 1.28 | 17FS | FS53 | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 39.375
29 | Sanitair | 1.29 | 24FS;18FS | FS33-1w;FS34-1w | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 11.375
30 | Elektriciteit | 1.30 | 20FS;25FS-1w | FS35-1w | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 11.375
31 | Isolatie zolder | 1.31 | 24FS | FS37 | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
32 | Schrijnwerk | 1.32 | 17FS | FS43+1w | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 18.375
33 | Elektriciteit | 1.33 | 29FS-1w | FS38-1w | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 11.375
34 | Keuken | 1.34 | 29FS-1w |  | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
35 | Schrijnwerk | 1.35 | 30FS-1w | FS39-1w | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 11.375
36 | Sanitair | 1.36 | 26FS+1w | FS40 | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
37 | Plakwerk | 1.37 | 31FS | FS45+2w | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 4.375
38 | Isolatie zolder | 1.38 | 33FS-1w | FS44+1w | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
39 | Sanitair | 1.39 | 35FS-1w | FS42-1w | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 11.375
40 | Isolatie chap/pure | 1.40 | 36FS | FS48+2w | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
41 | Sanitair | 1.41 | 27SS+3w | FS46+1w | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
42 | Keuken | 1.42 | 39FS-1w |  | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 11.375
43 | Schrijnwerk | 1.43 | 32FS+1w | FS47 | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
44 | Plakwerken | 1.44 | 38FS+1w |  | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 11.375
45 | Sanitair | 1.45 | 37FS+2w | FS49;FS55+1w | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 4.375
46 | Isolatie chap/pure | 1.46 | 41FS+1w | FS52+1w | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
47 | Elektriciteit | 1.47 | 43FS | FS50 | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
48 | Vloer | 1.48 | 40FS+2w |  | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
49 | Isolatie chap/pure | 1.49 | 45FS | FS52 | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
50 | Sanitair | 1.50 | 47FS | FS56-1w;FS57-1w;FS65+1w | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 11.375
51 | Spanten | 1.51 | 14FS | FS63;FS69+1w;FS66 | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 11.375
52 | Chape | 1.52 | 49FS;46FS+1w | FS58-1w;FS60-1w | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 11.375
53 | Elektriciteit | 1.53 | 28FS | FS59 | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
54 | Ruwbouw | 1.54 | 14FS | FS101;FS102 | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 67.375
55 | Isolatie chape/pure | 1.55 | 45FS+1w | FS68+2w | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
56 | Elektriciteit | 1.56 | 50FS-1w | FS64+1w;FS66+1w | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 4.375
57 | Isolatie chap/pure | 1.57 | 50FS-1w | FS62 | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
58 | Vloer | 1.58 | 52FS-1w | FS67 | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
59 | Sanitair | 1.59 | 53FS | FS67+1w | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
60 | Vloer deel 2 | 1.60 | 52FS-1w | FS73 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 18.375
61 | Spanten | 1.61 | 16FS | FS69 | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 11.375
62 | Chape | 1.62 | 57FS |  | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
63 | Dakwerken | 1.63 | 51FS |  | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 11.375
64 | Plakwerken | 1.64 | 56FS+1w | FS74+1w | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 4.375
65 | Isolatie chap/pure | 1.65 | 50FS+1w | FS70 | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
66 | Schrijnwerk | 1.66 | 56FS+1w;51FS | SS71+1w;SS74+2w;FS107 | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 39.375
67 | Elektriciteit | 1.67 | 58FS;59FS+1w | FS72 | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 4.375
68 | Vloer | 1.68 | 55FS+2w | FS76 | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
69 | Dakwerken | 1.69 | 61FS;51FS+1w | FS80;FS81;FS82 | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 11.375
70 | Chape | 1.70 | 65FS | FS75 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
71 | Sanitair | 1.71 | 66SS+1w | FS77 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
72 | Isolatie zolder | 1.72 | 67FS | FS78 | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
73 | Elektriciteit | 1.73 | 60FS | FS79-1w;FS85-1w | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 11.375
74 | Sanitair | 1.74 | 64FS+1w;66SS+2w | FS83 | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 4.375
75 | Vloer | 1.75 | 70FS | FS88 | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
76 | Elektriciteit | 1.76 | 68FS | FS84 | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
77 | keuken | 1.77 | 71FS |  | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 11.375
78 | Plakwerken | 1.78 | 72FS |  | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 4.375
79 | Schrijnwerk | 1.79 | 73FS-1w |  | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 11.375
80 | Schrijnwerk deel 2 | 1.80 | 69FS | FS98 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 32.375
81 | Schrijnwerk deel 3 | 1.81 | 69FS | FS95 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 18.375
82 | Schrijnwerk deel 4 | 1.82 | 69FS | FS106 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 39.375
83 | Isolatie chap/pure | 1.83 | 74FS | FS87 | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
84 | Schrijnwerk | 1.84 | 76FS | FS89 | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
85 | Sanitair | 1.85 | 73FS-1w | FS90-1w | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 11.375
86 | Ruwbouw | 1.86 |  | FS128 | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 81.375
87 | Chape | 1.87 | 83FS | FS91 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
88 | Elektriciteit | 1.88 | 75FS | FS92 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
89 | Sanitair | 1.89 | 84FS | FS93;FS94 | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 4.375
90 | Keuken | 1.90 | 85FS-1w |  | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 11.375
91 | Vloer | 1.91 | 87FS | FS98 | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
92 | Schrijnwerk | 1.92 | 88FS | FS96 | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
93 | Keuken | 1.93 | 89FS |  | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
94 | Isolatie chap/pure | 1.94 | 89FS | FS97 | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
95 | Elektriciteit | 1.95 | 81FS |  | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
96 | Sanitair | 1.96 | 92FS | FS99;FS98 | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 4.375
97 | Chape | 1.97 | 94FS | FS100 | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
98 | Elektriciteit | 1.98 | 91FS;80FS;96FS | FS103;FS104;FS105 | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 4.375
99 | Keuken | 1.99 | 96FS |  | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
100 | Vloer | 1.100 | 97FS | FS112+3w | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
101 | Spanten | 1.101 | 54FS | FS113+3w | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 11.375
102 | Ruwbouw | 1.102 | 54FS | FS166 | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 95.375
103 | Schrijnwerk | 1.103 | 98FS | FS110 | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
104 | Sanitair | 1.104 | 98FS | FS112+3w | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
105 | Isolatie zolder | 1.105 | 98FS | FS114+3w | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
106 | Elektriciteit | 1.106 | 82FS | FS110 | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 4.375
107 | Elektriciteit | 1.107 | 66FS | FS108 | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
108 | Sanitair | 1.108 | 107FS | FS109 | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
109 | Elektriciteit | 1.109 | 108FS | FS111 | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
110 | Sanitair | 1.110 | 103FS;106FS | FS115-1w;FS119-1w | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 11.375
111 | Isolatie zolder | 1.111 | 109FS | FS116 | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
112 | Elektriciteit | 1.112 | 100FS+3w;104FS+3w | FS117;FS118 | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 4.375
113 | Dakconstructie | 1.113 | 101FS+3w | FS121;FS123 | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 11.375
114 | Plakwerk | 1.114 | 105FS+3w | FS120+1w | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 4.375
115 | Keuken | 1.115 | 110FS-1w |  | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
116 | Plakwerk | 1.116 | 111FS | FS125+1w | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 4.375
117 | Schrijnwerk | 1.117 | 112FS | FS120 | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
118 | Isolatie zolder | 1.118 | 112FS | FS122-1w | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
119 | Elektriciteit | 1.119 | 110FS-1w | FS124-1w | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 11.375
120 | Sanitair | 1.120 | 117FS;114FS+1w | FS126;FS127 | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 4.375
121 | Schrijnwerk | 1.121 | 113FS | FS139 | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 25.375
122 | Plakwerk | 1.122 | 118FS-1w | SS130+2w | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 11.375
123 | Schrijnwerk deel 2 | 1.123 | 113FS | FS147 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 39.375
124 | Isolatie zolder | 1.124 | 119FS-1w | FS132-1w | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
125 | Sanitair | 1.125 | 116FS+1w | FS129 | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
126 | Keuken | 1.126 | 120FS |  | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
127 | Isolatie chap/pure | 1.127 | 120FS | FS131 | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
128 | Spanten | 1.128 | 86FS | FS136 | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 11.375
129 | Isolatie chap/pure | 1.129 | 125FS | FS133 | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
130 | Sanitair | 1.130 | 122SS+2w | FS134-1w | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 11.375
131 | Chape | 1.131 | 127FS | FS135 | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
132 | Plakwerk | 1.132 | 124FS-1w | SS137+2w | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 11.375
133 | Chape | 1.133 | 129FS | FS138 | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
134 | Isolatie chap/pure | 1.134 | 130FS-1w | FS140-1w | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
135 | Vloer | 1.135 | 131FS | FS144 | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
136 | Dakwerken | 1.136 | 128FS | FS145 | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 11.375
137 | Sanitair | 1.137 | 132SS+2w | FS141-1w | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 11.375
138 | Vloer | 1.138 | 133FS | FS147 | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
139 | Elektriciteit | 1.139 | 121FS | FS142 | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
140 | Chape | 1.140 | 134FS-1w | FS143-1w;FS148 | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
141 | Isolatie chap/pure | 1.141 | 137FS-1w | FS146-1w | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
142 | Sanitair | 1.142 | 139FS | FS147 | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
143 | Vloer | 1.143 | 140FS-1w | FS151 | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
144 | Elektriciteit | 1.144 | 135FS | FS149 | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
145 | Schrijnwerk | 1.145 | 136FS |  | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 | 32.375
146 | Chape | 1.146 | 141FS-1w | FS148-1w;FS153 | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 11.375
147 | Elektriciteit | 1.147 | 138FS;142FS;123FS | FS150;FS154+1w | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 | 4.375
148 | Vloer | 1.148 | 140FS;146FS-1w | FS157 | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 | 11.375
149 | Schrijnwerk | 1.149 | 144FS | FS152 | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
150 | Isolatie zolder | 1.150 | 147FS | FS155 | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
151 | Elektriciteit | 1.151 | 143FS | FS156-1w | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 11.375
152 | Sanitair | 1.152 | 149FS | FS157;FS158 | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 4.375
153 | Vloer | 1.153 | 146FS |  | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
154 | Schrijnwerk | 1.154 | 147FS+1w | FS159 | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
155 | Plakwerk | 1.155 | 150FS | FS163+2w | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 4.375
156 | Schrijnwerk | 1.156 | 151FS-1w | FS159-1w;FS163+1w | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 11.375
157 | Elektriciteit | 1.157 | 152FS;148FS | FS160-1w;FS161-1w | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 | 11.375
158 | Keuken | 1.158 | 152FS |  | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
159 | Sanitair | 1.159 | 154FS;156FS-1w | FS162;FS164+1w | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 4.375
160 | Schrijnwerk | 1.160 | 157FS-1w | FS165+1w | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 4.375
161 | Isolatie zolder | 1.161 | 157FS-1w | FS170+3w | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
162 | Keuken | 1.162 | 159FS |  | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
163 | Sanitair | 1.163 | 155FS+2w;156FS+1w | FS167 | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 4.375
164 | Keuken | 1.164 | 159FS+1w |  | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 11.375
165 | Sanitair deel 2 | 1.165 | 160FS+1w | FS168-1w | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 11.375
166 | Spanten | 1.166 | 102FS | FS171 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 11.375
167 | Isolatie chap/pure | 1.167 | 163FS | FS169 | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
168 | Keuken | 1.168 | 165FS-1w |  | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 11.375
169 | Chape | 1.169 | 167FS | FS172 | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
170 | Sanitair | 1.170 | 161FS+3w | FS173 | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
171 | Dakwerken | 1.171 | 166FS | FS175 | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 11.375
172 | Vloer | 1.172 | 169FS | FS176 | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
173 | Isolatie chap/pure | 1.173 | 170FS | FS174 | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
174 | Chape | 1.174 | 173FS | FS177 | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 4.375
175 | Schrijnwerk | 1.175 | 171FS |  | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 39.375
176 | Elektriciteit | 1.176 | 172FS | FS178 | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
177 | Vloer | 1.177 | 174FS | FS180+1w | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 11.375
178 | Schrijnwerk | 1.178 | 176FS | FS179+1w | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
179 | Sanitair | 1.179 | 178FS+1w | FS181 | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
180 | Elektriciteit | 1.180 | 177FS+1w | FS182 | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 4.375
181 | Keuken | 1.181 | 179FS |  | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375
182 | Schrijnwerk | 1.182 | 180FS | FS183 | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 4.375
183 | Sanitair | 1.183 | 182FS | FS184 | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 4.375
184 | Keuken | 1.184 | 183FS |  | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Family Residence (2) | 2080h |  |  |  |  | 99 | 100 | 101
1 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Plakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Schrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Schrijnwerk deel 2 | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Dakconstructie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Isolatie chap/pure | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Chape | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Ruwbouw | 360h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Ruwbouw deel 2 | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Dakconstructie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Schrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Elektriciteit deel 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Plakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Isolatie zolder | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Schrijnwerk | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Schrijnwerk | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Schrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Plakwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Keuken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | Plakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Chape | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
53 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | Ruwbouw | 400h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | Isolatie chape/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | Vloer deel 2 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | Dakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | Plakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Schrijnwerk | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Dakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | keuken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
78 | Plakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | Schrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | Schrijnwerk deel 2 | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | Schrijnwerk deel 3 | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | Schrijnwerk deel 4 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | Ruwbouw | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | Keuken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
92 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | Ruwbouw | 560h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | Dakconstructie | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | Plakwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
116 | Plakwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | Isolatie zolder | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | Schrijnwerk | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | Plakwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | Schrijnwerk deel 2 | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | Isolatie zolder | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | Plakwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | Isolatie chap/pure | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
135 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | Dakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | Sanitair | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | Chape | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | Isolatie chap/pure | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | Schrijnwerk | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | Chape | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
152 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | Plakwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | Schrijnwerk | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | Elektriciteit | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | Isolatie zolder | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | Keuken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
165 | Sanitair deel 2 | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | Spanten | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | Keuken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
169 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | Dakwerken | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | Isolatie chap/pure | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | Schrijnwerk | 240h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | Vloer | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
179 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
180 | Elektriciteit | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | Schrijnwerk | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | Sanitair | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | Keuken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-03-01 17:00 |  | TP Name | 01/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 25d | [5 empty] | 12408.4 |  | 8.637% |  | 12408.4 | 17112.8001
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 |  | 0 | 0 | 1420.8 | 10d | 0 | 0 | 0 | 1420.8 | 0% | Not Started | 0 | 1420.8 | 100 |  | 0 | 100 |  | 0
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 5d | 473.6 | 473.6 | 5d | 0 | 0 | 473.6 | 473.6 | 50% | Started | 473.6 | 947.2 | 100 | 50 | 50 | 100 | 50 | 50
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 5d | 2770.4001 | 22163.2007 | 40d | 0 | 0 | 2770.4001 | 22163.2007 | 11.11% | Started | 2770.4001 | 5540.8002 | 100 | 11.1111 | 11.1111 | 100 | 11.1111 | 11.1111
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 10d | 2216.7999 | 8867.1997 | 40d | 0 | 0 | 2216.7999 | 8867.1997 | 20% | Started | 2216.8 | 2216.7999 | 100 | 20 | 20 | 100 | 20 | 20
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 236.8 | 100 |  | 0 | 100 |  | 0
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 5d | 390 | 390 | 5d | 0 | 0 | 390 | 390 | 50% | Started | 390 | 390 | 100 | 50 | 50 | 100 | 50 | 50
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 173.2 | 100 |  | 0 | 100 |  | 0
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 197.2 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 |  | 0 | 0 | 532.4 | 5d | 0 | 0 | 0 | 532.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 |  | 0 | 0 | 848.8 | 10d | 0 | 0 | 0 | 848.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 |  | 0 | 0 | 1111.2 | 5d | 0 | 0 | 0 | 1111.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 |  | 0 | 0 | 1120.8 | 10d | 0 | 0 | 0 | 1120.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 5d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 |  | 0 | 0 | 848.8 | 10d | 0 | 0 | 0 | 848.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 |  | 0 | 0 | 2368.8 | 10d | 0 | 0 | 0 | 2368.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 |  | 0 | 0 | 198.4 | 10d | 0 | 0 | 0 | 198.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 |  | 0 | 0 | 5540.0002 | 50d | 0 | 0 | 0 | 5540.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 |  | 0 | 0 | 591.6 | 15d | 0 | 0 | 0 | 591.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 |  | 0 | 0 | 1420.8 | 10d | 0 | 0 | 0 | 1420.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 5d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 |  | 0 | 0 | 1950 | 25d | 0 | 0 | 0 | 1950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 |  | 0 | 0 | 6652.7998 | 60d | 0 | 0 | 0 | 6652.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 |  | 0 | 0 | 849.6 | 5d | 0 | 0 | 0 | 849.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 5d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 |  | 0 | 0 | 692.8 | 5d | 0 | 0 | 0 | 692.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 |  | 0 | 0 | 13260.8002 | 70d | 0 | 0 | 0 | 13260.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 |  | 0 | 0 | 1132 | 10d | 0 | 0 | 0 | 1132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 |  | 0 | 0 | 2216.7999 | 10d | 0 | 0 | 0 | 2216.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 |  | 0 | 0 | 780.8 | 20d | 0 | 0 | 0 | 780.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 5d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 |  | 0 | 0 | 788.8 | 10d | 0 | 0 | 0 | 788.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 10d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-04-12 17:00 |  | TP Name | 12/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 55d | [5 empty] | 46979.2003 |  | 26.66% |  | 38302.7001 | 51694.8004
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 35d | 19392.8006 | 16622.4005 | 30d | 0 | 0 | 19392.8006 | 16622.4005 | 53.85% | Started | 13425.7857 | 22163.2007 | 100 | 77.7778 | 53.8462 | 100 | 77.7778 | 53.8462
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 40d | 8867.1997 | 6650.3998 | 30d | 0 | 0 | 8867.1997 | 6650.3998 | 57.14% | Started | 6333.7144 | 8867.1997 | 100 | 80 | 57.1429 | 100 | 80 | 57.1429
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 5d | 236.8 | 236.8 | 5d | 0 | 0 | 236.8 | 236.8 | 50% | Started | 236.8 | 473.6 | 100 | 50 | 50 | 100 | 50 | 50
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 976 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 |  | 0 | 0 | 1120.8 | 10d | 0 | 0 | 0 | 1120.8 | 0% | Not Started | 0 | 560.4 | 100 |  | 0 | 100 |  | 0
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 5d | 566.4 | 566.4 | 5d | 0 | 0 | 566.4 | 566.4 | 50% | Started | 283.2 | 566.4 | 100 | 100 | 50 | 100 | 100 | 50
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 |  | 0 | 0 | 848.8 | 10d | 0 | 0 | 0 | 848.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 |  | 0 | 0 | 2368.8 | 10d | 0 | 0 | 0 | 2368.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 |  | 0 | 0 | 198.4 | 10d | 0 | 0 | 0 | 198.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 |  | 0 | 0 | 5540.0002 | 50d | 0 | 0 | 0 | 5540.0002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 |  | 0 | 0 | 591.6 | 15d | 0 | 0 | 0 | 591.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 |  | 0 | 0 | 1420.8 | 10d | 0 | 0 | 0 | 1420.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 5d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 |  | 0 | 0 | 1950 | 25d | 0 | 0 | 0 | 1950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 |  | 0 | 0 | 6652.7998 | 60d | 0 | 0 | 0 | 6652.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 |  | 0 | 0 | 849.6 | 5d | 0 | 0 | 0 | 849.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 5d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 |  | 0 | 0 | 692.8 | 5d | 0 | 0 | 0 | 692.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 |  | 0 | 0 | 13260.8002 | 70d | 0 | 0 | 0 | 13260.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 |  | 0 | 0 | 1132 | 10d | 0 | 0 | 0 | 1132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 |  | 0 | 0 | 2216.7999 | 10d | 0 | 0 | 0 | 2216.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 |  | 0 | 0 | 780.8 | 20d | 0 | 0 | 0 | 780.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 5d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 |  | 0 | 0 | 788.8 | 10d | 0 | 0 | 0 | 788.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 10d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-05-24 17:00 |  | TP Name | 24/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 85d | [5 empty] | 84670.0005 |  | 42.87% |  | 61599.5512 | 71426.8005
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 65d | 36015.2011 | 5540.8002 | 10d | 0 | 0 | 36015.2011 | 5540.8002 | 86.67% | Started | 21609.1209 | 24933.6008 | 100 | 144.4444 | 86.6667 | 100 | 144.4444 | 86.6667
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 70d | 15517.5995 | 3325.1999 | 15d | 0 | 0 | 15517.5995 | 3325.1999 | 82.35% | Started | 9127.9998 | 11083.9996 | 100 | 140 | 82.3529 | 100 | 140 | 82.3529
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 5d | 1184.4 | 4737.6001 | 20d | 0 | 0 | 1184.4 | 4737.6001 | 20% | Started | 473.76 | 2368.8 | 100 | 50 | 20 | 100 | 50 | 20
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 10d | 1108 | 2770.0001 | 25d | 0 | 0 | 1108 | 2770.0001 | 28.57% | Started | 1582.8573 | 2770.0001 | 100 | 20 | 28.5714 | 100 | 20 | 28.5714
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 947.2 | 100 |  | 0 | 100 |  | 0
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 473.6 | 100 |  | 0 | 100 |  | 0
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 10d | 390.4 | 780.8 | 20d | 0 | 0 | 390.4 | 780.8 | 33.33% | Started | 390.4 | 390.4 | 100 | 33.3333 | 33.3333 | 100 | 33.3333 | 33.3333
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 |  | 0 | 0 | 1420.8 | 10d | 0 | 0 | 0 | 1420.8 | 0% | Not Started | 0 | 1420.8 | 100 |  | 0 | 100 |  | 0
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 173.2 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 5d | 566.4 | 566.4 | 5d | 0 | 0 | 566.4 | 566.4 | 50% | Started | 283.2 | 0 | 100 | 100 | 50 | 100 | 100 | 50
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 0 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 0 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 0 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 5d | 195.2 | 390.4 | 10d | 0 | 0 | 195.2 | 390.4 | 33.33% | Started | 130.1333 | 0 | 100 | 50 | 33.3333 | 100 | 50 | 33.3333
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 |  | 0 | 0 | 1950 | 25d | 0 | 0 | 0 | 1950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 0 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 5d | 283.2 | 849.6 | 15d | 0 | 0 | 283.2 | 849.6 | 25% | Started | 141.6 | 0 | 100 | 50 | 25 | 100 | 50 | 25
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 |  | 0 | 0 | 6652.7998 | 60d | 0 | 0 | 0 | 6652.7998 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 |  | 0 | 0 | 849.6 | 5d | 0 | 0 | 0 | 849.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 1052.8 | 20d | 0 | 0 | 263.2 | 1052.8 | 20% | Started | 105.28 | 0 | 100 | 50 | 20 | 100 | 50 | 20
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 0 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 5d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 |  | 0 | 0 | 692.8 | 5d | 0 | 0 | 0 | 692.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 |  | 0 | 0 | 13260.8002 | 70d | 0 | 0 | 0 | 13260.8002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 |  | 0 | 0 | 1132 | 10d | 0 | 0 | 0 | 1132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 |  | 0 | 0 | 2216.7999 | 10d | 0 | 0 | 0 | 2216.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 |  | 0 | 0 | 780.8 | 20d | 0 | 0 | 0 | 780.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 5d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 |  | 0 | 0 | 788.8 | 10d | 0 | 0 | 0 | 788.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 10d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-07-05 17:00 |  | TP Name | 05/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 115d | [5 empty] | 114490.0008 |  | 55.93% |  | 80354.1338 | 92730.4005
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 35d | 3878.0001 | 4432.0001 | 40d | 0 | 0 | 3878.0001 | 4432.0001 | 46.67% | Started | 2585.3334 | 5540.0002 | 100 | 70 | 46.6667 | 100 | 70 | 46.6667
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 947.2 | 100 |  | 0 | 100 |  | 0
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 25d | 3552 | 4972.8001 | 35d | 0 | 0 | 3552 | 4972.8001 | 41.67% | Started | 592 | 1420.8 | 100 | 250 | 41.6667 | 100 | 250 | 41.6667
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 2340 | 100 |  | 0 | 100 |  | 0
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 |  | 0 | 0 | 6652.7998 | 60d | 0 | 0 | 0 | 6652.7998 | 0% | Not Started | 0 | 2771.9999 | 100 |  | 0 | 100 |  | 0
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 173.2 | 100 |  | 0 | 100 |  | 0
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 |  | 0 | 0 | 692.8 | 5d | 0 | 0 | 0 | 692.8 | 0% | Not Started | 0 | 692.8 | 100 |  | 0 | 100 |  | 0
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 197.2 | 100 |  | 0 | 100 |  | 0
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 |  | 0 | 0 | 13260.8002 | 70d | 0 | 0 | 0 | 13260.8002 | 0% | Not Started | 0 | 947.2 | 100 |  | 0 | 100 |  | 0
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 0 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 |  | 0 | 0 | 1132 | 10d | 0 | 0 | 0 | 1132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 5d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 |  | 0 | 0 | 2216.7999 | 10d | 0 | 0 | 0 | 2216.7999 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 |  | 0 | 0 | 780.8 | 20d | 0 | 0 | 0 | 780.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 5d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 |  | 0 | 0 | 788.8 | 10d | 0 | 0 | 0 | 788.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 10d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-08-16 17:00 |  | TP Name | 16/08, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 145d | [5 empty] | 132865.6008 |  | 67.76% |  | 97350.0938 | 109501.2004
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 65d | 7202.0002 | 1108 | 10d | 0 | 0 | 7202.0002 | 1108 | 86.67% | Started | 4801.3335 | 5540.0002 | 100 | 130 | 86.6667 | 100 | 130 | 86.6667
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 50 | 100 | 100 | 50 | 100
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 55d | 7814.4001 | 710.4 | 5d | 0 | 0 | 7814.4001 | 710.4 | 91.67% | Started | 1302.4 | 1420.8 | 100 | 550 | 91.6667 | 100 | 550 | 91.6667
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 |  | 0 | 0 | 1170 | 15d | 0 | 0 | 0 | 1170 | 0% | Not Started | 0 | 1170 | 100 |  | 0 | 100 |  | 0
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 2340 | 2340 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 10d | 1108.8 | 3326.3999 | 30d | 0 | 0 | 1108.8 | 3326.3999 | 25% | Started | 1663.2 | 6098.3998 | 100 | 16.6667 | 25 | 100 | 16.6667 | 25
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 173.2 | 100 |  | 0 | 100 |  | 0
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 692.8 | 692.8 | 100 | 100 | 100 | 100 | 100 | 100
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 50 | 100 | 100 | 50 | 100
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 10d | 1894.4 | 7577.6001 | 40d | 0 | 0 | 1894.4 | 7577.6001 | 20% | Started | 2652.1601 | 6630.4001 | 100 | 14.2857 | 20 | 100 | 14.2857 | 20
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 10d | 1132 | 1132 | 10d | 0 | 0 | 1132 | 1132 | 50% | Started | 566 | 1132 | 100 | 100 | 50 | 100 | 100 | 50
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 100% | Finished | 2216.7999 | 2216.7999 | 100 | 100 | 100 | 100 | 100 | 100
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 555.6 | 100 |  | 0 | 100 |  | 0
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 263.2 | 100 |  | 0 | 100 |  | 0
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 5d | 66 | 66 | 5d | 0 | 0 | 66 | 66 | 50% | Started | 66 | 66 | 100 | 50 | 50 | 100 | 50 | 50
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 173.2 | 519.6 | 15d | 0 | 0 | 173.2 | 519.6 | 25% | Started | 86.6 | 173.2 | 100 | 50 | 25 | 100 | 50 | 25
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 |  | 0 | 0 | 780.8 | 20d | 0 | 0 | 0 | 780.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 |  | 0 | 0 | 1110.4 | 10d | 0 | 0 | 0 | 1110.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 5d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 |  | 0 | 0 | 788.8 | 10d | 0 | 0 | 0 | 788.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 10d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-09-28 17:00 |  | TP Name | 28/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 175d | [5 empty] | 155086.6007 |  | 83.12% |  | 119422.4005 | 126012.0004
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 75d | 8310.0002 | 0 | 0 | 0 | 0 | 8310.0002 | 0 | 100% | Finished | 5540.0002 | 5540.0002 | 100 | 150 | 100 | 100 | 150 | 100
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 50 | 100 | 100 | 50 | 100
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 60d | 8524.8001 | 0 | 0 | 0 | 0 | 8524.8001 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 600 | 100 | 100 | 600 | 100
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-08-26 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 2340 | 2340 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 40d | 4435.1999 | 4435.1999 | 40d | 0 | 0 | 4435.1999 | 4435.1999 | 50% | Started | 3326.3999 | 6652.7998 | 100 | 66.6667 | 50 | 100 | 66.6667 | 50
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-08-26 08:00 | 5d | 173.2 | 0 | 0 | -86.6 | 0 | 86.6 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 50 | 100
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 692.8 | 692.8 | 100 | 100 | 100 | 100 | 100 | 100
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 50 | 100 | 100 | 50 | 100
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 40d | 7577.6001 | 0 | 0 | 0 | 0 | 7577.6001 | 0 | 100% | Finished | 13260.8002 | 12313.6002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 40d | 4527.9999 | 1132 | 10d | 0 | 0 | 4527.9999 | 1132 | 80% | Started | 905.6 | 1132 | 100 | 400 | 80 | 100 | 400 | 80
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 100% | Finished | 2216.7999 | 2216.7999 | 100 | 100 | 100 | 100 | 100 | 100
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 555.6 | 100 |  | 0 | 100 |  | 0
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-19 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 20d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-08-19 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 2013-08-19 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 780.8 | 780.8 | 100 | 100 | 100 | 100 | 100 | 100
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-08-19 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 |  | 0 | 0 | 1171.2 | 30d | 0 | 0 | 0 | 1171.2 | 0% | Not Started | 0 | 1171.2 | 100 |  | 0 | 100 |  | 0
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-02 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-08-26 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-26 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 473.6 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-02 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-09-09 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-09 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-09 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 394.4 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 473.6 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-23 08:00 | 5d | 283.2 | 283.2 | 5d | 0 | 0 | 283.2 | 283.2 | 50% | Started | 283.2 | 566.4 | 100 | 50 | 50 | 100 | 50 | 50
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-16 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-09-16 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-16 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 132 | 100 |  | 0 | 100 |  | 0
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-09-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-23 08:00 | 5d | 197.2 | 197.2 | 5d | 0 | 0 | 197.2 | 197.2 | 50% | Started | 197.2 | 197.2 | 100 | 50 | 50 | 100 | 50 | 50
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 173.2 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 195.2 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 |  | 0 | 0 | 132 | 10d | 0 | 0 | 0 | 132 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 5d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 |  | 0 | 0 | 788.8 | 10d | 0 | 0 | 0 | 788.8 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 |  | 0 | 0 | 346.4 | 10d | 0 | 0 | 0 | 346.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 |  | 0 | 0 | 555.6 | 5d | 0 | 0 | 0 | 555.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 |  | 0 | 0 | 390.4 | 10d | 0 | 0 | 0 | 390.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 |  | 0 | 0 | 519.2 | 10d | 0 | 0 | 0 | 519.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 |  | 0 | 0 | 566 | 5d | 0 | 0 | 0 | 566 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 |  | 0 | 0 | 947.2 | 10d | 0 | 0 | 0 | 947.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 |  | 0 | 0 | 2340 | 30d | 0 | 0 | 0 | 2340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-11-08 17:00 |  | TP Name | 08/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 205d | [5 empty] | 172121.8005 |  | 91.35% |  | 131247.7604 | 135674.0003
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 75d | 8310.0002 | 0 | 0 | 0 | 0 | 8310.0002 | 0 | 100% | Finished | 5540.0002 | 5540.0002 | 100 | 150 | 100 | 100 | 150 | 100
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 50 | 100 | 100 | 50 | 100
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 60d | 8524.8001 | 0 | 0 | 0 | 0 | 8524.8001 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 600 | 100 | 100 | 600 | 100
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-08-26 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 2340 | 2340 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 70d | 7761.5998 | 1108.8 | 10d | 0 | 0 | 7761.5998 | 1108.8 | 87.5% | Started | 5821.1999 | 6652.7998 | 100 | 116.6667 | 87.5 | 100 | 116.6667 | 87.5
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-08-26 08:00 | 5d | 173.2 | 0 | 0 | -86.6 | 0 | 86.6 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 50 | 100
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 692.8 | 692.8 | 100 | 100 | 100 | 100 | 100 | 100
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 50 | 100 | 100 | 50 | 100
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 40d | 7577.6001 | 0 | 0 | 0 | 0 | 7577.6001 | 0 | 100% | Finished | 13260.8002 | 13260.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 50d | 5659.9998 | 0 | 0 | 0 | 0 | 5659.9998 | 0 | 100% | Finished | 1132 | 1132 | 100 | 500 | 100 | 100 | 500 | 100
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 100% | Finished | 2216.7999 | 2216.7999 | 100 | 100 | 100 | 100 | 100 | 100
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-07 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-19 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 20d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-08-19 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 2013-08-19 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 780.8 | 780.8 | 100 | 100 | 100 | 100 | 100 | 100
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-08-19 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-10-14 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-02 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-08-26 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-26 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 473.6 | 100 |  | 0 | 100 |  | 0
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-02 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-09-09 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-09 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-09 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 394.4 | 100 |  | 0 | 100 |  | 0
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 |  | 0 | 0 | 473.6 | 10d | 0 | 0 | 0 | 473.6 | 0% | Not Started | 0 | 473.6 | 100 |  | 0 | 100 |  | 0
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-23 08:00 | 5d | 283.2 | 283.2 | 5d | 0 | 0 | 283.2 | 283.2 | 50% | Started | 283.2 | 566.4 | 100 | 50 | 50 | 100 | 50 | 50
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-16 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-09-16 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-16 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-14 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-09-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-23 08:00 | 5d | 197.2 | 197.2 | 5d | 0 | 0 | 197.2 | 197.2 | 50% | Started | 197.2 | 394.4 | 100 | 50 | 50 | 100 | 50 | 50
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 173.2 | 100 |  | 0 | 100 |  | 0
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 976 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-21 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 | 2013-10-14 08:00 | 20d | 2076.7999 | 519.2 | 5d | 0 | 0 | 2076.7999 | 519.2 | 80% | Started | 415.36 | 519.2 | 100 | 400 | 80 | 100 | 400 | 80
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 | 2013-09-30 08:00 | 20d | 1577.5999 | 0 | 0 | 0 | 0 | 1577.5999 | 0 | 100% | Finished | 788.8 | 788.8 | 100 | 200 | 100 | 100 | 200 | 100
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 195.2 | 100 |  | 0 | 100 |  | 0
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-10-07 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-10-07 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 5d | 566 | 566 | 5d | 0 | 0 | 566 | 566 | 50% | Started | 283 | 566 | 100 | 100 | 50 | 100 | 100 | 50
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-04 08:00 | 5d | 197.2 | 197.2 | 5d | 0 | 0 | 197.2 | 197.2 | 50% | Started | 197.2 | 394.4 | 100 | 50 | 50 | 100 | 50 | 50
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-10-28 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-21 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-10-21 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 | 2013-10-21 08:00 | 5d | 259.6 | 778.8 | 15d | 0 | 0 | 259.6 | 778.8 | 25% | Started | 129.8 | 519.2 | 100 | 50 | 25 | 100 | 50 | 25
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 263.2 | 100 |  | 0 | 100 |  | 0
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 15d | 1698 | 0 | 0 | 0 | 0 | 1698 | 0 | 100% | Finished | 566 | 566 | 100 | 300 | 100 | 100 | 300 | 100
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 |  | 0 | 0 | 390 | 5d | 0 | 0 | 0 | 390 | 0% | Not Started | 0 | 390 | 100 |  | 0 | 100 |  | 0
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 263.2 | 100 |  | 0 | 100 |  | 0
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-11-04 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-11-04 08:00 | 5d | 263.2 | 263.2 | 5d | 0 | 0 | 263.2 | 263.2 | 50% | Started | 263.2 | 263.2 | 100 | 50 | 50 | 100 | 50 | 50
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 |  | 0 | 0 | 566.4 | 10d | 0 | 0 | 0 | 566.4 | 0% | Not Started | 0 | 283.2 | 100 |  | 0 | 100 |  | 0
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 |  | 0 | 0 | 526.4 | 10d | 0 | 0 | 0 | 526.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 0 | 100 | 100 | 100 | 100 | 100 | 100
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-11-04 08:00 | 5d | 390 | 1950 | 25d | 0 | 0 | 390 | 1950 | 16.67% | Started | 390 | 0 | 100 | 16.6667 | 16.6667 | 100 | 16.6667 | 16.6667
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-12-20 17:00 |  | TP Name | 20/12, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 235d | [5 empty] | 183338.6003 |  | 97.94% |  | 140709.6003 | 141042.0003
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 75d | 8310.0002 | 0 | 0 | 0 | 0 | 8310.0002 | 0 | 100% | Finished | 5540.0002 | 5540.0002 | 100 | 150 | 100 | 100 | 150 | 100
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 50 | 100 | 100 | 50 | 100
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 60d | 8524.8001 | 0 | 0 | 0 | 0 | 8524.8001 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 600 | 100 | 100 | 600 | 100
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-08-26 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 2340 | 2340 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 80d | 8870.3998 | 0 | 0 | 0 | 0 | 8870.3998 | 0 | 100% | Finished | 6652.7998 | 6652.7998 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-08-26 08:00 | 5d | 173.2 | 0 | 0 | -86.6 | 0 | 86.6 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 50 | 100
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 692.8 | 692.8 | 100 | 100 | 100 | 100 | 100 | 100
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 50 | 100 | 100 | 50 | 100
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 40d | 7577.6001 | 0 | 0 | 0 | 0 | 7577.6001 | 0 | 100% | Finished | 13260.8002 | 13260.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 50d | 5659.9998 | 0 | 0 | 0 | 0 | 5659.9998 | 0 | 100% | Finished | 1132 | 1132 | 100 | 500 | 100 | 100 | 500 | 100
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 100% | Finished | 2216.7999 | 2216.7999 | 100 | 100 | 100 | 100 | 100 | 100
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-07 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-19 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 20d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-08-19 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 2013-08-19 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 780.8 | 780.8 | 100 | 100 | 100 | 100 | 100 | 100
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-08-19 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-10-14 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-02 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-08-26 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-26 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-11-25 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-02 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-09-09 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-09 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-09 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-11 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-12-09 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-23 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-16 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-09-16 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-16 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-14 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-09-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-23 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-11-25 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 |  | 0 | 0 | 976 | 25d | 0 | 0 | 0 | 976 | 0% | Not Started | 0 | 976 | 100 |  | 0 | 100 |  | 0
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-21 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 | 2013-10-14 08:00 | 25d | 2595.9999 | 0 | 0 | 0 | 0 | 2595.9999 | 0 | 100% | Finished | 519.2 | 519.2 | 100 | 500 | 100 | 100 | 500 | 100
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 | 2013-09-30 08:00 | 20d | 1577.5999 | 0 | 0 | 0 | 0 | 1577.5999 | 0 | 100% | Finished | 788.8 | 788.8 | 100 | 200 | 100 | 100 | 200 | 100
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-02 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-10-07 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-10-07 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 10d | 1132 | 0 | 0 | 0 | 0 | 1132 | 0 | 100% | Finished | 566 | 566 | 100 | 200 | 100 | 100 | 200 | 100
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-10-28 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-21 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-10-21 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 | 2013-10-21 08:00 | 20d | 1038.4 | 0 | 0 | 0 | 0 | 1038.4 | 0 | 100% | Finished | 519.2 | 519.2 | 100 | 200 | 100 | 100 | 200 | 100
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-12-16 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 15d | 1698 | 0 | 0 | 0 | 0 | 1698 | 0 | 100% | Finished | 566 | 566 | 100 | 300 | 100 | 100 | 300 | 100
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-11-11 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-12-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-11-11 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-11-04 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-11-04 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-11-25 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-12-02 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-18 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-11-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-25 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 |  | 0 | 0 | 66 | 5d | 0 | 0 | 0 | 66 | 0% | Not Started | 0 | 66 | 100 |  | 0 | 100 |  | 0
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-11-04 08:00 | 35d | 2730 | 0 | 0 | 0 | 0 | 2730 | 0 | 100% | Finished | 2340 | 1170 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-12-09 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 |  | 0 | 0 | 394.4 | 10d | 0 | 0 | 0 | 394.4 | 0% | Not Started | 0 | 394.4 | 100 |  | 0 | 100 |  | 0
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-16 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2014-01-31 17:00 |  | TP Name | 31/01, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 265d | [5 empty] | 184995.0003 |  | 99.23% |  | 142561.2003 | 143673.2003
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 75d | 8310.0002 | 0 | 0 | 0 | 0 | 8310.0002 | 0 | 100% | Finished | 5540.0002 | 5540.0002 | 100 | 150 | 100 | 100 | 150 | 100
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 50 | 100 | 100 | 50 | 100
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 60d | 8524.8001 | 0 | 0 | 0 | 0 | 8524.8001 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 600 | 100 | 100 | 600 | 100
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-08-26 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 2340 | 2340 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 80d | 8870.3998 | 0 | 0 | 0 | 0 | 8870.3998 | 0 | 100% | Finished | 6652.7998 | 6652.7998 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-08-26 08:00 | 5d | 173.2 | 0 | 0 | -86.6 | 0 | 86.6 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 50 | 100
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 692.8 | 692.8 | 100 | 100 | 100 | 100 | 100 | 100
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 50 | 100 | 100 | 50 | 100
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 40d | 7577.6001 | 0 | 0 | 0 | 0 | 7577.6001 | 0 | 100% | Finished | 13260.8002 | 13260.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 50d | 5659.9998 | 0 | 0 | 0 | 0 | 5659.9998 | 0 | 100% | Finished | 1132 | 1132 | 100 | 500 | 100 | 100 | 500 | 100
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 100% | Finished | 2216.7999 | 2216.7999 | 100 | 100 | 100 | 100 | 100 | 100
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-07 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-19 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 20d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-08-19 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 2013-08-19 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 780.8 | 780.8 | 100 | 100 | 100 | 100 | 100 | 100
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-08-19 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-10-14 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-02 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-08-26 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-26 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-11-25 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-02 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-09-09 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-09 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-09 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-11 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-12-09 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-23 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-16 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-09-16 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-16 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-14 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-09-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-23 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-11-25 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 | 2014-01-06 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 976 | 976 | 100 | 80 | 100 | 100 | 80 | 100
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-21 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 | 2013-10-14 08:00 | 25d | 2595.9999 | 0 | 0 | 0 | 0 | 2595.9999 | 0 | 100% | Finished | 519.2 | 519.2 | 100 | 500 | 100 | 100 | 500 | 100
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 | 2013-09-30 08:00 | 20d | 1577.5999 | 0 | 0 | 0 | 0 | 1577.5999 | 0 | 100% | Finished | 788.8 | 788.8 | 100 | 200 | 100 | 100 | 200 | 100
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-02 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-10-07 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-10-07 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 10d | 1132 | 0 | 0 | 0 | 0 | 1132 | 0 | 100% | Finished | 566 | 566 | 100 | 200 | 100 | 100 | 200 | 100
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-10-28 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-21 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-10-21 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 | 2013-10-21 08:00 | 20d | 1038.4 | 0 | 0 | 0 | 0 | 1038.4 | 0 | 100% | Finished | 519.2 | 519.2 | 100 | 200 | 100 | 100 | 200 | 100
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-12-16 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 15d | 1698 | 0 | 0 | 0 | 0 | 1698 | 0 | 100% | Finished | 566 | 566 | 100 | 300 | 100 | 100 | 300 | 100
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-11-11 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-12-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-11-11 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-11-04 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-11-04 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-11-25 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-12-02 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-18 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-11-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-25 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2014-01-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2014-01-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-11-04 08:00 | 35d | 2730 | 0 | 0 | 0 | 0 | 2730 | 0 | 100% | Finished | 2340 | 2340 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-12-09 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2014-01-27 08:00 | 5d | 197.2 | 197.2 | 5d | 0 | 0 | 197.2 | 197.2 | 50% | Started | 197.2 | 394.4 | 100 | 50 | 50 | 100 | 50 | 50
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-16 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-12-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 |  | 0 | 0 | 173.2 | 5d | 0 | 0 | 0 | 173.2 | 0% | Not Started | 0 | 173.2 | 100 |  | 0 | 100 |  | 0
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2014-01-13 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 |  | 0 | 0 | 195.2 | 5d | 0 | 0 | 0 | 195.2 | 0% | Not Started | 0 | 195.2 | 100 |  | 0 | 100 |  | 0
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 |  | 0 | 0 | 283.2 | 5d | 0 | 0 | 0 | 283.2 | 0% | Not Started | 0 | 283.2 | 100 |  | 0 | 100 |  | 0
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 |  | 0 | 0 | 263.2 | 5d | 0 | 0 | 0 | 263.2 | 0% | Not Started | 0 | 263.2 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2014-03-14 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Family Residence (2) | 2013-01-28 08:00 | 2014-01-24 17:00 | 260d |  |  | 0 |  |  | 143673.2003 |  | 290d | [5 empty] | 186107.0003 |  | 100% |  | 143673.2003 | 143673.2003
1 | Spanten | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-01-28 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
2 | Isolatie chap/pure | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-01-28 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
3 | Plakwerken | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-01-28 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
4 | Schrijnwerk | 2013-01-28 08:00 | 2013-02-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-01-28 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
5 | Schrijnwerk deel 2 | 2013-01-28 08:00 | 2013-02-01 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-01-28 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
6 | Chape | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
7 | Sanitair | 2013-02-04 08:00 | 2013-02-15 17:00 | 10d |  | 0 | 0 | 7.31 | 584.8 | 584.8 | 2013-02-04 08:00 | 10d | 584.8 | 0 | 0 | 0 | 0 | 584.8 | 0 | 100% | Finished | 584.8 | 584.8 | 100 | 100 | 100 | 100 | 100 | 100
8 | Elektriciteit | 2013-02-04 08:00 | 2013-02-08 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-04 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
9 | Spanten | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-03-25 08:00 | 10d | 1420.8 | 0 | 0 | 0 | 0 | 1420.8 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 100 | 100 | 100 | 100 | 100
10 | Dakconstructie | 2013-02-11 08:00 | 2013-02-22 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-02-25 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
11 | Isolatie chap/pure | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
12 | Chape | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-02-18 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
13 | Elektriciteit | 2013-02-18 08:00 | 2013-02-22 17:00 | 5d |  | 0 | 0 | 8.65 | 346 | 346 | 2013-02-18 08:00 | 5d | 346 | 0 | 0 | 0 | 0 | 346 | 0 | 100% | Finished | 346 | 346 | 100 | 100 | 100 | 100 | 100 | 100
14 | Ruwbouw | 2013-02-18 08:00 | 2013-04-19 17:00 | 45d |  | 0 | 0 | 69.26 | 24933.6008 | 24933.6008 | 2013-02-25 08:00 | 75d | 41556.0013 | 0 | 0 | 0 | 0 | 41556.0013 | 0 | 100% | Finished | 24933.6008 | 24933.6008 | 100 | 166.6667 | 100 | 100 | 166.6667 | 100
15 | Sanitair | 2013-02-18 08:00 | 2013-03-01 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-02-18 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
16 | Ruwbouw deel 2 | 2013-02-18 08:00 | 2013-04-26 17:00 | 50d |  | 0 | 0 | 27.71 | 11083.9996 | 11083.9996 | 2013-02-18 08:00 | 85d | 18842.7994 | 0 | 0 | 0 | 0 | 18842.7994 | 0 | 100% | Finished | 11083.9996 | 11083.9996 | 100 | 170 | 100 | 100 | 170 | 100
17 | Dakconstructie | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-04-08 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
18 | Schrijnwerk | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 9.75 | 780 | 780 | 2013-02-25 08:00 | 10d | 780 | 0 | 0 | 0 | 0 | 780 | 0 | 100% | Finished | 780 | 780 | 100 | 100 | 100 | 100 | 100 | 100
19 | Elektriciteit | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-03-04 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
20 | Vloer | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-02-18 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
21 | Isolatie zolder | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-02-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
22 | Sanitair | 2013-02-25 08:00 | 2013-03-01 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-02-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
23 | Elektriciteit deel 2 | 2013-02-25 08:00 | 2013-03-08 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-02-18 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
24 | Elektriciteit | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.31 | 532.4 | 532.4 | 2013-03-11 08:00 | 5d | 532.4 | 0 | 0 | 0 | 0 | 532.4 | 0 | 100% | Finished | 532.4 | 532.4 | 100 | 100 | 100 | 100 | 100 | 100
25 | Vloer | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-03-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
26 | Plakwerken | 2013-03-04 08:00 | 2013-03-08 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-03-04 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
27 | Isolatie zolder | 2013-03-04 08:00 | 2013-03-15 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-03-04 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
28 | Schrijnwerk | 2013-03-11 08:00 | 2013-04-19 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-03-18 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
29 | Sanitair | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-03-18 08:00 | 10d | 848.8 | 0 | 0 | 0 | 0 | 848.8 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 100 | 100 | 100 | 100 | 100
30 | Elektriciteit | 2013-03-11 08:00 | 2013-03-22 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-11 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
31 | Isolatie zolder | 2013-03-11 08:00 | 2013-03-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
32 | Schrijnwerk | 2013-03-11 08:00 | 2013-03-29 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-05-27 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
33 | Elektriciteit | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-03-25 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
34 | Keuken | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-03-25 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
35 | Schrijnwerk | 2013-03-18 08:00 | 2013-03-29 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-03-18 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
36 | Sanitair | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
37 | Plakwerk | 2013-03-18 08:00 | 2013-03-22 17:00 | 5d |  | 0 | 0 | 27.78 | 1111.2 | 1111.2 | 2013-03-18 08:00 | 5d | 1111.2 | 0 | 0 | 0 | 0 | 1111.2 | 0 | 100% | Finished | 1111.2 | 1111.2 | 100 | 100 | 100 | 100 | 100 | 100
38 | Isolatie zolder | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-08 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
39 | Sanitair | 2013-03-25 08:00 | 2013-04-05 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-03-25 08:00 | 10d | 566.4 | 0 | 0 | 283.2 | 0 | 849.6 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 150 | 100
40 | Isolatie chap/pure | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-03-25 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
41 | Sanitair | 2013-03-25 08:00 | 2013-03-29 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-03-25 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
42 | Keuken | 2013-04-01 08:00 | 2013-04-12 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-04-01 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
43 | Schrijnwerk | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-04-08 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
44 | Plakwerken | 2013-04-08 08:00 | 2013-04-19 17:00 | 10d |  | 0 | 0 | 14.01 | 1120.8 | 1120.8 | 2013-04-15 08:00 | 10d | 1120.8 | 0 | 0 | 0 | 0 | 1120.8 | 0 | 100% | Finished | 1120.8 | 1120.8 | 100 | 100 | 100 | 100 | 100 | 100
45 | Sanitair | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-04-08 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
46 | Isolatie chap/pure | 2013-04-08 08:00 | 2013-04-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
47 | Elektriciteit | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
48 | Vloer | 2013-04-15 08:00 | 2013-04-26 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-15 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
49 | Isolatie chap/pure | 2013-04-15 08:00 | 2013-04-19 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-15 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
50 | Sanitair | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 10.61 | 848.8 | 848.8 | 2013-04-22 08:00 | 20d | 1697.5999 | 0 | 0 | 0 | 0 | 1697.5999 | 0 | 100% | Finished | 848.8 | 848.8 | 100 | 200 | 100 | 100 | 200 | 100
51 | Spanten | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 29.61 | 2368.8 | 2368.8 | 2013-05-20 08:00 | 25d | 5922.0001 | 0 | 0 | 0 | 0 | 5922.0001 | 0 | 100% | Finished | 2368.8 | 2368.8 | 100 | 250 | 100 | 100 | 250 | 100
52 | Chape | 2013-04-22 08:00 | 2013-05-03 17:00 | 10d |  | 0 | 0 | 2.48 | 198.4 | 198.4 | 2013-04-22 08:00 | 10d | 198.4 | 0 | 0 | 0 | 0 | 198.4 | 0 | 100% | Finished | 198.4 | 198.4 | 100 | 100 | 100 | 100 | 100 | 100
53 | Elektriciteit | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-04-22 08:00 | 5d | 173.2 | 0 | 0 | 173.2 | 0 | 346.4 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 200 | 100
54 | Ruwbouw | 2013-04-22 08:00 | 2013-06-28 17:00 | 50d |  | 0 | 0 | 13.85 | 5540.0002 | 5540.0002 | 2013-05-13 08:00 | 75d | 8310.0002 | 0 | 0 | 0 | 0 | 8310.0002 | 0 | 100% | Finished | 5540.0002 | 5540.0002 | 100 | 150 | 100 | 100 | 150 | 100
55 | Isolatie chape/pure | 2013-04-22 08:00 | 2013-04-26 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-04-22 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
56 | Elektriciteit | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-04-29 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
57 | Isolatie chap/pure | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
58 | Vloer | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-04-29 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
59 | Sanitair | 2013-04-29 08:00 | 2013-05-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-04-29 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
60 | Vloer deel 2 | 2013-04-29 08:00 | 2013-05-17 17:00 | 15d |  | 0 | 0 | 4.93 | 591.6 | 591.6 | 2013-04-29 08:00 | 15d | 591.6 | 0 | 0 | 0 | 0 | 591.6 | 0 | 100% | Finished | 591.6 | 591.6 | 100 | 100 | 100 | 100 | 100 | 100
61 | Spanten | 2013-04-29 08:00 | 2013-05-10 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-08-05 08:00 | 5d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 50 | 100 | 100 | 50 | 100
62 | Chape | 2013-05-06 08:00 | 2013-05-10 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-06 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
63 | Dakwerken | 2013-05-06 08:00 | 2013-05-17 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-05-27 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
64 | Plakwerken | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-13 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
65 | Isolatie chap/pure | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
66 | Schrijnwerk | 2013-05-13 08:00 | 2013-06-21 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-05-13 08:00 | 30d | 1171.2 | 0 | 0 | 0 | 0 | 1171.2 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 100 | 100 | 100 | 100 | 100
67 | Elektriciteit | 2013-05-13 08:00 | 2013-05-17 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-05-06 08:00 | 10d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
68 | Vloer | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-05-13 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2013-05-13 08:00 | 2013-05-24 17:00 | 10d |  | 0 | 0 | 17.76 | 1420.8 | 1420.8 | 2013-06-03 08:00 | 60d | 8524.8001 | 0 | 0 | 0 | 0 | 8524.8001 | 0 | 100% | Finished | 1420.8 | 1420.8 | 100 | 600 | 100 | 100 | 600 | 100
70 | Chape | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
71 | Sanitair | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-05-20 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
72 | Isolatie zolder | 2013-05-20 08:00 | 2013-05-24 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-05-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
73 | Elektriciteit | 2013-05-20 08:00 | 2013-05-31 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 50 | 100 | 100 | 50 | 100
74 | Sanitair | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-05-20 08:00 | 10d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
75 | Vloer | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-03 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
76 | Elektriciteit | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-05-20 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
77 | keuken | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 50 | 100 | 100 | 50 | 100
78 | Plakwerken | 2013-05-27 08:00 | 2013-05-31 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-05-20 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
79 | Schrijnwerk | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-05-20 08:00 | 15d | 585.6 | 0 | 0 | 0 | 0 | 585.6 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 150 | 100 | 100 | 150 | 100
80 | Schrijnwerk deel 2 | 2013-05-27 08:00 | 2013-06-28 17:00 | 25d |  | 0 | 0 | 9.75 | 1950 | 1950 | 2013-06-10 08:00 | 15d | 1170 | 0 | 0 | 0 | 0 | 1170 | 0 | 100% | Finished | 1950 | 1950 | 100 | 60 | 100 | 100 | 60 | 100
81 | Schrijnwerk deel 3 | 2013-05-27 08:00 | 2013-06-14 17:00 | 15d |  | 0 | 0 | 9.75 | 1170 | 1170 | 2013-08-26 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 1170 | 1170 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
82 | Schrijnwerk deel 4 | 2013-05-27 08:00 | 2013-07-05 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-08-05 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 2340 | 2340 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
83 | Isolatie chap/pure | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-03 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
84 | Schrijnwerk | 2013-06-03 08:00 | 2013-06-07 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-05-20 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
85 | Sanitair | 2013-06-03 08:00 | 2013-06-14 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-05-20 08:00 | 20d | 1132.8 | 0 | 0 | 0 | 0 | 1132.8 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 200 | 100 | 100 | 200 | 100
86 | Ruwbouw | 2013-06-03 08:00 | 2013-08-23 17:00 | 60d |  | 0 | 0 | 13.86 | 6652.7998 | 6652.7998 | 2013-08-05 08:00 | 80d | 8870.3998 | 0 | 0 | 0 | 0 | 8870.3998 | 0 | 100% | Finished | 6652.7998 | 6652.7998 | 100 | 133.3333 | 100 | 100 | 133.3333 | 100
87 | Chape | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-10 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
88 | Elektriciteit | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-17 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
89 | Sanitair | 2013-06-10 08:00 | 2013-06-14 17:00 | 5d |  | 0 | 0 | 21.24 | 849.6 | 849.6 | 2013-06-10 08:00 | 5d | 849.6 | 0 | 0 | 0 | 0 | 849.6 | 0 | 100% | Finished | 849.6 | 849.6 | 100 | 100 | 100 | 100 | 100 | 100
90 | Keuken | 2013-06-10 08:00 | 2013-06-21 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-05-20 08:00 | 25d | 1316 | 0 | 0 | 0 | 0 | 1316 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 250 | 100 | 100 | 250 | 100
91 | Vloer | 2013-06-17 08:00 | 2013-06-28 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-06-17 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
92 | Schrijnwerk | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-06-24 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
93 | Keuken | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-05-20 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
94 | Isolatie chap/pure | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-17 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
95 | Elektriciteit | 2013-06-17 08:00 | 2013-06-21 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-08-26 08:00 | 5d | 173.2 | 0 | 0 | -86.6 | 0 | 86.6 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 50 | 100
96 | Sanitair | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 14.16 | 566.4 | 566.4 | 2013-07-01 08:00 | 5d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
97 | Chape | 2013-06-24 08:00 | 2013-06-28 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-06-24 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
98 | Elektriciteit | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 17.32 | 692.8 | 692.8 | 2013-07-08 08:00 | 5d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 692.8 | 692.8 | 100 | 100 | 100 | 100 | 100 | 100
99 | Keuken | 2013-07-01 08:00 | 2013-07-05 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-07-01 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
100 | Vloer | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-07-29 08:00 | 5d | 197.2 | 0 | 0 | 0 | 0 | 197.2 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 50 | 100 | 100 | 50 | 100
101 | Spanten | 2013-07-01 08:00 | 2013-07-12 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-06-24 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
102 | Ruwbouw | 2013-07-01 08:00 | 2013-10-04 17:00 | 70d |  | 0 | 0 | 23.68 | 13260.8002 | 13260.8002 | 2013-08-05 08:00 | 40d | 7577.6001 | 0 | 0 | 0 | 0 | 7577.6001 | 0 | 100% | Finished | 13260.8002 | 13260.8002 | 100 | 57.1429 | 100 | 100 | 57.1429 | 100
103 | Schrijnwerk | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-05 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
104 | Sanitair | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
105 | Isolatie zolder | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
106 | Elektriciteit | 2013-07-08 08:00 | 2013-07-12 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-12 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
107 | Elektriciteit | 2013-07-15 08:00 | 2013-07-19 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-06-24 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
108 | Sanitair | 2013-07-22 08:00 | 2013-07-26 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-07-08 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
109 | Elektriciteit | 2013-07-29 08:00 | 2013-08-02 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-07-15 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
110 | Sanitair | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 14.15 | 1132 | 1132 | 2013-08-05 08:00 | 50d | 5659.9998 | 0 | 0 | 0 | 0 | 5659.9998 | 0 | 100% | Finished | 1132 | 1132 | 100 | 500 | 100 | 100 | 500 | 100
111 | Isolatie zolder | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-08-05 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
112 | Elektriciteit | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 8.66 | 346.4 | 346.4 | 2013-08-05 08:00 | 5d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
113 | Dakconstructie | 2013-08-05 08:00 | 2013-08-16 17:00 | 10d |  | 0 | 0 | 27.71 | 2216.7999 | 2216.7999 | 2013-08-05 08:00 | 10d | 2216.7999 | 0 | 0 | 0 | 0 | 2216.7999 | 0 | 100% | Finished | 2216.7999 | 2216.7999 | 100 | 100 | 100 | 100 | 100 | 100
114 | Plakwerk | 2013-08-05 08:00 | 2013-08-09 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-07 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
115 | Keuken | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-19 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
116 | Plakwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-08-12 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
117 | Schrijnwerk | 2013-08-12 08:00 | 2013-08-16 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-08-12 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
118 | Isolatie zolder | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-08-12 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
119 | Elektriciteit | 2013-08-12 08:00 | 2013-08-23 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-08-12 08:00 | 20d | 692.8 | 0 | 0 | 0 | 0 | 692.8 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 200 | 100 | 100 | 200 | 100
120 | Sanitair | 2013-08-19 08:00 | 2013-08-23 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-08-19 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
121 | Schrijnwerk | 2013-08-19 08:00 | 2013-09-13 17:00 | 20d |  | 0 | 0 | 4.88 | 780.8 | 780.8 | 2013-08-19 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 780.8 | 780.8 | 100 | 100 | 100 | 100 | 100 | 100
122 | Plakwerk | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-08-19 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
123 | Schrijnwerk deel 2 | 2013-08-19 08:00 | 2013-09-27 17:00 | 30d |  | 0 | 0 | 4.88 | 1171.2 | 1171.2 | 2013-10-14 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 1171.2 | 1171.2 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
124 | Isolatie zolder | 2013-08-19 08:00 | 2013-08-30 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-02 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
125 | Sanitair | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-08-26 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
126 | Keuken | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-08-26 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
127 | Isolatie chap/pure | 2013-08-26 08:00 | 2013-08-30 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-16 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
128 | Spanten | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-11-25 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
129 | Isolatie chap/pure | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
130 | Sanitair | 2013-09-02 08:00 | 2013-09-13 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-02 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
131 | Chape | 2013-09-02 08:00 | 2013-09-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-04 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
132 | Plakwerk | 2013-08-26 08:00 | 2013-09-06 17:00 | 10d |  | 0 | 0 | 13.88 | 1110.4 | 1110.4 | 2013-09-09 08:00 | 10d | 1110.4 | 0 | 0 | 0 | 0 | 1110.4 | 0 | 100% | Finished | 1110.4 | 1110.4 | 100 | 100 | 100 | 100 | 100 | 100
133 | Chape | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-09-09 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
134 | Isolatie chap/pure | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-09 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
135 | Vloer | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-11 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
136 | Dakwerken | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 5.92 | 473.6 | 473.6 | 2013-12-09 08:00 | 10d | 473.6 | 0 | 0 | 0 | 0 | 473.6 | 0 | 100% | Finished | 473.6 | 473.6 | 100 | 100 | 100 | 100 | 100 | 100
137 | Sanitair | 2013-09-09 08:00 | 2013-09-20 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-09-23 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
138 | Vloer | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-16 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
139 | Elektriciteit | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-09-16 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
140 | Chape | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-09-16 08:00 | 10d | 132 | 0 | 0 | 0 | 0 | 132 | 0 | 100% | Finished | 132 | 132 | 100 | 100 | 100 | 100 | 100 | 100
141 | Isolatie chap/pure | 2013-09-16 08:00 | 2013-09-27 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-14 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
142 | Sanitair | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-09-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
143 | Vloer | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-09-23 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
144 | Elektriciteit | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-11-25 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
145 | Schrijnwerk | 2013-09-23 08:00 | 2013-10-25 17:00 | 25d |  | 0 | 0 | 4.88 | 976 | 976 | 2014-01-06 08:00 | 20d | 780.8 | 0 | 0 | 0 | 0 | 780.8 | 0 | 100% | Finished | 976 | 976 | 100 | 80 | 100 | 100 | 80 | 100
146 | Chape | 2013-09-23 08:00 | 2013-10-04 17:00 | 10d |  | 0 | 0 | 1.65 | 132 | 132 | 2013-10-21 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 132 | 132 | 100 | 50 | 100 | 100 | 50 | 100
147 | Elektriciteit | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 12.98 | 519.2 | 519.2 | 2013-10-14 08:00 | 25d | 2595.9999 | 0 | 0 | 0 | 0 | 2595.9999 | 0 | 100% | Finished | 519.2 | 519.2 | 100 | 500 | 100 | 100 | 500 | 100
148 | Vloer | 2013-09-30 08:00 | 2013-10-11 17:00 | 10d |  | 0 | 0 | 9.86 | 788.8 | 788.8 | 2013-09-30 08:00 | 20d | 1577.5999 | 0 | 0 | 0 | 0 | 1577.5999 | 0 | 100% | Finished | 788.8 | 788.8 | 100 | 200 | 100 | 100 | 200 | 100
149 | Schrijnwerk | 2013-09-30 08:00 | 2013-10-04 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-02 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
150 | Isolatie zolder | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-10-07 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
151 | Elektriciteit | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.33 | 346.4 | 346.4 | 2013-10-07 08:00 | 10d | 346.4 | 0 | 0 | 0 | 0 | 346.4 | 0 | 100% | Finished | 346.4 | 346.4 | 100 | 100 | 100 | 100 | 100 | 100
152 | Sanitair | 2013-10-07 08:00 | 2013-10-11 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 10d | 1132 | 0 | 0 | 0 | 0 | 1132 | 0 | 100% | Finished | 566 | 566 | 100 | 200 | 100 | 100 | 200 | 100
153 | Vloer | 2013-10-07 08:00 | 2013-10-18 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-04 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
154 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-10-28 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
155 | Plakwerk | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 13.89 | 555.6 | 555.6 | 2013-10-21 08:00 | 5d | 555.6 | 0 | 0 | 0 | 0 | 555.6 | 0 | 100% | Finished | 555.6 | 555.6 | 100 | 100 | 100 | 100 | 100 | 100
156 | Schrijnwerk | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 4.88 | 390.4 | 390.4 | 2013-10-21 08:00 | 10d | 390.4 | 0 | 0 | 0 | 0 | 390.4 | 0 | 100% | Finished | 390.4 | 390.4 | 100 | 100 | 100 | 100 | 100 | 100
157 | Elektriciteit | 2013-10-14 08:00 | 2013-10-25 17:00 | 10d |  | 0 | 0 | 6.49 | 519.2 | 519.2 | 2013-10-21 08:00 | 20d | 1038.4 | 0 | 0 | 0 | 0 | 1038.4 | 0 | 100% | Finished | 519.2 | 519.2 | 100 | 200 | 100 | 100 | 200 | 100
158 | Keuken | 2013-10-14 08:00 | 2013-10-18 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-12-16 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
159 | Sanitair | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-10-21 08:00 | 15d | 1698 | 0 | 0 | 0 | 0 | 1698 | 0 | 100% | Finished | 566 | 566 | 100 | 300 | 100 | 100 | 300 | 100
160 | Schrijnwerk | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 9.75 | 390 | 390 | 2013-11-11 08:00 | 5d | 390 | 0 | 0 | 0 | 0 | 390 | 0 | 100% | Finished | 390 | 390 | 100 | 100 | 100 | 100 | 100 | 100
161 | Isolatie zolder | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-12-02 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
162 | Keuken | 2013-10-28 08:00 | 2013-11-01 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2013-11-11 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
163 | Sanitair | 2013-11-04 08:00 | 2013-11-08 17:00 | 5d |  | 0 | 0 | 14.15 | 566 | 566 | 2013-11-04 08:00 | 5d | 566 | 0 | 0 | 0 | 0 | 566 | 0 | 100% | Finished | 566 | 566 | 100 | 100 | 100 | 100 | 100 | 100
164 | Keuken | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-11-04 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
165 | Sanitair deel 2 | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 7.08 | 566.4 | 566.4 | 2013-11-25 08:00 | 10d | 566.4 | 0 | 0 | 0 | 0 | 566.4 | 0 | 100% | Finished | 566.4 | 566.4 | 100 | 100 | 100 | 100 | 100 | 100
166 | Spanten | 2013-11-04 08:00 | 2013-11-15 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
167 | Isolatie chap/pure | 2013-11-11 08:00 | 2013-11-15 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-11 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
168 | Keuken | 2013-11-11 08:00 | 2013-11-22 17:00 | 10d |  | 0 | 0 | 6.58 | 526.4 | 526.4 | 2013-12-02 08:00 | 10d | 526.4 | 0 | 0 | 0 | 0 | 526.4 | 0 | 100% | Finished | 526.4 | 526.4 | 100 | 100 | 100 | 100 | 100 | 100
169 | Chape | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2013-11-18 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
170 | Sanitair | 2013-11-18 08:00 | 2013-11-22 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-11-18 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
171 | Dakwerken | 2013-11-18 08:00 | 2013-11-29 17:00 | 10d |  | 0 | 0 | 11.84 | 947.2 | 947.2 | 2013-10-14 08:00 | 10d | 947.2 | 0 | 0 | 0 | 0 | 947.2 | 0 | 100% | Finished | 947.2 | 947.2 | 100 | 100 | 100 | 100 | 100 | 100
172 | Vloer | 2013-11-25 08:00 | 2013-12-06 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2013-11-25 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
173 | Isolatie chap/pure | 2013-11-25 08:00 | 2013-11-29 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2014-01-13 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
174 | Chape | 2013-12-02 08:00 | 2013-12-06 17:00 | 5d |  | 0 | 0 | 1.65 | 66 | 66 | 2014-01-20 08:00 | 5d | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 100% | Finished | 66 | 66 | 100 | 100 | 100 | 100 | 100 | 100
175 | Schrijnwerk | 2013-12-02 08:00 | 2014-01-10 17:00 | 30d |  | 0 | 0 | 9.75 | 2340 | 2340 | 2013-11-04 08:00 | 35d | 2730 | 0 | 0 | 0 | 0 | 2730 | 0 | 100% | Finished | 2340 | 2340 | 100 | 116.6667 | 100 | 100 | 116.6667 | 100
176 | Elektriciteit | 2013-12-09 08:00 | 2013-12-13 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2013-12-09 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
177 | Vloer | 2013-12-09 08:00 | 2013-12-20 17:00 | 10d |  | 0 | 0 | 4.93 | 394.4 | 394.4 | 2014-01-27 08:00 | 10d | 394.4 | 0 | 0 | 0 | 0 | 394.4 | 0 | 100% | Finished | 394.4 | 394.4 | 100 | 100 | 100 | 100 | 100 | 100
178 | Schrijnwerk | 2013-12-16 08:00 | 2013-12-20 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2013-12-16 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
179 | Sanitair | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2013-12-23 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
180 | Elektriciteit | 2013-12-30 08:00 | 2014-01-03 17:00 | 5d |  | 0 | 0 | 4.33 | 173.2 | 173.2 | 2014-02-10 08:00 | 5d | 173.2 | 0 | 0 | 0 | 0 | 173.2 | 0 | 100% | Finished | 173.2 | 173.2 | 100 | 100 | 100 | 100 | 100 | 100
181 | Keuken | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2014-01-13 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100
182 | Schrijnwerk | 2014-01-06 08:00 | 2014-01-10 17:00 | 5d |  | 0 | 0 | 4.88 | 195.2 | 195.2 | 2014-02-17 08:00 | 5d | 195.2 | 0 | 0 | 0 | 0 | 195.2 | 0 | 100% | Finished | 195.2 | 195.2 | 100 | 100 | 100 | 100 | 100 | 100
183 | Sanitair | 2014-01-13 08:00 | 2014-01-17 17:00 | 5d |  | 0 | 0 | 7.08 | 283.2 | 283.2 | 2014-02-24 08:00 | 5d | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 100% | Finished | 283.2 | 283.2 | 100 | 100 | 100 | 100 | 100 | 100
184 | Keuken | 2014-01-20 08:00 | 2014-01-24 17:00 | 5d |  | 0 | 0 | 6.58 | 263.2 | 263.2 | 2014-03-03 08:00 | 5d | 263.2 | 0 | 0 | 0 | 0 | 263.2 | 0 | 100% | Finished | 263.2 | 263.2 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
01/03, 2013 | 2013-01-28 08:00 | 2013-03-01 17:00 | 17112.8001 | 12408.4 | 12408.4 | 2013-02-25 16:00 | -4704.4001 | 72.51% | 5.3674e-05 | 100% | -4d 1h | 83.5% | 80.1% | 2014-02-06 12:00 | 2014-06-12 14:00 | 2014-06-12 14:00 | 2014-02-04 16:00 | 2014-06-12 14:00 | 2014-06-12 14:00 | 2014-01-31 09:00 | 2014-04-08 11:00 | 2014-04-08 11:00 | 143673.2002 | 143673.1997 | 193439.6595 | 169611.7536 | 193439.6587 | 169611.7529 | 151310.1671 | 148152.7638 | 0.835 | 1 | 0.72509 | 0.801 | -4.125 | 1 | 1 | 0.835 | 1
12/04, 2013 | 2013-03-01 17:00 | 2013-04-12 17:00 | 51694.8004 | 38302.7001 | 46979.2003 | 2013-03-27 09:00 | -13392.1003 | 74.09% | -8676.5002 | 81.53% | -12d 7h | 76.59% | 92.7% | 2014-02-28 10:00 | 2014-06-02 16:00 | 2014-09-22 11:00 | 2014-02-14 10:00 | 2014-06-02 16:00 | 2014-09-03 16:00 | 2014-02-12 16:00 | 2014-05-16 12:00 | 2014-08-14 16:00 | 152349.7005 | 176218.7011 | 189191.2889 | 184554.9276 | 221405.812 | 215719.2013 | 178620.3626 | 177804.1352 | 0.76591 | 0.81531 | 0.74094 | 0.927 | -12.875 | 0.81531 | 1 | 0.76591 | 1
24/05, 2013 | 2013-04-12 17:00 | 2013-05-24 17:00 | 71426.8005 | 61599.5512 | 84670.0005 | 2013-04-30 10:00 | -9827.2493 | 86.24% | -23070.4493 | 72.75% | -18d 6h | 77.94% | 87.69% | 2014-02-19 15:00 | 2014-03-25 12:00 | 2014-08-29 11:00 | 2014-02-11 15:00 | 2014-03-25 12:00 | 2014-07-16 12:00 | 2014-02-20 15:00 | 2014-05-08 14:00 | 2014-09-16 14:00 | 166743.6496 | 197482.1196 | 179837.2224 | 189972.0408 | 215479.5367 | 229410.0779 | 193448.4117 | 195895.6108 | 0.77941 | 0.72753 | 0.86242 | 0.87688 | -18.75 | 0.72753 | 1 | 0.77941 | 1
05/07, 2013 | 2013-05-24 17:00 | 2013-07-05 17:00 | 92730.4005 | 80354.1338 | 114490.0008 | 2013-06-11 11:00 | -12376.2667 | 86.65% | -34135.867 | 70.18% | -18d 5h | 83.8% | 92.9% | 2014-02-26 11:00 | 2014-03-21 17:00 | 2014-09-17 12:00 | 2014-02-17 11:00 | 2014-03-21 17:00 | 2014-07-10 14:00 | 2014-02-20 14:00 | 2014-04-07 10:00 | 2014-07-31 10:00 | 177809.0673 | 204708.1344 | 187561.5669 | 190045.8259 | 218603.6694 | 222143.286 | 200663.916 | 201337.4248 | 0.83804 | 0.70184 | 0.86653 | 0.92896 | -18.625 | 0.70184 | 1 | 0.83804 | 1
16/08, 2013 | 2013-07-05 17:00 | 2013-08-16 17:00 | 109501.2004 | 97350.0938 | 132865.6008 | 2013-07-19 14:00 | -12151.1065 | 88.9% | -35515.507 | 73.27% | -20d 3h | 85.95% | 95.31% | 2014-02-25 17:00 | 2014-03-12 12:00 | 2014-08-08 09:00 | 2014-02-18 09:00 | 2014-03-12 12:00 | 2014-05-27 10:00 | 2014-02-24 11:00 | 2014-03-26 12:00 | 2014-06-13 17:00 | 179188.7073 | 196088.4199 | 184970.6945 | 186762.0938 | 203979.8063 | 206424.7484 | 193500.8566 | 193973.5776 | 0.85948 | 0.7327 | 0.88903 | 0.95315 | -20.375 | 0.7327 | 1 | 0.85948 | 1
28/09, 2013 | 2013-08-16 17:00 | 2013-09-28 17:00 | 126012.0004 | 119422.4005 | 155086.6007 | 2013-09-10 11:00 | -6589.5999 | 94.77% | -35664.2002 | 77% | -13d 5h | 92.21% | 95.47% | 2014-02-11 16:00 | 2014-02-14 11:00 | 2014-06-10 10:00 | 2014-02-07 09:00 | 2014-02-14 11:00 | 2014-03-27 17:00 | 2014-02-13 14:00 | 2014-02-25 17:00 | 2014-04-10 16:00 | 179337.4005 | 186579.638 | 180675.5336 | 181384.9119 | 188317.39 | 189238.6163 | 185190.4718 | 185382.7534 | 0.92214 | 0.77004 | 0.94771 | 0.95472 | -13.625 | 0.77004 | 1 | 0.92214 | 1
08/11, 2013 | 2013-09-28 17:00 | 2013-11-08 17:00 | 135674.0003 | 131247.7604 | 172121.8005 | 2013-10-16 15:00 | -4426.2399 | 96.74% | -40874.04 | 76.25% | -17d 2h | 91.59% | 96.67% | 2014-02-05 17:00 | 2014-02-06 15:00 | 2014-06-04 12:00 | 2014-02-04 15:00 | 2014-02-06 15:00 | 2014-03-06 14:00 | 2014-02-19 10:00 | 2014-02-27 16:00 | 2014-04-03 12:00 | 184547.2403 | 188416.8525 | 184966.2797 | 185688.8586 | 188966.3918 | 189914.0011 | 187585.9851 | 187786.8818 | 0.91585 | 0.76253 | 0.96738 | 0.96672 | -17.25 | 0.76253 | 1 | 0.91585 | 1
20/12, 2013 | 2013-11-08 17:00 | 2013-12-20 17:00 | 141042.0003 | 140709.6003 | 183338.6003 | 2013-12-18 16:00 | -332.4 | 99.76% | -42629 | 76.75% | -2d 1h | 99.1% | 98.99% | 2014-01-27 14:00 | 2014-01-27 14:00 | 2014-05-16 14:00 | 2014-01-27 12:00 | 2014-01-27 14:00 | 2014-02-06 11:00 | 2014-01-29 09:00 | 2014-01-29 11:00 | 2014-02-10 14:00 | 186302.2003 | 187200.0445 | 186309.2013 | 186329.2434 | 187209.1665 | 187235.2805 | 186981.5502 | 186987.5479 | 0.99096 | 0.76748 | 0.99764 | 0.98992 | -2.125 | 0.76748 | 1 | 0.99096 | 1
31/01, 2014 | 2013-12-20 17:00 | 2014-01-31 17:00 | 143673.2003 | 142561.2003 | 184995.0003 | 2014-01-07 14:00 | -1112 | 99.23% | -42433.8 | 77.06% | -18d 3h | 93.07% | 99.7% | 2014-01-28 17:00 | 2014-01-28 17:00 | 2014-05-16 17:00 | 2014-02-04 17:00 | 2014-02-05 09:00 | 2014-02-05 14:00 | 2014-02-20 11:00 | 2014-02-21 11:00 | 2014-02-27 14:00 | 186107.0003 | 186437.9907 | 186115.6741 | 186189.8508 | 186449.2462 | 186545.5019 | 186359.5019 | 186380.4463 | 0.93066 | 0.77062 | 0.99226 | 0.99696 | -18.375 | 0.77062 | 1 | 0.93066 | 1
Actual Schedule | 2014-01-31 17:00 | 2014-03-14 17:00 | 143673.2003 | 143673.2003 | 186107.0003 | 2014-01-24 17:00 | 0 | 100% | -42433.8 | 77.2% | -35d | 88.14% | 100% | 2014-01-24 17:00 | 2014-01-24 17:00 | 2014-05-13 15:00 | 2014-03-14 17:00 | 2014-03-14 17:00 | 2014-03-14 17:00 | 2014-03-14 17:00 | 2014-03-14 17:00 | 2014-03-14 17:00 | 186107.0003 | 186107.0003 | 186107.0003 | 186107.0003 | 186107.0003 | 186107.0003 | 186107.0003 | 186107.0003 | 0.88136 | 0.77199 | 1 | 1 | -35 | 0.77199 | 1 | 0.88136 | 1