## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Garden Center | 1 |  |  | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 | 266.375
22 | Montagewerken | 1.1 |  |  | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 | 77.375
1 | Voorlopige plint | 1.1.1 |  |  | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
2 | prefabplint inkom sluiten | 1.1.2 | 8FS |  | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
3 | sandwich laagbouw | 1.1.3 |  |  | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 6.375
4 | dakdekking voorbereiding | 1.1.4 |  |  | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2.375
5 | start dakdekking | 1.1.5 |  |  | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 15.375
6 | maken resterende doorvoerer | 1.1.6 |  |  | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2.375
7 | diverse dakdoorvoeren | 1.1.7 |  |  | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
8 | welfsels tellerlokaal | 1.1.8 |  | FS2;FS54 | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
9 | andere welfsels | 1.1.9 |  | FS10;FS11 | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
10 | afmontage staal hoogbouw | 1.1.10 | 9FS |  | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
11 | randbeveiliging tussenvloeren | 1.1.11 | 9FS |  | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
19 | Buitenwanden kantoor | 1.1.12 |  |  | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 | 76.375
12 | Aanvullen en grondwerken | 1.1.12.1 |  |  | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 0.375
13 | sandwichpanelen inkom | 1.1.12.2 |  |  | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 6.375
14 | netten demonteren lage zone | 1.1.12.3 |  |  | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 0.375
15 | beveiliging hoge dak | 1.1.12.4 |  |  | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 0.375
16 | welfsels traphal | 1.1.12.5 | 27FS |  | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 0.375
17 | steeldeck hoogbouw-inkom | 1.1.12.6 |  |  | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 1.375
18 | dakbedekking hoogbouw | 1.1.12.7 |  |  | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 7.375
20 | regenwaterafvoer laagbouw | 1.1.13 |  |  | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 0.375
21 | regenwaterafvoer hoogbouw | 1.1.14 |  |  | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 1.375
52 | Ruwbouwwerken | 1.2 |  |  | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 | 60.375
23 | Wachtbuizen | 1.2.1 |  |  | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
24 | grondwerken | 1.2.2 |  | FS35 | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
25 | metselwerken tellerlokaal | 1.2.3 |  |  | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 14.375
26 | metselwerken kantoren | 1.2.4 |  | FS37 | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 8.375
27 | metselwerken traphal | 1.2.5 |  | FS16;FS29 | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 44.375
28 | prefab bordessen | 1.2.6 |  |  | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 11.375
29 | trapsledes | 1.2.7 | 27FS | FS30 | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
30 | welfsels traphal | 1.2.8 | 29FS | FS31;FS33 | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 3.375
31 | voegwerken metselwerken | 1.2.9 | 30FS |  | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2.375
32 | schilderwerken metselwerken | 1.2.10 | 60FS-1w |  | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2.375
33 | koepsels traphal | 1.2.11 | 30FS | FS34 | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
34 | koepsels laag dak | 1.2.12 | 33FS |  | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
35 | riolering overloop | 1.2.13 | 24FS | FS36-1d | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
36 | riolering overloop recup | 1.2.14 | 35FS-1d |  | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
37 | riolering inkom | 1.2.15 | 26FS |  | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
38 | arduinen dorpels | 1.2.16 |  |  | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 0.375
51 | Buitenschrijnwerk | 1.2.17 |  |  | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 | 46.375
39 | atelier alu | 1.2.17.1 |  |  | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 4.375
40 | plaatsing alu | 1.2.17.2 |  | FS41 | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
41 | plaatsing glas deel 1 | 1.2.17.3 | 40FS | FS48 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
42 | opmeting restant | 1.2.17.4 |  | FS43+1w 3d | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
43 | plaatsing alu restant | 1.2.17.5 | 42FS+1w 3d | FS44;FS45 | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
44 | alu raam | 1.2.17.6 | 43FS |  | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
45 | plaatsing glas restant | 1.2.17.7 | 43FS | FS49 | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
46 | sectionaal poorten | 1.2.17.8 | 63FS-3w | FS47 | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 3.375
47 | poorten berging en tellerlokaal | 1.2.17.9 | 46FS |  | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
48 | RF behandeling laagbouw | 1.2.17.10 | 41FS | FS50;FS118 | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
49 | RF behandeling hoogbouw | 1.2.17.11 | 45FS |  | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
50 | Retouche staalconstructie | 1.2.17.12 | 48FS |  | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
66 | Betonvloer | 1.3 |  |  | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 | 86.375
53 | druklaag welfsels kelder | 1.3.1 |  |  | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
54 | grondwerk inkomzone | 1.3.2 | 8FS | FS55+2d | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
55 | ondervloer inkom | 1.3.3 | 54FS+2d | FS56;FS135 | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
56 | arduin inkom | 1.3.4 | 55FS | FS57 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
57 | overige arduinen dorpels | 1.3.5 | 56FS |  | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
58 | polivloer tellerlokaal | 1.3.6 |  | FS59-1d | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
59 | polivloer berging | 1.3.7 | 58FS-1d | FS60 | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
60 | vloerisolatie | 1.3.8 | 59FS | FS32-1w;FS61+3d | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2.375
61 | folie en vloerverwarming | 1.3.9 | 60FS+3d | FS63;FS123-2d | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 6.375
62 | druklaag welfsels | 1.3.10 |  |  | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 7.375
63 | polivloer winkel en inkom | 1.3.11 | 61FS | FS46-3w;FS64+2w 4d;FS138-1d | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 0.375
64 | nabehandeling polivloer | 1.3.12 | 63FS+2w 4d | FS165 | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
65 | binnenwand berging | 1.3.13 |  |  | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2.375
77 | Wegeniswerken achter | 1.4 |  |  | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 | 46.375
67 | opruimen werfkeet | 1.4.1 |  | FS68 | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 0.375
68 | riolering naar hangar | 1.4.2 | 67FS |  | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 3.375
69 | nutsleidingen ondergronds | 1.4.3 |  | FS70 | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
70 | riolering bestrating | 1.4.4 | 69FS |  | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
71 | funderingskoffer | 1.4.5 |  | FS72 | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
72 | fijnnivelleren funderingskoffer | 1.4.6 | 71FS | FS73 | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
73 | klinkerverharding | 1.4.7 | 72FS |  | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 0.375
74 | Asfaltverharding | 1.4.8 |  | FS75 | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 1.375
75 | herkwerken | 1.4.9 | 74FS |  | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 0.375
76 | Afwerken groenzones | 1.4.10 |  |  | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 21.375
91 | Wegeniswerken voor | 1.5 |  |  | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 | 21.375
78 | opruimen voorterrein | 1.5.1 |  | FS79 | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 1.375
79 | grondwerken/braakwerken | 1.5.2 | 78FS |  | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 6.375
80 | herinrichting werf | 1.5.3 |  |  | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 0.375
81 | plaatsing riolering | 1.5.4 |  |  | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 1.375
82 | nutsleidingen fase 1 | 1.5.5 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
83 | nutsleidingen fase 2 | 1.5.6 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
84 | riolering bestrating | 1.5.7 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 0.375
85 | funderingskoffer | 1.5.8 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
86 | fijnniverllerinn funderingskoffer | 1.5.9 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
87 | klinkerverharding | 1.5.10 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 0.375
88 | asfaltverharding | 1.5.11 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 0.375
89 | herkwerken | 1.5.12 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 0.375
90 | afwerken groenzones | 1.5.13 |  |  | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 0.375
115 | afbouw +2 | 1.6 |  |  | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 | 46.375
92 | voorbereid werk wanden | 1.6.1 |  | FS93-2d;FS96 | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 6.375
93 | technieken in holle wanden | 1.6.2 | 92FS-2d | FS94;FS95 | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2.375
94 | wanden sluiten | 1.6.3 | 93FS |  | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 4.375
95 | wanden afwerken | 1.6.4 | 93FS |  | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 4.375
96 | technieken boven gyproc | 1.6.5 | 92FS | FS97;FS98 | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 3.375
97 | technieken boven plafond | 1.6.6 | 96FS |  | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 0.375
98 | gyproc plafond | 1.6.7 | 96FS | FS99 | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2.375
99 | pur isolatie | 1.6.8 | 98FS | FS100;FS122-1d | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
100 | folie en vloerverwarming | 1.6.9 | 99FS | FS101+1d | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
101 | chappewerken | 1.6.10 | 100FS+1d | FS102;FS104;FS106+2d;FS124 | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
102 | vloer tegelwerken | 1.6.11 | 101FS | FS103;FS108;FS110;FS156-3d | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 3.375
103 | vloertegelplinten | 1.6.12 | 102FS |  | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
104 | binnendeuren | 1.6.13 | 101FS | FS105 | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 3.375
105 | afwerking met plinten | 1.6.14 | 104FS |  | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
106 | schilderwerken | 1.6.15 | 101FS+2d | FS107+2d | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 6.375
107 | afbouw technieken wanden | 1.6.16 | 106FS+2d |  | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 3.375
108 | plaatsing keuken | 1.6.17 | 102FS | FS109 | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
109 | plaatsing wandtegels keuken | 1.6.18 | 108FS |  | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
110 | plaatsing wandtegels sanitair | 1.6.19 | 102FS | FS111;FS113+2d;FS126 | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 5.375
111 | restant raster en plafondtegel | 1.6.20 | 110FS | FS112 | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 4.375
112 | afbouw plafonds | 1.6.21 | 111FS |  | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
113 | afbouw sanitair | 1.6.22 | 110FS+2d | FS114 | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
114 | inrichting kantoren | 1.6.23 | 113FS |  | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 6.375
134 | gyprocwerken gvl | 1.7 |  |  | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 | 62.375
116 | technieken in betonblokken | 1.7.1 |  | FS152+2d | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 1.375
117 | pleisterwerken betonblokken | 1.7.2 |  |  | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2.375
118 | voorbereidend werk gyproc | 1.7.3 | 48FS | FS119-1d | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
119 | technieken in wanden | 1.7.4 | 118FS-1d | FS120;FS121 | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 3.375
120 | technieken plafonds | 1.7.5 | 119FS |  | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 1.375
121 | wanden dicht | 1.7.6 | 119FS | FS125 | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
122 | vloerisolatie | 1.7.7 | 99FS-1d |  | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
123 | folie en vloerverwarming | 1.7.8 | 61FS-2d |  | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
124 | chappevloer | 1.7.9 | 101FS |  | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
125 | wanden afwerken | 1.7.10 | 121FS |  | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
126 | vloertegelwerken | 1.7.11 | 110FS | FS127;FS128;FS130 | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 4.375
127 | afwerking met plinten | 1.7.12 | 126FS |  | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
128 | binnendeuren | 1.7.13 | 126FS | FS129 | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
129 | restant plinten | 1.7.14 | 128FS |  | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
130 | schilderwerken | 1.7.15 | 126FS | FS131 | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2.375
131 | plafondraster | 1.7.16 | 130FS | FS132 | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 3.375
132 | afbouw technieken | 1.7.17 | 131FS | FS133 | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
133 | inrichting kantoren gvl | 1.7.18 | 132FS |  | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 4.375
151 | gyprocwerken inkomzone | 1.8 |  |  | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 | 127.375
135 | sandwich deel 1 | 1.8.1 | 55FS |  | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 1.375
136 | vloerisolatie | 1.8.2 | 145FS | FS137 | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
137 | folie en vloerverwarming | 1.8.3 | 136FS |  | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
138 | polivloer inkom | 1.8.4 | 63FS-1d | FS139+1w 2d | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
139 | sandwich deel 2 | 1.8.5 | 138FS+1w 2d | FS140 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 1.375
140 | voorbereid werk gyproc | 1.8.6 | 139FS | FS141-1d;FS144-2d | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 4.375
141 | technieken in wanden | 1.8.7 | 140FS-1d | FS142 | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 1.375
142 | wanden dicht | 1.8.8 | 141FS | FS143 | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
143 | wanden afwerken | 1.8.9 | 142FS | FS145 | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
144 | technieken boven plafonds | 1.8.10 | 140FS-2d |  | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 3.375
145 | plafond sanitair | 1.8.11 | 143FS | FS136;FS146;FS149 | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2.375
146 | wandtegelwerken sanitair | 1.8.12 | 145FS | FS147 | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 4.375
147 | binnnenschrijnwerk | 1.8.13 | 146FS | FS148 | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
148 | schilderwerk binnenschrijnwerk | 1.8.14 | 147FS |  | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
149 | schilderwerk wanden | 1.8.15 | 145FS |  | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
150 | afbouw sanitaire ruimten | 1.8.16 |  |  | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
164 | traphal afwerking | 1.9 |  |  | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 | 57.375
152 | technieken ingewerkt in beton | 1.9.1 | 116FS+2d | FS153;FS155 | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 1.375
153 | technieken in spouw | 1.9.2 | 152FS |  | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 0.375
154 | raam en deur in traphal | 1.9.3 | 155FS-2d |  | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
155 | pleisterwerk betonblokken | 1.9.4 | 152FS | FS154-2d;FS157;FS161;FS162+6w | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 6.375
156 | tegelplinten betontrappen | 1.9.5 | 102FS-3d |  | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
157 | vloertegels inkom en plinten | 1.9.6 | 155FS |  | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
158 | opmeting leuning | 1.9.7 |  | FS159 | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
159 | plaatsing leuningen | 1.9.8 | 158FS | FS160 | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
160 | rolstoellift | 1.9.9 | 159FS |  | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 3.375
161 | plafondraster en bekleding | 1.9.10 | 155FS |  | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
162 | schilderwerk pleisterwerk | 1.9.11 | 155FS+6w | FS163 | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 5.375
163 | plafondtegels | 1.9.12 | 162FS |  | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
198 | Fase 2 | 1.10 |  |  | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 | 266.375
165 | inrichting winkel | 1.10.1 | 64FS | FS166-3d | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 11.375
166 | inrichting kantoor | 1.10.2 | 165FS-3d | FS167-2d | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 6.375
167 | ontmanteling bestaande winkel | 1.10.3 | 166FS-2d | FS168 | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 4.375
168 | sloop bestaande winkel | 1.10.4 | 167FS | FS169-4d;FS170 | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 4.375
169 | voorlopige wand te behouden | 1.10.5 | 168FS-4d |  | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 1.375
170 | uitzetten assen en grondwerk | 1.10.6 | 168FS | FS171 | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
171 | inzagen van bestaande beton | 1.10.7 | 170FS | FS172 | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
172 | uitzetten paalfundering | 1.10.8 | 171FS | FS173+2d | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
173 | maken van paalfundering | 1.10.9 | 172FS+2d | FS174+1w | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
174 | akoestisch doormeten | 1.10.10 | 173FS+1w | FS175+1d | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 0.375
175 | maken van fundering | 1.10.11 | 174FS+1d | FS176+2d | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
176 | staalconstructie fase 2 | 1.10.12 | 175FS+2d | FS177 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 3.375
177 | houten spanten | 1.10.13 | 176FS | FS178 | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
178 | afmontage staal | 1.10.14 | 177FS | FS179;FS182 | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
179 | prefabplinten | 1.10.15 | 178FS | FS180;FS187;FS188 | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 1.375
180 | voorbereidingen wand | 1.10.16 | 179FS | FS181 | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 1.375
181 | sandwichwand | 1.10.17 | 180FS | FS184-1w | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 | 5.375
182 | veiligheidsnetten | 1.10.18 | 178FS | FS183 | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
183 | dakplaten plaatsen | 1.10.19 | 182FS |  | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2.375
184 | dakbedekking | 1.10.20 | 181FS-1w | FS185+1w;FS190 | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 | 13.375
185 | plaatsing rookluiken | 1.10.21 | 184FS+1w | FS186 | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
186 | plaatsing rookscherm | 1.10.22 | 185FS |  | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
187 | grondwerk blinde vlek | 1.10.23 | 179FS |  | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 1.375
188 | ondervloer tussen gebouwen | 1.10.24 | 179FS |  | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2.375
189 | technieken onder dak | 1.10.25 |  |  | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 | 8.375
190 | uitvullaag | 1.10.26 | 184FS | FS191+1w;FS192+1w | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 1.375
191 | stellen dillatieprofielen | 1.10.27 | 190FS+1w |  | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2.375
192 | folie en vloerverwarming | 1.10.28 | 190FS+1w | FS193 | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 6.375
193 | polybetonvloer | 1.10.29 | 192FS | FS194;FS195 | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
194 | afwerkingsformule beton | 1.10.30 | 193FS |  | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 0.375
195 | afwerkingslaag beton | 1.10.31 | 193FS | FS196;FS197 | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 | 27.375
196 | afbouw technieken dak | 1.10.32 | 195FS |  | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 6.375
197 | winkelinrichting | 1.10.33 | 195FS |  | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 6.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Garden Center | 1528h |  |  |  |  | 99 | 100 | 101
22 | Montagewerken | 448h |  |  |  |  | 99 | 100 | 101
1 | Voorlopige plint | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | prefabplint inkom sluiten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | sandwich laagbouw | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | dakdekking voorbereiding | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | start dakdekking | 96h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | maken resterende doorvoerer | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | diverse dakdoorvoeren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | welfsels tellerlokaal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | andere welfsels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | afmontage staal hoogbouw | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | randbeveiliging tussenvloeren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Buitenwanden kantoor | 440h |  |  |  |  | 99 | 100 | 101
12 | Aanvullen en grondwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | sandwichpanelen inkom | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | netten demonteren lage zone | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | beveiliging hoge dak | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | welfsels traphal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | steeldeck hoogbouw-inkom | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | dakbedekking hoogbouw | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | regenwaterafvoer laagbouw | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | regenwaterafvoer hoogbouw | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | Ruwbouwwerken | 360h |  |  |  |  | 99 | 100 | 101
23 | Wachtbuizen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | grondwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | metselwerken tellerlokaal | 88h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | metselwerken kantoren | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | metselwerken traphal | 264h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | prefab bordessen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | trapsledes | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | welfsels traphal | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | voegwerken metselwerken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | schilderwerken metselwerken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | koepsels traphal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | koepsels laag dak | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | riolering overloop | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | riolering overloop recup | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | riolering inkom | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | arduinen dorpels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
51 | Buitenschrijnwerk | 280h |  |  |  |  | 99 | 100 | 101
39 | atelier alu | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | plaatsing alu | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | plaatsing glas deel 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | opmeting restant | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
43 | plaatsing alu restant | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
44 | alu raam | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
45 | plaatsing glas restant | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | sectionaal poorten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
47 | poorten berging en tellerlokaal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
48 | RF behandeling laagbouw | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
49 | RF behandeling hoogbouw | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | Retouche staalconstructie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
66 | Betonvloer | 504h |  |  |  |  | 99 | 100 | 101
53 | druklaag welfsels kelder | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
54 | grondwerk inkomzone | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | ondervloer inkom | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | arduin inkom | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | overige arduinen dorpels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | polivloer tellerlokaal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
59 | polivloer berging | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
60 | vloerisolatie | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
61 | folie en vloerverwarming | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
62 | druklaag welfsels | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
63 | polivloer winkel en inkom | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
64 | nabehandeling polivloer | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
65 | binnenwand berging | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
77 | Wegeniswerken achter | 264h |  |  |  |  | 99 | 100 | 101
67 | opruimen werfkeet | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | riolering naar hangar | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | nutsleidingen ondergronds | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | riolering bestrating | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | funderingskoffer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | fijnnivelleren funderingskoffer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
73 | klinkerverharding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Asfaltverharding | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
75 | herkwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
76 | Afwerken groenzones | 128h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
91 | Wegeniswerken voor | 128h |  |  |  |  | 99 | 100 | 101
78 | opruimen voorterrein | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
79 | grondwerken/braakwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
80 | herinrichting werf | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
81 | plaatsing riolering | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
82 | nutsleidingen fase 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
83 | nutsleidingen fase 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
84 | riolering bestrating | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
85 | funderingskoffer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
86 | fijnniverllerinn funderingskoffer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
87 | klinkerverharding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
88 | asfaltverharding | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
89 | herkwerken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
90 | afwerken groenzones | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
115 | afbouw +2 | 264h |  |  |  |  | 99 | 100 | 101
92 | voorbereid werk wanden | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
93 | technieken in holle wanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
94 | wanden sluiten | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
95 | wanden afwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
96 | technieken boven gyproc | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
97 | technieken boven plafond | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
98 | gyproc plafond | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
99 | pur isolatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
100 | folie en vloerverwarming | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
101 | chappewerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
102 | vloer tegelwerken | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
103 | vloertegelplinten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
104 | binnendeuren | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
105 | afwerking met plinten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
106 | schilderwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
107 | afbouw technieken wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
108 | plaatsing keuken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
109 | plaatsing wandtegels keuken | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
110 | plaatsing wandtegels sanitair | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
111 | restant raster en plafondtegel | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
112 | afbouw plafonds | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
113 | afbouw sanitair | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
114 | inrichting kantoren | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
134 | gyprocwerken gvl | 360h |  |  |  |  | 99 | 100 | 101
116 | technieken in betonblokken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
117 | pleisterwerken betonblokken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
118 | voorbereidend werk gyproc | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
119 | technieken in wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
120 | technieken plafonds | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
121 | wanden dicht | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
122 | vloerisolatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
123 | folie en vloerverwarming | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
124 | chappevloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
125 | wanden afwerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
126 | vloertegelwerken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
127 | afwerking met plinten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
128 | binnendeuren | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
129 | restant plinten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
130 | schilderwerken | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
131 | plafondraster | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
132 | afbouw technieken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
133 | inrichting kantoren gvl | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
151 | gyprocwerken inkomzone | 736h |  |  |  |  | 99 | 100 | 101
135 | sandwich deel 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
136 | vloerisolatie | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
137 | folie en vloerverwarming | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
138 | polivloer inkom | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
139 | sandwich deel 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
140 | voorbereid werk gyproc | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
141 | technieken in wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
142 | wanden dicht | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
143 | wanden afwerken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
144 | technieken boven plafonds | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
145 | plafond sanitair | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
146 | wandtegelwerken sanitair | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
147 | binnnenschrijnwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
148 | schilderwerk binnenschrijnwerk | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
149 | schilderwerk wanden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
150 | afbouw sanitaire ruimten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
164 | traphal afwerking | 336h |  |  |  |  | 99 | 100 | 101
152 | technieken ingewerkt in beton | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
153 | technieken in spouw | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
154 | raam en deur in traphal | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
155 | pleisterwerk betonblokken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
156 | tegelplinten betontrappen | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
157 | vloertegels inkom en plinten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
158 | opmeting leuning | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
159 | plaatsing leuningen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
160 | rolstoellift | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
161 | plafondraster en bekleding | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
162 | schilderwerk pleisterwerk | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
163 | plafondtegels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
198 | Fase 2 | 1528h |  |  |  |  | 99 | 100 | 101
165 | inrichting winkel | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
166 | inrichting kantoor | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
167 | ontmanteling bestaande winkel | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
168 | sloop bestaande winkel | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
169 | voorlopige wand te behouden | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
170 | uitzetten assen en grondwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
171 | inzagen van bestaande beton | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
172 | uitzetten paalfundering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
173 | maken van paalfundering | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
174 | akoestisch doormeten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
175 | maken van fundering | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
176 | staalconstructie fase 2 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
177 | houten spanten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
178 | afmontage staal | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
179 | prefabplinten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
180 | voorbereidingen wand | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
181 | sandwichwand | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
182 | veiligheidsnetten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
183 | dakplaten plaatsen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
184 | dakbedekking | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
185 | plaatsing rookluiken | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
186 | plaatsing rookscherm | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
187 | grondwerk blinde vlek | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
188 | ondervloer tussen gebouwen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
189 | technieken onder dak | 56h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
190 | uitvullaag | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
191 | stellen dillatieprofielen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
192 | folie en vloerverwarming | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
193 | polybetonvloer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
194 | afwerkingsformule beton | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
195 | afwerkingslaag beton | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
196 | afbouw technieken dak | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
197 | winkelinrichting | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-07-08 17:00 |  | TP Name | 08/07, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 25d | [5 empty] | 103464.0009 |  | 22.14% |  | 103464.0017 | 90660.3207
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 25d | [5 empty] | 34521.2804 |  | 56.7% |  | 34521.2806 | 25123.0403
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 0 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 2d | 2659.04 | 1329.52 | 1d | 0 | 0 | 2659.04 | 1329.52 | 66.67% | Started | 2659.0401 | 2659.04 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 2d | 2659.04 | 13295.2002 | 10d | 0 | 0 | 2659.04 | 13295.2002 | 16.67% | Started | 2659.0401 | 0 | 100 | 16.6667 | 16.6667 | 100 | 16.6667 | 16.6667
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 0 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 25d | [5 empty] | 9168.8 |  | 58.82% |  | 9168.8 | 8251.92
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 |  | 0 | 0 | 916.88 | 1d | 0 | 0 | 0 | 916.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 |  | 0 | 0 | 5501.28 | 6d | 0 | 0 | 0 | 5501.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 0 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 12d | [5 empty] | 57432.8004 |  | 45.4% |  | 57432.8011 | 52322.4803
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 8d | 10231.04 | 3836.64 | 3d | 0 | 0 | 10231.04 | 3836.64 | 72.73% | Started | 10231.0403 | 10231.04 | 100 | 72.7273 | 72.7273 | 100 | 72.7273 | 72.7273
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 12d | 15346.5601 | 26856.4801 | 21d | 0 | 0 | 15346.5601 | 26856.4801 | 36.36% | Started | 15346.5605 | 15346.5601 | 100 | 36.3636 | 36.3636 | 100 | 36.3636 | 36.3636
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 7d | 8952.16 | 3836.64 | 3d | 0 | 0 | 8952.16 | 3836.64 | 70% | Started | 8952.1599 | 8952.16 | 100 | 70 | 70 | 100 | 70 | 70
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 0 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 |  | 0 | 0 | 3836.64 | 3d | 0 | 0 | 0 | 3836.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 0 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 2d | [5 empty] | 2557.76 |  | 9.524% |  | 2557.76 | 2557.76
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 2d | 2557.76 | 3836.64 | 3d | 0 | 0 | 2557.76 | 3836.64 | 40% | Started | 2557.76 | 2557.76 | 100 | 40 | 40 | 100 | 40 | 40
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 5d | [5 empty] | 11509.92 |  | 32.14% |  | 11509.92 | 5115.52
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 |  | 0 | 0 | 3836.64 | 3d | 0 | 0 | 0 | 3836.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 |  | 0 | 0 | 6394.4 | 5d | 0 | 0 | 0 | 6394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 3d | 3836.64 | 3836.64 | 3d | 0 | 0 | 3836.64 | 3836.64 | 50% | Started | 3836.64 | 3836.64 | 100 | 50 | 50 | 100 | 50 | 50
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 |  | 0 | 0 | 3836.64 | 3d | 0 | 0 | 0 | 3836.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 |  | 0 | 0 | 251.6 | 1d | 0 | 0 | 0 | 251.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 |  | 0 | 0 | 2483.3601 | 2d | 0 | 0 | 0 | 2483.3601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 |  | 0 | 0 | 955.04 | 2d | 0 | 0 | 0 | 955.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 |  | 0 | 0 | 7640.3198 | 16d | 0 | 0 | 0 | 7640.3198 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 |  | 0 | 0 | 503.2 | 2d | 0 | 0 | 0 | 503.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 |  | 0 | 0 | 251.6 | 1d | 0 | 0 | 0 | 251.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 |  | 0 | 0 | 2483.3601 | 2d | 0 | 0 | 0 | 2483.3601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 |  | 0 | 0 | 2850 | 3d | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 |  | 0 | 0 | 950 | 1d | 0 | 0 | 0 | 950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1449.28
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 |  | 0 | 0 | 950 | 1d | 0 | 0 | 0 | 950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6650
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 |  | 0 | 0 | 2516.0001 | 10d | 0 | 0 | 0 | 2516.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 |  | 0 | 0 | 503.2 | 2d | 0 | 0 | 0 | 503.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 |  | 0 | 0 | 3667.52 | 4d | 0 | 0 | 0 | 3667.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 |  | 0 | 0 | 13295.2002 | 10d | 0 | 0 | 0 | 13295.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 |  | 0 | 0 | 6650 | 7d | 0 | 0 | 0 | 6650 | 0% | Not Started | 0 | 6650 | 100 |  | 0 | 100 |  | 0
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-08-12 17:00 |  | TP Name | 12/08, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 50d | [5 empty] | 190249.8415 |  | 40.71% |  | 190249.8415 | 188637.1214
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 50d | [5 empty] | 54464.0807 |  | 89.46% |  | 54464.0807 | 46991.2006
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 7977.1201 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 50d | [5 empty] | 9168.8 |  | 58.82% |  | 9168.8 | 11002.5601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 |  | 0 | 0 | 916.88 | 1d | 0 | 0 | 0 | 916.88 | 0% | Not Started | 0 | 916.88 | 100 |  | 0 | 100 |  | 0
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 |  | 0 | 0 | 5501.28 | 6d | 0 | 0 | 0 | 5501.28 | 0% | Not Started | 0 | 916.88 | 100 |  | 0 | 100 |  | 0
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 37d | [5 empty] | 100914.7206 |  | 79.78% |  | 100914.7206 | 98362.1605
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 1278.88 | 100 |  | 0 | 100 |  | 0
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 2557.76 | 100 |  | 0 | 100 |  | 0
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 |  | 0 | 0 | 3836.64 | 3d | 0 | 0 | 0 | 3836.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 1278.88 | 100 |  | 0 | 100 |  | 0
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 0 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 27d | [5 empty] | 11509.92 |  | 42.86% |  | 11509.92 | 7673.28
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 0 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 30d | [5 empty] | 21740.9601 |  | 60.71% |  | 21740.9601 | 14067.6801
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 0 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 0 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 |  | 0 | 0 | 3836.64 | 3d | 0 | 0 | 0 | 3836.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 |  | 0 | 0 | 6394.4 | 5d | 0 | 0 | 0 | 6394.4 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 24d | [5 empty] | 13130.0801 |  | 75.34% |  | 13130.0801 | 13130.0801
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 7d | 3342.6399 | 4297.6799 | 9d | 0 | 0 | 3342.6399 | 4297.6799 | 43.75% | Started | 3342.6399 | 3342.6399 | 100 | 43.75 | 43.75 | 100 | 43.75 | 43.75
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2012.8
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 |  | 0 | 0 | 503.2 | 2d | 0 | 0 | 0 | 503.2 | 0% | Not Started | 0 | 503.2 | 100 |  | 0 | 100 |  | 0
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 1258 | 100 |  | 0 | 100 |  | 0
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 |  | 0 | 0 | 251.6 | 1d | 0 | 0 | 0 | 251.6 | 0% | Not Started | 0 | 251.6 | 100 |  | 0 | 100 |  | 0
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 |  | 0 | 0 | 2483.3601 | 2d | 0 | 0 | 0 | 2483.3601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 |  | 0 | 0 | 1241.6801 | 1d | 0 | 0 | 0 | 1241.6801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 |  | 0 | 0 | 477.52 | 1d | 0 | 0 | 0 | 477.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 |  | 0 | 0 | 2850 | 3d | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 |  | 0 | 0 | 950 | 1d | 0 | 0 | 0 | 950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3349.28
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 1900 | 100 |  | 0 | 100 |  | 0
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1449.28
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2624.64
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 |  | 0 | 0 | 1900 | 2d | 0 | 0 | 0 | 1900 | 0% | Not Started | 0 | 1900 | 100 |  | 0 | 100 |  | 0
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 |  | 0 | 0 | 950 | 1d | 0 | 0 | 0 | 950 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 724.64 | 100 |  | 0 | 100 |  | 0
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6650
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 |  | 0 | 0 | 2516.0001 | 10d | 0 | 0 | 0 | 2516.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 |  | 0 | 0 | 503.2 | 2d | 0 | 0 | 0 | 503.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 |  | 0 | 0 | 3667.52 | 4d | 0 | 0 | 0 | 3667.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 |  | 0 | 0 | 13295.2002 | 10d | 0 | 0 | 0 | 13295.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 |  | 0 | 0 | 6650 | 7d | 0 | 0 | 0 | 6650 | 0% | Not Started | 0 | 6650 | 100 |  | 0 | 100 |  | 0
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-09-16 17:00 |  | TP Name | 16/09, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 75d | [5 empty] | 317609.1227 |  | 66.01% |  | 308462.7226 | 325752.3229
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 100% |  | 60882.2407 | 60882.2407
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 15954.2402 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 100% |  | 15586.9601 | 15586.9601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 5501.28 | 5501.28 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 62d | [5 empty] | 125213.4407 |  | 98.99% |  | 125213.4407 | 126492.3207
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 1273.6801 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 52d | [5 empty] | 25577.6001 |  | 95.24% |  | 25577.6001 | 26856.4801
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 |  | 0 | 0 | 1278.88 | 1d | 0 | 0 | 0 | 1278.88 | 0% | Not Started | 0 | 1278.88 | 100 |  | 0 | 100 |  | 0
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 55d | [5 empty] | 33250.8801 |  | 92.86% |  | 33250.8801 | 33250.8801
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 100% |  | 17427.76 | 17427.76
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 100% | Finished | 7640.3198 | 7640.3198 | 100 | 100 | 100 | 100 | 100 | 100
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 17d | [5 empty] | 10306.9602 |  | 80.58% |  | 10306.9602 | 12790.3203
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 |  | 0 | 0 | 2483.3601 | 2d | 0 | 0 | 0 | 2483.3601 | 0% | Not Started | 0 | 2483.3601 | 100 |  | 0 | 100 |  | 0
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 18d | [5 empty] | 20001.5203 |  | 45.55% |  | 20001.5203 | 33045.0406
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 2850 | 2850 | 100 | 100 | 100 | 100 | 100 | 100
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 100% | Finished | 950 | 950 | 100 | 100 | 100 | 100 | 100 | 100
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 2898.5601 | 100 |  | 0 | 100 |  | 0
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 724.64 | 100 |  | 0 | 100 |  | 0
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 724.64 | 100 |  | 0 | 100 |  | 0
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 3623.2001 | 100 |  | 0 | 100 |  | 0
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 724.64 | 100 |  | 0 | 100 |  | 0
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 724.64 | 100 |  | 0 | 100 |  | 0
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 2173.92 | 100 |  | 0 | 100 |  | 0
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 22d | [5 empty] | 18743.5203 |  | 55.39% |  | 14395.6802 | 14395.6802
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 23d | [5 empty] | 24178.5603 |  | 75.24% |  | 17612.4803 | 4924.5601
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 300 | 100 | 100 | 300 | 100
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 0 | 100 | 100 | 100 | 100 | 100 | 100
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 724.64 | 0 | 100 | 500 | 100 | 100 | 500 | 100
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 0 | 100 | 100 | 100 | 100 | 100 | 100
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 0 | 100 | 100 | 100 | 100 | 100 | 100
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 0 | 100 | 100 | 100 | 100 | 100 | 100
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 0 | 100 | 100 | 100 | 100 | 100 | 100
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 0 | 100 | 100 | 100 | 100 | 100 | 100
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 0 | 100 | 100 | 100 | 100 | 100 | 100
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 2d | 1449.28 | 724.64 | 1d | 0 | 0 | 1449.28 | 724.64 | 66.67% | Started | 1449.2801 | 0 | 100 | 66.6667 | 66.6667 | 100 | 66.6667 | 66.6667
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 17d | [5 empty] | 11271.7601 |  | 48.02% |  | 9371.7601 | 15893.5203
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 950 | 950 | 100 | 300 | 100 | 100 | 300 | 100
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 724.64 | 100 |  | 0 | 100 |  | 0
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 2898.5601 | 100 |  | 0 | 100 |  | 0
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 |  | 0 | 0 | 2898.5601 | 4d | 0 | 0 | 0 | 2898.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 6650
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 |  | 0 | 0 | 2516.0001 | 10d | 0 | 0 | 0 | 2516.0001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 |  | 0 | 0 | 1258 | 5d | 0 | 0 | 0 | 1258 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 |  | 0 | 0 | 503.2 | 2d | 0 | 0 | 0 | 503.2 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 |  | 0 | 0 | 3667.52 | 4d | 0 | 0 | 0 | 3667.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 |  | 0 | 0 | 13295.2002 | 10d | 0 | 0 | 0 | 13295.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 |  | 0 | 0 | 6650 | 7d | 0 | 0 | 0 | 6650 | 0% | Not Started | 0 | 6650 | 100 |  | 0 | 100 |  | 0
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2014-10-21 17:00 |  | TP Name | 21/10, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 100d | [5 empty] | 379212.884 |  | 79.19% |  | 370066.4839 | 378668.9639
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 100% |  | 60882.2407 | 60882.2407
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 15954.2402 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 100% |  | 15586.9601 | 15586.9601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 5501.28 | 5501.28 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 71d | [5 empty] | 126492.3207 |  | 100% |  | 126492.3207 | 126492.3207
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 1273.6801 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 61d | [5 empty] | 26856.4801 |  | 100% |  | 26856.4801 | 26856.4801
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-29 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 64d | [5 empty] | 35808.6401 |  | 100% |  | 35808.6401 | 35808.6401
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-09-26 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 100% |  | 17427.76 | 17427.76
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 100% | Finished | 7640.3198 | 7640.3198 | 100 | 100 | 100 | 100 | 100 | 100
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 20d | [5 empty] | 12790.3203 |  | 100% |  | 12790.3203 | 12790.3203
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-09-18 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 36d | [5 empty] | 43914.6408 |  | 100% |  | 43914.6408 | 43914.6408
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 2850 | 2850 | 100 | 100 | 100 | 100 | 100 | 100
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 100% | Finished | 950 | 950 | 100 | 100 | 100 | 100 | 100 | 100
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-18 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-24 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-18 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-24 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-06 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-02 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-10-06 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 44d | [5 empty] | 30337.7605 |  | 100% |  | 25989.9204 | 25989.9204
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-06 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-03 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-14 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 33d | [5 empty] | 29975.6804 |  | 100% |  | 23409.6003 | 23409.6003
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 300 | 100 | 100 | 300 | 100
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 500 | 100 | 100 | 500 | 100
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-18 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-23 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-25 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 42d | [5 empty] | 19967.4403 |  | 92.57% |  | 18067.4403 | 19516.7203
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 950 | 950 | 100 | 300 | 100 | 100 | 300 | 100
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-19 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-01 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-02 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-20 08:00 | 2d | 1449.28 | 1449.28 | 2d | 0 | 0 | 1449.28 | 1449.28 | 50% | Started | 1449.28 | 2898.5601 | 100 | 50 | 50 | 100 | 50 | 50
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 16d | [5 empty] | 5283.6001 |  | 5.228% |  | 5283.6001 | 12436.8001
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 2014-09-30 08:00 | 10d | 2516.0001 | 0 | 0 | 0 | 0 | 2516.0001 | 0 | 100% | Finished | 2516.0001 | 2516.0001 | 100 | 100 | 100 | 100 | 100 | 100
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-09 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-14 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-21 08:00 | 1d | 251.6 | 1006.4 | 4d | 0 | 0 | 251.6 | 1006.4 | 20% | Started | 251.6 | 503.2 | 100 | 20 | 20 | 100 | 20 | 20
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 |  | 0 | 0 | 503.2 | 2d | 0 | 0 | 0 | 503.2 | 0% | Not Started | 0 | 251.6 | 100 |  | 0 | 100 |  | 0
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 |  | 0 | 0 | 1329.52 | 1d | 0 | 0 | 0 | 1329.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 |  | 0 | 0 | 3667.52 | 4d | 0 | 0 | 0 | 3667.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 |  | 0 | 0 | 13295.2002 | 10d | 0 | 0 | 0 | 13295.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 |  | 0 | 0 | 6650 | 7d | 0 | 0 | 0 | 6650 | 0% | Not Started | 0 | 6650 | 100 |  | 0 | 100 |  | 0
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2014-11-25 17:00 |  | TP Name | 25/11, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 125d | [5 empty] | 392807.9242 |  | 82.39% |  | 384991.0441 | 395477.6841
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 100% |  | 60882.2407 | 60882.2407
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 15954.2402 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 100% |  | 15586.9601 | 15586.9601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 5501.28 | 5501.28 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 71d | [5 empty] | 126492.3207 |  | 100% |  | 126492.3207 | 126492.3207
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 1273.6801 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 61d | [5 empty] | 26856.4801 |  | 100% |  | 26856.4801 | 26856.4801
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-29 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 64d | [5 empty] | 35808.6401 |  | 100% |  | 35808.6401 | 35808.6401
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-09-26 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 100% |  | 17427.76 | 17427.76
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 100% | Finished | 7640.3198 | 7640.3198 | 100 | 100 | 100 | 100 | 100 | 100
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 20d | [5 empty] | 12790.3203 |  | 100% |  | 12790.3203 | 12790.3203
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-09-18 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 36d | [5 empty] | 43914.6408 |  | 100% |  | 43914.6408 | 43914.6408
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 2850 | 2850 | 100 | 100 | 100 | 100 | 100 | 100
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 100% | Finished | 950 | 950 | 100 | 100 | 100 | 100 | 100 | 100
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-18 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-24 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-18 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-24 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-06 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-02 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-10-06 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 44d | [5 empty] | 30337.7605 |  | 100% |  | 25989.9204 | 25989.9204
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-06 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-03 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-14 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 33d | [5 empty] | 29975.6804 |  | 100% |  | 23409.6003 | 23409.6003
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 300 | 100 | 100 | 300 | 100
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 500 | 100 | 100 | 500 | 100
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-18 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-23 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-25 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 44d | [5 empty] | 21416.7203 |  | 100% |  | 19516.7203 | 19516.7203
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 950 | 950 | 100 | 300 | 100 | 100 | 300 | 100
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-19 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-01 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-02 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-20 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 41d | [5 empty] | 17429.3603 |  | 18.56% |  | 18758.8803 | 29245.5204
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 2014-09-30 08:00 | 10d | 2516.0001 | 0 | 0 | 0 | 0 | 2516.0001 | 0 | 100% | Finished | 2516.0001 | 2516.0001 | 100 | 100 | 100 | 100 | 100 | 100
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-09 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-14 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-21 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-10-22 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-12 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-13 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 50 | 100 | 100 | 50 | 100
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-17 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-19 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-21 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-24 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 2557.76 | 100 |  | 0 | 100 |  | 0
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 1278.88 | 100 |  | 0 | 100 |  | 0
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 |  | 0 | 0 | 2557.76 | 2d | 0 | 0 | 0 | 2557.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 |  | 0 | 0 | 1833.76 | 2d | 0 | 0 | 0 | 1833.76 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 |  | 0 | 0 | 3667.52 | 4d | 0 | 0 | 0 | 3667.52 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 |  | 0 | 0 | 13295.2002 | 10d | 0 | 0 | 0 | 13295.2002 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 |  | 0 | 0 | 2659.04 | 2d | 0 | 0 | 0 | 2659.04 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 |  | 0 | 0 | 3988.5601 | 3d | 0 | 0 | 0 | 3988.5601 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 |  | 0 | 0 | 6650 | 7d | 0 | 0 | 0 | 6650 | 0% | Not Started | 0 | 6650 | 100 |  | 0 | 100 |  | 0
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2014-12-30 17:00 |  | TP Name | 30/12, 2014
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 150d | [5 empty] | 443059.5247 |  | 92.87% |  | 433963.7646 | 436862.3246
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 100% |  | 60882.2407 | 60882.2407
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 15954.2402 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 100% |  | 15586.9601 | 15586.9601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 5501.28 | 5501.28 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 71d | [5 empty] | 126492.3207 |  | 100% |  | 126492.3207 | 126492.3207
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 1273.6801 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 61d | [5 empty] | 26856.4801 |  | 100% |  | 26856.4801 | 26856.4801
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-29 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 64d | [5 empty] | 35808.6401 |  | 100% |  | 35808.6401 | 35808.6401
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-09-26 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 100% |  | 17427.76 | 17427.76
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 100% | Finished | 7640.3198 | 7640.3198 | 100 | 100 | 100 | 100 | 100 | 100
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 20d | [5 empty] | 12790.3203 |  | 100% |  | 12790.3203 | 12790.3203
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-09-18 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 36d | [5 empty] | 43914.6408 |  | 100% |  | 43914.6408 | 43914.6408
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 2850 | 2850 | 100 | 100 | 100 | 100 | 100 | 100
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 100% | Finished | 950 | 950 | 100 | 100 | 100 | 100 | 100 | 100
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-18 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-24 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-18 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-24 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-06 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-02 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-10-06 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 44d | [5 empty] | 30337.7605 |  | 100% |  | 25989.9204 | 25989.9204
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-06 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-03 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-14 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 33d | [5 empty] | 29975.6804 |  | 100% |  | 23409.6003 | 23409.6003
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 300 | 100 | 100 | 300 | 100
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 500 | 100 | 100 | 500 | 100
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-18 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-23 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-25 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 44d | [5 empty] | 21416.7203 |  | 100% |  | 19516.7203 | 19516.7203
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 950 | 950 | 100 | 300 | 100 | 100 | 300 | 100
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-19 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-01 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-02 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-20 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 66d | [5 empty] | 67680.9608 |  | 67.02% |  | 67731.6008 | 70630.1609
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 2014-09-30 08:00 | 10d | 2516.0001 | 0 | 0 | 0 | 0 | 2516.0001 | 0 | 100% | Finished | 2516.0001 | 2516.0001 | 100 | 100 | 100 | 100 | 100 | 100
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-09 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-14 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-21 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-10-22 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-12 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-13 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 50 | 100 | 100 | 50 | 100
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-17 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-19 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-21 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-24 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-11-28 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-02 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-04 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 150 | 100 | 100 | 150 | 100
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-12-11 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 | 2014-12-15 08:00 | 4d | 3667.52 | 0 | 0 | 0 | 0 | 3667.52 | 0 | 100% | Finished | 3667.52 | 3667.52 | 100 | 100 | 100 | 100 | 100 | 100
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-09 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-10 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 | 2014-12-15 08:00 | 10d | 13295.2002 | 0 | 0 | 0 | 0 | 13295.2002 | 0 | 100% | Finished | 13295.2002 | 13295.2002 | 100 | 100 | 100 | 100 | 100 | 100
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-11 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-11 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 | 2014-12-15 08:00 | 7d | 6650 | 0 | 0 | 0 | 0 | 6650 | 0 | 100% | Finished | 6650 | 6650 | 100 | 100 | 100 | 100 | 100 | 100
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 |  | 0 | 0 | 2173.92 | 3d | 0 | 0 | 0 | 2173.92 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 |  | 0 | 0 | 724.64 | 1d | 0 | 0 | 0 | 724.64 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2015-02-03 17:00 |  | TP Name | 03/02, 2015
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 175d | [5 empty] | 451030.5648 |  | 94.73% |  | 442659.4447 | 452079.7649
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 100% |  | 60882.2407 | 60882.2407
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 15954.2402 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 100% |  | 15586.9601 | 15586.9601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 5501.28 | 5501.28 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 71d | [5 empty] | 126492.3207 |  | 100% |  | 126492.3207 | 126492.3207
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 1273.6801 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 61d | [5 empty] | 26856.4801 |  | 100% |  | 26856.4801 | 26856.4801
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-29 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 64d | [5 empty] | 35808.6401 |  | 100% |  | 35808.6401 | 35808.6401
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-09-26 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 100% |  | 17427.76 | 17427.76
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 100% | Finished | 7640.3198 | 7640.3198 | 100 | 100 | 100 | 100 | 100 | 100
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 20d | [5 empty] | 12790.3203 |  | 100% |  | 12790.3203 | 12790.3203
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-09-18 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 36d | [5 empty] | 43914.6408 |  | 100% |  | 43914.6408 | 43914.6408
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 2850 | 2850 | 100 | 100 | 100 | 100 | 100 | 100
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 100% | Finished | 950 | 950 | 100 | 100 | 100 | 100 | 100 | 100
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-18 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-24 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-18 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-24 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-06 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-02 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-10-06 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 44d | [5 empty] | 30337.7605 |  | 100% |  | 25989.9204 | 25989.9204
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-06 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-03 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-14 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 33d | [5 empty] | 29975.6804 |  | 100% |  | 23409.6003 | 23409.6003
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 300 | 100 | 100 | 300 | 100
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 500 | 100 | 100 | 500 | 100
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-18 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-23 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-25 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 44d | [5 empty] | 21416.7203 |  | 100% |  | 19516.7203 | 19516.7203
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 950 | 950 | 100 | 300 | 100 | 100 | 300 | 100
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-19 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-01 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-02 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-20 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 91d | [5 empty] | 75652.0009 |  | 75.62% |  | 76427.281 | 85847.6012
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 2014-09-30 08:00 | 10d | 2516.0001 | 0 | 0 | 0 | 0 | 2516.0001 | 0 | 100% | Finished | 2516.0001 | 2516.0001 | 100 | 100 | 100 | 100 | 100 | 100
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-09 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-14 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-21 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-10-22 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-12 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-13 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 50 | 100 | 100 | 50 | 100
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-17 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-19 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-21 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-24 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-11-28 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-02 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-04 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 150 | 100 | 100 | 150 | 100
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-12-11 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 | 2014-12-15 08:00 | 4d | 3667.52 | 0 | 0 | 0 | 0 | 3667.52 | 0 | 100% | Finished | 3667.52 | 3667.52 | 100 | 100 | 100 | 100 | 100 | 100
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-09 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-10 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 | 2014-12-15 08:00 | 10d | 13295.2002 | 0 | 0 | 0 | 0 | 13295.2002 | 0 | 100% | Finished | 13295.2002 | 13295.2002 | 100 | 100 | 100 | 100 | 100 | 100
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 |  | 0 | 0 | 1449.28 | 2d | 0 | 0 | 0 | 1449.28 | 0% | Not Started | 0 | 1449.28 | 100 |  | 0 | 100 |  | 0
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-11 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-11 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 | 2014-12-15 08:00 | 7d | 6650 | 0 | 0 | 0 | 0 | 6650 | 0 | 100% | Finished | 6650 | 6650 | 100 | 100 | 100 | 100 | 100 | 100
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-01-05 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2015-01-14 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-01-14 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2015-01-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2015-01-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 |  | 0 | 0 | 14492.8003 | 20d | 0 | 0 | 0 | 14492.8003 | 0% | Not Started | 0 | 6521.7601 | 100 |  | 0 | 100 |  | 0
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 |  | 0 | 0 | 3623.2001 | 5d | 0 | 0 | 0 | 3623.2001 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2015-03-10 17:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Garden Center | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 467297.2052 |  | 186d | [5 empty] | 461900.1651 |  | 100% |  | 467297.2052 | 467297.2052
22 | Montagewerken | 2014-06-04 08:00 | 2014-08-20 17:00 | 56d |  |  | 0 |  |  | 60882.2407 |  | 65d | [5 empty] | 57214.7207 |  | 100% |  | 60882.2407 | 60882.2407
1 | Voorlopige plint | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-04 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
2 | prefabplint inkom sluiten | 2014-08-12 08:00 | 2014-08-13 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-06-12 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
3 | sandwich laagbouw | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 166.19 | 6647.6001 | 6647.6001 | 2014-06-04 08:00 | 5d | 6647.6001 | 0 | 0 | 0 | 0 | 6647.6001 | 0 | 100% | Finished | 6647.6001 | 6647.6001 | 100 | 100 | 100 | 100 | 100 | 100
4 | dakdekking voorbereiding | 2014-07-07 08:00 | 2014-07-09 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-07 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
5 | start dakdekking | 2014-08-05 08:00 | 2014-08-20 17:00 | 12d |  | 0 | 0 | 166.19 | 15954.2402 | 15954.2402 | 2014-07-07 08:00 | 12d | 15954.2402 | 0 | 0 | 0 | 0 | 15954.2402 | 0 | 100% | Finished | 15954.2402 | 15954.2402 | 100 | 100 | 100 | 100 | 100 | 100
6 | maken resterende doorvoerer | 2014-07-09 08:00 | 2014-07-11 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-07-09 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
7 | diverse dakdoorvoeren | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-11 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
8 | welfsels tellerlokaal | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-02 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
9 | andere welfsels | 2014-07-03 08:00 | 2014-07-03 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-03 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
10 | afmontage staal hoogbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
11 | randbeveiliging tussenvloeren | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-04 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
19 | Buitenwanden kantoor | 2014-06-04 08:00 | 2014-08-19 17:00 | 55d |  |  | 0 |  |  | 15586.9601 |  | 65d | [5 empty] | 11919.4401 |  | 100% |  | 15586.9601 | 15586.9601
12 | Aanvullen en grondwerken | 2014-06-04 08:00 | 2014-06-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-06-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
13 | sandwichpanelen inkom | 2014-06-04 08:00 | 2014-06-10 17:00 | 5d |  | 0 | 0 | 114.61 | 4584.4 | 4584.4 | 2014-06-04 08:00 | 5d | 4584.4 | 0 | 0 | 0 | 0 | 4584.4 | 0 | 100% | Finished | 4584.4 | 4584.4 | 100 | 100 | 100 | 100 | 100 | 100
14 | netten demonteren lage zone | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
15 | beveiliging hoge dak | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-07 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
16 | welfsels traphal | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-08-29 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
17 | steeldeck hoogbouw-inkom | 2014-07-08 08:00 | 2014-07-09 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
18 | dakbedekking hoogbouw | 2014-08-12 08:00 | 2014-08-19 17:00 | 6d |  | 0 | 0 | 114.61 | 5501.28 | 5501.28 | 2014-09-01 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 5501.28 | 5501.28 | 100 | 33.3333 | 100 | 100 | 33.3333 | 100
20 | regenwaterafvoer laagbouw | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 114.61 | 916.88 | 916.88 | 2014-07-04 08:00 | 1d | 916.88 | 0 | 0 | 0 | 0 | 916.88 | 0 | 100% | Finished | 916.88 | 916.88 | 100 | 100 | 100 | 100 | 100 | 100
21 | regenwaterafvoer hoogbouw | 2014-07-09 08:00 | 2014-07-10 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-07-07 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
52 | Ruwbouwwerken | 2014-06-23 08:00 | 2014-08-22 17:00 | 45d |  |  | 0 |  |  | 126492.3207 |  | 71d | [5 empty] | 126492.3207 |  | 100% |  | 126492.3207 | 126492.3207
23 | Wachtbuizen | 2014-07-04 08:00 | 2014-07-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
24 | grondwerken | 2014-07-07 08:00 | 2014-07-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
25 | metselwerken tellerlokaal | 2014-06-27 08:00 | 2014-07-11 17:00 | 11d |  | 0 | 0 | 159.86 | 14067.6801 | 14067.6801 | 2014-06-27 08:00 | 11d | 14067.6801 | 0 | 0 | 0 | 0 | 14067.6801 | 0 | 100% | Finished | 14067.6801 | 14067.6801 | 100 | 100 | 100 | 100 | 100 | 100
26 | metselwerken kantoren | 2014-06-23 08:00 | 2014-07-01 17:00 | 7d |  | 0 | 0 | 159.86 | 8952.16 | 8952.16 | 2014-06-23 08:00 | 7d | 8952.16 | 0 | 0 | 0 | 0 | 8952.16 | 0 | 100% | Finished | 8952.16 | 8952.16 | 100 | 100 | 100 | 100 | 100 | 100
27 | metselwerken traphal | 2014-06-23 08:00 | 2014-08-06 17:00 | 33d |  | 0 | 0 | 159.86 | 42203.0402 | 42203.0402 | 2014-06-23 08:00 | 33d | 42203.0402 | 0 | 0 | 0 | 0 | 42203.0402 | 0 | 100% | Finished | 42203.0402 | 42203.0402 | 100 | 100 | 100 | 100 | 100 | 100
28 | prefab bordessen | 2014-06-30 08:00 | 2014-07-11 17:00 | 10d |  | 0 | 0 | 159.86 | 12788.8 | 12788.8 | 2014-06-30 08:00 | 10d | 12788.8 | 0 | 0 | 0 | 0 | 12788.8 | 0 | 100% | Finished | 12788.8 | 12788.8 | 100 | 100 | 100 | 100 | 100 | 100
29 | trapsledes | 2014-08-07 08:00 | 2014-08-07 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-28 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
30 | welfsels traphal | 2014-08-08 08:00 | 2014-08-11 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-29 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
31 | voegwerken metselwerken | 2014-08-12 08:00 | 2014-08-14 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-06-30 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
32 | schilderwerken metselwerken | 2014-08-18 08:00 | 2014-08-20 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-09-08 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
33 | koepsels traphal | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
34 | koepsels laag dak | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
35 | riolering overloop | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
36 | riolering overloop recup | 2014-07-08 08:00 | 2014-07-08 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
37 | riolering inkom | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-08 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
38 | arduinen dorpels | 2014-08-14 08:00 | 2014-08-14 17:00 | 1d |  | 0 | 0 | 159.21 | 1273.6801 | 1273.6801 | 2014-07-04 08:00 | 1d | 1273.6801 | 0 | 0 | 0 | 0 | 1273.6801 | 0 | 100% | Finished | 1273.6801 | 1273.6801 | 100 | 100 | 100 | 100 | 100 | 100
51 | Buitenschrijnwerk | 2014-07-07 08:00 | 2014-08-22 17:00 | 35d |  |  | 0 |  |  | 26856.4801 |  | 61d | [5 empty] | 26856.4801 |  | 100% |  | 26856.4801 | 26856.4801
39 | atelier alu | 2014-07-07 08:00 | 2014-07-11 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-07-07 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
40 | plaatsing alu | 2014-08-14 08:00 | 2014-08-15 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-07 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
41 | plaatsing glas deel 1 | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-11 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
42 | opmeting restant | 2014-08-06 08:00 | 2014-08-06 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-06 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
43 | plaatsing alu restant | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-18 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
44 | alu raam | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-19 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
45 | plaatsing glas restant | 2014-08-20 08:00 | 2014-08-20 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-08-19 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
46 | sectionaal poorten | 2014-08-15 08:00 | 2014-08-18 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-25 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
47 | poorten berging en tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
48 | RF behandeling laagbouw | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
49 | RF behandeling hoogbouw | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-08-13 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
50 | Retouche staalconstructie | 2014-08-21 08:00 | 2014-08-21 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-29 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
66 | Betonvloer | 2014-07-02 08:00 | 2014-09-26 17:00 | 63d |  |  | 0 |  |  | 35808.6401 |  | 64d | [5 empty] | 35808.6401 |  | 100% |  | 35808.6401 | 35808.6401
53 | druklaag welfsels kelder | 2014-07-02 08:00 | 2014-07-02 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-02 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
54 | grondwerk inkomzone | 2014-08-12 08:00 | 2014-08-12 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
55 | ondervloer inkom | 2014-08-15 08:00 | 2014-08-15 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-07 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
56 | arduin inkom | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-08 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
57 | overige arduinen dorpels | 2014-08-19 08:00 | 2014-08-20 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-07-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
58 | polivloer tellerlokaal | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
59 | polivloer berging | 2014-08-19 08:00 | 2014-08-19 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-07-03 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
60 | vloerisolatie | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-22 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
61 | folie en vloerverwarming | 2014-08-28 08:00 | 2014-09-03 17:00 | 5d |  | 0 | 0 | 159.86 | 6394.4 | 6394.4 | 2014-08-28 08:00 | 5d | 6394.4 | 0 | 0 | 0 | 0 | 6394.4 | 0 | 100% | Finished | 6394.4 | 6394.4 | 100 | 100 | 100 | 100 | 100 | 100
62 | druklaag welfsels | 2014-07-04 08:00 | 2014-07-11 17:00 | 6d |  | 0 | 0 | 159.86 | 7673.28 | 7673.28 | 2014-07-04 08:00 | 6d | 7673.28 | 0 | 0 | 0 | 0 | 7673.28 | 0 | 100% | Finished | 7673.28 | 7673.28 | 100 | 100 | 100 | 100 | 100 | 100
63 | polivloer winkel en inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 159.86 | 1278.88 | 1278.88 | 2014-09-04 08:00 | 1d | 1278.88 | 0 | 0 | 0 | 0 | 1278.88 | 0 | 100% | Finished | 1278.88 | 1278.88 | 100 | 100 | 100 | 100 | 100 | 100
64 | nabehandeling polivloer | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-09-26 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
65 | binnenwand berging | 2014-08-05 08:00 | 2014-08-07 17:00 | 3d |  | 0 | 0 | 159.86 | 3836.64 | 3836.64 | 2014-08-05 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 3836.64 | 3836.64 | 100 | 100 | 100 | 100 | 100 | 100
77 | Wegeniswerken achter | 2014-07-10 08:00 | 2014-08-25 17:00 | 33d |  |  | 0 |  |  | 17427.76 |  | 33d | [5 empty] | 17427.76 |  | 100% |  | 17427.76 | 17427.76
67 | opruimen werfkeet | 2014-07-10 08:00 | 2014-07-10 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-07-10 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
68 | riolering naar hangar | 2014-07-11 08:00 | 2014-07-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-07-11 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
69 | nutsleidingen ondergronds | 2014-07-14 08:00 | 2014-07-14 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-14 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
70 | riolering bestrating | 2014-07-15 08:00 | 2014-07-15 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-07-15 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
71 | funderingskoffer | 2014-07-16 08:00 | 2014-07-16 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-16 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
72 | fijnnivelleren funderingskoffer | 2014-07-18 08:00 | 2014-07-18 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-07-18 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
73 | klinkerverharding | 2014-07-21 08:00 | 2014-07-21 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-21 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
74 | Asfaltverharding | 2014-07-21 08:00 | 2014-07-22 17:00 | 2d |  | 0 | 0 | 59.69 | 955.04 | 955.04 | 2014-07-21 08:00 | 2d | 955.04 | 0 | 0 | 0 | 0 | 955.04 | 0 | 100% | Finished | 955.04 | 955.04 | 100 | 100 | 100 | 100 | 100 | 100
75 | herkwerken | 2014-07-28 08:00 | 2014-07-28 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-07-28 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
76 | Afwerken groenzones | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  | 0 | 0 | 59.69 | 7640.3198 | 7640.3198 | 2014-08-04 08:00 | 16d | 7640.3198 | 0 | 0 | 0 | 0 | 7640.3198 | 0 | 100% | Finished | 7640.3198 | 7640.3198 | 100 | 100 | 100 | 100 | 100 | 100
91 | Wegeniswerken voor | 2014-08-04 08:00 | 2014-08-25 17:00 | 16d |  |  | 0 |  |  | 12790.3203 |  | 20d | [5 empty] | 12790.3203 |  | 100% |  | 12790.3203 | 12790.3203
78 | opruimen voorterrein | 2014-08-04 08:00 | 2014-08-05 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-09-08 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
79 | grondwerken/braakwerken | 2014-08-06 08:00 | 2014-08-12 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-09-08 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
80 | herinrichting werf | 2014-08-05 08:00 | 2014-08-05 17:00 | 1d |  | 0 | 0 | 31.45 | 251.6 | 251.6 | 2014-09-08 08:00 | 1d | 251.6 | 0 | 0 | 0 | 0 | 251.6 | 0 | 100% | Finished | 251.6 | 251.6 | 100 | 100 | 100 | 100 | 100 | 100
81 | plaatsing riolering | 2014-08-13 08:00 | 2014-08-14 17:00 | 2d |  | 0 | 0 | 155.21 | 2483.3601 | 2483.3601 | 2014-09-18 08:00 | 2d | 2483.3601 | 0 | 0 | 0 | 0 | 2483.3601 | 0 | 100% | Finished | 2483.3601 | 2483.3601 | 100 | 100 | 100 | 100 | 100 | 100
82 | nutsleidingen fase 1 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
83 | nutsleidingen fase 2 | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
84 | riolering bestrating | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 155.21 | 1241.6801 | 1241.6801 | 2014-08-25 08:00 | 1d | 1241.6801 | 0 | 0 | 0 | 0 | 1241.6801 | 0 | 100% | Finished | 1241.6801 | 1241.6801 | 100 | 100 | 100 | 100 | 100 | 100
85 | funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
86 | fijnniverllerinn funderingskoffer | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-08-25 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
87 | klinkerverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
88 | asfaltverharding | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
89 | herkwerken | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
90 | afwerken groenzones | 2014-08-25 08:00 | 2014-08-25 17:00 | 1d |  | 0 | 0 | 59.69 | 477.52 | 477.52 | 2014-08-25 08:00 | 1d | 477.52 | 0 | 0 | 0 | 0 | 477.52 | 0 | 100% | Finished | 477.52 | 477.52 | 100 | 100 | 100 | 100 | 100 | 100
115 | afbouw +2 | 2014-08-15 08:00 | 2014-09-30 17:00 | 33d |  |  | 0 |  |  | 43914.6408 |  | 36d | [5 empty] | 43914.6408 |  | 100% |  | 43914.6408 | 43914.6408
92 | voorbereid werk wanden | 2014-08-15 08:00 | 2014-08-21 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-08-22 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
93 | technieken in holle wanden | 2014-08-20 08:00 | 2014-08-22 17:00 | 3d |  | 0 | 0 | 118.75 | 2850 | 2850 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 2850 | 2850 | 100 | 100 | 100 | 100 | 100 | 100
94 | wanden sluiten | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
95 | wanden afwerken | 2014-08-25 08:00 | 2014-08-29 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-08-29 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
96 | technieken boven gyproc | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-28 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
97 | technieken boven plafond | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-09-01 08:00 | 1d | 950 | 0 | 0 | 0 | 0 | 950 | 0 | 100% | Finished | 950 | 950 | 100 | 100 | 100 | 100 | 100 | 100
98 | gyproc plafond | 2014-08-26 08:00 | 2014-08-28 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-01 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
99 | pur isolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
100 | folie en vloerverwarming | 2014-09-01 08:00 | 2014-09-02 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
101 | chappewerken | 2014-09-04 08:00 | 2014-09-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
102 | vloer tegelwerken | 2014-09-08 08:00 | 2014-09-11 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-18 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
103 | vloertegelplinten | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
104 | binnendeuren | 2014-09-12 08:00 | 2014-09-15 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-24 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
105 | afwerking met plinten | 2014-09-16 08:00 | 2014-09-16 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
106 | schilderwerken | 2014-09-10 08:00 | 2014-09-16 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-18 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
107 | afbouw technieken wanden | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
108 | plaatsing keuken | 2014-09-12 08:00 | 2014-09-12 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
109 | plaatsing wandtegels keuken | 2014-09-15 08:00 | 2014-09-15 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
110 | plaatsing wandtegels sanitair | 2014-09-12 08:00 | 2014-09-17 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-09-24 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
111 | restant raster en plafondtegel | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
112 | afbouw plafonds | 2014-09-23 08:00 | 2014-09-24 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-06 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
113 | afbouw sanitair | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-02 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
114 | inrichting kantoren | 2014-09-24 08:00 | 2014-09-30 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-10-06 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
134 | gyprocwerken gvl | 2014-08-05 08:00 | 2014-10-06 17:00 | 45d |  |  | 0 |  |  | 25989.9204 |  | 44d | [5 empty] | 30337.7605 |  | 100% |  | 25989.9204 | 25989.9204
116 | technieken in betonblokken | 2014-08-05 08:00 | 2014-08-06 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
117 | pleisterwerken betonblokken | 2014-08-11 08:00 | 2014-08-13 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-25 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
118 | voorbereidend werk gyproc | 2014-08-21 08:00 | 2014-08-22 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-18 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
119 | technieken in wanden | 2014-08-22 08:00 | 2014-08-25 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
120 | technieken plafonds | 2014-08-26 08:00 | 2014-08-27 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-21 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
121 | wanden dicht | 2014-08-26 08:00 | 2014-08-26 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
122 | vloerisolatie | 2014-08-29 08:00 | 2014-08-29 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
123 | folie en vloerverwarming | 2014-09-02 08:00 | 2014-09-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-28 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
124 | chappevloer | 2014-09-08 08:00 | 2014-09-08 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-08 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
125 | wanden afwerken | 2014-08-27 08:00 | 2014-08-28 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 250 | 100 | 100 | 250 | 100
126 | vloertegelwerken | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-30 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
127 | afwerking met plinten | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
128 | binnendeuren | 2014-09-23 08:00 | 2014-09-23 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-03 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
129 | restant plinten | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-06 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
130 | schilderwerken | 2014-09-23 08:00 | 2014-09-25 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-03 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
131 | plafondraster | 2014-09-26 08:00 | 2014-09-29 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
132 | afbouw technieken | 2014-09-30 08:00 | 2014-10-01 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-10-10 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
133 | inrichting kantoren gvl | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-10-14 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
151 | gyprocwerken inkomzone | 2014-06-04 08:00 | 2014-10-09 17:00 | 92d |  |  | 0 |  |  | 23409.6003 |  | 33d | [5 empty] | 29975.6804 |  | 100% |  | 23409.6003 | 23409.6003
135 | sandwich deel 1 | 2014-08-18 08:00 | 2014-08-19 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-08-19 08:00 | 6d | 5501.28 | 0 | 0 | 0 | 0 | 5501.28 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 300 | 100 | 100 | 300 | 100
136 | vloerisolatie | 2014-10-02 08:00 | 2014-10-02 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-26 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
137 | folie en vloerverwarming | 2014-10-03 08:00 | 2014-10-03 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-27 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 500 | 100 | 100 | 500 | 100
138 | polivloer inkom | 2014-09-04 08:00 | 2014-09-04 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-09 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
139 | sandwich deel 2 | 2014-09-16 08:00 | 2014-09-17 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-09-05 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
140 | voorbereid werk gyproc | 2014-09-18 08:00 | 2014-09-22 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
141 | technieken in wanden | 2014-09-22 08:00 | 2014-09-23 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-19 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
142 | wanden dicht | 2014-09-24 08:00 | 2014-09-24 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
143 | wanden afwerken | 2014-09-25 08:00 | 2014-09-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-08-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
144 | technieken boven plafonds | 2014-09-19 08:00 | 2014-09-22 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-26 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
145 | plafond sanitair | 2014-09-29 08:00 | 2014-10-01 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-08-26 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
146 | wandtegelwerken sanitair | 2014-10-02 08:00 | 2014-10-06 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2014-09-15 08:00 | 3d | 2173.92 | 0 | 0 | 0 | 0 | 2173.92 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 100 | 100 | 100 | 100 | 100
147 | binnnenschrijnwerk | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-18 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
148 | schilderwerk binnenschrijnwerk | 2014-10-08 08:00 | 2014-10-09 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-23 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
149 | schilderwerk wanden | 2014-10-02 08:00 | 2014-10-03 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-25 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
150 | afbouw sanitaire ruimten | 2014-06-04 08:00 | 2014-06-05 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-29 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
164 | traphal afwerking | 2014-08-11 08:00 | 2014-10-07 17:00 | 42d |  |  | 0 |  |  | 19516.7203 |  | 44d | [5 empty] | 21416.7203 |  | 100% |  | 19516.7203 | 19516.7203
152 | technieken ingewerkt in beton | 2014-08-11 08:00 | 2014-08-12 17:00 | 2d |  | 0 | 0 | 118.75 | 1900 | 1900 | 2014-08-25 08:00 | 2d | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 100% | Finished | 1900 | 1900 | 100 | 100 | 100 | 100 | 100 | 100
153 | technieken in spouw | 2014-08-13 08:00 | 2014-08-13 17:00 | 1d |  | 0 | 0 | 118.75 | 950 | 950 | 2014-08-26 08:00 | 3d | 2850 | 0 | 0 | 0 | 0 | 2850 | 0 | 100% | Finished | 950 | 950 | 100 | 300 | 100 | 100 | 300 | 100
154 | raam en deur in traphal | 2014-08-18 08:00 | 2014-08-18 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-08-25 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
155 | pleisterwerk betonblokken | 2014-08-13 08:00 | 2014-08-19 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2014-09-01 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
156 | tegelplinten betontrappen | 2014-09-09 08:00 | 2014-09-10 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-19 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
157 | vloertegels inkom en plinten | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-08 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
158 | opmeting leuning | 2014-08-11 08:00 | 2014-08-11 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-02 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
159 | plaatsing leuningen | 2014-09-01 08:00 | 2014-09-01 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-10-01 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
160 | rolstoellift | 2014-09-02 08:00 | 2014-09-05 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-02 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
161 | plafondraster en bekleding | 2014-08-20 08:00 | 2014-08-21 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2014-09-22 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
162 | schilderwerk pleisterwerk | 2014-10-01 08:00 | 2014-10-06 17:00 | 4d |  | 0 | 0 | 90.58 | 2898.5601 | 2898.5601 | 2014-10-20 08:00 | 4d | 2898.5601 | 0 | 0 | 0 | 0 | 2898.5601 | 0 | 100% | Finished | 2898.5601 | 2898.5601 | 100 | 100 | 100 | 100 | 100 | 100
163 | plafondtegels | 2014-10-07 08:00 | 2014-10-07 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2014-09-24 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
198 | Fase 2 | 2014-06-04 08:00 | 2015-02-25 17:00 | 191d |  |  | 0 |  |  | 101065.0415 |  | 102d | [5 empty] | 86521.6012 |  | 100% |  | 101065.0415 | 101065.0415
165 | inrichting winkel | 2014-09-29 08:00 | 2014-10-10 17:00 | 10d |  | 0 | 0 | 31.45 | 2516.0001 | 2516.0001 | 2014-09-30 08:00 | 10d | 2516.0001 | 0 | 0 | 0 | 0 | 2516.0001 | 0 | 100% | Finished | 2516.0001 | 2516.0001 | 100 | 100 | 100 | 100 | 100 | 100
166 | inrichting kantoor | 2014-10-08 08:00 | 2014-10-14 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-09 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
167 | ontmanteling bestaande winkel | 2014-10-13 08:00 | 2014-10-17 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-14 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
168 | sloop bestaande winkel | 2014-10-20 08:00 | 2014-10-24 17:00 | 5d |  | 0 | 0 | 31.45 | 1258 | 1258 | 2014-10-21 08:00 | 5d | 1258 | 0 | 0 | 0 | 0 | 1258 | 0 | 100% | Finished | 1258 | 1258 | 100 | 100 | 100 | 100 | 100 | 100
169 | voorlopige wand te behouden | 2014-10-21 08:00 | 2014-10-22 17:00 | 2d |  | 0 | 0 | 31.45 | 503.2 | 503.2 | 2014-10-22 08:00 | 2d | 503.2 | 0 | 0 | 0 | 0 | 503.2 | 0 | 100% | Finished | 503.2 | 503.2 | 100 | 100 | 100 | 100 | 100 | 100
170 | uitzetten assen en grondwerk | 2014-10-27 08:00 | 2014-10-27 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-12 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
171 | inzagen van bestaande beton | 2014-10-28 08:00 | 2014-10-29 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-13 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 50 | 100 | 100 | 50 | 100
172 | uitzetten paalfundering | 2014-10-30 08:00 | 2014-10-30 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-17 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
173 | maken van paalfundering | 2014-11-04 08:00 | 2014-11-05 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-19 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
174 | akoestisch doormeten | 2014-11-13 08:00 | 2014-11-13 17:00 | 1d |  | 0 | 0 | 166.19 | 1329.52 | 1329.52 | 2014-11-21 08:00 | 1d | 1329.52 | 0 | 0 | 0 | 0 | 1329.52 | 0 | 100% | Finished | 1329.52 | 1329.52 | 100 | 100 | 100 | 100 | 100 | 100
175 | maken van fundering | 2014-11-17 08:00 | 2014-11-18 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-11-24 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
176 | staalconstructie fase 2 | 2014-11-21 08:00 | 2014-11-24 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-11-28 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
177 | houten spanten | 2014-11-25 08:00 | 2014-11-26 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-02 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
178 | afmontage staal | 2014-11-27 08:00 | 2014-11-28 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-04 08:00 | 3d | 3836.64 | 0 | 0 | 0 | 0 | 3836.64 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 150 | 100 | 100 | 150 | 100
179 | prefabplinten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 159.86 | 2557.76 | 2557.76 | 2014-12-09 08:00 | 2d | 2557.76 | 0 | 0 | 0 | 0 | 2557.76 | 0 | 100% | Finished | 2557.76 | 2557.76 | 100 | 100 | 100 | 100 | 100 | 100
180 | voorbereidingen wand | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 114.61 | 1833.76 | 1833.76 | 2014-12-11 08:00 | 2d | 1833.76 | 0 | 0 | 0 | 0 | 1833.76 | 0 | 100% | Finished | 1833.76 | 1833.76 | 100 | 100 | 100 | 100 | 100 | 100
181 | sandwichwand | 2014-12-05 08:00 | 2014-12-10 17:00 | 4d |  | 0 | 0 | 114.61 | 3667.52 | 3667.52 | 2014-12-15 08:00 | 4d | 3667.52 | 0 | 0 | 0 | 0 | 3667.52 | 0 | 100% | Finished | 3667.52 | 3667.52 | 100 | 100 | 100 | 100 | 100 | 100
182 | veiligheidsnetten | 2014-12-01 08:00 | 2014-12-02 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-09 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
183 | dakplaten plaatsen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-10 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
184 | dakbedekking | 2014-12-04 08:00 | 2014-12-17 17:00 | 10d |  | 0 | 0 | 166.19 | 13295.2002 | 13295.2002 | 2014-12-15 08:00 | 10d | 13295.2002 | 0 | 0 | 0 | 0 | 13295.2002 | 0 | 100% | Finished | 13295.2002 | 13295.2002 | 100 | 100 | 100 | 100 | 100 | 100
185 | plaatsing rookluiken | 2014-12-25 08:00 | 2014-12-26 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-02-12 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
186 | plaatsing rookscherm | 2014-12-29 08:00 | 2014-12-30 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-02-16 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
187 | grondwerk blinde vlek | 2014-12-03 08:00 | 2014-12-04 17:00 | 2d |  | 0 | 0 | 166.19 | 2659.04 | 2659.04 | 2014-12-11 08:00 | 2d | 2659.04 | 0 | 0 | 0 | 0 | 2659.04 | 0 | 100% | Finished | 2659.04 | 2659.04 | 100 | 100 | 100 | 100 | 100 | 100
188 | ondervloer tussen gebouwen | 2014-12-03 08:00 | 2014-12-05 17:00 | 3d |  | 0 | 0 | 166.19 | 3988.5601 | 3988.5601 | 2014-12-11 08:00 | 3d | 3988.5601 | 0 | 0 | 0 | 0 | 3988.5601 | 0 | 100% | Finished | 3988.5601 | 3988.5601 | 100 | 100 | 100 | 100 | 100 | 100
189 | technieken onder dak | 2014-06-04 08:00 | 2014-06-12 17:00 | 7d |  | 0 | 0 | 118.75 | 6650 | 6650 | 2014-12-15 08:00 | 7d | 6650 | 0 | 0 | 0 | 0 | 6650 | 0 | 100% | Finished | 6650 | 6650 | 100 | 100 | 100 | 100 | 100 | 100
190 | uitvullaag | 2015-01-05 08:00 | 2015-01-06 17:00 | 2d |  | 0 | 0 | 90.58 | 1449.28 | 1449.28 | 2015-01-05 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 1449.28 | 1449.28 | 100 | 100 | 100 | 100 | 100 | 100
191 | stellen dillatieprofielen | 2015-01-14 08:00 | 2015-01-16 17:00 | 3d |  | 0 | 0 | 90.58 | 2173.92 | 2173.92 | 2015-01-14 08:00 | 2d | 1449.28 | 0 | 0 | 0 | 0 | 1449.28 | 0 | 100% | Finished | 2173.92 | 2173.92 | 100 | 66.6667 | 100 | 100 | 66.6667 | 100
192 | folie en vloerverwarming | 2015-01-14 08:00 | 2015-01-20 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-01-14 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
193 | polybetonvloer | 2015-01-21 08:00 | 2015-01-21 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2015-01-21 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
194 | afwerkingsformule beton | 2015-01-22 08:00 | 2015-01-22 17:00 | 1d |  | 0 | 0 | 90.58 | 724.64 | 724.64 | 2015-01-22 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 724.64 | 724.64 | 100 | 100 | 100 | 100 | 100 | 100
195 | afwerkingslaag beton | 2015-01-22 08:00 | 2015-02-18 17:00 | 20d |  | 0 | 0 | 90.58 | 14492.8003 | 14492.8003 | 2015-02-11 08:00 | 1d | 724.64 | 0 | 0 | 0 | 0 | 724.64 | 0 | 100% | Finished | 14492.8003 | 14492.8003 | 100 | 5 | 100 | 100 | 5 | 100
196 | afbouw technieken dak | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-02-12 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100
197 | winkelinrichting | 2015-02-19 08:00 | 2015-02-25 17:00 | 5d |  | 0 | 0 | 90.58 | 3623.2001 | 3623.2001 | 2015-02-12 08:00 | 5d | 3623.2001 | 0 | 0 | 0 | 0 | 3623.2001 | 0 | 100% | Finished | 3623.2001 | 3623.2001 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
08/07, 2014 | 2014-06-04 08:00 | 2014-07-08 17:00 | 90660.3207 | 103464.0017 | 103464.0009 | 2014-07-10 10:00 | 12803.681 | 114.1% | 0.00080642 | 100% | 1d 2h | 105% | 81.55% | 2015-02-18 15:00 | 2015-01-23 11:00 | 2015-01-23 11:00 | 2015-02-20 12:00 | 2015-01-23 11:00 | 2015-01-23 11:00 | 2015-02-24 15:00 | 2015-02-12 16:00 | 2015-02-12 16:00 | 467297.2044 | 467297.2016 | 422272.8076 | 449971.8138 | 422272.8051 | 449971.8111 | 457302.8846 | 463694.8933 | 1.05 | 1 | 1.1412 | 0.81549 | 1.25 | 1 | 1 | 1.05 | 1
12/08, 2014 | 2014-07-08 17:00 | 2014-08-12 17:00 | 188637.1214 | 190249.8415 | 190249.8415 | 2014-08-13 10:00 | 1612.7201 | 100.9% | 0 | 100% | 2h | 100.5% | 87.13% | 2015-02-25 11:00 | 2015-02-24 11:00 | 2015-02-24 11:00 | 2015-02-25 14:00 | 2015-02-24 11:00 | 2015-02-24 11:00 | 2015-02-25 15:00 | 2015-02-24 17:00 | 2015-02-24 17:00 | 467297.2052 | 467297.2052 | 464948.7152 | 465918.8601 | 464948.7152 | 465918.8601 | 466824.3002 | 467020.4346 | 1.005 | 1 | 1.0085 | 0.87127 | 0.25 | 1 | 1 | 1.005 | 1
16/09, 2014 | 2014-08-12 17:00 | 2014-09-16 17:00 | 325752.3229 | 308462.7226 | 317609.1227 | 2014-09-05 09:00 | -17289.6003 | 94.69% | -9146.4001 | 97.12% | -7d 7h | 89.5% | 94.71% | 2015-03-09 09:00 | 2015-03-12 15:00 | 2015-03-20 14:00 | 2015-03-03 17:00 | 2015-03-12 15:00 | 2015-03-18 12:00 | 2015-03-09 16:00 | 2015-03-30 11:00 | 2015-04-03 12:00 | 476443.6053 | 481153.2951 | 485346.4144 | 495077.8184 | 490320.0863 | 500340.0416 | 481975.0635 | 483760.6059 | 0.895 | 0.9712 | 0.94692 | 0.94714 | -7.875 | 0.9712 | 1 | 0.895 | 1
21/10, 2014 | 2014-09-16 17:00 | 2014-10-21 17:00 | 378668.9639 | 370066.4839 | 379212.884 | 2014-10-06 11:00 | -8602.48 | 97.73% | -9146.4001 | 97.59% | -11d 5h | 88.38% | 97.93% | 2015-03-03 12:00 | 2015-03-04 12:00 | 2015-03-11 10:00 | 2015-03-02 10:00 | 2015-03-04 12:00 | 2015-03-06 15:00 | 2015-03-13 14:00 | 2015-04-02 09:00 | 2015-04-06 17:00 | 476443.6054 | 478846.717 | 478703.8083 | 489233.5022 | 481162.7821 | 491952.7234 | 478818.1025 | 480764.16 | 0.88375 | 0.97588 | 0.97728 | 0.97933 | -11.625 | 0.97588 | 1 | 0.88375 | 1
25/11, 2014 | 2014-10-21 17:00 | 2014-11-25 17:00 | 395477.6841 | 384991.0441 | 392807.9242 | 2014-10-30 16:00 | -10486.64 | 97.35% | -7816.8801 | 98.01% | -18d 1h | 85.5% | 98.27% | 2015-03-04 10:00 | 2015-03-05 10:00 | 2015-03-11 09:00 | 2015-03-03 11:00 | 2015-03-05 10:00 | 2015-03-06 14:00 | 2015-03-24 09:00 | 2015-04-13 11:00 | 2015-04-15 11:00 | 475114.0854 | 476785.2343 | 477355.9949 | 489072.4402 | 479072.6637 | 491027.0004 | 476898.7691 | 478985.1676 | 0.855 | 0.9801 | 0.97348 | 0.98272 | -18.125 | 0.9801 | 1 | 0.855 | 1
30/12, 2014 | 2014-11-25 17:00 | 2014-12-30 17:00 | 436862.3246 | 433963.7646 | 443059.5247 | 2014-12-24 17:00 | -2898.5601 | 99.34% | -9095.7601 | 97.95% | -4d | 97.33% | 100% | 2015-02-27 09:00 | 2015-02-27 10:00 | 2015-03-05 10:00 | 2015-02-26 17:00 | 2015-02-27 10:00 | 2015-03-02 09:00 | 2015-03-03 17:00 | 2015-03-05 10:00 | 2015-03-06 10:00 | 476392.9654 | 477091.625 | 476615.6083 | 477306.2103 | 477318.9345 | 478024.0113 | 476995.3443 | 477134.3267 | 0.97333 | 0.97947 | 0.99337 | 1 | -4 | 0.97947 | 1 | 0.97333 | 1
03/02, 2015 | 2014-12-30 17:00 | 2015-02-03 17:00 | 452079.7649 | 442659.4447 | 451030.5648 | 2015-01-16 17:00 | -9420.3202 | 97.92% | -8371.1201 | 98.14% | -12d | 93.14% | 99.35% | 2015-03-03 16:00 | 2015-03-04 09:00 | 2015-03-09 15:00 | 2015-03-03 14:00 | 2015-03-04 09:00 | 2015-03-04 12:00 | 2015-03-13 17:00 | 2015-03-17 17:00 | 2015-03-18 14:00 | 475668.3253 | 476134.2493 | 476192.6462 | 477482.1482 | 476668.4856 | 477982.3733 | 476145.907 | 476392.7263 | 0.93143 | 0.98144 | 0.97916 | 0.99345 | -12 | 0.98144 | 1 | 0.93143 | 1
Actual Schedule | 2015-02-03 17:00 | 2015-03-10 17:00 | 467297.2052 | 467297.2052 | 461900.1651 | 2015-02-25 17:00 | 0 | 100% | 5397.0402 | 101.2% | -9d | 95.5% | 100% | 2015-02-25 17:00 | 2015-02-25 17:00 | 2015-02-23 15:00 | 2015-03-10 17:00 | 2015-03-10 17:00 | 2015-03-10 17:00 | 2015-03-10 17:00 | 2015-03-10 17:00 | 2015-03-10 17:00 | 461900.1651 | 461900.1651 | 461900.1651 | 461900.1651 | 461900.1651 | 461900.1651 | 461900.1651 | 461900.1651 | 0.955 | 1.0117 | 1 | 1 | -9 | 1.0117 | 1 | 0.955 | 1