## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Premium Payment System | 1 |  |  | 2014-01-28 08:00 | 2014-10-10 17:00 | 184d |  |  | 0 |  |  | 132570 | 255.375
67 | supporting tasks | 1.1 |  |  | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h |  |  | 0 |  |  | 44145 | 44.3333
1 | project management | 1.1.1 |  | FS55 | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h | Employee A | 23670 | 0 | 0 | 0 | 23670 | 44.3333
2 | validation and support | 1.1.2 |  | FS55 | 2014-02-10 08:00 | 2014-02-25 10:00 | 11d 2h | Employee C | 6750 | 0 | 0 | 0 | 6750 | 15.0833
3 | validation and support | 1.1.3 |  | FS55 | 2014-02-10 08:00 | 2014-02-19 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 9.1667
4 | validation and support | 1.1.4 |  | FS55 | 2014-02-10 08:00 | 2014-02-10 15:00 | 6h | Employee H | 450 | 0 | 0 | 0 | 450 | 0.29167
5 | validation and support | 1.1.5 |  | FS55 | 2014-02-10 08:00 | 2014-02-12 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2.3333
6 | validation and support | 1.1.6 |  | FS55 | 2014-02-10 08:00 | 2014-02-17 11:00 | 5d 3h | Employee J | 3225 | 0 | 0 | 0 | 3225 | 7.125
7 | validation and support | 1.1.7 |  | FS55 | 2014-02-10 08:00 | 2014-02-18 10:00 | 6d 2h | Employee K | 3750 | 0 | 0 | 0 | 3750 | 8.0833
8 | validation and support | 1.1.8 |  | FS55 | 2014-02-10 08:00 | 2014-02-10 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 0.041667
68 | analysis | 1.2 |  |  | 2014-02-11 08:00 | 2014-04-25 17:00 | 54d |  |  | 0 |  |  | 22200 | 73.375
9 | analysis - aanpassing aanbieding | 1.2.1 |  | FS16 | 2014-02-11 08:00 | 2014-02-24 15:00 | 9d 6h | Employee G | 5850 | 0 | 0 | 0 | 5850 | 13.2917
10 | analysis - boeking teruggave | 1.2.2 |  | FS16 | 2014-02-17 08:00 | 2014-02-21 09:00 | 4d 1h | Employee C | 2475 | 0 | 0 | 0 | 2475 | 4.0417
11 | analysis - convertie teruggaves | 1.2.3 |  | FS16 | 2014-02-17 08:00 | 2014-02-25 14:00 | 6d 5h | Employee K | 3975 | 0 | 0 | 0 | 3975 | 8.25
14 | analysis - lay-out brief | 1.2.4 |  | FS16 | 2014-02-17 08:00 | 2014-02-27 17:00 | 9d | Employee K | 5400 | 0 | 0 | 0 | 5400 | 10.375
15 | analysis - methode fractioneren | 1.2.5 |  | FS16 | 2014-02-11 08:00 | 2014-02-12 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 1.2917
16 | analysis - proces opzetten | 1.2.6 | 9FS;10FS;11FS;14FS;15FS | FS17 | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 0.375
17 | analysis - stopzetten afbetalingsplan | 1.2.7 | 16FS | FS18 | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 4.2917
18 | analysis validated | 1.2.8 | 17FS | FS55 | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
69 | design | 1.3 |  |  | 2014-02-10 08:00 | 2014-05-29 17:00 | 79d |  |  | 0 |  |  | 29175 | 108.375
19 | design - aanleveren input | 1.3.1 | 21FS | FS28 | 2014-03-17 08:00 | 2014-03-26 12:00 | 7d 4h | Employee I | 4500 | 0 | 0 | 0 | 4500 | 9.1667
20 | design - aanpassingen aanbieding | 1.3.2 | 21FS | FS28 | 2014-03-17 08:00 | 2014-03-25 14:00 | 6d 5h | Employee E | 3975 | 0 | 0 | 0 | 3975 | 8.25
21 | design - boeking teruggave | 1.3.3 | 29FS | FS19;FS20;FS25 | 2014-03-10 08:00 | 2014-03-14 15:00 | 4d 6h | Employee E | 2850 | 0 | 0 | 0 | 2850 | 4.2917
22 | design - convertie teruggaves | 1.3.4 | 28FS | FS30 | 2014-05-05 08:00 | 2014-05-08 15:00 | 3d 6h | Employee E | 2250 | 0 | 0 | 0 | 2250 | 3.2917
23 | design - creatie artikels | 1.3.5 | 29FS |  | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 0.375
24 | design - impact op andere progs | 1.3.6 |  | FS29 | 2014-02-10 08:00 | 2014-02-17 12:00 | 5d 4h | Employee L | 3300 | 0 | 0 | 0 | 3300 | 7.1667
25 | design - lay-out brief | 1.3.7 | 21FS | FS28 | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 4.2917
26 | design - mailoptie | 1.3.8 | 28FS | FS30 | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee I | 1125 | 0 | 0 | 0 | 1125 | 1.3333
27 | design - methode fractioneren | 1.3.9 |  | FS29 | 2014-02-11 08:00 | 2014-02-14 12:00 | 3d 4h | Employee E | 2100 | 0 | 0 | 0 | 2100 | 3.1667
28 | design - opzet OMS | 1.3.10 | 19FS;20FS;25FS | FS22;FS26 | 2014-04-07 08:00 | 2014-04-08 16:00 | 1d 7h | Employee M | 1125 | 0 | 0 | 0 | 1125 | 1.3333
29 | design - proces opzetten | 1.3.11 | 27FS;24FS | FS23;FS21 | 2014-03-06 08:00 | 2014-03-07 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 1.0833
30 | design - stopzetting afbetalingsplan | 1.3.12 | 22FS;26FS | FS31 | 2014-05-21 08:00 | 2014-05-29 10:00 | 6d 2h | Employee E | 3750 | 0 | 0 | 0 | 3750 | 8.0833
31 | design validated | 1.3.13 | 30FS | FS55 | 2014-05-29 17:00 | 2014-05-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
70 | development | 1.4 |  |  | 2014-02-11 08:00 | 2014-09-26 17:00 | 164d |  |  | 0 |  |  | 25800 | 227.375
33 | development - boeking teruggave | 1.4.1 | 40FS | FS37 | 2014-04-07 08:00 | 2014-04-15 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 8.25
35 | development - impact op andere progs | 1.4.2 |  | FS38 | 2014-02-11 08:00 | 2014-03-03 11:00 | 14d 3h | Employee N | 8625 | 0 | 0 | 0 | 8625 | 20.125
36 | development - landscape document voorzien | 1.4.3 |  | FS38 | 2014-02-11 08:00 | 2014-02-17 16:00 | 4d 7h | Employee O | 2925 | 0 | 0 | 0 | 2925 | 6.3333
37 | development - lay-out brief | 1.4.4 | 33FS |  | 2014-04-28 08:00 | 2014-05-02 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 4.2917
38 | development - methode fractioneren | 1.4.5 | 35FS;36FS | FS40 | 2014-03-10 08:00 | 2014-03-18 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 8.25
40 | development - proces opzetten | 1.4.6 | 38FS | FS33 | 2014-03-31 08:00 | 2014-04-02 16:00 | 2d 7h | Employee Q | 1725 | 0 | 0 | 0 | 1725 | 2.3333
42 | development - impact op andere progs | 1.4.7 |  |  | 2014-07-07 08:00 | 2014-07-09 16:00 | 2d 7h | Employee M | 1725 | 0 | 0 | 0 | 1725 | 2.3333
46 | development completed | 1.4.8 |  | FS55 | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
71 | test ict | 1.5 |  |  | 2014-06-02 08:00 | 2014-08-29 17:00 | 65d |  |  | 0 |  |  | 11250 | 88.375
49 | test ict - preparation | 1.5.1 |  |  | 2014-06-02 08:00 | 2014-06-26 15:00 | 18d 6h | Employee E | 11250 | 0 | 0 | 0 | 11250 | 24.2917
50 | ict test completed | 1.5.2 |  | FS55 | 2014-08-29 17:00 | 2014-08-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
72 | implementation | 1.6 |  |  | 2014-07-01 17:00 | 2014-10-10 17:00 | 73d |  |  | 0 |  |  | 0 | 101
51 | uat | 1.6.1 |  | FS55 | 2014-07-01 17:00 | 2014-07-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
52 | code freeze | 1.6.2 |  | FS55 | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
55 | go live | 1.6.3 | 1FS;2FS;3FS;4FS;5FS;6FS;7FS;8FS;18FS;31FS;46FS;50FS;51FS;52FS |  | 2014-10-10 17:00 | 2014-10-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Employee A | Renewable | 1 | 0 | 90 | 1; | 23670
2 | Employee B | Renewable | 1 | 0 | 75 | 8; | 75
3 | Employee C | Renewable | 1 | 0 | 75 | 2;10; | 9225
4 | Employee D | Renewable | 1 | 0 | 75 |  | 0
5 | Employee E | Renewable | 1 | 0 | 75 | 20;21;22;27;30;49; | 26175
6 | Employee F | Renewable | 1 | 0 | 75 |  | 0
7 | Employee G | Renewable | 1 | 0 | 75 | 3;9;15; | 11400
8 | Employee H | Renewable | 1 | 0 | 75 | 4; | 450
9 | Employee I | Renewable | 1 | 0 | 75 | 5;19;26;29; | 8100
10 | Employee J | Renewable | 1 | 0 | 75 | 6; | 3225
11 | Employee K | Renewable | 1 | 0 | 75 | 7;11;14;16;17; | 16575
12 | Employee L | Renewable | 1 | 0 | 75 | 23;24;33;38; | 11850
13 | Employee M | Renewable | 1 | 0 | 75 | 25;28;37;42; | 8550
14 | Employee N | Renewable | 1 | 0 | 75 | 35; | 8625
15 | Employee O | Renewable | 1 | 0 | 75 | 36; | 2925
16 | Employee P | Renewable | 1 | 0 | 75 |  | 0
17 | Employee Q | Renewable | 1 | 0 | 75 | 40; | 1725

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Premium Payment System | 1472h |  |  |  |  | 99 | 100 | 101
67 | supporting tasks | 263h |  |  |  |  | 99 | 100 | 101
1 | project management | 263h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | validation and support | 90h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | validation and support | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | validation and support | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | validation and support | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | validation and support | 43h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | validation and support | 50h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | validation and support | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
68 | analysis | 432h |  |  |  |  | 99 | 100 | 101
9 | analysis - aanpassing aanbieding | 78h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | analysis - boeking teruggave | 33h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | analysis - convertie teruggaves | 53h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | analysis - lay-out brief | 72h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | analysis - methode fractioneren | 14h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | analysis - proces opzetten | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | analysis - stopzetten afbetalingsplan | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | analysis validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | design | 632h |  |  |  |  | 99 | 100 | 101
19 | design - aanleveren input | 60h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | design - aanpassingen aanbieding | 53h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | design - boeking teruggave | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
22 | design - convertie teruggaves | 30h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | design - creatie artikels | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | design - impact op andere progs | 44h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | design - lay-out brief | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | design - mailoptie | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | design - methode fractioneren | 28h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | design - opzet OMS | 15h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | design - proces opzetten | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | design - stopzetting afbetalingsplan | 50h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | design validated | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
70 | development | 1312h |  |  |  |  | 99 | 100 | 101
33 | development - boeking teruggave | 53h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | development - impact op andere progs | 115h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | development - landscape document voorzien | 39h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | development - lay-out brief | 38h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | development - methode fractioneren | 53h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | development - proces opzetten | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | development - impact op andere progs | 23h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
46 | development completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | test ict | 520h |  |  |  |  | 99 | 100 | 101
49 | test ict - preparation | 150h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
50 | ict test completed | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
72 | implementation | 584h |  |  |  |  | 99 | 100 | 101
51 | uat | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
52 | code freeze | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
55 | go live | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2014-02-24 22:00 |  | TP Name | Tracking 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Premium Payment System | 2014-01-28 08:00 | 2014-10-10 17:00 | 184d |  |  | 0 |  |  | 132570 |  | 20d | [5 empty] | 13995 |  | 21.16% |  | 28045.7999 | 65625
67 | supporting tasks | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h |  |  | 0 |  |  | 44145 |  | 20d | [5 empty] | 3195 |  | 25.9% |  | 11432.5499 | 34725
1 | project management | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h | Employee A | 23670 | 0 | 0 | 0 | 23670 | 2014-01-28 08:00 | 1d 5h | 1170 | 7650 | 10d 5h | 0 | 0 | 1170 | 7650 | 24% | Started | 5680.7999 | 14400 | 100 | 4.943 | 24 | 100 | 4.943 | 24
2 | validation and support | 2014-02-10 08:00 | 2014-02-25 10:00 | 11d 2h | Employee C | 6750 | 0 | 0 | 0 | 6750 |  | 0 | 0 | 6750 | 11d 2h | 0 | 0 | 0 | 6750 | 0% | Not Started | 0 | 6600 | 100 |  | 0 | 100 |  | 0
3 | validation and support | 2014-02-10 08:00 | 2014-02-19 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 2014-02-10 08:00 | 6h | 450 | 75 | 1h | 0 | 0 | 450 | 75 | 28% | Started | 1260 | 4500 | 100 | 10 | 28 | 100 | 10 | 28
4 | validation and support | 2014-02-10 08:00 | 2014-02-10 15:00 | 6h | Employee H | 450 | 0 | 0 | 0 | 450 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 450 | 450 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
5 | validation and support | 2014-02-10 08:00 | 2014-02-12 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2014-02-24 08:00 | 6h | 450 | 2700 | 4d 4h | 0 | 0 | 450 | 2700 | 15% | Started | 258.75 | 1725 | 100 | 26.087 | 15 | 100 | 26.087 | 15
6 | validation and support | 2014-02-10 08:00 | 2014-02-17 11:00 | 5d 3h | Employee J | 3225 | 0 | 0 | 0 | 3225 |  | 0 | 0 | 3225 | 5d 3h | 0 | 0 | 0 | 3225 | 0% | Not Started | 0 | 3225 | 100 |  | 0 | 100 |  | 0
7 | validation and support | 2014-02-10 08:00 | 2014-02-18 10:00 | 6d 2h | Employee K | 3750 | 0 | 0 | 0 | 3750 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 3750 | 3750 | 100 | 2 | 100 | 100 | 2 | 100
8 | validation and support | 2014-02-10 08:00 | 2014-02-10 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-02-10 08:00 | 1d 5h | 975 | 2475 | 4d 1h | 0 | 0 | 975 | 2475 | 44% | Started | 33 | 75 | 100 | 1300 | 44 | 100 | 1300 | 44
68 | analysis | 2014-02-11 08:00 | 2014-04-25 17:00 | 54d |  |  | 0 |  |  | 22200 |  | 11d | [5 empty] | 5475 |  | 19.71% |  | 4374.75 | 16575
9 | analysis - aanpassing aanbieding | 2014-02-11 08:00 | 2014-02-24 15:00 | 9d 6h | Employee G | 5850 | 0 | 0 | 0 | 5850 | 2014-02-10 08:00 | 3h | 225 | 375 | 5h | 0 | 0 | 225 | 375 | 10% | Started | 585 | 5850 | 100 | 3.8462 | 10 | 100 | 3.8462 | 10
10 | analysis - boeking teruggave | 2014-02-17 08:00 | 2014-02-21 09:00 | 4d 1h | Employee C | 2475 | 0 | 0 | 0 | 2475 | 2014-02-17 08:00 | 1d 6h | 1050 | 75 | 1h | 0 | 0 | 1050 | 75 | 47% | Started | 1163.25 | 2475 | 100 | 42.4242 | 47 | 100 | 42.4242 | 47
11 | analysis - convertie teruggaves | 2014-02-17 08:00 | 2014-02-25 14:00 | 6d 5h | Employee K | 3975 | 0 | 0 | 0 | 3975 |  | 0 | 0 | 3975 | 6d 5h | 0 | 0 | 0 | 3975 | 0% | Not Started | 0 | 3600 | 100 |  | 0 | 100 |  | 0
14 | analysis - lay-out brief | 2014-02-17 08:00 | 2014-02-27 17:00 | 9d | Employee K | 5400 | 0 | 0 | 0 | 5400 | 2014-02-17 08:00 | 6d | 3600 | 1875 | 3d 1h | 0 | 0 | 3600 | 1875 | 43% | Started | 2322 | 3600 | 100 | 66.6667 | 43 | 100 | 66.6667 | 43
15 | analysis - methode fractioneren | 2014-02-11 08:00 | 2014-02-12 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-10 08:00 | 1d | 600 | 2250 | 3d 6h | 0 | 0 | 600 | 2250 | 29% | Started | 304.5 | 1050 | 100 | 57.1429 | 29 | 100 | 57.1429 | 29
16 | analysis - proces opzetten | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | analysis - stopzetten afbetalingsplan | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | analysis validated | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | design | 2014-02-10 08:00 | 2014-05-29 17:00 | 79d |  |  | 0 |  |  | 29175 |  | 11d | [5 empty] | 5100 |  | 13.59% |  | 3965.9999 | 5400
19 | design - aanleveren input | 2014-03-17 08:00 | 2014-03-26 12:00 | 7d 4h | Employee I | 4500 | 0 | 0 | 0 | 4500 |  | 0 | 0 | 4500 | 7d 4h | 0 | 0 | 0 | 4500 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | design - aanpassingen aanbieding | 2014-03-17 08:00 | 2014-03-25 14:00 | 6d 5h | Employee E | 3975 | 0 | 0 | 0 | 3975 |  | 0 | 0 | 3975 | 6d 5h | 0 | 0 | 0 | 3975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | design - boeking teruggave | 2014-03-10 08:00 | 2014-03-14 15:00 | 4d 6h | Employee E | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | design - convertie teruggaves | 2014-05-05 08:00 | 2014-05-08 15:00 | 3d 6h | Employee E | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | design - creatie artikels | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 |  | 0 | 0 | 600 | 1d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | design - impact op andere progs | 2014-02-10 08:00 | 2014-02-17 12:00 | 5d 4h | Employee L | 3300 | 0 | 0 | 0 | 3300 | 2014-02-10 08:00 | 5d 4h | 3300 | 75 | 1h | 0 | 0 | 3300 | 75 | 96% | Started | 3167.9999 | 3300 | 100 | 100 | 96 | 100 | 100 | 96
25 | design - lay-out brief | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | design - mailoptie | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee I | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | design - methode fractioneren | 2014-02-11 08:00 | 2014-02-14 12:00 | 3d 4h | Employee E | 2100 | 0 | 0 | 0 | 2100 | 2014-02-10 08:00 | 3d | 1800 | 225 | 3h | 0 | 0 | 1800 | 225 | 38% | Started | 798 | 2100 | 100 | 85.7143 | 38 | 100 | 85.7143 | 38
28 | design - opzet OMS | 2014-04-07 08:00 | 2014-04-08 16:00 | 1d 7h | Employee M | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | design - proces opzetten | 2014-03-06 08:00 | 2014-03-07 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 |  | 0 | 0 | 750 | 1d 2h | 0 | 0 | 0 | 750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | design - stopzetting afbetalingsplan | 2014-05-21 08:00 | 2014-05-29 10:00 | 6d 2h | Employee E | 3750 | 0 | 0 | 0 | 3750 |  | 0 | 0 | 3750 | 6d 2h | 0 | 0 | 0 | 3750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | design validated | 2014-05-29 17:00 | 2014-05-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | development | 2014-02-11 08:00 | 2014-09-26 17:00 | 164d |  |  | 0 |  |  | 25800 |  | 11d | [5 empty] | 225 |  | 32.06% |  | 8272.5 | 8925
33 | development - boeking teruggave | 2014-04-07 08:00 | 2014-04-15 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 |  | 0 | 0 | 3975 | 6d 5h | 0 | 0 | 0 | 3975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | development - impact op andere progs | 2014-02-11 08:00 | 2014-03-03 11:00 | 14d 3h | Employee N | 8625 | 0 | 0 | 0 | 8625 | 2014-02-10 08:00 | 2h | 150 | 675 | 1d 1h | 0 | 0 | 150 | 675 | 62% | Started | 5347.5 | 6000 | 100 | 1.7391 | 62 | 100 | 1.7391 | 62
36 | development - landscape document voorzien | 2014-02-11 08:00 | 2014-02-17 16:00 | 4d 7h | Employee O | 2925 | 0 | 0 | 0 | 2925 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2925 | 2925 | 100 | 2.5641 | 100 | 100 | 2.5641 | 100
37 | development - lay-out brief | 2014-04-28 08:00 | 2014-05-02 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | development - methode fractioneren | 2014-03-10 08:00 | 2014-03-18 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 |  | 0 | 0 | 3975 | 6d 5h | 0 | 0 | 0 | 3975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
40 | development - proces opzetten | 2014-03-31 08:00 | 2014-04-02 16:00 | 2d 7h | Employee Q | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | development - impact op andere progs | 2014-07-07 08:00 | 2014-07-09 16:00 | 2d 7h | Employee M | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | development completed | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | test ict | 2014-06-02 08:00 | 2014-08-29 17:00 | 65d |  |  | 0 |  |  | 11250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | test ict - preparation | 2014-06-02 08:00 | 2014-06-26 15:00 | 18d 6h | Employee E | 11250 | 0 | 0 | 0 | 11250 |  | 0 | 0 | 11250 | 18d 6h | 0 | 0 | 0 | 11250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | ict test completed | 2014-08-29 17:00 | 2014-08-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | implementation | 2014-07-01 17:00 | 2014-10-10 17:00 | 73d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | uat | 2014-07-01 17:00 | 2014-07-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | code freeze | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | go live | 2014-10-10 17:00 | 2014-10-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2014-03-31 22:00 |  | TP Name | Tracking 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Premium Payment System | 2014-01-28 08:00 | 2014-10-10 17:00 | 184d |  |  | 0 |  |  | 132570 |  | 45d | [5 empty] | 47835 |  | 69.37% |  | 91958.7003 | 103395
67 | supporting tasks | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h |  |  | 0 |  |  | 44145 |  | 45d | [5 empty] | 10110 |  | 88.52% |  | 39078.4501 | 44145
1 | project management | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h | Employee A | 23670 | 0 | 0 | 0 | 23670 | 2014-01-28 08:00 | 5d 4h | 3960 | 4860 | 6d 6h | 0 | 0 | 3960 | 4860 | 81% | Started | 19172.7001 | 23670 | 100 | 16.73 | 81 | 100 | 16.73 | 81
2 | validation and support | 2014-02-10 08:00 | 2014-02-25 10:00 | 11d 2h | Employee C | 6750 | 0 | 0 | 0 | 6750 | 2014-03-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 6750 | 6750 | 100 | 2.2222 | 100 | 100 | 2.2222 | 100
3 | validation and support | 2014-02-10 08:00 | 2014-02-19 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 2014-02-10 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 4500 | 4500 | 100 | 36.6667 | 100 | 100 | 36.6667 | 100
4 | validation and support | 2014-02-10 08:00 | 2014-02-10 15:00 | 6h | Employee H | 450 | 0 | 0 | 0 | 450 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 450 | 450 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
5 | validation and support | 2014-02-10 08:00 | 2014-02-12 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2014-02-24 08:00 | 3d | 1800 | 1350 | 2d 2h | 0 | 0 | 1800 | 1350 | 67% | Started | 1155.75 | 1725 | 100 | 104.3478 | 67 | 100 | 104.3478 | 67
6 | validation and support | 2014-02-10 08:00 | 2014-02-17 11:00 | 5d 3h | Employee J | 3225 | 0 | 0 | 0 | 3225 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 3225 | 3225 | 100 | 6.9767 | 100 | 100 | 6.9767 | 100
7 | validation and support | 2014-02-10 08:00 | 2014-02-18 10:00 | 6d 2h | Employee K | 3750 | 0 | 0 | 0 | 3750 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 3750 | 3750 | 100 | 2 | 100 | 100 | 2 | 100
8 | validation and support | 2014-02-10 08:00 | 2014-02-10 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-02-10 08:00 | 3d 5h | 2175 | 0 | 0 | 0 | 0 | 2175 | 0 | 100% | Finished | 75 | 75 | 100 | 2900 | 100 | 100 | 2900 | 100
68 | analysis | 2014-02-11 08:00 | 2014-04-25 17:00 | 54d |  |  | 0 |  |  | 22200 |  | 36d | [5 empty] | 18525 |  | 87.91% |  | 19516.5002 | 22200
9 | analysis - aanpassing aanbieding | 2014-02-11 08:00 | 2014-02-24 15:00 | 9d 6h | Employee G | 5850 | 0 | 0 | 0 | 5850 | 2014-02-10 08:00 | 2d 5h | 1575 | 75 | 1h | 0 | 0 | 1575 | 75 | 80% | Started | 4680.0001 | 5850 | 100 | 26.9231 | 80 | 100 | 26.9231 | 80
10 | analysis - boeking teruggave | 2014-02-17 08:00 | 2014-02-21 09:00 | 4d 1h | Employee C | 2475 | 0 | 0 | 0 | 2475 | 2014-02-17 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2475 | 2475 | 100 | 90.9091 | 100 | 100 | 90.9091 | 100
11 | analysis - convertie teruggaves | 2014-02-17 08:00 | 2014-02-25 14:00 | 6d 5h | Employee K | 3975 | 0 | 0 | 0 | 3975 | 2014-03-17 08:00 | 6d 2h | 3750 | 3000 | 5d | 0 | 0 | 3750 | 3000 | 66% | Started | 2623.5001 | 3975 | 100 | 94.3396 | 66 | 100 | 94.3396 | 66
14 | analysis - lay-out brief | 2014-02-17 08:00 | 2014-02-27 17:00 | 9d | Employee K | 5400 | 0 | 0 | 0 | 5400 | 2014-02-17 08:00 | 14d 3h | 8625 | 0 | 0 | 0 | 0 | 8625 | 0 | 100% | Finished | 5400 | 5400 | 100 | 159.7222 | 100 | 100 | 159.7222 | 100
15 | analysis - methode fractioneren | 2014-02-11 08:00 | 2014-02-12 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-10 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 100% | Finished | 1050 | 1050 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
16 | analysis - proces opzetten | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 4h | 300 | 825 | 1d 3h | 0 | 0 | 300 | 825 | 73% | Started | 438 | 600 | 100 | 50 | 73 | 100 | 50 | 73
17 | analysis - stopzetten afbetalingsplan | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2850 | 2850 | 100 | 2.6316 | 100 | 100 | 2.6316 | 100
18 | analysis validated | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | design | 2014-02-10 08:00 | 2014-05-29 17:00 | 79d |  |  | 0 |  |  | 29175 |  | 36d | [5 empty] | 15825 |  | 55.23% |  | 16113.75 | 20925
19 | design - aanleveren input | 2014-03-17 08:00 | 2014-03-26 12:00 | 7d 4h | Employee I | 4500 | 0 | 0 | 0 | 4500 | 2014-03-17 08:00 | 3d 7h | 2325 | 1350 | 2d 2h | 0 | 0 | 2325 | 1350 | 68% | Started | 3060 | 4500 | 100 | 51.6667 | 68 | 100 | 51.6667 | 68
20 | design - aanpassingen aanbieding | 2014-03-17 08:00 | 2014-03-25 14:00 | 6d 5h | Employee E | 3975 | 0 | 0 | 0 | 3975 | 2014-03-17 08:00 | 1d | 600 | 3375 | 5d 5h | 0 | 0 | 600 | 3375 | 36% | Started | 1431.0001 | 3975 | 100 | 15.0943 | 36 | 100 | 15.0943 | 36
21 | design - boeking teruggave | 2014-03-10 08:00 | 2014-03-14 15:00 | 4d 6h | Employee E | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 1d 4h | 900 | 1950 | 3d 2h | 0 | 0 | 900 | 1950 | 39% | Started | 1111.5 | 2850 | 100 | 31.5789 | 39 | 100 | 31.5789 | 39
22 | design - convertie teruggaves | 2014-05-05 08:00 | 2014-05-08 15:00 | 3d 6h | Employee E | 2250 | 0 | 0 | 0 | 2250 |  | 0 | 0 | 2250 | 3d 6h | 0 | 0 | 0 | 2250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | design - creatie artikels | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 2014-03-31 08:00 | 1h | 75 | 1050 | 1d 6h | 0 | 0 | 75 | 1050 | 85% | Started | 510 | 600 | 100 | 12.5 | 85 | 100 | 12.5 | 85
24 | design - impact op andere progs | 2014-02-10 08:00 | 2014-02-17 12:00 | 5d 4h | Employee L | 3300 | 0 | 0 | 0 | 3300 | 2014-02-10 08:00 | 5d 5h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 100% | Finished | 3300 | 3300 | 100 | 102.2727 | 100 | 100 | 102.2727 | 100
25 | design - lay-out brief | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 2014-03-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 2850 | 2850 | 100 | 5.2632 | 100 | 100 | 5.2632 | 100
26 | design - mailoptie | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee I | 1125 | 0 | 0 | 0 | 1125 |  | 0 | 0 | 1125 | 1d 7h | 0 | 0 | 0 | 1125 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | design - methode fractioneren | 2014-02-11 08:00 | 2014-02-14 12:00 | 3d 4h | Employee E | 2100 | 0 | 0 | 0 | 2100 | 2014-02-10 08:00 | 7d 7h | 4725 | 0 | 0 | 0 | 0 | 4725 | 0 | 100% | Finished | 2100 | 2100 | 100 | 225 | 100 | 100 | 225 | 100
28 | design - opzet OMS | 2014-04-07 08:00 | 2014-04-08 16:00 | 1d 7h | Employee M | 1125 | 0 | 0 | 0 | 1125 | 2014-03-17 08:00 | 3d 7h | 2325 | 75 | 1h | 0 | 0 | 2325 | 75 | 89% | Started | 1001.25 | 0 | 100 | 206.6667 | 89 | 100 | 206.6667 | 89
29 | design - proces opzetten | 2014-03-06 08:00 | 2014-03-07 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 2014-03-03 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 750 | 750 | 100 | 180 | 100 | 100 | 180 | 100
30 | design - stopzetting afbetalingsplan | 2014-05-21 08:00 | 2014-05-29 10:00 | 6d 2h | Employee E | 3750 | 0 | 0 | 0 | 3750 |  | 0 | 0 | 3750 | 6d 2h | 0 | 0 | 0 | 3750 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | design validated | 2014-05-29 17:00 | 2014-05-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | development | 2014-02-11 08:00 | 2014-09-26 17:00 | 164d |  |  | 0 |  |  | 25800 |  | 36d | [5 empty] | 3375 |  | 66.86% |  | 17250 | 16125
33 | development - boeking teruggave | 2014-04-07 08:00 | 2014-04-15 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 |  | 0 | 0 | 3975 | 6d 5h | 0 | 0 | 0 | 3975 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | development - impact op andere progs | 2014-02-11 08:00 | 2014-03-03 11:00 | 14d 3h | Employee N | 8625 | 0 | 0 | 0 | 8625 | 2014-02-10 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 8625 | 8625 | 100 | 3.4783 | 100 | 100 | 3.4783 | 100
36 | development - landscape document voorzien | 2014-02-11 08:00 | 2014-02-17 16:00 | 4d 7h | Employee O | 2925 | 0 | 0 | 0 | 2925 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2925 | 2925 | 100 | 2.5641 | 100 | 100 | 2.5641 | 100
37 | development - lay-out brief | 2014-04-28 08:00 | 2014-05-02 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 |  | 0 | 0 | 2850 | 4d 6h | 0 | 0 | 0 | 2850 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | development - methode fractioneren | 2014-03-10 08:00 | 2014-03-18 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 2014-03-10 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 3975 | 3975 | 100 | 73.5849 | 100 | 100 | 73.5849 | 100
40 | development - proces opzetten | 2014-03-31 08:00 | 2014-04-02 16:00 | 2d 7h | Employee Q | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1725 | 600 | 100 | 4.3478 | 100 | 100 | 4.3478 | 100
42 | development - impact op andere progs | 2014-07-07 08:00 | 2014-07-09 16:00 | 2d 7h | Employee M | 1725 | 0 | 0 | 0 | 1725 |  | 0 | 0 | 1725 | 2d 7h | 0 | 0 | 0 | 1725 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | development completed | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | test ict | 2014-06-02 08:00 | 2014-08-29 17:00 | 65d |  |  | 0 |  |  | 11250 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
49 | test ict - preparation | 2014-06-02 08:00 | 2014-06-26 15:00 | 18d 6h | Employee E | 11250 | 0 | 0 | 0 | 11250 |  | 0 | 0 | 11250 | 18d 6h | 0 | 0 | 0 | 11250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | ict test completed | 2014-08-29 17:00 | 2014-08-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | implementation | 2014-07-01 17:00 | 2014-10-10 17:00 | 73d |  |  | 0 |  |  | 0 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | uat | 2014-07-01 17:00 | 2014-07-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | code freeze | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
55 | go live | 2014-10-10 17:00 | 2014-10-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2014-10-13 08:00 |  | TP Name | Closure
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Premium Payment System | 2014-01-28 08:00 | 2014-10-10 17:00 | 184d |  |  | 0 |  |  | 132570 |  | 183d 7h | [5 empty] | 58410 |  | 100% |  | 132570 | 132570
67 | supporting tasks | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h |  |  | 0 |  |  | 44145 |  | 34d 3h | [5 empty] | 11910 |  | 100% |  | 44145 | 44145
1 | project management | 2014-01-28 08:00 | 2014-03-13 16:00 | 32d 7h | Employee A | 23670 | 0 | 0 | 0 | 23670 | 2014-01-28 08:00 | 6d 6h | 4860 | 0 | 0 | 0 | 0 | 4860 | 0 | 100% | Finished | 23670 | 23670 | 100 | 20.5323 | 100 | 100 | 20.5323 | 100
2 | validation and support | 2014-02-10 08:00 | 2014-02-25 10:00 | 11d 2h | Employee C | 6750 | 0 | 0 | 0 | 6750 | 2014-03-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 6750 | 6750 | 100 | 2.2222 | 100 | 100 | 2.2222 | 100
3 | validation and support | 2014-02-10 08:00 | 2014-02-19 12:00 | 7d 4h | Employee G | 4500 | 0 | 0 | 0 | 4500 | 2014-02-10 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 4500 | 4500 | 100 | 36.6667 | 100 | 100 | 36.6667 | 100
4 | validation and support | 2014-02-10 08:00 | 2014-02-10 15:00 | 6h | Employee H | 450 | 0 | 0 | 0 | 450 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 450 | 450 | 100 | 16.6667 | 100 | 100 | 16.6667 | 100
5 | validation and support | 2014-02-10 08:00 | 2014-02-12 16:00 | 2d 7h | Employee I | 1725 | 0 | 0 | 0 | 1725 | 2014-02-24 08:00 | 4d 4h | 2700 | 0 | 0 | 0 | 0 | 2700 | 0 | 100% | Finished | 1725 | 1725 | 100 | 156.5217 | 100 | 100 | 156.5217 | 100
6 | validation and support | 2014-02-10 08:00 | 2014-02-17 11:00 | 5d 3h | Employee J | 3225 | 0 | 0 | 0 | 3225 | 2014-03-17 08:00 | 3h | 225 | 0 | 0 | 0 | 0 | 225 | 0 | 100% | Finished | 3225 | 3225 | 100 | 6.9767 | 100 | 100 | 6.9767 | 100
7 | validation and support | 2014-02-10 08:00 | 2014-02-18 10:00 | 6d 2h | Employee K | 3750 | 0 | 0 | 0 | 3750 | 2014-02-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 3750 | 3750 | 100 | 2 | 100 | 100 | 2 | 100
8 | validation and support | 2014-02-10 08:00 | 2014-02-10 09:00 | 1h | Employee B | 75 | 0 | 0 | 0 | 75 | 2014-02-10 08:00 | 3d 5h | 2175 | 0 | 0 | 0 | 0 | 2175 | 0 | 100% | Finished | 75 | 75 | 100 | 2900 | 100 | 100 | 2900 | 100
68 | analysis | 2014-02-11 08:00 | 2014-04-25 17:00 | 54d |  |  | 0 |  |  | 22200 |  | 54d 7h | [5 empty] | 20700 |  | 100% |  | 22200 | 22200
9 | analysis - aanpassing aanbieding | 2014-02-11 08:00 | 2014-02-24 15:00 | 9d 6h | Employee G | 5850 | 0 | 0 | 0 | 5850 | 2014-02-10 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 5850 | 5850 | 100 | 28.2051 | 100 | 100 | 28.2051 | 100
10 | analysis - boeking teruggave | 2014-02-17 08:00 | 2014-02-21 09:00 | 4d 1h | Employee C | 2475 | 0 | 0 | 0 | 2475 | 2014-02-17 08:00 | 3d 6h | 2250 | 0 | 0 | 0 | 0 | 2250 | 0 | 100% | Finished | 2475 | 2475 | 100 | 90.9091 | 100 | 100 | 90.9091 | 100
11 | analysis - convertie teruggaves | 2014-02-17 08:00 | 2014-02-25 14:00 | 6d 5h | Employee K | 3975 | 0 | 0 | 0 | 3975 | 2014-03-17 08:00 | 9d 4h | 5700 | 0 | 0 | 0 | 0 | 5700 | 0 | 100% | Finished | 3975 | 3975 | 100 | 143.3962 | 100 | 100 | 143.3962 | 100
14 | analysis - lay-out brief | 2014-02-17 08:00 | 2014-02-27 17:00 | 9d | Employee K | 5400 | 0 | 0 | 0 | 5400 | 2014-02-17 08:00 | 14d 3h | 8625 | 0 | 0 | 0 | 0 | 8625 | 0 | 100% | Finished | 5400 | 5400 | 100 | 159.7222 | 100 | 100 | 159.7222 | 100
15 | analysis - methode fractioneren | 2014-02-11 08:00 | 2014-02-12 15:00 | 1d 6h | Employee G | 1050 | 0 | 0 | 0 | 1050 | 2014-02-10 08:00 | 3d 2h | 1950 | 0 | 0 | 0 | 0 | 1950 | 0 | 100% | Finished | 1050 | 1050 | 100 | 185.7143 | 100 | 100 | 185.7143 | 100
16 | analysis - proces opzetten | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee K | 600 | 0 | 0 | 0 | 600 | 2014-03-17 08:00 | 6h | 450 | 0 | 0 | 0 | 0 | 450 | 0 | 100% | Finished | 600 | 600 | 100 | 75 | 100 | 100 | 75 | 100
17 | analysis - stopzetten afbetalingsplan | 2014-03-24 08:00 | 2014-03-28 15:00 | 4d 6h | Employee K | 2850 | 0 | 0 | 0 | 2850 | 2014-03-24 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2850 | 2850 | 100 | 2.6316 | 100 | 100 | 2.6316 | 100
18 | analysis validated | 2014-04-25 17:00 | 2014-04-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-04-25 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
69 | design | 2014-02-10 08:00 | 2014-05-29 17:00 | 79d |  |  | 0 |  |  | 29175 |  | 78d 7h | [5 empty] | 20700 |  | 100% |  | 29175 | 29175
19 | design - aanleveren input | 2014-03-17 08:00 | 2014-03-26 12:00 | 7d 4h | Employee I | 4500 | 0 | 0 | 0 | 4500 | 2014-03-17 08:00 | 7d 1h | 4275 | 0 | 0 | 0 | 0 | 4275 | 0 | 100% | Finished | 4500 | 4500 | 100 | 95 | 100 | 100 | 95 | 100
20 | design - aanpassingen aanbieding | 2014-03-17 08:00 | 2014-03-25 14:00 | 6d 5h | Employee E | 3975 | 0 | 0 | 0 | 3975 | 2014-03-17 08:00 | 2d 6h | 1650 | 0 | 0 | 0 | 0 | 1650 | 0 | 100% | Finished | 3975 | 3975 | 100 | 41.5094 | 100 | 100 | 41.5094 | 100
21 | design - boeking teruggave | 2014-03-10 08:00 | 2014-03-14 15:00 | 4d 6h | Employee E | 2850 | 0 | 0 | 0 | 2850 | 2014-03-31 08:00 | 3d 5h | 2175 | 0 | 0 | 0 | 0 | 2175 | 0 | 100% | Finished | 2850 | 2850 | 100 | 76.3158 | 100 | 100 | 76.3158 | 100
22 | design - convertie teruggaves | 2014-05-05 08:00 | 2014-05-08 15:00 | 3d 6h | Employee E | 2250 | 0 | 0 | 0 | 2250 | 2014-05-05 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2250 | 2250 | 100 | 3.3333 | 100 | 100 | 3.3333 | 100
23 | design - creatie artikels | 2014-03-10 08:00 | 2014-03-10 17:00 | 1d | Employee L | 600 | 0 | 0 | 0 | 600 | 2014-03-31 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 600 | 600 | 100 | 25 | 100 | 100 | 25 | 100
24 | design - impact op andere progs | 2014-02-10 08:00 | 2014-02-17 12:00 | 5d 4h | Employee L | 3300 | 0 | 0 | 0 | 3300 | 2014-02-10 08:00 | 5d 5h | 3375 | 0 | 0 | 0 | 0 | 3375 | 0 | 100% | Finished | 3300 | 3300 | 100 | 102.2727 | 100 | 100 | 102.2727 | 100
25 | design - lay-out brief | 2014-03-17 08:00 | 2014-03-21 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 2014-03-10 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 2850 | 2850 | 100 | 5.2632 | 100 | 100 | 5.2632 | 100
26 | design - mailoptie | 2014-05-12 08:00 | 2014-05-13 16:00 | 1d 7h | Employee I | 1125 | 0 | 0 | 0 | 1125 | 2014-05-12 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1125 | 1125 | 100 | 6.6667 | 100 | 100 | 6.6667 | 100
27 | design - methode fractioneren | 2014-02-11 08:00 | 2014-02-14 12:00 | 3d 4h | Employee E | 2100 | 0 | 0 | 0 | 2100 | 2014-02-10 08:00 | 7d 7h | 4725 | 0 | 0 | 0 | 0 | 4725 | 0 | 100% | Finished | 2100 | 2100 | 100 | 225 | 100 | 100 | 225 | 100
28 | design - opzet OMS | 2014-04-07 08:00 | 2014-04-08 16:00 | 1d 7h | Employee M | 1125 | 0 | 0 | 0 | 1125 | 2014-03-17 08:00 | 4d 3h | 2625 | 0 | 0 | 0 | 0 | 2625 | 0 | 100% | Finished | 1125 | 1125 | 100 | 233.3333 | 100 | 100 | 233.3333 | 100
29 | design - proces opzetten | 2014-03-06 08:00 | 2014-03-07 10:00 | 1d 2h | Employee I | 750 | 0 | 0 | 0 | 750 | 2014-03-03 08:00 | 2d 2h | 1350 | 0 | 0 | 0 | 0 | 1350 | 0 | 100% | Finished | 750 | 750 | 100 | 180 | 100 | 100 | 180 | 100
30 | design - stopzetting afbetalingsplan | 2014-05-21 08:00 | 2014-05-29 10:00 | 6d 2h | Employee E | 3750 | 0 | 0 | 0 | 3750 | 2014-05-21 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 3750 | 3750 | 100 | 2 | 100 | 100 | 2 | 100
31 | design validated | 2014-05-29 17:00 | 2014-05-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-05-29 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
70 | development | 2014-02-11 08:00 | 2014-09-26 17:00 | 164d |  |  | 0 |  |  | 25800 |  | 164d 7h | [5 empty] | 3675 |  | 100% |  | 25800 | 25800
33 | development - boeking teruggave | 2014-04-07 08:00 | 2014-04-15 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 2014-04-28 08:00 | 2h | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 100% | Finished | 3975 | 3975 | 100 | 3.7736 | 100 | 100 | 3.7736 | 100
35 | development - impact op andere progs | 2014-02-11 08:00 | 2014-03-03 11:00 | 14d 3h | Employee N | 8625 | 0 | 0 | 0 | 8625 | 2014-02-10 08:00 | 4h | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 100% | Finished | 8625 | 8625 | 100 | 3.4783 | 100 | 100 | 3.4783 | 100
36 | development - landscape document voorzien | 2014-02-11 08:00 | 2014-02-17 16:00 | 4d 7h | Employee O | 2925 | 0 | 0 | 0 | 2925 | 2014-02-10 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2925 | 2925 | 100 | 2.5641 | 100 | 100 | 2.5641 | 100
37 | development - lay-out brief | 2014-04-28 08:00 | 2014-05-02 15:00 | 4d 6h | Employee M | 2850 | 0 | 0 | 0 | 2850 | 2014-04-28 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 2850 | 2850 | 100 | 2.6316 | 100 | 100 | 2.6316 | 100
38 | development - methode fractioneren | 2014-03-10 08:00 | 2014-03-18 14:00 | 6d 5h | Employee L | 3975 | 0 | 0 | 0 | 3975 | 2014-03-10 08:00 | 4d 7h | 2925 | 0 | 0 | 0 | 0 | 2925 | 0 | 100% | Finished | 3975 | 3975 | 100 | 73.5849 | 100 | 100 | 73.5849 | 100
40 | development - proces opzetten | 2014-03-31 08:00 | 2014-04-02 16:00 | 2d 7h | Employee Q | 1725 | 0 | 0 | 0 | 1725 | 2014-03-31 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1725 | 1725 | 100 | 4.3478 | 100 | 100 | 4.3478 | 100
42 | development - impact op andere progs | 2014-07-07 08:00 | 2014-07-09 16:00 | 2d 7h | Employee M | 1725 | 0 | 0 | 0 | 1725 | 2014-07-07 08:00 | 1h | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 1725 | 1725 | 100 | 4.3478 | 100 | 100 | 4.3478 | 100
46 | development completed | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-26 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
71 | test ict | 2014-06-02 08:00 | 2014-08-29 17:00 | 65d |  |  | 0 |  |  | 11250 |  | 104d 7h | [5 empty] | 1425 |  | 100% |  | 11250 | 11250
49 | test ict - preparation | 2014-06-02 08:00 | 2014-06-26 15:00 | 18d 6h | Employee E | 11250 | 0 | 0 | 0 | 11250 | 2014-04-07 08:00 | 2d 3h | 1425 | 0 | 0 | 0 | 0 | 1425 | 0 | 100% | Finished | 11250 | 11250 | 100 | 12.6667 | 100 | 100 | 12.6667 | 100
50 | ict test completed | 2014-08-29 17:00 | 2014-08-29 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-08-29 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
72 | implementation | 2014-07-01 17:00 | 2014-10-10 17:00 | 73d |  |  | 0 |  |  | 0 |  | 73d | [5 empty] | 0 |  | 0% |  | 0 | 0
51 | uat | 2014-07-01 17:00 | 2014-07-01 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-07-01 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
52 | code freeze | 2014-09-26 17:00 | 2014-09-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-09-26 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
55 | go live | 2014-10-10 17:00 | 2014-10-10 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2014-10-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking 1 | 2014-01-28 08:00 | 2014-02-24 22:00 | 65625 | 28045.7999 | 13995 | 2014-02-13 11:00 | -37579.2001 | 42.74% | 14050.7999 | 200.4% | -7d 5h | 61.88% | 58.03% | 2014-12-24 09:00 | 2015-09-22 12:00 | 2014-11-24 16:00 | 2014-10-28 12:00 | 2015-09-22 12:00 | 2014-12-08 16:00 | 2014-10-22 14:00 | 2015-03-19 11:00 | 2014-09-05 11:00 | 118519.2001 | 66153.1195 | 258573.5344 | 182923.0002 | 136040.9607 | 98290.9506 | 75892.6218 | 74520.6801 | 0.61875 | 2.004 | 0.42736 | 0.58035 | -7.625 | 2.004 | 1 | 0.61875 | 1
Tracking 2 | 2014-02-24 22:00 | 2014-03-31 22:00 | 103395 | 91958.7003 | 47835 | 2014-03-18 15:00 | -11436.2997 | 88.94% | 44123.7003 | 192.2% | -9d 2h | 79.44% | 89.56% | 2014-11-03 16:00 | 2014-11-12 16:00 | 2014-06-26 14:00 | 2014-10-17 17:00 | 2014-11-12 16:00 | 2014-07-28 10:00 | 2014-10-24 10:00 | 2014-12-17 14:00 | 2014-08-14 09:00 | 88446.2997 | 68960.152 | 93496.8603 | 98954.1185 | 71587.3484 | 74426.1004 | 71503.8782 | 71768.7625 | 0.79444 | 1.9224 | 0.88939 | 0.89562 | -9.25 | 1.9224 | 1 | 0.79444 | 1
Closure | 2014-03-31 22:00 | 2014-10-13 08:00 | 132570 | 132570 | 58410 | 2014-10-10 17:00 | 0 | 100% | 74160 | 227% | 0 | 100% | 100% | 2014-10-10 17:00 | 2014-10-10 17:00 | 2014-05-21 09:00 | 2014-10-10 17:00 | 2014-10-10 17:00 | 2014-10-10 17:00 | 2014-10-10 17:00 | 2014-10-10 17:00 | 2014-10-10 17:00 | 58410 | 58410 | 58410 | 58410 | 58410 | 58410 | 58410 | 58410 | 1 | 2.2696 | 1 | 1 | 0 | 2.2696 | 1 | 1 | 1