## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Roadworks Poperinge | 1 |  |  | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 | 200.375
1 | opbraak &amp;amp;amp; grondwerken | 1.1 |  | SS2+1w;FS5 | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 39.375
2 | riolering | 1.2 | 1SS+1w | SS3+2w | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 39.375
3 | huisaansluiting | 1.3 | 2SS+2w | SS4+2w | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 32.375
4 | koffer | 1.4 | 3SS+2w | SS6+3w | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 25.375
5 | opbraak oude rioleringsbuizen | 1.5 | 1FS | SS6+1w | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 11.375
6 | boorstenen/greppel prefab | 1.6 | 4SS+3w;5SS+1w | SS7+2w | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 | 18.375
7 | boorstenen/greppel ter plaatse | 1.7 | 6SS+2w | FS8 | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 | 32.375
8 | fundering | 1.8 | 7FS | SS9+2w | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 | 18.375
9 | betonstraatstenen | 1.9 | 8SS+2w | SS10+1w | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 | 46.375
10 | plaatsen aanrijelement | 1.10 | 9SS+1w | FS11 | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 | 4.375
11 | KWS onderlaag | 1.11 | 10FS | FS12 | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 | 4.375
12 | KWS bovenlaag | 1.12 | 11FS | FS13 | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 | 4.375
13 | opkuis &amp;amp;amp; afwerken | 1.13 | 12FS |  | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 | 4.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Roadworks Poperinge | 960h |  |  |  |  | 99 | 100 | 101
1 | opbraak &amp;amp;amp; grondwerken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | riolering | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | huisaansluiting | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | koffer | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | opbraak oude rioleringsbuizen | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | boorstenen/greppel prefab | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | boorstenen/greppel ter plaatse | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | fundering | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | betonstraatstenen | 280h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | plaatsen aanrijelement | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | KWS onderlaag | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | KWS bovenlaag | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | opkuis &amp;amp;amp; afwerken | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2013-06-30 17:00 |  | TP Name | 30/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 10d | [5 empty] | 26568.125 |  | 5.425% |  | 27738.2717 | 309979.3477
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 9d | 27028.5216 | 48050.705 | 16d | -1732.3966 | 0 | 25296.125 | 48050.705 | 36% | Started | 27028.5226 | 75079.2266 | 100 | 36 | 36 | 100 | 33.6926 | 36
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 |  | 0 | 0 | 122638.4609 | 25d | 0 | 0 | 0 | 122638.4609 | 0% | Not Started | 0 | 122638.4609 | 100 |  | 0 | 100 |  | 0
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 |  | 0 | 0 | 71968.0703 | 20d | 0 | 0 | 0 | 71968.0703 | 0% | Not Started | 0 | 71968.0703 | 100 |  | 0 | 100 |  | 0
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 |  | 0 | 0 | 10302.5 | 20d | 0 | 0 | 0 | 10302.5 | 0% | Not Started | 0 | 10302.5 | 100 |  | 0 | 100 |  | 0
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 1d | 709.749 | 6387.7412 | 9d | 562.251 | 0 | 1272 | 6387.7412 | 10% | Started | 709.749 | 7097.4902 | 100 | 10 | 10 | 100 | 17.9218 | 10
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 |  | 0 | 0 | 15305.5996 | 15d | 0 | 0 | 0 | 15305.5996 | 0% | Not Started | 0 | 15305.5996 | 100 |  | 0 | 100 |  | 0
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 |  | 0 | 0 | 18970 | 25d | 0 | 0 | 0 | 18970 | 0% | Not Started | 0 | 7588 | 100 |  | 0 | 100 |  | 0
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 |  | 0 | 0 | 71018.25 | 15d | 0 | 0 | 0 | 71018.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 |  | 0 | 0 | 46090.7617 | 35d | 0 | 0 | 0 | 46090.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 |  | 0 | 0 | 9399.1504 | 5d | 0 | 0 | 0 | 9399.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 |  | 0 | 0 | 29674.5 | 5d | 0 | 0 | 0 | 29674.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 |  | 0 | 0 | 32715.25 | 5d | 0 | 0 | 0 | 32715.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 |  | 0 | 0 | 1066.6 | 5d | 0 | 0 | 0 | 1066.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2013-07-31 16:00 |  | TP Name | 31/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 25d | [5 empty] | 138211.1172 |  | 27.8% |  | 142153.7612 | 321361.3477
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 10d | 30031.6906 | 48050.705 | 16d | -4023.6242 | 0 | 26008.0664 | 48050.705 | 38.46% | Started | 28876.6261 | 75079.2266 | 100 | 40 | 38.4615 | 100 | 34.6408 | 38.4615
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 13d | 63771.9997 | 58866.4613 | 12d | 21532.2503 | 0 | 85304.25 | 58866.4613 | 52% | Started | 63771.9973 | 122638.4609 | 100 | 52 | 52 | 100 | 69.5575 | 52
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 8d | 28787.2281 | 17992.0176 | 5d | -10134.4273 | 0 | 18652.8008 | 17992.0176 | 61.54% | Started | 44288.0449 | 71968.0703 | 100 | 40 | 61.5385 | 100 | 25.9182 | 61.5385
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 7d | 3605.875 | 4636.125 | 9d | 3368.125 | 0 | 6974 | 4636.125 | 43.75% | Started | 4507.3438 | 10302.5 | 100 | 35 | 43.75 | 100 | 67.6923 | 43.75
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 1d | 709.749 | 6387.7412 | 9d | 562.251 | 0 | 1272 | 6387.7412 | 10% | Started | 709.749 | 7097.4902 | 100 | 10 | 10 | 100 | 17.9218 | 10
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 |  | 0 | 0 | 15305.5996 | 15d | 0 | 0 | 0 | 15305.5996 | 0% | Not Started | 0 | 15305.5996 | 100 |  | 0 | 100 |  | 0
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 |  | 0 | 0 | 18970 | 25d | 0 | 0 | 0 | 18970 | 0% | Not Started | 0 | 18970 | 100 |  | 0 | 100 |  | 0
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 |  | 0 | 0 | 71018.25 | 15d | 0 | 0 | 0 | 71018.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 |  | 0 | 0 | 46090.7617 | 35d | 0 | 0 | 0 | 46090.7617 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 |  | 0 | 0 | 9399.1504 | 5d | 0 | 0 | 0 | 9399.1504 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 |  | 0 | 0 | 29674.5 | 5d | 0 | 0 | 0 | 29674.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 |  | 0 | 0 | 32715.25 | 5d | 0 | 0 | 0 | 32715.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 |  | 0 | 0 | 1066.6 | 5d | 0 | 0 | 0 | 1066.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-09-30 16:00 |  | TP Name | 30/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 55d 7h | [5 empty] | 234732.3285 |  | 41.3% |  | 211186.9742 | 491658.3452
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 15d | 45047.5359 | 30031.6906 | 10d | -7570.0789 | 0 | 37477.457 | 30031.6906 | 60% | Started | 45047.5377 | 75079.2266 | 100 | 60 | 60 | 100 | 49.9172 | 60
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 18d | 88299.6919 | 34338.7691 | 7d | 26417.4693 | 0 | 114717.1611 | 34338.7691 | 72% | Started | 88299.6954 | 122638.4609 | 100 | 72 | 72 | 100 | 93.5409 | 72
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 26d | 93558.4914 | 7196.807 | 2d | -22595.2811 | 0 | 70963.2103 | 7196.807 | 92.86% | Started | 66827.492 | 71968.0703 | 100 | 130 | 92.8571 | 100 | 98.6037 | 92.8571
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 21d | 10817.625 | 0 | 0 | -515.125 | 0 | 10302.5 | 0 | 100% | Finished | 10302.5 | 10302.5 | 100 | 105 | 100 | 100 | 100 | 100
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 1d | 709.749 | 6387.7412 | 9d | 562.251 | 0 | 1272 | 6387.7412 | 10% | Started | 709.749 | 7097.4902 | 100 | 10 | 10 | 100 | 17.9218 | 10
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 |  | 0 | 0 | 15305.5996 | 15d | 0 | 0 | 0 | 15305.5996 | 0% | Not Started | 0 | 15305.5996 | 100 |  | 0 | 100 |  | 0
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 |  | 0 | 0 | 18970 | 25d | 0 | 0 | 0 | 18970 | 0% | Not Started | 0 | 18970 | 100 |  | 0 | 100 |  | 0
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 |  | 0 | 0 | 71018.25 | 15d | 0 | 0 | 0 | 71018.25 | 0% | Not Started | 0 | 71018.25 | 100 |  | 0 | 100 |  | 0
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 |  | 0 | 0 | 46090.7617 | 35d | 0 | 0 | 0 | 46090.7617 | 0% | Not Started | 0 | 27489.8472 | 100 |  | 0 | 100 |  | 0
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 |  | 0 | 0 | 9399.1504 | 5d | 0 | 0 | 0 | 9399.1504 | 0% | Not Started | 0 | 9399.1504 | 100 |  | 0 | 100 |  | 0
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 |  | 0 | 0 | 29674.5 | 5d | 0 | 0 | 0 | 29674.5 | 0% | Not Started | 0 | 29674.5 | 100 |  | 0 | 100 |  | 0
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 |  | 0 | 0 | 32715.25 | 5d | 0 | 0 | 0 | 32715.25 | 0% | Not Started | 0 | 32715.25 | 100 |  | 0 | 100 |  | 0
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 |  | 0 | 0 | 1066.6 | 5d | 0 | 0 | 0 | 1066.6 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-10-31 16:00 |  | TP Name | 31/10, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 75d | [5 empty] | 288477.417 |  | 48.22% |  | 246584.5129 | 511325.8597
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 15d | 45047.5359 | 30031.6906 | 10d | -7570.0789 | 0 | 37477.457 | 30031.6906 | 60% | Started | 45047.5377 | 75079.2266 | 100 | 60 | 60 | 100 | 49.9172 | 60
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 18d | 88299.6919 | 34338.7691 | 7d | 26417.4693 | 0 | 114717.1611 | 34338.7691 | 72% | Started | 88299.6954 | 122638.4609 | 100 | 72 | 72 | 100 | 93.5409 | 72
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 27d | 97156.8949 | 3598.4035 | 1d | -23093.1247 | 0 | 74063.7703 | 3598.4035 | 96.43% | Started | 69397.7833 | 71968.0703 | 100 | 135 | 96.4286 | 100 | 102.912 | 96.4286
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 21d | 10817.625 | 0 | 0 | -515.125 | 0 | 10302.5 | 0 | 100% | Finished | 10302.5 | 10302.5 | 100 | 105 | 100 | 100 | 100 | 100
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 1d | 709.749 | 6387.7412 | 9d | 562.251 | 0 | 1272 | 6387.7412 | 10% | Started | 709.749 | 7097.4902 | 100 | 10 | 10 | 100 | 17.9218 | 10
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 | 2013-10-16 08:00 | 2d | 2040.7466 | 13264.853 | 13d | -968.8775 | 0 | 1071.8691 | 13264.853 | 13.33% | Started | 2040.7467 | 15305.5996 | 100 | 13.3333 | 13.3333 | 100 | 7.0031 | 13.3333
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 | 2013-10-21 08:00 | 3d | 2276.4 | 3794 | 5d | 15555.4 | 0 | 17831.8 | 3794 | 37.5% | Started | 7113.75 | 18970 | 100 | 12 | 37.5 | 100 | 94 | 37.5
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 | 2013-10-24 08:00 | 5d | 23672.75 | 47345.5 | 10d | 8068.1094 | 0 | 31740.8594 | 47345.5 | 33.33% | Started | 23672.7507 | 71018.25 | 100 | 33.3333 | 33.3333 | 100 | 44.6939 | 33.3333
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 |  | 0 | 0 | 46090.7617 | 35d | 0 | 0 | 0 | 46090.7617 | 0% | Not Started | 0 | 46090.7617 | 100 |  | 0 | 100 |  | 0
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 |  | 0 | 0 | 9399.1504 | 5d | 0 | 0 | 0 | 9399.1504 | 0% | Not Started | 0 | 9399.1504 | 100 |  | 0 | 100 |  | 0
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 |  | 0 | 0 | 29674.5 | 5d | 0 | 0 | 0 | 29674.5 | 0% | Not Started | 0 | 29674.5 | 100 |  | 0 | 100 |  | 0
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 |  | 0 | 0 | 32715.25 | 5d | 0 | 0 | 0 | 32715.25 | 0% | Not Started | 0 | 32715.25 | 100 |  | 0 | 100 |  | 0
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 |  | 0 | 0 | 1066.6 | 5d | 0 | 0 | 0 | 1066.6 | 0% | Not Started | 0 | 1066.6 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-11-30 16:00 |  | TP Name | 30/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 95d | [5 empty] | 395246.7723 |  | 59.47% |  | 304066.6009 | 511325.8597
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 15d | 45047.5359 | 30031.6906 | 10d | -4698.0477 | 0 | 40349.4883 | 30031.6906 | 60% | Started | 45047.5377 | 75079.2266 | 100 | 60 | 60 | 100 | 53.7425 | 60
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 18d | 88299.6919 | 34338.7691 | 7d | 26417.4693 | 0 | 114717.1611 | 34338.7691 | 72% | Started | 88299.6954 | 122638.4609 | 100 | 72 | 72 | 100 | 93.5409 | 72
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 27d | 97156.8949 | 3598.4035 | 1d | -16438.1645 | 0 | 80718.7305 | 3598.4035 | 96.43% | Started | 69397.7833 | 71968.0703 | 100 | 135 | 96.4286 | 100 | 112.1591 | 96.4286
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 21d | 10817.625 | 0 | 0 | -515.125 | 0 | 10302.5 | 0 | 100% | Finished | 10302.5 | 10302.5 | 100 | 105 | 100 | 100 | 100 | 100
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 2d | 1419.498 | 4968.2432 | 7d | 3426.4021 | 0 | 4845.9001 | 4968.2432 | 22.22% | Started | 1577.2201 | 7097.4902 | 100 | 20 | 22.2222 | 100 | 68.2762 | 22.2222
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 | 2013-10-16 08:00 | 6d | 6122.2398 | 13264.853 | 13d | 2053.5097 | 0 | 8175.7495 | 13264.853 | 31.58% | Started | 4833.3471 | 15305.5996 | 100 | 40 | 31.5789 | 100 | 53.4167 | 31.5789
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 | 2013-10-21 08:00 | 3d | 2276.4 | 3794 | 5d | 15555.4 | 0 | 17831.8 | 3794 | 37.5% | Started | 7113.75 | 18970 | 100 | 12 | 37.5 | 100 | 94 | 37.5
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 | 2013-10-24 08:00 | 16d | 75752.8 | 47345.5 | 10d | -15576.8996 | 0 | 60175.9004 | 47345.5 | 61.54% | Started | 43703.5401 | 71018.25 | 100 | 106.6667 | 61.5385 | 100 | 84.733 | 61.5385
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 | 2013-11-08 08:00 | 2d | 2633.7578 | 23703.8203 | 18d | 23298.2441 | 0 | 25932.002 | 23703.8203 | 10% | Started | 4609.0762 | 46090.7617 | 100 | 5.7143 | 10 | 100 | 56.2629 | 10
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 | 2013-11-22 08:00 | 5d | 9399.1504 | 0 | 0 | -626.61 | 0 | 8772.5404 | 0 | 100% | Finished | 9399.1504 | 9399.1504 | 100 | 100 | 100 | 100 | 93.3333 | 100
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 | 2013-11-06 08:00 | 2d | 11869.8 | 5934.9 | 1d | 11555.2 | 0 | 23425 | 5934.9 | 66.67% | Started | 19783.0006 | 29674.5 | 100 | 40 | 66.6667 | 100 | 78.9398 | 66.6667
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 |  | 0 | 0 | 32715.25 | 5d | 0 | 0 | 0 | 32715.25 | 0% | Not Started | 0 | 32715.25 | 100 |  | 0 | 100 |  | 0
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 |  | 0 | 0 | 1066.6 | 5d | 0 | 0 | 0 | 1066.6 | 0% | Not Started | 0 | 1066.6 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-12-31 16:00 |  | TP Name | 31/12, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 110d | [5 empty] | 410601.8194 |  | 91.46% |  | 467652.5104 | 511325.8597
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 15d | 45047.5359 | 0 | 0 | -4565.6102 | 0 | 40481.9258 | 0 | 100% | Finished | 75079.2266 | 75079.2266 | 100 | 60 | 100 | 100 | 53.9189 | 100
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 18d | 88299.6919 | 0 | 0 | 26789.3491 | 0 | 115089.041 | 0 | 100% | Finished | 122638.4609 | 122638.4609 | 100 | 72 | 100 | 100 | 93.8442 | 100
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 27d | 97156.8949 | 0 | 0 | -17026.3446 | 0 | 80130.5503 | 0 | 100% | Finished | 71968.0703 | 71968.0703 | 100 | 135 | 100 | 100 | 111.3418 | 100
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 21d | 10817.625 | 0 | 0 | -515.125 | 0 | 10302.5 | 0 | 100% | Finished | 10302.5 | 10302.5 | 100 | 105 | 100 | 100 | 100 | 100
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 2d | 1419.498 | 0 | 0 | 3408.4021 | 0 | 4827.9001 | 0 | 100% | Finished | 7097.4902 | 7097.4902 | 100 | 20 | 100 | 100 | 68.0226 | 100
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 | 2013-10-16 08:00 | 7d | 7142.6132 | 0 | 0 | 1344.4664 | 0 | 8487.0796 | 0 | 100% | Finished | 15305.5996 | 15305.5996 | 100 | 46.6667 | 100 | 100 | 55.4508 | 100
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 | 2013-10-21 08:00 | 10d | 7588 | 0 | 0 | 10855.58 | 0 | 18443.58 | 0 | 100% | Finished | 18970 | 18970 | 100 | 40 | 100 | 100 | 97.225 | 100
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 | 2013-10-24 08:00 | 18d | 85221.9 | 0 | 0 | -22181.4 | 0 | 63040.5 | 0 | 100% | Finished | 71018.25 | 71018.25 | 100 | 120 | 100 | 100 | 88.7666 | 100
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 | 2013-11-08 08:00 | 8d | 10535.0312 | 0 | 0 | 27066.1709 | 0 | 37601.2021 | 0 | 100% | Finished | 46090.7617 | 46090.7617 | 100 | 22.8571 | 100 | 100 | 81.5808 | 100
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 | 2013-11-22 08:00 | 5d | 9399.1504 | 0 | 0 | -626.61 | 0 | 8772.5404 | 0 | 100% | Finished | 9399.1504 | 9399.1504 | 100 | 100 | 100 | 100 | 93.3333 | 100
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 | 2013-11-06 08:00 | 2d | 11869.8 | 5934.9 | 1d | 11555.2 | 0 | 23425 | 5934.9 | 66.67% | Started | 19783.0006 | 29674.5 | 100 | 40 | 66.6667 | 100 | 78.9398 | 66.6667
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 |  | 0 | 0 | 32715.25 | 5d | 0 | 0 | 0 | 32715.25 | 0% | Not Started | 0 | 32715.25 | 100 |  | 0 | 100 |  | 0
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 |  | 0 | 0 | 1066.6 | 5d | 0 | 0 | 0 | 1066.6 | 0% | Not Started | 0 | 1066.6 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2014-04-30 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Roadworks Poperinge | 2013-04-08 08:00 | 2013-10-25 17:00 | 120d |  |  | 0 |  |  | 511325.8597 |  | 193d | [5 empty] | 440394.1596 |  | 100% |  | 511325.8597 | 511325.8597
1 | opbraak &amp;amp;amp; grondwerken | 2013-04-08 08:00 | 2013-05-17 17:00 | 25d |  | 0 | 0 | 375.3961 | 75079.2266 | 75079.2266 | 2013-06-17 08:00 | 15d | 45047.5359 | 0 | 0 | -4565.6102 | 0 | 40481.9258 | 0 | 100% | Finished | 75079.2266 | 75079.2266 | 100 | 60 | 100 | 100 | 53.9189 | 100
2 | riolering | 2013-04-15 08:00 | 2013-05-24 17:00 | 25d |  | 0 | 0 | 613.1923 | 122638.4609 | 122638.4609 | 2013-07-01 08:00 | 18d | 88299.6919 | 0 | 0 | 26789.3491 | 0 | 115089.041 | 0 | 100% | Finished | 122638.4609 | 122638.4609 | 100 | 72 | 100 | 100 | 93.8442 | 100
3 | huisaansluiting | 2013-04-29 08:00 | 2013-05-31 17:00 | 20d |  | 0 | 0 | 449.8004 | 71968.0703 | 71968.0703 | 2013-07-01 08:00 | 27d | 97156.8949 | 0 | 0 | -17026.3446 | 0 | 80130.5503 | 0 | 100% | Finished | 71968.0703 | 71968.0703 | 100 | 135 | 100 | 100 | 111.3418 | 100
4 | koffer | 2013-05-13 08:00 | 2013-06-07 17:00 | 20d |  | 0 | 0 | 64.3906 | 10302.5 | 10302.5 | 2013-07-05 08:00 | 21d | 10817.625 | 0 | 0 | -515.125 | 0 | 10302.5 | 0 | 100% | Finished | 10302.5 | 10302.5 | 100 | 105 | 100 | 100 | 100 | 100
5 | opbraak oude rioleringsbuizen | 2013-05-27 08:00 | 2013-06-07 17:00 | 10d |  | 0 | 0 | 88.7186 | 7097.4902 | 7097.4902 | 2013-06-20 08:00 | 2d | 1419.498 | 0 | 0 | 3408.4021 | 0 | 4827.9001 | 0 | 100% | Finished | 7097.4902 | 7097.4902 | 100 | 20 | 100 | 100 | 68.0226 | 100
6 | boorstenen/greppel prefab | 2013-06-03 08:00 | 2013-06-21 17:00 | 15d |  | 0 | 0 | 127.5467 | 15305.5996 | 15305.5996 | 2013-10-16 08:00 | 7d | 7142.6132 | 0 | 0 | 1344.4664 | 0 | 8487.0796 | 0 | 100% | Finished | 15305.5996 | 15305.5996 | 100 | 46.6667 | 100 | 100 | 55.4508 | 100
7 | boorstenen/greppel ter plaatse | 2013-06-17 08:00 | 2013-07-19 17:00 | 25d |  | 0 | 0 | 94.85 | 18970 | 18970 | 2013-10-21 08:00 | 10d | 7588 | 0 | 0 | 10855.58 | 0 | 18443.58 | 0 | 100% | Finished | 18970 | 18970 | 100 | 40 | 100 | 100 | 97.225 | 100
8 | fundering | 2013-08-19 08:00 | 2013-09-06 17:00 | 15d |  | 0 | 0 | 591.8188 | 71018.25 | 71018.25 | 2013-10-24 08:00 | 18d | 85221.9 | 0 | 0 | -22181.4 | 0 | 63040.5 | 0 | 100% | Finished | 71018.25 | 71018.25 | 100 | 120 | 100 | 100 | 88.7666 | 100
9 | betonstraatstenen | 2013-09-02 08:00 | 2013-10-18 17:00 | 35d |  | 0 | 0 | 164.6099 | 46090.7617 | 46090.7617 | 2013-11-08 08:00 | 8d | 10535.0312 | 0 | 0 | 27066.1709 | 0 | 37601.2021 | 0 | 100% | Finished | 46090.7617 | 46090.7617 | 100 | 22.8571 | 100 | 100 | 81.5808 | 100
10 | plaatsen aanrijelement | 2013-09-09 08:00 | 2013-09-13 17:00 | 5d |  | 0 | 0 | 234.9788 | 9399.1504 | 9399.1504 | 2013-11-22 08:00 | 5d | 9399.1504 | 0 | 0 | -626.61 | 0 | 8772.5404 | 0 | 100% | Finished | 9399.1504 | 9399.1504 | 100 | 100 | 100 | 100 | 93.3333 | 100
11 | KWS onderlaag | 2013-09-16 08:00 | 2013-09-20 17:00 | 5d |  | 0 | 0 | 741.8625 | 29674.5 | 29674.5 | 2013-11-06 08:00 | 3d | 17804.7 | 0 | 0 | 7025.8 | 0 | 24830.5 | 0 | 100% | Finished | 29674.5 | 29674.5 | 100 | 60 | 100 | 100 | 83.6762 | 100
12 | KWS bovenlaag | 2013-09-23 08:00 | 2013-09-27 17:00 | 5d |  | 0 | 0 | 817.8813 | 32715.25 | 32715.25 | 2014-04-03 08:00 | 2d | 13086.1 | 0 | 0 | 14234.1402 | 0 | 27320.2402 | 0 | 100% | Finished | 32715.25 | 32715.25 | 100 | 40 | 100 | 100 | 83.5092 | 100
13 | opkuis &amp;amp;amp; afwerken | 2013-10-21 08:00 | 2013-10-25 17:00 | 5d |  | 0 | 0 | 26.665 | 1066.6 | 1066.6 | 2014-04-28 08:00 | 3d | 639.96 | 0 | 0 | 426.64 | 0 | 1066.6 | 0 | 100% | Finished | 1066.6 | 1066.6 | 100 | 60 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes | 2013-05-06
1:00 - 2:00 | No | Tuesday | Yes | 2013-05-07
2:00 - 3:00 | No | Wednesday | Yes | 2013-05-08
3:00 - 4:00 | No | Thursday | Yes | 2013-05-09
4:00 - 5:00 | No | Friday | Yes | 2013-05-10
5:00 - 6:00 | No | Saturday | No | 2013-07-22
6:00 - 7:00 | No | Sunday | No | 2013-07-23
7:00 - 8:00 | No |  |  | 2013-07-24
8:00 - 9:00 | Yes |  |  | 2013-07-25
9:00 - 10:00 | Yes |  |  | 2013-07-26
10:00 - 11:00 | Yes |  |  | 2013-07-29
11:00 - 12:00 | Yes |  |  | 2013-07-30
12:00 - 13:00 | No |  |  | 2013-07-31
13:00 - 14:00 | Yes |  |  | 2013-08-01
14:00 - 15:00 | Yes |  |  | 2013-08-02
15:00 - 16:00 | Yes |  |  | 2013-08-05
16:00 - 17:00 | Yes |  |  | 2013-08-06
17:00 - 18:00 | No |  |  | 2013-08-07
18:00 - 19:00 | No |  |  | 2013-08-08
19:00 - 20:00 | No |  |  | 2013-08-09
20:00 - 21:00 | No |  |  | 2013-08-12
21:00 - 22:00 | No |  |  | 2013-08-13
22:00 - 23:00 | No |  |  | 2013-08-14
23:00 - 0:00 | No |  |  | 2013-08-15
2013-08-16
2013-12-23
Generated by PMConverter v1.1.3 |  |  |  | 2013-12-24
2013-12-25
2013-12-26
2013-12-27
2013-12-30
2013-12-31
2014-01-01
2014-01-02
2014-01-03
2013-10-28
2013-10-29
2013-10-30
2013-10-31
2013-11-01

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/06, 2013 | 2013-04-08 08:00 | 2013-06-30 17:00 | 309979.3477 | 27738.2717 | 26568.125 | 2013-04-16 12:00 | -282241.076 | 8.948% | 1170.1467 | 104.4% | -48d 4h | 11.82% | 72.62% | 2014-02-18 10:00 | 2018-07-23 17:00 | 2018-05-04 12:00 | 2014-01-27 09:00 | 2018-07-23 17:00 | 2018-05-08 15:00 | 2014-01-23 12:00 | 2017-04-24 11:00 | 2017-02-24 16:00 | 510155.7131 | 489755.4368 | 5430731.9772 | 4118463.101 | 5202755.8288 | 3945845.3785 | 593406.4306 | 589618.463 | 0.11818 | 1.044 | 0.089484 | 0.72624 | -48.5 | 1.044 | 1 | 0.11818 | 1
31/07, 2013 | 2013-06-30 17:00 | 2013-07-31 16:00 | 321361.3477 | 142153.7612 | 138211.1172 | 2013-05-03 09:00 | -179207.5865 | 44.23% | 3942.644 | 102.9% | -50d 7h | 27.32% | 75.93% | 2014-01-14 17:00 | 2014-06-17 10:00 | 2014-06-05 15:00 | 2014-01-09 17:00 | 2014-06-17 10:00 | 2014-06-09 15:00 | 2014-01-27 16:00 | 2015-02-06 10:00 | 2015-01-22 17:00 | 507383.2158 | 497144.2032 | 972783.7809 | 1489429.2558 | 949636.8528 | 1451953.1312 | 543320.1431 | 558937.393 | 0.27321 | 1.0285 | 0.44235 | 0.75929 | -50.875 | 1.0285 | 1 | 0.27321 | 1
30/09, 2013 | 2013-07-31 16:00 | 2013-09-30 16:00 | 491658.3452 | 211186.9742 | 234732.3285 | 2013-05-17 16:00 | -280471.371 | 42.95% | -23545.3543 | 89.97% | -76d | 24.66% | 81.52% | 2014-02-17 16:00 | 2014-06-27 11:00 | 2014-08-11 12:00 | 2014-02-05 12:00 | 2014-06-27 11:00 | 2014-07-25 10:00 | 2014-03-03 17:00 | 2015-04-14 14:00 | 2015-06-12 14:00 | 534871.2141 | 568333.8669 | 933477.0707 | 1451878.4624 | 1011380.5143 | 1587578.7683 | 607269.2033 | 624993.0929 | 0.24659 | 0.89969 | 0.42954 | 0.8152 | -76 | 0.89969 | 1 | 0.24659 | 1
31/10, 2013 | 2013-09-30 16:00 | 2013-10-31 16:00 | 511325.8597 | 246584.5129 | 288477.417 | 2013-05-23 15:00 | -264741.3469 | 48.22% | -41892.9041 | 85.48% | -91d 2h | 23.96% | 76.28% | 2014-02-12 09:00 | 2014-05-15 16:00 | 2014-07-15 09:00 | 2014-02-12 09:00 | 2014-05-15 16:00 | 2014-06-16 15:00 | 2014-03-25 10:00 | 2015-05-04 16:00 | 2015-08-03 14:00 | 553218.7638 | 598196.3812 | 837453.8925 | 1393484.7778 | 930720.978 | 1581217.4414 | 627770.8756 | 650274.394 | 0.23958 | 0.85478 | 0.48225 | 0.76284 | -91.25 | 0.85478 | 1 | 0.23958 | 1
30/11, 2013 | 2013-10-31 16:00 | 2013-11-30 16:00 | 511325.8597 | 304066.6009 | 395246.7723 | 2013-06-20 15:00 | -207259.2589 | 59.47% | -91180.1715 | 76.93% | -91d 2h | 34.82% | 73.14% | 2014-01-23 14:00 | 2014-03-11 15:00 | 2014-06-04 10:00 | 2014-03-04 15:00 | 2014-04-28 11:00 | 2014-06-05 17:00 | 2014-03-25 10:00 | 2014-09-26 14:00 | 2014-12-22 17:00 | 602506.0312 | 664656.6743 | 743779.0296 | 990452.8492 | 848293.0765 | 1168936.7471 | 677470.5289 | 697775.5266 | 0.34821 | 0.76931 | 0.59466 | 0.73135 | -91.25 | 0.76931 | 1 | 0.34821 | 1
31/12, 2013 | 2013-11-30 16:00 | 2013-12-31 16:00 | 511325.8597 | 467652.5104 | 410601.8194 | 2013-09-24 17:00 | -43673.3494 | 91.46% | 57050.691 | 113.9% | -58d | 62.58% | 95.08% | 2013-11-18 10:00 | 2013-11-19 10:00 | 2013-10-21 10:00 | 2014-01-23 10:00 | 2014-01-24 12:00 | 2014-01-22 15:00 | 2014-02-05 17:00 | 2014-02-25 15:00 | 2014-02-19 10:00 | 454275.1688 | 448947.2924 | 458353.7558 | 480389.1303 | 452528.3172 | 471875.5134 | 450519.9553 | 452744.6852 | 0.62581 | 1.1389 | 0.91459 | 0.95079 | -58 | 1.1389 | 1 | 0.62581 | 1
Actual Schedule | 2013-12-31 16:00 | 2014-04-30 16:00 | 511325.8597 | 511325.8597 | 440394.1596 | 2013-10-25 17:00 | 0 | 100% | 70931.7001 | 116.1% | -117d 7h | 50.45% | 100% | 2013-10-25 17:00 | 2013-10-25 17:00 | 2013-10-03 11:00 | 2014-04-30 16:00 | 2014-04-30 16:00 | 2014-04-30 16:00 | 2014-04-30 16:00 | 2014-04-30 16:00 | 2014-04-30 16:00 | 440394.1596 | 440394.1596 | 440394.1596 | 440394.1596 | 440394.1596 | 440394.1596 | 440394.1596 | 440394.1596 | 0.50447 | 1.1611 | 1 | 1 | -117.875 | 1.1611 | 1 | 0.50447 | 1