## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Retirement Apartments | 1 |  |  | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 | 1187.375
1 | afbraak | 1.1 |  | FS2;FS10 | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 81.375
2 | gesloten ruwbouw | 1.2 | 1FS | FS3-25w | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 674.375
3 | voltooiing | 1.3 | 2FS-25w | SS4-18w;SS5;SS6-18w;SS7;SS8 | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 480.375
11 | technische installaties | 1.4 |  |  | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 | 480.375
4 | electrische installaties | 1.4.1 | 3SS-18w | FS9-22w | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 480.375
5 | HVAC | 1.4.2 | 3SS |  | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 345.375
6 | sanitaire installaties | 1.4.3 | 3SS-18w | FS9-22w | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 480.375
7 | liftinstallatie | 1.4.4 | 3SS |  | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 345.375
12 | uitrusting | 1.5 |  |  | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 | 387.375
8 | keukeninstallaties | 1.5.1 | 3SS |  | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 345.375
9 | vast meubilair | 1.5.2 | 4FS-22w;6FS-22w |  | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 177.375
10 | omgevingswerken | 1.6 | 1FS |  | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 55.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Retirement Apartments | 6800h |  |  |  |  | 99 | 100 | 101
1 | afbraak | 480h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | gesloten ruwbouw | 3864h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | voltooiing | 2760h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | technische installaties | 2760h |  |  |  |  | 99 | 100 | 101
4 | electrische installaties | 2760h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | HVAC | 1984h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | sanitaire installaties | 2760h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | liftinstallatie | 1984h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | uitrusting | 2224h |  |  |  |  | 99 | 100 | 101
8 | keukeninstallaties | 1984h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | vast meubilair | 1024h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | omgevingswerken | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2008-09-30 17:00 |  | TP Name | 30/09, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 22d | [5 empty] | 21040 |  | 0.3728% |  | 55759.0353 | 67840.1568
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 22d | 67840.1568 | 157265.818 | 51d | -46800.1568 | 0 | 21040 | 157265.818 | 30.14% | Started | 55759.0353 | 67840.1568 | 100 | 36.6667 | 30.137 | 100 | 11.3718 | 30.137
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 |  | 0 | 0 | 6076079 | 483d | 0 | 0 | 0 | 6076079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2008-10-31 16:00 |  | TP Name | 31/10, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 44d 7h | [5 empty] | 85856.8516 |  | 0.4948% |  | 74007.4449 | 138378.5016
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 32d | 98676.5917 | 148014.8875 | 48d | -12819.7401 | 0 | 85856.8516 | 148014.8875 | 40% | Started | 74007.4449 | 138378.5016 | 100 | 53.3333 | 40 | 100 | 46.4044 | 40
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 |  | 0 | 0 | 6076079 | 483d | 0 | 0 | 0 | 6076079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2008-11-30 16:00 |  | TP Name | 30/11, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 65d | [5 empty] | 120985.9805 |  | 0.9137% |  | 136661.4748 | 185018.6094
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 65d | 200436.8268 | 70923.8003 | 23d | -79450.8464 | 0 | 120985.9805 | 70923.8003 | 73.86% | Started | 136661.4748 | 185018.6094 | 100 | 108.3333 | 73.8636 | 100 | 65.3912 | 73.8636
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 |  | 0 | 0 | 6076079 | 483d | 0 | 0 | 0 | 6076079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2008-12-31 16:00 |  | TP Name | 31/12, 2008
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 87d 7h | [5 empty] | 173497.3594 |  | 1.123% |  | 168027.1015 | 185018.6094
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 89d | 274444.2706 | 27752.7914 | 9d | -100946.9112 | 0 | 173497.3594 | 27752.7914 | 90.82% | Started | 168027.1015 | 185018.6094 | 100 | 148.3333 | 90.8163 | 100 | 93.7729 | 90.8163
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 |  | 0 | 0 | 6076079 | 483d | 0 | 0 | 0 | 6076079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2009-01-31 16:00 |  | TP Name | 31/01, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 110d | [5 empty] | 228795.6094 |  | 1.237% |  | 185018.6094 | 185018.6094
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 |  | 0 | 0 | 6076079 | 483d | 0 | 0 | 0 | 6076079 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2009-04-30 16:00 |  | TP Name | 30/04, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 173d 7h | [5 empty] | 304874.6094 |  | 3.904% |  | 583834.6136 | 611161.8312
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 34d | 427715.706 | 6088658.8737 | 484d | -351636.706 | 0 | 76079 | 6088658.8737 | 6.564% | Started | 398816.0042 | 426143.2218 | 100 | 7.0393 | 6.5637 | 100 | 1.2521 | 6.5637
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2009-05-31 16:00 |  | TP Name | 31/05, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 195d | [5 empty] | 402230.1094 |  | 5.432% |  | 812376.6899 | 876911.6632
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 54d | 679313.1801 | 5899960.7681 | 469d | -505878.6801 | 0 | 173434.5 | 5899960.7681 | 10.33% | Started | 627358.0805 | 691893.0538 | 100 | 11.1801 | 10.325 | 100 | 2.8544 | 10.325
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2009-06-30 16:00 |  | TP Name | 30/06, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 216d 7h | [5 empty] | 686985.1094 |  | 7.107% |  | 1062931.1859 | 1152096.4005
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 76d | 956070.4017 | 5660943.1677 | 450d | -497880.9017 | 0 | 458189.5 | 5660943.1677 | 14.45% | Started | 877912.5765 | 967077.7911 | 100 | 15.735 | 14.4487 | 100 | 7.5409 | 14.4487
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2009-07-31 16:00 |  | TP Name | 31/07, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 239d 7h | [5 empty] | 686985.1094 |  | 8.883% |  | 1328615.2479 | 1441433.4958
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 99d | 1245407.4969 | 5371606.0725 | 427d | -787217.9969 | 0 | 458189.5 | 5371606.0725 | 18.82% | Started | 1143596.6385 | 1256414.8864 | 100 | 20.4969 | 18.8213 | 100 | 7.5409 | 18.8213
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2009-08-31 16:00 |  | TP Name | 31/08, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 260d 7h | [5 empty] | 991534.6094 |  | 10.51% |  | 1571196.3284 | 1705610.8436
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 120d | 1509584.8447 | 5107428.7246 | 406d | -746845.8447 | 0 | 762739 | 5107428.7246 | 22.81% | Started | 1386177.719 | 1520592.2342 | 100 | 24.8447 | 22.8137 | 100 | 12.5531 | 22.8137
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2009-09-30 16:00 |  | TP Name | 30/09, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 282d 7h | [5 empty] | 1243936.1094 |  | 12.2% |  | 1825328.9449 | 1982368.0651
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 142d | 1786342.0663 | 4830671.5031 | 384d | -771201.5663 | 0 | 1015140.5 | 4830671.5031 | 27% | Started | 1640310.3355 | 1797349.4557 | 100 | 29.3996 | 26.9962 | 100 | 16.7072 | 26.9962
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2009-10-31 16:00 |  | TP Name | 31/10, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 305d | [5 empty] | 1468075.6094 |  | 13.44% |  | 2010068.0516 | 2260697.7709
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 164d | 2063099.2878 | 4805511.7557 | 382d | -823819.2878 | 0 | 1239280 | 4805511.7557 | 30.04% | Started | 1825049.4423 | 2075679.1615 | 100 | 33.9545 | 30.0366 | 100 | 20.396 | 30.0366
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP13
| TP Status Date | 2009-11-30 16:00 |  | TP Name | 30/11, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 325d 7h | [5 empty] | 1613780.1094 |  | 15% |  | 2243763.3839 | 2523302.6345
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 185d | 2327276.6356 | 4541334.4079 | 361d | -942292.1356 | 0 | 1384984.5 | 4541334.4079 | 33.88% | Started | 2058744.7745 | 2338284.0251 | 100 | 38.3023 | 33.8828 | 100 | 22.7941 | 33.8828
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP14
| TP Status Date | 2009-12-31 16:00 |  | TP Name | 31/12, 2009
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 348d 7h | [5 empty] | 1686239.6094 |  | 16.51% |  | 2469012.3616 | 2812639.7297
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 209d | 2629193.6046 | 4365216.176 | 347d | -1171749.6046 | 0 | 1457444 | 4365216.176 | 37.59% | Started | 2283993.7522 | 2627621.1203 | 100 | 43.2712 | 37.5899 | 100 | 23.9866 | 37.5899
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP15
| TP Status Date | 2010-01-31 16:00 |  | TP Name | 31/01, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 370d | [5 empty] | 1807855.1094 |  | 18.04% |  | 2698504.6165 | 3078389.5618
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 230d | 2893370.9524 | 4101038.8282 | 326d | -1314311.4524 | 0 | 1579059.5 | 4101038.8282 | 41.37% | Started | 2513486.0072 | 2893370.9524 | 100 | 47.619 | 41.3669 | 100 | 25.9881 | 41.3669
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP16
| TP Status Date | 2010-02-28 16:00 |  | TP Name | 28/02, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 390d | [5 empty] | 2116364.1094 |  | 19.34% |  | 2892718.6194 | 3329987.0359
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 250d | 3144968.4265 | 3912340.7226 | 311d | -1257399.9265 | 0 | 1887568.5 | 3912340.7226 | 44.56% | Started | 2707700.01 | 3144968.4265 | 100 | 51.7598 | 44.5633 | 100 | 31.0656 | 44.5633
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP17
| TP Status Date | 2010-03-31 16:00 |  | TP Name | 31/03, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 412d 7h | [5 empty] | 2559687.6094 |  | 21.01% |  | 3141827.0457 | 3617751.6469
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 273d | 3434305.5217 | 3623003.6273 | 288d | -1103413.5217 | 0 | 2330892 | 3623003.6273 | 48.66% | Started | 2956808.4363 | 3432733.0375 | 100 | 56.5217 | 48.6631 | 100 | 38.3618 | 48.6631
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 |  | 0 | 0 | 919103 | 345d | 0 | 0 | 0 | 919103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP18
| TP Status Date | 2010-04-30 16:00 |  | TP Name | 30/04, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 434d 7h | [5 empty] | 2899625.9219 |  | 22.87% |  | 3420065.8212 | 3983339.1186
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 295d | 3711062.7433 | 3346246.4058 | 266d | -1084363.2433 | 0 | 2626699.5 | 3346246.4058 | 52.58% | Started | 3195086.211 | 3709490.2591 | 100 | 61.0766 | 52.5847 | 100 | 43.2302 | 52.5847
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 14d 7h | [5 empty] | 44130.8125 |  | 1.152% |  | 39961.0007 | 88830.2501
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 15d | 39961 | 879142 | 330d | 4169.8125 | 0 | 44130.8125 | 879142 | 4.348% | Started | 39961.0007 | 39627.9917 | 100 | 4.3478 | 4.3478 | 100 | 4.8015 | 4.3478
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 49202.2585 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP19
| TP Status Date | 2010-05-31 16:00 |  | TP Name | 31/05, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 455d 7h | [5 empty] | 3419244.4219 |  | 24.74% |  | 3700793.9131 | 4372923.8784
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 316d | 3975240.0911 | 3082069.058 | 245d | -828922.0911 | 0 | 3146318 | 3082069.058 | 56.33% | Started | 3422532.972 | 3973667.6069 | 100 | 65.4244 | 56.328 | 100 | 51.782 | 56.328
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 35d 7h | [5 empty] | 44130.8125 |  | 2.687% |  | 93242.3316 | 214237.6621
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 35d | 93242.3333 | 825860.6667 | 310d | -49111.5208 | 0 | 44130.8125 | 825860.6667 | 10.14% | Started | 93242.3316 | 95573.3917 | 100 | 10.1449 | 10.1449 | 100 | 4.8015 | 10.1449
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 118664.2704 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP20
| TP Status Date | 2010-06-30 16:00 |  | TP Name | 30/06, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 477d 7h | [5 empty] | 3922660.1719 |  | 26.87% |  | 4019342.6343 | 4781060.2934
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 340d | 4277157.06 | 2780152.089 | 221d | -627423.31 | 0 | 3649733.75 | 2780152.089 | 60.61% | Started | 3682472.231 | 4250424.8284 | 100 | 70.3934 | 60.6061 | 100 | 60.0673 | 60.6061
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 57d 7h | [5 empty] | 44130.8125 |  | 4.376% |  | 151851.7939 | 345616.8556
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 57d | 151851.8 | 767251.2 | 288d | -107720.9875 | 0 | 44130.8125 | 767251.2 | 16.52% | Started | 151851.7939 | 154182.8583 | 100 | 16.5217 | 16.5217 | 100 | 4.8015 | 16.5217
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 191433.9972 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP21
| TP Status Date | 2010-07-31 16:00 |  | TP Name | 31/07, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 500d | [5 empty] | 4257200.1719 |  | 28.28% |  | 4230096.2269 | 5191515.6653
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 362d | 4553914.2816 | 2666933.2257 | 212d | -569640.5316 | 0 | 3984273.75 | 2666933.2257 | 63.07% | Started | 3831952.2803 | 4528754.5342 | 100 | 74.9482 | 63.0662 | 100 | 65.5731 | 63.0662
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 |  | 0 | 0 | 4047450.5 | 345d | 0 | 0 | 0 | 4047450.5 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 80d | [5 empty] | 44130.8125 |  | 6.142% |  | 213125.3373 | 477742.5217
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 80d | 213125.3333 | 705977.6667 | 265d | -168994.5208 | 0 | 44130.8125 | 705977.6667 | 23.19% | Started | 213125.3373 | 213125.3333 | 100 | 23.1884 | 23.1884 | 100 | 4.8015 | 23.1884
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 |  | 0 | 0 | 1193592.375 | 248d | 0 | 0 | 0 | 1193592.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 |  | 0 | 0 | 1141161.625 | 345d | 0 | 0 | 0 | 1141161.625 | 0% | Not Started | 0 | 264617.1884 | 100 |  | 0 | 100 |  | 0
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP22
| TP Status Date | 2010-08-31 16:00 |  | TP Name | 31/08, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 521d 7h | [5 empty] | 4573279.9844 |  | 32.45% |  | 4853930.6789 | 5920757.4708
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 384d | 4830671.5031 | 2390176.0041 | 190d | -532477.1281 | 0 | 4298194.375 | 2390176.0041 | 66.9% | Started | 4064833.29 | 4803939.2715 | 100 | 79.5031 | 66.899 | 100 | 70.7396 | 66.899
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 16d 7h | 197973.1223 | 3849477.3777 | 328d 1h | -197973.1223 | 0 | 0 | 3849477.3777 | 4.891% | Started | 197973.1203 | 197973.1223 | 100 | 4.8913 | 4.8913 | 100 |  | 4.8913
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 101d 7h | [5 empty] | 46290 |  | 11.7% |  | 406105.6592 | 704314.4742
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 101d | 269070.7333 | 650032.2667 | 244d | -222780.7333 | 0 | 46290 | 650032.2667 | 29.28% | Started | 269070.7459 | 271401.7917 | 100 | 29.2754 | 29.2754 | 100 | 5.0364 | 29.2754
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 16d 7h | 81217.2231 | 1112375.1519 | 231d 1h | -81217.2231 | 0 | 0 | 1112375.1519 | 6.804% | Started | 81217.2257 | 81217.2231 | 100 | 6.8044 | 6.8044 | 100 |  | 6.8044
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 16d 7h | 55817.6882 | 1085343.9368 | 328d 1h | -55817.6882 | 0 | 0 | 1085343.9368 | 4.891% | Started | 55817.6876 | 336973.4509 | 100 | 4.8913 | 4.8913 | 100 |  | 4.8913
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 14722.0086 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 29511.9934
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 29511.9934 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP23
| TP Status Date | 2010-09-30 16:00 |  | TP Name | 30/09, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 543d 7h | [5 empty] | 5171155.6094 |  | 36.5% |  | 5459046.5216 | 6750543.4054
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 407d | 5120008.5983 | 2415335.7516 | 192d | -326678.7233 | 0 | 4793329.875 | 2415335.7516 | 67.95% | Started | 4128487.7007 | 5080696.493 | 100 | 84.265 | 67.9466 | 100 | 78.8885 | 67.9466
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 43d | 504464.8449 | 3542985.6551 | 302d | -504464.8449 | 0 | 0 | 3542985.6551 | 12.46% | Started | 504464.8332 | 456071.415 | 100 | 12.4638 | 12.4638 | 100 |  | 12.4638
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 123d 7h | [5 empty] | 149030.125 |  | 18.47% |  | 641075.3783 | 960769.9993
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 123d | 327680.2 | 591422.8 | 222d | -259840.2 | 0 | 67840 | 591422.8 | 35.65% | Started | 327680.1876 | 330011.2583 | 100 | 35.6522 | 35.6522 | 100 | 7.3811 | 35.6522
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 39d | 187702.0267 | 1005890.3483 | 209d | -144003.4017 | 0 | 43698.625 | 1005890.3483 | 15.73% | Started | 187702.0256 | 187100.4177 | 100 | 15.7258 | 15.7258 | 100 | 3.6611 | 15.7258
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 38d | 125693.1645 | 1015468.4605 | 307d | -88201.6645 | 0 | 37491.5 | 1015468.4605 | 11.01% | Started | 125693.1651 | 409743.1777 | 100 | 11.0145 | 11.0145 | 100 | 3.2854 | 11.0145
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 33915.1457 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 67986.8886
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 67986.8886 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP24
| TP Status Date | 2010-10-31 16:00 |  | TP Name | 31/10, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 565d | [5 empty] | 5599948.4219 |  | 41.24% |  | 6167425.0681 | 7547326.4903
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 428d | 5384185.9462 | 2151158.4037 | 171d | -288432.6962 | 0 | 5095753.25 | 2151158.4037 | 71.45% | Started | 4341505.5443 | 5346446.3251 | 100 | 88.6128 | 71.4524 | 100 | 83.8658 | 71.4524
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 65d | 762563.1377 | 3284887.3623 | 280d | -741913.1377 | 0 | 20650 | 3284887.3623 | 18.84% | Started | 762563.1368 | 703904.4348 | 100 | 18.8406 | 18.8406 | 100 | 0.5102 | 18.8406
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 145d | [5 empty] | 254749.5625 |  | 25.31% |  | 878337.7776 | 1207025.5888
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 145d | 386289.6667 | 532813.3333 | 200d | -291417.3542 | 0 | 94872.3125 | 532813.3333 | 42.03% | Started | 386289.6567 | 386289.6667 | 100 | 42.029 | 42.029 | 100 | 10.3223 | 42.029
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 61d | 293585.2213 | 900007.1537 | 187d | -214207.2213 | 0 | 79378 | 900007.1537 | 24.6% | Started | 293585.2259 | 288772.3488 | 100 | 24.5968 | 24.5968 | 100 | 6.6503 | 24.5968
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 60d | 198462.8913 | 942698.7337 | 285d | -117963.6413 | 0 | 80499.25 | 942698.7337 | 17.39% | Started | 198462.895 | 479618.654 | 100 | 17.3913 | 17.3913 | 100 | 7.0541 | 17.3913
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 52344.9194 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 104931.5323
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 104931.5323 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP25
| TP Status Date | 2010-11-30 16:00 |  | TP Name | 30/11, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 586d 7h | [5 empty] | 6372564.4219 |  | 45.77% |  | 6846184.3816 | 8372397.732
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 450d | 5660943.1677 | 1874401.1822 | 149d | -273356.2927 | 0 | 5387586.875 | 1874401.1822 | 75.13% | Started | 4564667.1983 | 5621631.0624 | 100 | 93.1677 | 75.1252 | 100 | 88.6688 | 75.1252
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 86d | 1008929.6899 | 3108911.2536 | 265d | -848607.1899 | 0 | 160322.5 | 3108911.2536 | 24.5% | Started | 991683.0498 | 960536.26 | 100 | 24.9275 | 24.5014 | 100 | 3.9611 | 24.5014
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 166d 7h | [5 empty] | 595859.4375 |  | 31.84% |  | 1104815.5242 | 1462023.9803
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 166d | 442235.0667 | 476867.9333 | 179d | -163078.0042 | 0 | 279157.0625 | 476867.9333 | 48.12% | Started | 442235.0653 | 444566.125 | 100 | 48.1159 | 48.1159 | 100 | 30.3728 | 48.1159
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 82d | 394655.5433 | 798936.8317 | 166d | -302641.0433 | 0 | 92014.5 | 798936.8317 | 33.06% | Started | 394655.5583 | 394053.9343 | 100 | 33.0645 | 33.0645 | 100 | 7.709 | 33.0645
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 81d | 267924.9033 | 873236.7217 | 264d | -43237.0283 | 0 | 224687.875 | 873236.7217 | 23.48% | Started | 267924.9006 | 551974.9164 | 100 | 23.4783 | 23.4783 | 100 | 19.6894 | 23.4783
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 71429.0045 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 143187.8201
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 143187.8201 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP26
| TP Status Date | 2010-12-31 16:00 |  | TP Name | 31/12, 2010
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 609d 7h | [5 empty] | 8698517.4531 |  | 50.94% |  | 7618694.0209 | 9239901.2091
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 473d | 5950280.2629 | 1585064.087 | 126d | 31047.4871 | 0 | 5981327.75 | 1585064.087 | 78.96% | Started | 4797972.3004 | 5910968.1576 | 100 | 97.9296 | 78.9649 | 100 | 98.4406 | 78.9649
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 110d | 1290491.4638 | 2815617.7391 | 240d | -158399.9638 | 0 | 1132091.5 | 2815617.7391 | 31.43% | Started | 1272055.9162 | 1230366.2933 | 100 | 31.8841 | 31.4286 | 100 | 27.9705 | 31.4286
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 189d 7h | [5 empty] | 1356302.5938 |  | 39.3% |  | 1363647.1949 | 1730136.5747
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 190d | 506172.6667 | 412930.3333 | 155d | -48493.3229 | 0 | 457679.3438 | 412930.3333 | 55.07% | Started | 506172.6556 | 505839.6583 | 100 | 55.0725 | 55.0725 | 100 | 49.7963 | 55.0725
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 106d | 510164.4829 | 683427.8921 | 142d | -181505.2954 | 0 | 328659.1875 | 683427.8921 | 42.74% | Started | 510164.4943 | 504750.0013 | 100 | 42.7419 | 42.7419 | 100 | 27.5353 | 42.7419
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 105d | 347310.0598 | 793851.5652 | 240d | 222654.0027 | 0 | 569964.0625 | 793851.5652 | 30.43% | Started | 347310.045 | 628052.3581 | 100 | 30.4348 | 30.4348 | 100 | 49.946 | 30.4348
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 91494.557 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 183411.5741
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 183411.5741 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP27
| TP Status Date | 2011-01-31 16:00 |  | TP Name | 31/01, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 630d 7h | [5 empty] | 8993259.9531 |  | 54.47% |  | 8146977.0377 | 9932903.0958
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 494d | 6214457.6108 | 1559904.3395 | 124d | -233129.8608 | 0 | 5981327.75 | 1559904.3395 | 79.94% | Started | 4856930.5495 | 6076079 | 100 | 102.2774 | 79.9353 | 100 | 98.4406 | 79.9353
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 131d | 1536858.0159 | 2569251.187 | 219d | -349050.7659 | 0 | 1187807.25 | 2569251.187 | 37.43% | Started | 1514902.9559 | 1476732.8455 | 100 | 37.971 | 37.4286 | 100 | 29.347 | 37.4286
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 210d 7h | [5 empty] | 1595329.3438 |  | 45.82% |  | 1590124.9229 | 1974935.0305
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 211d | 562118.0667 | 356984.9333 | 134d | -102575.7229 | 0 | 459542.3438 | 356984.9333 | 61.16% | Started | 562118.0641 | 561785.0583 | 100 | 61.1594 | 61.1594 | 100 | 49.999 | 61.1594
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 127d | 611234.8049 | 582357.5701 | 121d | -76771.4924 | 0 | 534463.3125 | 582357.5701 | 51.21% | Started | 611234.7912 | 605820.3234 | 100 | 51.2097 | 51.2097 | 100 | 44.7777 | 51.2097
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 126d | 416772.0717 | 724389.5533 | 219d | 184551.6158 | 0 | 601323.6875 | 724389.5533 | 36.52% | Started | 416772.0676 | 697514.3701 | 100 | 36.5217 | 36.5217 | 100 | 52.694 | 36.5217
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 109815.2787 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 220137.6104
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 220137.6104 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP28
| TP Status Date | 2011-02-28 16:00 |  | TP Name | 28/02, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 650d 7h | [5 empty] | 9277757.8906 |  | 58.78% |  | 8790589.8447 | 10435656.4713
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 514d | 6466055.0849 | 1308306.8654 | 104d | -484727.3349 | 0 | 5981327.75 | 1308306.8654 | 83.17% | Started | 5053567.4197 | 6076079 | 100 | 106.4182 | 83.1715 | 100 | 98.4406 | 83.1715
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 151d | 1771492.8275 | 2334616.3754 | 199d | -467678.8275 | 0 | 1303814 | 2334616.3754 | 43.14% | Started | 1746185.8278 | 1711367.6571 | 100 | 43.7681 | 43.1429 | 100 | 32.2132 | 43.1429
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 230d 7h | [5 empty] | 1763820.5312 |  | 52.04% |  | 1805817.9878 | 2208076.417
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 231d | 615399.4 | 303703.6 | 114d | -152878.65 | 0 | 462520.75 | 303703.6 | 66.96% | Started | 615399.3848 | 615066.3917 | 100 | 66.9565 | 66.9565 | 100 | 50.3231 | 66.9565
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 147d | 707492.2545 | 486100.1205 | 101d | -19648.7858 | 0 | 687843.4688 | 486100.1205 | 59.27% | Started | 707492.2201 | 702077.773 | 100 | 59.2742 | 59.2742 | 100 | 57.628 | 59.2742
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 146d | 482926.3688 | 658235.2562 | 199d | 130529.9437 | 0 | 613456.3125 | 658235.2562 | 42.32% | Started | 482926.3829 | 763668.6672 | 100 | 42.3188 | 42.3188 | 100 | 53.7572 | 42.3188
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 |  | 0 | 0 | 216359 | 248d | 0 | 0 | 0 | 216359 | 0% | Not Started | 0 | 127263.5852 | 100 |  | 0 | 100 |  | 0
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 255114.7878
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 255114.7878 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP29
| TP Status Date | 2011-03-31 16:00 |  | TP Name | 31/03, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 673d 7h | [5 empty] | 9753794.5703 |  | 62.35% |  | 9324578.7343 | 11091135.7931
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 537d | 6755392.1801 | 1366488.7813 | 108d 5h | -645469.2504 | 0 | 6109922.9297 | 1366488.7813 | 83.17% | Started | 5053567.4197 | 6076079 | 100 | 111.1801 | 83.1715 | 100 | 100.557 | 83.1715
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 174d | 2041322.8609 | 2064786.342 | 176d | -485816.3609 | 0 | 1555506.5 | 2064786.342 | 49.71% | Started | 2012161.0823 | 1981197.6904 | 100 | 50.4348 | 49.7143 | 100 | 38.4318 | 49.7143
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 253d 7h | [5 empty] | 1859569.5312 |  | 59.76% |  | 2073831.6229 | 2476189.0115
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 254d | 676672.9333 | 242430.0667 | 91d | -212942.2771 | 0 | 463730.6562 | 242430.0667 | 73.62% | Started | 676672.9144 | 676339.925 | 100 | 73.6232 | 73.6232 | 100 | 50.4547 | 73.6232
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 170d | 818188.3216 | 375404.0534 | 78d | -130344.8528 | 0 | 687843.4688 | 375404.0534 | 68.55% | Started | 818188.3239 | 812773.84 | 100 | 68.5484 | 68.5484 | 100 | 57.628 | 68.5484
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 169d | 559003.8105 | 582157.8145 | 176d | 106717.5957 | 0 | 665721.4062 | 582157.8145 | 48.99% | Started | 559003.8201 | 839746.1088 | 100 | 48.9855 | 48.9855 | 100 | 58.3372 | 48.9855
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 22d 7h | 19956.5005 | 196293.4476 | 225d | 22317.4995 | 0 | 42274 | 196293.4476 | 9.228% | Started | 19966.5645 | 147329.1376 | 100 | 9.2238 | 9.2284 | 100 | 19.5388 | 9.2284
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 372651.4819
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 295338.5418 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 77312.9401 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP30
| TP Status Date | 2011-04-30 16:00 |  | TP Name | 30/04, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 695d | [5 empty] | 10115268.1328 |  | 65.76% |  | 9835544.459 | 11708698.0981
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 558d | 7019569.528 | 1419953.2446 | 112d 7h | -855391.4108 | 0 | 6164178.1172 | 1419953.2446 | 83.17% | Started | 5053567.4197 | 6076079 | 100 | 115.528 | 83.1715 | 100 | 101.4499 | 83.1715
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 196d | 2299421.1536 | 1806688.0493 | 154d | -656883.4036 | 0 | 1642537.75 | 1806688.0493 | 56% | Started | 2266572.2896 | 2229030.7101 | 100 | 56.8116 | 56 | 100 | 40.582 | 56
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 275d | [5 empty] | 2079756.6562 |  | 67.15% |  | 2330386.1402 | 2722444.6009
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 276d | 735282.4 | 183820.6 | 69d | -271551.7438 | 0 | 463730.6562 | 183820.6 | 80% | Started | 735282.411 | 732618.3333 | 100 | 80 | 80 | 100 | 50.4547 | 80
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 192d | 924071.5161 | 269520.8589 | 56d | -109751.0474 | 0 | 814320.4688 | 269520.8589 | 77.42% | Started | 924071.4886 | 914445.7712 | 100 | 77.4194 | 77.4194 | 100 | 68.2243 | 77.4194
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 191d | 631773.5373 | 509388.0877 | 154d | 54812.4939 | 0 | 686586.0312 | 509388.0877 | 55.36% | Started | 631773.5499 | 909621.5851 | 100 | 55.3623 | 55.3623 | 100 | 60.1655 | 55.3623
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 45d | 39258.6895 | 177100.3105 | 203d | 75860.8105 | 0 | 115119.5 | 177100.3105 | 18.15% | Started | 39258.6908 | 165758.9113 | 100 | 18.1452 | 18.1452 | 100 | 53.2076 | 18.1452
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 496125.1777
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 332283.1855 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 163841.9922 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP31
| TP Status Date | 2011-05-31 16:00 |  | TP Name | 31/05, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 716d 7h | [5 empty] | 10365846.8906 |  | 69.63% |  | 10414331.8439 | 12348185.6921
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 580d | 7296326.7495 | 1320886.7391 | 105d | -1112575.1557 | 0 | 6183751.5938 | 1320886.7391 | 84.67% | Started | 5144709.2421 | 6076079 | 100 | 120.0828 | 84.6715 | 100 | 101.7721 | 84.6715
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 217d | 2545787.7058 | 1560321.4971 | 133d | -765194.9558 | 0 | 1780592.75 | 1560321.4971 | 62% | Started | 2509419.3293 | 2485662.5353 | 100 | 62.8986 | 62 | 100 | 43.9929 | 62
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 296d 7h | [5 empty] | 2172706.9375 |  | 74.21% |  | 2575184.663 | 2977442.9924
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 297d | 791227.8 | 127875.2 | 48d | -297394.4875 | 0 | 493833.3125 | 127875.2 | 86.09% | Started | 791227.8195 | 790894.7917 | 100 | 86.087 | 86.087 | 100 | 53.7299 | 86.087
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 213d | 1025141.8382 | 168450.5368 | 35d | -188197.9945 | 0 | 836943.8438 | 168450.5368 | 85.89% | Started | 1025141.8566 | 1019727.3567 | 100 | 85.8871 | 85.8871 | 100 | 70.1197 | 85.8871
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 212d | 701235.5493 | 439926.0757 | 133d | 11961.732 | 0 | 713197.2812 | 439926.0757 | 61.45% | Started | 701235.5725 | 981977.8476 | 100 | 61.4493 | 61.4493 | 100 | 62.4975 | 61.4493
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 66d | 57579.4113 | 158779.5887 | 182d | 71153.0887 | 0 | 128732.5 | 158779.5887 | 26.61% | Started | 57579.4144 | 184842.9965 | 100 | 26.6129 | 26.6129 | 100 | 59.4995 | 26.6129
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 623982.555
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 370539.4733 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 |  | 0 | 0 | 524294.375 | 128d | 0 | 0 | 0 | 524294.375 | 0% | Not Started | 0 | 253443.0817 | 100 |  | 0 | 100 |  | 0
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 |  | 0 | 0 | 219538.7656 | 40d | 0 | 0 | 0 | 219538.7656 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP32
| TP Status Date | 2011-06-30 16:00 |  | TP Name | 30/06, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 738d 7h | [5 empty] | 11224846.4844 |  | 74.39% |  | 11125759.6815 | 13034549.1953
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 603d | 7585663.8447 | 1283147.118 | 102d | -922783.0322 | 0 | 6662880.8125 | 1283147.118 | 85.53% | Started | 5196986.6791 | 6076079 | 100 | 124.8447 | 85.5319 | 100 | 109.6576 | 85.5319
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 241d | 2827349.4797 | 1278759.7232 | 109d | -814411.9797 | 0 | 2012937.5 | 1278759.7232 | 68.86% | Started | 2786958.8721 | 2743760.8281 | 100 | 69.8551 | 68.8571 | 100 | 49.7335 | 68.8571
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 318d 7h | [5 empty] | 2253625.4375 |  | 82.27% |  | 2854954.2039 | 3233898.5175
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 321d | 855165.4 | 63937.6 | 24d | -330585.5875 | 0 | 524579.8125 | 63937.6 | 93.04% | Started | 855165.3824 | 849504.2583 | 100 | 93.0435 | 93.0435 | 100 | 57.0752 | 93.0435
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 237d | 1140650.7777 | 52941.5973 | 11d | -283569.559 | 0 | 857081.2188 | 52941.5973 | 95.56% | Started | 1140650.7571 | 1125610.5512 | 100 | 95.5645 | 95.5645 | 100 | 71.8069 | 95.5645
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 236d | 780620.7058 | 360540.9192 | 109d | -41068.7995 | 0 | 739551.9062 | 360540.9192 | 68.41% | Started | 780620.6829 | 1054747.5744 | 100 | 68.4058 | 68.4058 | 100 | 64.8069 | 68.4058
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 90d | 78517.379 | 137841.621 | 158d | 53895.121 | 0 | 132412.5 | 137841.621 | 36.29% | Started | 78517.3815 | 204036.1336 | 100 | 36.2903 | 36.2903 | 100 | 61.2004 | 36.2903
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 18d 7h | [5 empty] | 66607.125 |  | 8.339% |  | 79887.4401 | 752570.5458
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 409014.3684 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 18d 7h | 77312.9401 | 430085.2295 | 105d | -10705.8151 | 0 | 66607.125 | 430085.2295 | 15.24% | Started | 79887.4401 | 343556.1774 | 100 | 14.7461 | 15.2371 | 100 | 12.7041 | 15.2371
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 4d | 21953.8766 | 197584.8891 | 36d | -21953.8766 | 0 | 0 | 197584.8891 | 10% | Started | 21953.8769 | 43221.6945 | 100 | 10 | 10 | 100 |  | 10

## TP33
| TP Status Date | 2011-07-31 16:00 |  | TP Name | 31/07, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 760d | [5 empty] | 11751144.4219 |  | 78.1% |  | 11680692.1687 | 13716016.3842
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 624d | 7849841.1925 | 1018969.7702 | 81d | -1186960.38 | 0 | 6662880.8125 | 1018969.7702 | 88.51% | Started | 5377976.3172 | 6076079 | 100 | 129.1925 | 88.5106 | 100 | 109.6576 | 88.5106
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 263d | 3085447.7725 | 1020661.4304 | 87d | -691918.6475 | 0 | 2393529.125 | 1020661.4304 | 75.14% | Started | 3041369.8382 | 2991593.8478 | 100 | 76.2319 | 75.1429 | 100 | 59.1367 | 75.1429
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 340d | [5 empty] | 2386876.0312 |  | 82.82% |  | 2874147.3356 | 3440357.0924
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 343d | 913774.8667 | 68266.7083 | 25d 5h | -349363.3042 | 0 | 564411.5625 | 68266.7083 | 93.04% | Started | 855165.3824 | 905782.6667 | 100 | 99.4203 | 93.0435 | 100 | 61.409 | 93.0435
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 259d | 1246533.9723 | 57754.4698 | 12d | -389452.7535 | 0 | 857081.2188 | 57754.4698 | 95.56% | Started | 1140650.7571 | 1193592.375 | 100 | 104.4355 | 95.5645 | 100 | 71.8069 | 95.5645
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 258d | 853390.4326 | 394031.5321 | 119d 1h | -20419.6826 | 0 | 832970.75 | 394031.5321 | 68.41% | Started | 780620.6829 | 1124623.0507 | 100 | 74.7826 | 68.4058 | 100 | 72.9932 | 68.4058
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 112d | 97710.5161 | 118648.4839 | 136d | 34701.9839 | 0 | 132412.5 | 118648.4839 | 45.16% | Started | 97710.5132 | 216359 | 100 | 45.1613 | 45.1613 | 100 | 61.2004 | 45.1613
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 40d | [5 empty] | 79062.8438 |  | 18.81% |  | 180226.1914 | 863802.2295
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 433717 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 44d | 180226.1914 | 344068.1836 | 84d | -101163.3477 | 0 | 79062.8438 | 344068.1836 | 34.38% | Started | 180226.1914 | 430085.2295 | 100 | 34.375 | 34.375 | 100 | 15.0799 | 34.375
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 4d | 21953.8766 | 197584.8891 | 36d | -21953.8766 | 0 | 0 | 197584.8891 | 10% | Started | 21953.8769 | 159165.6051 | 100 | 10 | 10 | 100 |  | 10

## TP34
| TP Status Date | 2011-08-31 16:00 |  | TP Name | 31/08, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 782d 7h | [5 empty] | 12242780.9219 |  | 81.92% |  | 12251828.3653 | 14168309.1574
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 624d | 7849841.1925 | 729632.6749 | 58d | -1186960.38 | 0 | 6662880.8125 | 729632.6749 | 91.5% | Started | 5559345.1394 | 6076079 | 100 | 129.1925 | 91.4956 | 100 | 109.6576 | 91.4956
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 285d | 3343546.0652 | 762563.1377 | 65d | -668907.4402 | 0 | 2674638.625 | 762563.1377 | 81.43% | Started | 3295781.0456 | 3259957.4136 | 100 | 82.6087 | 81.4286 | 100 | 66.0821 | 81.4286
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 362d 7h | [5 empty] | 2536217.6562 |  | 83.38% |  | 2893340.4802 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 365d | 972384.3333 | 72595.8167 | 27d 2h | -329785.3958 | 0 | 642598.9375 | 72595.8167 | 93.04% | Started | 855165.3824 | 919103 | 100 | 105.7971 | 93.0435 | 100 | 69.9159 | 93.0435
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 281d | 1352417.1668 | 62567.3422 | 13d | -495335.9481 | 0 | 857081.2188 | 62567.3422 | 95.56% | Started | 1140650.7571 | 1193592.375 | 100 | 113.3065 | 95.5645 | 100 | 71.8069 | 95.5645
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 280d | 926160.1594 | 427935.6094 | 129d 3h | -53514.1594 | 0 | 872646 | 427935.6094 | 68.41% | Started | 780620.6829 | 1141161.625 | 100 | 81.1594 | 68.4058 | 100 | 76.47 | 68.4058
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 134d | 116903.6532 | 99455.3468 | 114d | 46987.8468 | 0 | 163891.5 | 99455.3468 | 54.03% | Started | 116903.6578 | 216359 | 100 | 54.0323 | 54.0323 | 100 | 75.7498 | 54.0323
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 62d 7h | [5 empty] | 104294.375 |  | 28.65% |  | 274435.3369 | 957499.3688
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 433717 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 67d | 274435.3369 | 249859.0381 | 61d | -170140.9619 | 0 | 104294.375 | 249859.0381 | 52.34% | Started | 274435.3369 | 523782.3688 | 100 | 52.3438 | 52.3438 | 100 | 19.8923 | 52.3438
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 8d | 43907.7531 | 175631.0125 | 32d | -7953.9094 | 0 | 35953.8438 | 175631.0125 | 20% | Started | 43907.7538 | 219538.7656 | 100 | 20 | 20 | 100 | 16.377 | 20

## TP35
| TP Status Date | 2011-09-30 16:00 |  | TP Name | 30/09, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 809d | [5 empty] | 13311177.7852 |  | 87.78% |  | 13128630.4988 | 14426919.4563
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 308d | 3613376.0986 | 492733.1043 | 42d | -602193.6611 | 0 | 3011182.4375 | 492733.1043 | 88% | Started | 3561756.4207 | 3518055.7063 | 100 | 89.2754 | 88 | 100 | 74.397 | 88
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 384d 7h | [5 empty] | 2941612.9062 |  | 85.3% |  | 2959991.0356 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 388d | 1033657.8667 | 77257.9333 | 29d | -333923.3198 | 0 | 699734.5469 | 77257.9333 | 93.04% | Started | 855165.3824 | 919103 | 100 | 112.4638 | 93.0435 | 100 | 76.1323 | 93.0435
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 304d | 1463113.2339 | 67981.8238 | 14d 1h | -443980.3589 | 0 | 1019132.875 | 67981.8238 | 95.56% | Started | 1140650.7571 | 1193592.375 | 100 | 122.5806 | 95.5645 | 100 | 85.3837 | 95.5645
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 303d | 1002237.6011 | 380387.2083 | 115d | 24171.3833 | 0 | 1026408.9844 | 380387.2083 | 72.49% | Started | 827205.6921 | 1141161.625 | 100 | 87.8261 | 72.488 | 100 | 89.9442 | 72.488
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 157d | 136969.2056 | 79389.7944 | 91d | 59367.2944 | 0 | 196336.5 | 79389.7944 | 63.31% | Started | 136969.204 | 216359 | 100 | 63.3065 | 63.3065 | 100 | 90.7457 | 63.3065
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 84d 7h | [5 empty] | 151548.6562 |  | 28.65% |  | 274435.3369 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 |  | 0 | 0 | 433717 | 248d | 0 | 0 | 0 | 433717 | 0% | Not Started | 0 | 433717 | 100 |  | 0 | 100 |  | 0
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 89d | 364548.4326 | 331780.0342 | 81d | -212999.7764 | 0 | 151548.6562 | 331780.0342 | 52.34% | Started | 274435.3369 | 524294.375 | 100 | 69.5312 | 52.3438 | 100 | 28.9053 | 52.3438
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 13d | 71350.0988 | 148188.6668 | 27d | 109740.577 | 0 | 181090.6758 | 148188.6668 | 32.5% | Started | 71350.0962 | 219538.7656 | 100 | 32.5 | 32.5 | 100 | 82.4869 | 32.5

## TP36
| TP Status Date | 2011-10-31 16:00 |  | TP Name | 31/10, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 834d | [5 empty] | 15522444.0088 |  | 93.04% |  | 13915729.0735 | 14673286.0085
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 100% | Finished | 4047450.5 | 3764422.2585 | 100 | 95.3623 | 100 | 100 | 107.4576 | 100
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 410d | [5 empty] | 3390270.5596 |  | 90.85% |  | 3152522.0415 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 100% | Finished | 919103 | 919103 | 100 | 118.5507 | 100 | 100 | 107.064 | 100
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 100% | Finished | 1193592.375 | 1193592.375 | 100 | 131.0484 | 100 | 100 | 99.1542 | 100
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 324d | 1071699.613 | 310925.1964 | 94d | -45290.6287 | 0 | 1026408.9844 | 310925.1964 | 77.51% | Started | 884536.7454 | 1141161.625 | 100 | 93.913 | 77.512 | 100 | 89.9442 | 77.512
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 178d | 155289.9274 | 61069.0726 | 70d | 41046.5726 | 0 | 196336.5 | 61069.0726 | 71.77% | Started | 155289.9212 | 216359 | 100 | 71.7742 | 71.7742 | 100 | 90.7457 | 71.7742
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 105d 7h | [5 empty] | 576047.6641 |  | 40.01% |  | 383308.8263 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 20d | 34977.1774 | 122420.121 | 70d | 315444.1741 | 0 | 350421.3516 | 122420.121 | 22.22% | Started | 96381.5563 | 433717 | 100 | 8.0645 | 22.2222 | 100 | 80.7949 | 22.2222
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 110d | 450565.4785 | 372740.5322 | 91d | -224939.166 | 0 | 225626.3125 | 372740.5322 | 54.73% | Started | 286927.2701 | 524294.375 | 100 | 85.9375 | 54.7264 | 100 | 43.0343 | 54.7264
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 13d | 71350.0988 | 148188.6668 | 27d | 109740.577 | 0 | 181090.6758 | 148188.6668 | 32.5% | Started | 71350.0962 | 219538.7656 | 100 | 32.5 | 32.5 | 100 | 82.4869 | 32.5

## TP37
| TP Status Date | 2011-11-30 16:00 |  | TP Name | 30/11, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 847d 7h | [5 empty] | 15645518.6494 |  | 94.65% |  | 14155658.4983 | 14931384.3013
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 100% | Finished | 4047450.5 | 4022520.5513 | 100 | 95.3623 | 100 | 100 | 107.4576 | 100
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 427d 7h | [5 empty] | 3390270.5596 |  | 93.05% |  | 3229046.3074 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 100% | Finished | 919103 | 919103 | 100 | 118.5507 | 100 | 100 | 107.064 | 100
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 100% | Finished | 1193592.375 | 1193592.375 | 100 | 131.0484 | 100 | 100 | 99.1542 | 100
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 345d | 1141161.625 | 241463.1844 | 73d | -114752.6406 | 0 | 1026408.9844 | 241463.1844 | 82.54% | Started | 941867.8666 | 1141161.625 | 100 | 100 | 82.5359 | 100 | 89.9442 | 82.5359
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 200d | 174483.0645 | 41875.9355 | 48d | 21853.4355 | 0 | 196336.5 | 41875.9355 | 80.65% | Started | 174483.0658 | 216359 | 100 | 80.6452 | 80.6452 | 100 | 90.7457 | 80.6452
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 127d 7h | [5 empty] | 699122.3047 |  | 57.07% |  | 546713.9853 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 42d | 73452.0726 | 83945.2258 | 48d | 276969.279 | 0 | 350421.3516 | 83945.2258 | 46.67% | Started | 202401.2675 | 433717 | 100 | 16.9355 | 46.6667 | 100 | 80.7949 | 46.6667
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 132d | 540678.5742 | 282627.4365 | 69d | -191977.6211 | 0 | 348700.9531 | 282627.4365 | 65.67% | Started | 344312.7178 | 524294.375 | 100 | 103.125 | 65.6716 | 100 | 66.5086 | 65.6716
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 13d | 71350.0988 | 148188.6668 | 27d | 109740.577 | 0 | 181090.6758 | 148188.6668 | 32.5% | Started | 71350.0962 | 219538.7656 | 100 | 32.5 | 32.5 | 100 | 82.4869 | 32.5

## TP38
| TP Status Date | 2011-12-31 16:00 |  | TP Name | 31/12, 2011
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 870d | [5 empty] | 15706710.6729 |  | 96.06% |  | 14366992.8402 | 14956314.25
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 100% | Finished | 4047450.5 | 4047450.5 | 100 | 95.3623 | 100 | 100 | 107.4576 | 100
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 450d | [5 empty] | 3390270.5596 |  | 95.33% |  | 3308300.5522 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 100% | Finished | 919103 | 919103 | 100 | 118.5507 | 100 | 100 | 107.064 | 100
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 100% | Finished | 1193592.375 | 1193592.375 | 100 | 131.0484 | 100 | 100 | 99.1542 | 100
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 367d | 1213931.3518 | 168693.4576 | 51d | -187522.3674 | 0 | 1026408.9844 | 168693.4576 | 87.8% | Started | 1001928.9797 | 1141161.625 | 100 | 106.3768 | 87.799 | 100 | 89.9442 | 87.799
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 222d | 193676.2016 | 22682.7984 | 26d | 2660.2984 | 0 | 196336.5 | 22682.7984 | 89.52% | Started | 193676.1975 | 216359 | 100 | 89.5161 | 89.5161 | 100 | 90.7457 | 89.5161
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 150d | [5 empty] | 760314.3281 |  | 70.85% |  | 678794.0824 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 64d | 111926.9677 | 45470.3306 | 26d | 238494.3838 | 0 | 350421.3516 | 45470.3306 | 71.11% | Started | 308420.9852 | 433717 | 100 | 25.8065 | 71.1111 | 100 | 80.7949 | 71.1111
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 154d | 630791.6699 | 262147.1875 | 64d | -220898.6934 | 0 | 409892.9766 | 262147.1875 | 70.64% | Started | 370373.0972 | 524294.375 | 100 | 120.3125 | 70.6422 | 100 | 78.1799 | 70.6422
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 13d | 71350.0988 | 148188.6668 | 27d | 109740.577 | 0 | 181090.6758 | 148188.6668 | 32.5% | Started | 71350.0962 | 219538.7656 | 100 | 32.5 | 32.5 | 100 | 82.4869 | 32.5

## TP39
| TP Status Date | 2012-01-31 16:00 |  | TP Name | 31/01, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 895d | [5 empty] | 16036916.27 |  | 99.32% |  | 14855303.3968 | 14956314.25
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 100% | Finished | 4047450.5 | 4047450.5 | 100 | 95.3623 | 100 | 100 | 107.4576 | 100
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 475d | [5 empty] | 3526000.4902 |  | 100% |  | 3470216 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 100% | Finished | 919103 | 919103 | 100 | 118.5507 | 100 | 100 | 107.064 | 100
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 100% | Finished | 1193592.375 | 1193592.375 | 100 | 131.0484 | 100 | 100 | 99.1542 | 100
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 389d | 1286701.0786 | 0 | 0 | -148372.1636 | 0 | 1138328.915 | 0 | 100% | Finished | 1141161.625 | 1141161.625 | 100 | 112.7536 | 100 | 100 | 99.7518 | 100
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 244d | 212869.3387 | 0 | 0 | 7277.1613 | 0 | 220146.5 | 0 | 100% | Finished | 216359 | 216359 | 100 | 98.3871 | 100 | 100 | 101.7506 | 100
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 171d 7h | [5 empty] | 914627.2148 |  | 89.46% |  | 857000.5218 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 74d | 129415.5565 | 0 | 0 | 269195.4435 | 0 | 398611 | 0 | 100% | Finished | 433717 | 433717 | 100 | 29.8387 | 100 | 100 | 91.9058 | 100
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 176d | 720904.7656 | 172034.0918 | 42d | -204888.5508 | 0 | 516016.2148 | 172034.0918 | 80.73% | Started | 423283.5218 | 524294.375 | 100 | 137.5 | 80.7339 | 100 | 98.4211 | 80.7339
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 35d | 192096.4199 | 0 | 0 | 29157.0356 | 0 | 221253.4556 | 0 | 100% | Finished | 219538.7656 | 219538.7656 | 100 | 87.5 | 100 | 100 | 100.781 | 100

## TP40
| TP Status Date | 2012-02-29 16:00 |  | TP Name | 29/02, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 912d 7h | [5 empty] | 16058066.3501 |  | 99.32% |  | 14855303.3968 | 14956314.25
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 100% | Finished | 4047450.5 | 4047450.5 | 100 | 95.3623 | 100 | 100 | 107.4576 | 100
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 475d | [5 empty] | 3526000.4902 |  | 100% |  | 3470216 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 100% | Finished | 919103 | 919103 | 100 | 118.5507 | 100 | 100 | 107.064 | 100
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 100% | Finished | 1193592.375 | 1193592.375 | 100 | 131.0484 | 100 | 100 | 99.1542 | 100
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 389d | 1286701.0786 | 0 | 0 | -148372.1636 | 0 | 1138328.915 | 0 | 100% | Finished | 1141161.625 | 1141161.625 | 100 | 112.7536 | 100 | 100 | 99.7518 | 100
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 244d | 212869.3387 | 0 | 0 | 7277.1613 | 0 | 220146.5 | 0 | 100% | Finished | 216359 | 216359 | 100 | 98.3871 | 100 | 100 | 101.7506 | 100
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 192d 7h | [5 empty] | 935777.2949 |  | 89.46% |  | 857000.5218 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 74d | 129415.5565 | 0 | 0 | 269195.4435 | 0 | 398611 | 0 | 100% | Finished | 433717 | 433717 | 100 | 29.8387 | 100 | 100 | 91.9058 | 100
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 198d | 811017.8613 | 193538.3533 | 47d 2h | -273851.5664 | 0 | 537166.2949 | 193538.3533 | 80.73% | Started | 423283.5218 | 524294.375 | 100 | 154.6875 | 80.7339 | 100 | 102.4551 | 80.7339
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 35d | 192096.4199 | 0 | 0 | 29157.0356 | 0 | 221253.4556 | 0 | 100% | Finished | 219538.7656 | 219538.7656 | 100 | 87.5 | 100 | 100 | 100.781 | 100

## TP41
| TP Status Date | 2012-03-31 16:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Retirement Apartments | 2008-09-01 08:00 | 2011-12-02 17:00 | 850d |  |  | 0 |  |  | 14956314.25 |  | 951d | [5 empty] | 16068878.2993 |  | 100% |  | 14956314.25 | 14956314.25
1 | afbraak | 2008-09-01 08:00 | 2008-11-21 17:00 | 60d |  | 0 | 0 | 385.4554 | 185018.6094 | 185018.6094 | 2008-09-01 08:00 | 98d | 302197.062 | 0 | 0 | -73401.4526 | 0 | 228795.6094 | 0 | 100% | Finished | 185018.6094 | 185018.6094 | 100 | 163.3333 | 100 | 100 | 123.6609 | 100
2 | gesloten ruwbouw | 2009-03-16 08:00 | 2011-01-19 17:00 | 483d |  | 0 | 0 | 1572.4842 | 6076079 | 6076079 | 2009-03-16 08:00 | 669d | 8415935.5093 | 0 | 0 | -1618988.0093 | 0 | 6796947.5 | 0 | 100% | Finished | 6076079 | 6076079 | 100 | 138.5093 | 100 | 100 | 111.864 | 100
3 | voltooiing | 2010-08-09 08:00 | 2011-12-02 17:00 | 345d |  | 0 | 0 | 1466.4676 | 4047450.5 | 4047450.5 | 2010-08-09 08:00 | 329d | 3859742.6507 | 0 | 0 | 489549.3493 | 0 | 4349292 | 0 | 100% | Finished | 4047450.5 | 4047450.5 | 100 | 95.3623 | 100 | 100 | 107.4576 | 100
11 | technische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  |  | 0 |  |  | 3470216 |  | 475d | [5 empty] | 3526000.4902 |  | 100% |  | 3470216 | 3470216
4 | electrische installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 333.0083 | 919103 | 919103 | 2010-04-12 08:00 | 409d | 1089603.2667 | 0 | 0 | -105574.626 | 0 | 984028.6406 | 0 | 100% | Finished | 919103 | 919103 | 100 | 118.5507 | 100 | 100 | 107.064 | 100
5 | HVAC | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 601.6091 | 1193592.375 | 1193592.375 | 2010-08-09 08:00 | 325d | 1564183.5559 | 0 | 0 | -380687.1214 | 0 | 1183496.4346 | 0 | 100% | Finished | 1193592.375 | 1193592.375 | 100 | 131.0484 | 100 | 100 | 99.1542 | 100
6 | sanitaire installaties | 2010-04-12 08:00 | 2011-08-05 17:00 | 345d |  | 0 | 0 | 413.4644 | 1141161.625 | 1141161.625 | 2010-08-09 08:00 | 389d | 1286701.0786 | 0 | 0 | -148372.1636 | 0 | 1138328.915 | 0 | 100% | Finished | 1141161.625 | 1141161.625 | 100 | 112.7536 | 100 | 100 | 99.7518 | 100
7 | liftinstallatie | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 109.0519 | 216359 | 216359 | 2011-03-01 08:00 | 244d | 212869.3387 | 0 | 0 | 7277.1613 | 0 | 220146.5 | 0 | 100% | Finished | 216359 | 216359 | 100 | 98.3871 | 100 | 100 | 101.7506 | 100
12 | uitrusting | 2010-08-09 08:00 | 2011-08-31 17:00 | 278d |  |  | 0 |  |  | 958011.375 |  | 231d | [5 empty] | 946589.2441 |  | 100% |  | 958011.375 | 958011.375
8 | keukeninstallaties | 2010-08-09 08:00 | 2011-07-20 17:00 | 248d |  | 0 | 0 | 218.6074 | 433717 | 433717 | 2011-10-03 08:00 | 74d | 129415.5565 | 0 | 0 | 269195.4435 | 0 | 398611 | 0 | 100% | Finished | 433717 | 433717 | 100 | 29.8387 | 100 | 100 | 91.9058 | 100
9 | vast meubilair | 2011-03-07 08:00 | 2011-08-31 17:00 | 128d |  | 0 | 0 | 512.0062 | 524294.375 | 524294.375 | 2011-06-06 08:00 | 231d | 946187.5049 | 0 | 0 | -398209.2607 | 0 | 547978.2441 | 0 | 100% | Finished | 524294.375 | 524294.375 | 100 | 180.4688 | 100 | 100 | 104.5173 | 100
10 | omgevingswerken | 2011-06-21 08:00 | 2011-08-15 17:00 | 40d |  | 0 | 0 | 686.0586 | 219538.7656 | 219538.7656 | 2011-06-21 08:00 | 35d | 192096.4199 | 0 | 0 | 29157.0356 | 0 | 221253.4556 | 0 | 100% | Finished | 219538.7656 | 219538.7656 | 100 | 87.5 | 100 | 100 | 100.781 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/09, 2008 | 2008-09-01 08:00 | 2008-09-30 17:00 | 67840.1568 | 55759.0353 | 21040 | 2008-09-24 17:00 | -12081.1215 | 82.19% | 34719.0353 | 265% | -4d | 81.82% | 100% | 2011-12-05 14:00 | 2012-08-17 09:00 | 2010-03-01 10:00 | 2011-12-08 16:00 | 2012-08-17 09:00 | 2010-03-18 16:00 | 2011-12-08 17:00 | 2012-08-23 16:00 | 2010-03-22 15:00 | 14921595.2147 | 5643584.9384 | 18150048.0832 | 18232829.7069 | 6861802.7211 | 6893039.3691 | 6543500.8763 | 6545634.9151 | 0.81818 | 2.6501 | 0.82192 | 1 | -4 | 2.6501 | 1 | 0.81818 | 1
31/10, 2008 | 2008-09-30 17:00 | 2008-10-31 16:00 | 138378.5016 | 74007.4449 | 85856.8516 | 2008-10-02 17:00 | -64371.0567 | 53.48% | -11849.4067 | 86.2% | -20d 7h | 53.48% | 100% | 2011-12-08 14:00 | 2014-10-03 11:00 | 2015-09-24 15:00 | 2012-01-02 16:00 | 2014-10-03 11:00 | 2015-09-15 14:00 | 2012-01-02 16:00 | 2014-10-03 11:00 | 2015-09-15 14:00 | 14968163.6567 | 17350984.8237 | 27912669.682 | 27912670.0966 | 32368048.7768 | 32368049.2579 | 18769243.0973 | 18769243.1346 | 0.53482 | 0.86199 | 0.53482 | 1 | -20.875 | 0.86199 | 1 | 0.53482 | 1
30/11, 2008 | 2008-10-31 16:00 | 2008-11-30 16:00 | 185018.6094 | 136661.4748 | 120985.9805 | 2008-10-31 10:00 | -48357.1345 | 73.86% | 15675.4944 | 113% | -20d 6h | 68.08% | 100% | 2011-12-07 15:00 | 2013-01-28 15:00 | 2012-07-26 15:00 | 2011-12-27 17:00 | 2013-01-28 15:00 | 2012-08-07 10:00 | 2012-01-02 15:00 | 2013-06-13 14:00 | 2012-12-05 16:00 | 14940638.7556 | 13240778.6896 | 20184515.5971 | 21889967.4581 | 17883166.6184 | 19392997.8696 | 14216430.1077 | 14373317.7373 | 0.68077 | 1.1296 | 0.73864 | 1 | -20.75 | 1.1296 | 1 | 0.68077 | 1
31/12, 2008 | 2008-11-30 16:00 | 2008-12-31 16:00 | 185018.6094 | 168027.1015 | 173497.3594 | 2008-11-14 11:00 | -16991.5079 | 90.82% | -5470.2579 | 96.85% | -33d 4h | 61.88% | 100% | 2011-12-05 17:00 | 2012-04-02 17:00 | 2012-05-15 11:00 | 2011-12-15 09:00 | 2012-04-02 17:00 | 2012-05-10 14:00 | 2012-01-19 12:00 | 2013-12-05 14:00 | 2014-02-03 12:00 | 14961784.5079 | 15443229.1285 | 16457229.5592 | 24072729.2338 | 16987359.6001 | 24850788.0115 | 15635798.993 | 16631775.3766 | 0.61878 | 0.96847 | 0.90816 | 1 | -33.5 | 0.96847 | 1 | 0.61878 | 1
31/01, 2009 | 2008-12-31 16:00 | 2009-01-31 16:00 | 185018.6094 | 185018.6094 | 228795.6094 | 2009-01-30 17:00 | 0 | 100% | -43777 | 80.87% | 0 | 100% | 100% | 2011-12-02 17:00 | 2011-12-02 17:00 | 2012-09-11 09:00 | 2011-12-02 17:00 | 2011-12-02 17:00 | 2012-08-06 09:00 | 2011-12-02 17:00 | 2011-12-02 17:00 | 2012-08-06 09:00 | 15000091.25 | 18495107.2997 | 15000091.25 | 15000091.25 | 18495107.2997 | 18495107.2997 | 17669770.2698 | 17669770.2698 | 1 | 0.80866 | 1 | 1 | 0 | 0.80866 | 1 | 1 | 1
30/04, 2009 | 2009-01-31 16:00 | 2009-04-30 16:00 | 611161.8312 | 583834.6136 | 304874.6094 | 2009-04-28 14:00 | -27327.2176 | 95.53% | 278960.0042 | 191.5% | -2d 2h | 98.71% | 100% | 2011-12-06 12:00 | 2012-01-27 15:00 | 2010-06-11 14:00 | 2011-12-14 15:00 | 2012-01-27 15:00 | 2010-10-06 15:00 | 2011-12-07 10:00 | 2011-12-20 09:00 | 2010-09-15 15:00 | 14677354.2458 | 7810089.2938 | 15350078.7975 | 14865777.1398 | 8161381.6463 | 7908482.4943 | 8646144.2189 | 8615494.5947 | 0.98706 | 1.915 | 0.95529 | 1 | -2.25 | 1.915 | 1 | 0.98706 | 1
31/05, 2009 | 2009-04-30 16:00 | 2009-05-31 16:00 | 876911.6632 | 812376.6899 | 402230.1094 | 2009-05-22 15:00 | -64534.9733 | 92.64% | 410146.5805 | 202% | -5d 2h | 97.31% | 100% | 2011-12-08 14:00 | 2012-03-07 12:00 | 2010-05-28 10:00 | 2011-12-23 11:00 | 2012-03-07 12:00 | 2010-10-13 15:00 | 2011-12-12 10:00 | 2012-01-05 12:00 | 2010-09-13 17:00 | 14546167.6695 | 7405283.7701 | 15669758.0492 | 14937501.9103 | 7961604.3624 | 7599044.148 | 8255494.8113 | 8215003.9862 | 0.97308 | 2.0197 | 0.92641 | 1 | -5.25 | 2.0197 | 1 | 0.97308 | 1
30/06, 2009 | 2009-05-31 16:00 | 2009-06-30 16:00 | 1152096.4005 | 1062931.1859 | 686985.1094 | 2009-06-19 15:00 | -89165.2147 | 92.26% | 375946.0765 | 154.7% | -7d 1h | 96.71% | 100% | 2011-12-12 09:00 | 2012-03-13 10:00 | 2010-12-13 12:00 | 2011-12-27 15:00 | 2012-03-13 10:00 | 2011-03-30 09:00 | 2011-12-14 09:00 | 2012-01-12 16:00 | 2011-02-18 15:00 | 14580368.1735 | 9666444.3735 | 15745830.717 | 15052312.6519 | 10419696.7228 | 9971467.7216 | 10455142.2985 | 10394343.6019 | 0.96715 | 1.5472 | 0.92261 | 1 | -7.125 | 1.5472 | 1 | 0.96715 | 1
31/07, 2009 | 2009-06-30 16:00 | 2009-07-31 16:00 | 1441433.4958 | 1328615.2479 | 686985.1094 | 2009-07-20 16:00 | -112818.2479 | 92.17% | 641630.1385 | 193.4% | -9d | 96.25% | 100% | 2011-12-13 11:00 | 2012-03-14 09:00 | 2010-06-29 16:00 | 2011-12-29 15:00 | 2012-03-14 09:00 | 2010-12-08 14:00 | 2011-12-15 17:00 | 2012-01-19 09:00 | 2010-11-10 12:00 | 14314684.1115 | 7733439.1556 | 15471868.7262 | 14845920.889 | 8331782.8826 | 8008124.9658 | 8557306.708 | 8520437.3737 | 0.96248 | 1.934 | 0.92173 | 1 | -9 | 1.934 | 1 | 0.96248 | 1
31/08, 2009 | 2009-07-31 16:00 | 2009-08-31 16:00 | 1705610.8436 | 1571196.3284 | 991534.6094 | 2009-08-17 09:00 | -134414.5152 | 92.12% | 579661.719 | 158.5% | -10d 6h | 95.88% | 100% | 2011-12-14 14:00 | 2012-03-14 15:00 | 2010-11-24 10:00 | 2012-01-02 12:00 | 2012-03-14 15:00 | 2011-04-07 12:00 | 2011-12-19 15:00 | 2012-01-24 12:00 | 2011-03-07 15:00 | 14376652.531 | 9438478.782 | 15521738.0333 | 14951924.9654 | 10161107.7023 | 9801515.8629 | 10210398.2958 | 10162897.1159 | 0.95879 | 1.5846 | 0.92119 | 1 | -10.75 | 1.5846 | 1 | 0.95879 | 1
30/09, 2009 | 2009-08-31 16:00 | 2009-09-30 16:00 | 1982368.0651 | 1825328.9449 | 1243936.1094 | 2009-09-14 11:00 | -157039.1203 | 92.08% | 581392.8355 | 146.7% | -12d 4h | 95.58% | 100% | 2011-12-15 16:00 | 2012-03-15 09:00 | 2011-01-28 09:00 | 2012-01-04 11:00 | 2012-03-15 09:00 | 2011-06-03 10:00 | 2011-12-21 12:00 | 2012-01-27 10:00 | 2011-05-03 09:00 | 14374921.4145 | 10192518.6751 | 15504623.7545 | 14981994.2441 | 10962394.9966 | 10606230.3055 | 10912852.8256 | 10863230.2694 | 0.95581 | 1.4674 | 0.92078 | 1 | -12.5 | 1.4674 | 1 | 0.95581 | 1
31/10, 2009 | 2009-09-30 16:00 | 2009-10-31 16:00 | 2260697.7709 | 2010068.0516 | 1468075.6094 | 2009-10-02 17:00 | -250629.7192 | 88.91% | 541992.4423 | 136.9% | -20d | 93.44% | 100% | 2011-12-23 10:00 | 2012-04-30 17:00 | 2011-05-05 10:00 | 2012-01-19 16:00 | 2012-04-30 17:00 | 2011-08-29 12:00 | 2011-12-30 17:00 | 2012-02-24 14:00 | 2011-07-12 14:00 | 14414321.8077 | 10923510.8427 | 16028552.7524 | 15322830.3129 | 12102482.4082 | 11587050.1573 | 11636543.1483 | 11564710.5403 | 0.93443 | 1.3692 | 0.88914 | 1 | -20 | 1.3692 | 1 | 0.93443 | 1
30/11, 2009 | 2009-10-31 16:00 | 2009-11-30 16:00 | 2523302.6345 | 2243763.3839 | 1613780.1094 | 2009-10-29 14:00 | -279539.2506 | 88.92% | 629983.2745 | 139% | -22d 2h | 93.17% | 100% | 2011-12-26 16:00 | 2012-04-30 16:00 | 2011-04-20 12:00 | 2012-01-24 09:00 | 2012-04-30 16:00 | 2011-08-25 17:00 | 2012-01-04 10:00 | 2012-02-29 10:00 | 2011-07-13 14:00 | 14326330.9755 | 10757017.7051 | 15910124.0653 | 15257921.7759 | 11896127.9179 | 11427044.997 | 11467360.8493 | 11402858.2847 | 0.93172 | 1.3904 | 0.88922 | 1 | -22.25 | 1.3904 | 1 | 0.93172 | 1
31/12, 2009 | 2009-11-30 16:00 | 2009-12-31 16:00 | 2812639.7297 | 2469012.3616 | 1686239.6094 | 2009-11-24 12:00 | -343627.3682 | 87.78% | 782772.7522 | 146.4% | -27d 3h | 92.15% | 100% | 2011-12-30 12:00 | 2012-05-17 10:00 | 2011-03-15 10:00 | 2012-02-01 14:00 | 2012-05-17 10:00 | 2011-08-16 16:00 | 2012-01-11 11:00 | 2012-03-14 11:00 | 2011-07-04 12:00 | 14173541.4978 | 10214582.1104 | 15911474.7501 | 15236807.0941 | 11401523.0646 | 10940751.2425 | 10957140.3251 | 10897362.8631 | 0.92153 | 1.4642 | 0.87783 | 1 | -27.375 | 1.4642 | 1 | 0.92153 | 1
31/01, 2010 | 2009-12-31 16:00 | 2010-01-31 16:00 | 3078389.5618 | 2698504.6165 | 1807855.1094 | 2009-12-18 15:00 | -379884.9452 | 87.66% | 890649.5072 | 149.3% | -30d 2h | 91.82% | 100% | 2012-01-03 14:00 | 2012-05-18 14:00 | 2011-02-25 14:00 | 2012-02-06 14:00 | 2012-05-18 14:00 | 2011-08-16 15:00 | 2012-01-16 10:00 | 2012-03-19 14:00 | 2011-07-06 10:00 | 14065664.7428 | 10019938.0682 | 15791271.3298 | 15157051.7669 | 11176003.048 | 10751109.5457 | 10758797.1371 | 10704683.6924 | 0.91824 | 1.4927 | 0.8766 | 1 | -30.25 | 1.4927 | 1 | 0.91824 | 1
28/02, 2010 | 2010-01-31 16:00 | 2010-02-28 16:00 | 3329987.0359 | 2892718.6194 | 2116364.1094 | 2010-01-11 09:00 | -437268.4165 | 86.87% | 776354.51 | 136.7% | -34d 7h | 91.06% | 100% | 2012-01-06 16:00 | 2012-05-31 12:00 | 2011-05-30 16:00 | 2012-02-14 10:00 | 2012-05-31 12:00 | 2011-10-24 12:00 | 2012-01-20 16:00 | 2012-03-29 12:00 | 2011-09-07 14:00 | 14179959.74 | 10942304.0578 | 16003513.9988 | 15364663.4291 | 12276448.6092 | 11809054.2322 | 11636210.9245 | 11573685.8595 | 0.91058 | 1.3668 | 0.86869 | 1 | -34.875 | 1.3668 | 1 | 0.91058 | 1
31/03, 2010 | 2010-02-28 16:00 | 2010-03-31 16:00 | 3617751.6469 | 3141827.0457 | 2559687.6094 | 2010-02-05 17:00 | -475924.6012 | 86.84% | 582139.4363 | 122.7% | -37d 7h | 90.83% | 100% | 2012-01-10 17:00 | 2012-05-31 15:00 | 2011-09-21 11:00 | 2012-02-17 11:00 | 2012-05-31 15:00 | 2012-01-05 16:00 | 2012-01-25 16:00 | 2012-04-02 16:00 | 2011-11-17 17:00 | 14374174.8137 | 12185104.944 | 16163835.7433 | 15567438.0213 | 13643165.1236 | 13157272.0948 | 12783102.1724 | 12713133.7846 | 0.90827 | 1.2274 | 0.86845 | 1 | -37.875 | 1.2274 | 1 | 0.90827 | 1
30/04, 2010 | 2010-03-31 16:00 | 2010-04-30 16:00 | 3983339.1186 | 3420065.8212 | 2899625.9219 | 2010-03-10 09:00 | -563273.2974 | 85.86% | 520439.8993 | 117.9% | -37d 6h | 91.32% | 98.84% | 2012-01-17 17:00 | 2012-06-15 17:00 | 2011-11-18 11:00 | 2012-02-28 12:00 | 2012-06-15 17:00 | 2012-02-20 12:00 | 2012-01-25 15:00 | 2012-03-26 15:00 | 2011-12-12 11:00 | 14435874.3507 | 12680374.8123 | 16335855.53 | 15532489.7191 | 14291231.1427 | 13610115.5 | 13243192.0243 | 13142898.4447 | 0.91319 | 1.1795 | 0.85859 | 0.98844 | -37.75 | 1.1795 | 1 | 0.91319 | 1
31/05, 2010 | 2010-04-30 16:00 | 2010-05-31 16:00 | 4372923.8784 | 3700793.9131 | 3419244.4219 | 2010-04-09 11:00 | -672129.9653 | 84.63% | 281549.4912 | 108.2% | -36d 4h | 91.99% | 97.51% | 2012-01-26 10:00 | 2012-07-06 11:00 | 2012-03-21 17:00 | 2012-03-12 09:00 | 2012-07-06 11:00 | 2012-05-09 14:00 | 2012-01-24 12:00 | 2012-03-15 17:00 | 2012-01-26 11:00 | 14674764.7588 | 13818465.7866 | 16718967.3464 | 15654380.8358 | 15707149.2581 | 14723554.5015 | 14292740.2004 | 14140207.6465 | 0.91993 | 1.0823 | 0.8463 | 0.97514 | -36.5 | 1.0823 | 1 | 0.91993 | 1
30/06, 2010 | 2010-05-31 16:00 | 2010-06-30 16:00 | 4781060.2934 | 4019342.6343 | 3922660.1719 | 2010-05-04 15:00 | -761717.6591 | 84.07% | 96682.4624 | 102.5% | -41d 1h | 91.39% | 97.36% | 2012-02-02 10:00 | 2012-07-17 09:00 | 2012-06-12 15:00 | 2012-03-20 09:00 | 2012-07-17 09:00 | 2012-06-28 10:00 | 2012-01-31 09:00 | 2012-03-23 17:00 | 2012-03-09 09:00 | 14859631.7876 | 14596550.6216 | 16932330.0308 | 15889472.5608 | 16619391.5652 | 15601619.2988 | 14994108.138 | 14832290.9426 | 0.91394 | 1.0246 | 0.84068 | 0.97362 | -41.125 | 1.0246 | 1 | 0.91394 | 1
31/07, 2010 | 2010-06-30 16:00 | 2010-07-31 16:00 | 5191515.6653 | 4230096.2269 | 4257200.1719 | 2010-05-20 09:00 | -961419.4383 | 81.48% | -27103.9449 | 99.36% | -51d 7h | 89.62% | 96.75% | 2012-02-17 14:00 | 2012-08-30 10:00 | 2012-09-07 16:00 | 2012-04-11 14:00 | 2012-08-30 10:00 | 2012-09-04 14:00 | 2012-02-14 16:00 | 2012-04-19 11:00 | 2012-04-24 10:00 | 14983418.1949 | 15052145.4312 | 17421281.06 | 16225086.3901 | 17505628.674 | 16301769.4989 | 15455205.7624 | 15267972.7871 | 0.89625 | 0.99363 | 0.81481 | 0.96755 | -51.875 | 0.99363 | 1 | 0.89625 | 1
31/08, 2010 | 2010-07-31 16:00 | 2010-08-31 16:00 | 5920757.4708 | 4853930.6789 | 4573279.9844 | 2010-07-06 15:00 | -1066826.7919 | 81.98% | 280650.6945 | 106.1% | -40d 1h | 92.31% | 92.11% | 2012-02-27 14:00 | 2012-08-21 16:00 | 2012-05-29 16:00 | 2012-04-12 17:00 | 2012-08-21 16:00 | 2012-07-10 17:00 | 2012-01-30 09:00 | 2012-03-12 15:00 | 2012-02-08 15:00 | 14675663.5555 | 14091551.1828 | 16896027.6621 | 15517091.9743 | 16183535.4732 | 14884328.8306 | 14545455.327 | 14346154.0702 | 0.92311 | 1.0614 | 0.81982 | 0.92113 | -40.125 | 1.0614 | 1 | 0.92311 | 1
30/09, 2010 | 2010-08-31 16:00 | 2010-09-30 16:00 | 6750543.4054 | 5459046.5216 | 5171155.6094 | 2010-08-13 14:00 | -1291496.8838 | 80.87% | 287890.9122 | 105.6% | -34d 2h | 93.7% | 87.1% | 2012-03-15 11:00 | 2012-09-11 09:00 | 2012-06-25 14:00 | 2012-04-26 17:00 | 2012-09-11 09:00 | 2012-08-03 11:00 | 2012-01-20 10:00 | 2012-02-22 09:00 | 2012-01-25 17:00 | 14668423.3378 | 14167570.8429 | 16915279.3825 | 15306699.3637 | 16295935.6028 | 14772186.4362 | 14609204.605 | 14374441.3478 | 0.93703 | 1.0557 | 0.80868 | 0.87099 | -34.25 | 1.0557 | 1 | 0.93703 | 1
31/10, 2010 | 2010-09-30 16:00 | 2010-10-31 16:00 | 7547326.4903 | 6167425.0681 | 5599948.4219 | 2010-09-09 11:00 | -1379901.4221 | 81.72% | 567476.6462 | 110.1% | -36d 5h | 93.52% | 87.59% | 2012-03-22 11:00 | 2012-08-27 09:00 | 2012-04-13 12:00 | 2012-04-26 10:00 | 2012-08-27 09:00 | 2012-06-26 12:00 | 2012-01-24 14:00 | 2012-02-23 16:00 | 2012-01-11 10:00 | 14388837.6038 | 13580155.0009 | 16355266.1452 | 14998050.8828 | 15365648.669 | 14133313.394 | 14014376.9354 | 13828442.3044 | 0.93518 | 1.1013 | 0.81717 | 0.87585 | -36.625 | 1.1013 | 1 | 0.93518 | 1
30/11, 2010 | 2010-10-31 16:00 | 2010-11-30 16:00 | 8372397.732 | 6846184.3816 | 6372564.4219 | 2010-10-05 11:00 | -1526213.3504 | 81.77% | 473619.9598 | 107.4% | -40d 4h | 93.1% | 88.22% | 2012-04-03 15:00 | 2012-08-24 12:00 | 2012-05-16 14:00 | 2012-05-01 17:00 | 2012-08-24 12:00 | 2012-07-12 09:00 | 2012-01-30 12:00 | 2012-02-29 17:00 | 2012-01-30 12:00 | 14482694.2902 | 13921634.4111 | 16290677.8017 | 15083856.971 | 15604541.3792 | 14481208.5764 | 14300361.5896 | 14128589.3986 | 0.93099 | 1.0743 | 0.81771 | 0.88224 | -40.5 | 1.0743 | 1 | 0.93099 | 1
31/12, 2010 | 2010-11-30 16:00 | 2010-12-31 16:00 | 9239901.2091 | 7618694.0209 | 8698517.4531 | 2010-11-02 16:00 | -1621207.1882 | 82.45% | -1079823.4323 | 87.59% | -43d | 92.95% | 88.54% | 2012-04-11 09:00 | 2012-08-13 16:00 | 2013-03-05 17:00 | 2012-05-01 17:00 | 2012-08-13 16:00 | 2012-11-05 12:00 | 2012-02-01 17:00 | 2012-03-02 12:00 | 2012-05-02 14:00 | 16036137.6823 | 17076123.5694 | 17597534.2454 | 16592728.9411 | 18858822.1814 | 17711602.4016 | 17175459.6708 | 16974765.9088 | 0.92949 | 0.87586 | 0.82454 | 0.88543 | -43 | 0.87586 | 1 | 0.92949 | 1
31/01, 2011 | 2010-12-31 16:00 | 2011-01-31 16:00 | 9932903.0958 | 8146977.0377 | 8993259.9531 | 2010-11-22 16:00 | -1785926.0581 | 82.02% | -846282.9155 | 90.59% | -50d | 92.07% | 87.68% | 2012-04-24 12:00 | 2012-08-21 11:00 | 2013-01-17 17:00 | 2012-05-10 11:00 | 2012-08-21 11:00 | 2012-10-18 12:00 | 2012-02-10 17:00 | 2012-03-15 09:00 | 2012-04-26 12:00 | 15802597.1655 | 16509930.1703 | 17295294.728 | 16388724.7499 | 18157684.5642 | 17156942.8854 | 16654886.684 | 16485372.2919 | 0.92074 | 0.9059 | 0.8202 | 0.87682 | -50 | 0.9059 | 1 | 0.92074 | 1
28/02, 2011 | 2011-01-31 16:00 | 2011-02-28 16:00 | 10435656.4713 | 8790589.8447 | 9277757.8906 | 2010-12-15 16:00 | -1645066.6265 | 84.24% | -487168.0459 | 94.75% | -53d | 91.86% | 87.99% | 2012-04-12 12:00 | 2012-07-13 09:00 | 2012-09-28 17:00 | 2012-04-25 14:00 | 2012-07-13 09:00 | 2012-08-09 16:00 | 2012-02-15 17:00 | 2012-03-19 11:00 | 2012-04-09 12:00 | 15443482.2959 | 15785182.2231 | 16597332.9051 | 15990057.0707 | 17002978.3873 | 16362047.7713 | 15932867.0667 | 15825150.527 | 0.91857 | 0.94749 | 0.84236 | 0.8799 | -53 | 0.94749 | 1 | 0.91857 | 1
31/03, 2011 | 2011-02-28 16:00 | 2011-03-31 16:00 | 11091135.7931 | 9324578.7343 | 9753794.5703 | 2011-01-04 17:00 | -1766557.0588 | 84.07% | -429215.836 | 95.6% | -61d 7h | 90.82% | 86.9% | 2012-04-23 11:00 | 2012-07-16 17:00 | 2012-09-19 14:00 | 2012-05-02 11:00 | 2012-07-16 17:00 | 2012-08-07 12:00 | 2012-02-28 16:00 | 2012-04-02 17:00 | 2012-04-18 17:00 | 15385530.086 | 15644762.1797 | 16452471.812 | 15954915.1106 | 16760815.86 | 16240356.3313 | 15790336.3816 | 15704285.6883 | 0.90818 | 0.95599 | 0.84072 | 0.86902 | -61.875 | 0.95599 | 1 | 0.90818 | 1
30/04, 2011 | 2011-03-31 16:00 | 2011-04-30 16:00 | 11708698.0981 | 9835544.459 | 10115268.1328 | 2011-01-25 17:00 | -1873153.6391 | 84% | -279723.6738 | 97.23% | -68d | 90.22% | 86.21% | 2012-05-01 12:00 | 2012-07-17 16:00 | 2012-08-27 14:00 | 2012-05-08 09:00 | 2012-07-17 16:00 | 2012-07-30 16:00 | 2012-03-07 17:00 | 2012-04-11 09:00 | 2012-04-20 10:00 | 15236037.9238 | 15381673.0277 | 16211275.0964 | 15791400.5168 | 16384646.0237 | 15952830.1773 | 15529024.0101 | 15458817.0666 | 0.90216 | 0.97235 | 0.84002 | 0.86213 | -68 | 0.97235 | 1 | 0.90216 | 1
31/05, 2011 | 2011-04-30 16:00 | 2011-05-31 16:00 | 12348185.6921 | 10414331.8439 | 10365846.8906 | 2011-02-25 17:00 | -1933853.8482 | 84.34% | 48484.9532 | 100.5% | -66d 7h | 90.67% | 87.39% | 2012-05-04 16:00 | 2012-07-11 16:00 | 2012-07-05 09:00 | 2012-05-09 10:00 | 2012-07-11 16:00 | 2012-07-10 12:00 | 2012-03-06 16:00 | 2012-04-04 12:00 | 2012-04-03 11:00 | 14907829.2968 | 14886683.6479 | 15751237.2356 | 15375129.4097 | 15726165.0175 | 15351808.1989 | 15036650.8772 | 14976600.8454 | 0.90671 | 1.0047 | 0.84339 | 0.87388 | -66.875 | 1.0047 | 1 | 0.90671 | 1
30/06, 2011 | 2011-05-31 16:00 | 2011-06-30 16:00 | 13034549.1953 | 11125759.6815 | 11224846.4844 | 2011-04-01 17:00 | -1908789.5138 | 85.36% | -99086.8029 | 99.12% | -63d 7h | 91.36% | 88.21% | 2012-05-03 12:00 | 2012-06-25 16:00 | 2012-07-06 15:00 | 2012-05-03 10:00 | 2012-06-25 16:00 | 2012-06-28 09:00 | 2012-03-01 16:00 | 2012-03-26 11:00 | 2012-03-28 09:00 | 15055401.0529 | 15089516.2429 | 15712589.6496 | 15417885.013 | 15752557.8078 | 15455228.5108 | 15199894.5167 | 15151010.0495 | 0.91355 | 0.99117 | 0.85356 | 0.88214 | -63.875 | 0.99117 | 1 | 0.91355 | 1
31/07, 2011 | 2011-06-30 16:00 | 2011-07-31 16:00 | 13716016.3842 | 11680692.1687 | 11751144.4219 | 2011-04-28 17:00 | -2035324.2155 | 85.16% | -70452.2532 | 99.4% | -66d | 91.32% | 89.54% | 2012-05-14 14:00 | 2012-06-28 09:00 | 2012-07-06 09:00 | 2012-05-09 15:00 | 2012-06-28 09:00 | 2012-06-29 12:00 | 2012-03-05 17:00 | 2012-03-26 16:00 | 2012-03-27 16:00 | 15026766.5032 | 15046523.4622 | 15597533.4446 | 15338280.9951 | 15620732.9922 | 15359916.858 | 15143723.4543 | 15101015.3987 | 0.91316 | 0.994 | 0.85161 | 0.89541 | -66 | 0.994 | 1 | 0.91316 | 1
31/08, 2011 | 2011-07-31 16:00 | 2011-08-31 16:00 | 14168309.1574 | 12251828.3653 | 12242780.9219 | 2011-05-26 12:00 | -1916480.7921 | 86.47% | 9047.4434 | 100.1% | -69d 3h | 91.14% | 90.72% | 2012-05-03 16:00 | 2012-06-06 17:00 | 2012-06-06 10:00 | 2012-04-30 16:00 | 2012-06-06 17:00 | 2012-06-06 16:00 | 2012-03-09 11:00 | 2012-03-28 14:00 | 2012-03-28 12:00 | 14947266.8066 | 14945269.6612 | 15370313.4814 | 15210229.2568 | 15368003.9344 | 15208037.9251 | 15020777.7732 | 14994407.4915 | 0.91138 | 1.0007 | 0.86473 | 0.90722 | -69.375 | 1.0007 | 1 | 0.91138 | 1
30/09, 2011 | 2011-08-31 16:00 | 2011-09-30 16:00 | 14426919.4563 | 13128630.4988 | 13311177.7852 | 2011-07-05 12:00 | -1298288.9576 | 91% | -182547.2864 | 98.63% | -63d 3h | 92.13% | 93.9% | 2012-03-15 15:00 | 2012-03-29 17:00 | 2012-04-17 17:00 | 2012-03-14 11:00 | 2012-03-29 17:00 | 2012-04-02 16:00 | 2012-03-01 11:00 | 2012-03-14 14:00 | 2012-03-16 10:00 | 15138861.5364 | 15164274.599 | 15319600.9998 | 15295071.1894 | 15347527.1577 | 15322656.2721 | 15193387.675 | 15189035.7499 | 0.92126 | 0.98629 | 0.91001 | 0.93902 | -63.375 | 0.98629 | 1 | 0.92126 | 1
31/10, 2011 | 2011-09-30 16:00 | 2011-10-31 16:00 | 14673286.0085 | 13915729.0735 | 15522444.0088 | 2011-08-10 16:00 | -757556.9351 | 94.84% | -1606714.9353 | 89.65% | -58d | 92.98% | 93.09% | 2012-02-01 17:00 | 2012-02-07 10:00 | 2012-06-29 15:00 | 2012-02-01 14:00 | 2012-02-07 10:00 | 2012-02-17 11:00 | 2012-02-22 17:00 | 2012-03-02 10:00 | 2012-03-16 11:00 | 16563029.1853 | 16683175.513 | 16619677.4941 | 16641627.8378 | 16746364.4552 | 16770849.1933 | 16669894.6852 | 16674621.0155 | 0.92977 | 0.89649 | 0.94837 | 0.9309 | -58 | 0.89649 | 1 | 0.92977 | 1
30/11, 2011 | 2011-10-31 16:00 | 2011-11-30 16:00 | 14931384.3013 | 14155658.4983 | 15645518.6494 | 2011-08-30 17:00 | -775725.803 | 94.8% | -1489860.1511 | 90.48% | -65d 7h | 92.23% | 94.37% | 2012-02-03 09:00 | 2012-02-07 14:00 | 2012-06-18 17:00 | 2012-02-02 17:00 | 2012-02-07 14:00 | 2012-02-14 15:00 | 2012-03-05 16:00 | 2012-03-13 14:00 | 2012-03-23 11:00 | 16446174.4011 | 16530442.1234 | 16490050.0941 | 16513620.9454 | 16578935.662 | 16604987.3074 | 16522057.5487 | 16527025.9382 | 0.92231 | 0.90477 | 0.94805 | 0.94372 | -65.875 | 0.90477 | 1 | 0.92231 | 1
31/12, 2011 | 2011-11-30 16:00 | 2011-12-31 16:00 | 14956314.25 | 14366992.8402 | 15706710.6729 | 2011-09-23 15:00 | -589321.4098 | 96.06% | -1339717.8327 | 91.47% | -70d 2h | 91.93% | 95.9% | 2012-01-19 12:00 | 2012-01-20 16:00 | 2012-05-16 11:00 | 2012-02-17 10:00 | 2012-02-20 14:00 | 2012-02-23 17:00 | 2012-03-12 10:00 | 2012-03-16 14:00 | 2012-03-23 15:00 | 16296032.0827 | 16350986.1298 | 16320205.5286 | 16347798.0458 | 16377413.7424 | 16407579.2537 | 16344585.3698 | 16350345.9789 | 0.91925 | 0.9147 | 0.9606 | 0.95898 | -70.25 | 0.9147 | 1 | 0.91925 | 1
31/01, 2012 | 2011-12-31 16:00 | 2012-01-31 16:00 | 14956314.25 | 14855303.3968 | 16036916.27 | 2011-11-22 11:00 | -101010.8532 | 99.32% | -1181612.8732 | 92.63% | -50d 4h | 94.34% | 99.32% | 2011-12-12 15:00 | 2011-12-12 15:00 | 2012-03-15 16:00 | 2012-02-08 16:00 | 2012-02-08 17:00 | 2012-02-09 11:00 | 2012-02-13 12:00 | 2012-02-13 17:00 | 2012-02-14 15:00 | 16137927.1232 | 16145961.6764 | 16138613.9616 | 16143989.8754 | 16146703.1469 | 16152506.6688 | 16144408.4031 | 16145561.5277 | 0.94338 | 0.92632 | 0.99325 | 0.9932 | -50.5 | 0.92632 | 1 | 0.94338 | 1
29/02, 2012 | 2012-01-31 16:00 | 2012-02-29 16:00 | 14956314.25 | 14855303.3968 | 16058066.3501 | 2011-11-22 11:00 | -101010.8532 | 99.32% | -1202762.9533 | 92.51% | -71d 4h | 92.17% | 99.32% | 2011-12-12 15:00 | 2011-12-12 15:00 | 2012-03-19 09:00 | 2012-03-08 17:00 | 2012-03-09 09:00 | 2012-03-09 14:00 | 2012-03-13 12:00 | 2012-03-14 10:00 | 2012-03-14 17:00 | 16159077.2033 | 16167255.5696 | 16159764.0417 | 16167661.0999 | 16167998.018 | 16176534.4633 | 16165670.2482 | 16167336.4354 | 0.92168 | 0.9251 | 0.99325 | 0.9932 | -71.5 | 0.9251 | 1 | 0.92168 | 1
Actual Schedule | 2012-02-29 16:00 | 2012-03-31 16:00 | 14956314.25 | 14956314.25 | 16068878.2993 | 2011-12-02 17:00 | 0 | 100% | -1112564.0493 | 93.08% | -85d | 90.91% | 100% | 2011-12-02 17:00 | 2011-12-02 17:00 | 2012-03-01 10:00 | 2012-03-30 17:00 | 2012-03-30 17:00 | 2012-03-30 17:00 | 2012-03-30 17:00 | 2012-03-30 17:00 | 2012-03-30 17:00 | 16068878.2993 | 16068878.2993 | 16068878.2993 | 16068878.2993 | 16068878.2993 | 16068878.2993 | 16068878.2993 | 16068878.2993 | 0.90909 | 0.93076 | 1 | 1 | -85 | 0.93076 | 1 | 0.90909 | 1