## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Railway Bridge (1) | 1 |  |  | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 | 314.375
1 | Voorbereidende studie | 1.1 |  | SF2+1w 1d | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 21.375
2 | Goedkeuring controlebureau | 1.2 | 1SF+1w 1d | SF3+1w | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0
3 | Goedkeuring bedrijf | 1.3 | 2SF+1w |  | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0
4 | Werfinrichting | 1.4 |  |  | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 4.375
7 | Voorbereiding afbraak | 1.5 |  |  | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 1.375
8 | Afbraak brug | 1.6 |  | FS9 | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 0.375
9 | Uitgraving bouwputten | 1.7 | 8FS |  | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 11.375
10 | Uitvoering paalfunderingen zijde A | 1.8 |  |  | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 11.375
11 | Uitvoering paalfunderingen zijde B | 1.9 |  | FS12 | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 11.375
12 | Uitvoeren van funderingsbalken zijde A | 1.10 | 11FS |  | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 11.375
13 | Uitvoering van funderingsbalken zijde B | 1.11 |  | SF14 | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 11.375
31 | 1e fase brug | 1.12 |  |  | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 | 27.375
14 | Plaatsen bekisting | 1.12.1 | 13SF | FS15;FS16 | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 1.375
15 | Wapening | 1.12.2 | 14FS |  | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 6.375
16 | Bekisting + beton | 1.12.3 | 14FS | FS17 | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 9.375
17 | Uitharden | 1.12.4 | 16FS | FS18 | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 13.375
32 | 2e fase brug | 1.13 |  |  | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 | 27.375
18 | Plaatsen bekisting | 1.13.1 | 17FS | FS19;FS20 | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 1.375
19 | Wapening | 1.13.2 | 18FS |  | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 4.375
20 | Bekisting + beton | 1.13.3 | 18FS | FS21 | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 9.375
21 | Uitharden | 1.13.4 | 20FS | FS22 | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 13.375
33 | 3e fase brug | 1.14 |  |  | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 | 23.375
22 | Plaatsen bekisting | 1.14.1 | 21FS | FS23;FS24 | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 1.375
23 | Wapening | 1.14.2 | 22FS |  | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 6.375
24 | Bekisting + beton | 1.14.3 | 22FS | FS25 | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 11.375
25 | Uitharden | 1.14.4 | 24FS | FS26 | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 6.375
26 | Ontkisten | 1.14.5 | 25FS | FS27 | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 1.375
27 | Verbindingsbalken brug | 1.15 | 26FS | FS28 | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 6.375
28 | Aanbrengen waterdichte rok | 1.16 | 27FS | FS29 | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 6.375
29 | Aanvullingen en wegeniswerken | 1.17 | 28FS | FS30 | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 34.375
30 | Afwerkingen | 1.18 | 29FS |  | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 | 55.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Railway Bridge (1) | 1800h |  |  |  |  | 99 | 100 | 101
1 | Voorbereidende studie | 128h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
2 | Goedkeuring controlebureau | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Goedkeuring bedrijf | 0 | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Werfinrichting | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
7 | Voorbereiding afbraak | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
8 | Afbraak brug | 8h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
9 | Uitgraving bouwputten | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
10 | Uitvoering paalfunderingen zijde A | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
11 | Uitvoering paalfunderingen zijde B | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
12 | Uitvoeren van funderingsbalken zijde A | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
13 | Uitvoering van funderingsbalken zijde B | 80h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
31 | 1e fase brug | 160h |  |  |  |  | 99 | 100 | 101
14 | Plaatsen bekisting | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
15 | Wapening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Bekisting + beton | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Uitharden | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
32 | 2e fase brug | 160h |  |  |  |  | 99 | 100 | 101
18 | Plaatsen bekisting | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
19 | Wapening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Bekisting + beton | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Uitharden | 80h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
33 | 3e fase brug | 144h |  |  |  |  | 99 | 100 | 101
22 | Plaatsen bekisting | 16h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
23 | Wapening | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Bekisting + beton | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Uitharden | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
26 | Ontkisten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Verbindingsbalken brug | 40h | manual - relative | 80 | 100 | 200 | 80 | 100 | 200
28 | Aanbrengen waterdichte rok | 40h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
29 | Aanvullingen en wegeniswerken | 200h | manual - relative | 50 | 100 | 120 | 50 | 100 | 120
30 | Afwerkingen | 320h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2012-11-05 07:00 |  | TP Name | 05/11, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 7d | [5 empty] | 16205.54 |  | 2.414% |  | 16205.54 | 16205.54
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 7d | 16205.54 | 7920 | 9d | 0 | 0 | 16205.54 | 7920 | 43.75% | Started | 16205.54 | 16205.54 | 100 | 43.75 | 43.75 | 100 | 67.1717 | 43.75
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 |  | 0 | 0 | 24173.9004 | 5d | 0 | 0 | 0 | 24173.9004 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 |  | 0 | 0 | 4724.28 | 2d | 0 | 0 | 0 | 4724.28 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 |  | 0 | 0 | 42159.0195 | 1d | 0 | 0 | 0 | 42159.0195 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 |  | 0 | 0 | 23378.1602 | 10d | 0 | 0 | 0 | 23378.1602 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 |  | 0 | 0 | 15530.29 | 10d | 0 | 0 | 0 | 15530.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 |  | 0 | 0 | 13684.03 | 10d | 0 | 0 | 0 | 13684.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 |  | 0 | 0 | 53267.0508 | 10d | 0 | 0 | 0 | 53267.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 |  | 0 | 0 | 49507.8203 | 10d | 0 | 0 | 0 | 49507.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 |  | 0 | 0 | 15810.8799 | 2d | 0 | 0 | 0 | 15810.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 |  | 0 | 0 | 21662.75 | 5d | 0 | 0 | 0 | 21662.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 |  | 0 | 0 | 24199.1299 | 8d | 0 | 0 | 0 | 24199.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2012-12-03 07:00 |  | TP Name | 03/12, 2012
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 27d | [5 empty] | 118560.9001 |  | 17.66% |  | 118560.9001 | 118560.9001
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 |  | 0 | 0 | 15530.29 | 10d | 0 | 0 | 0 | 15530.29 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 |  | 0 | 0 | 13684.03 | 10d | 0 | 0 | 0 | 13684.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 |  | 0 | 0 | 53267.0508 | 10d | 0 | 0 | 0 | 53267.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 |  | 0 | 0 | 49507.8203 | 10d | 0 | 0 | 0 | 49507.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 |  | 0 | 0 | 15810.8799 | 2d | 0 | 0 | 0 | 15810.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 |  | 0 | 0 | 21662.75 | 5d | 0 | 0 | 0 | 21662.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 |  | 0 | 0 | 24199.1299 | 8d | 0 | 0 | 0 | 24199.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2013-01-07 07:00 |  | TP Name | 07/01, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 52d | [5 empty] | 134091.1902 |  | 18.9% |  | 126891.1902 | 134091.1902
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 10d | 15530.29 | 28800 | 30d | 0 | 0 | 15530.29 | 28800 | 25% | Started | 8330.29 | 15530.29 | 100 | 100 | 25 | 100 | 100 | 25
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 |  | 0 | 0 | 13684.03 | 10d | 0 | 0 | 0 | 13684.03 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 |  | 0 | 0 | 53267.0508 | 10d | 0 | 0 | 0 | 53267.0508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 |  | 0 | 0 | 49507.8203 | 10d | 0 | 0 | 0 | 49507.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 |  | 0 | 0 | 15810.8799 | 2d | 0 | 0 | 0 | 15810.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 |  | 0 | 0 | 21662.75 | 5d | 0 | 0 | 0 | 21662.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 |  | 0 | 0 | 24199.1299 | 8d | 0 | 0 | 0 | 24199.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2013-02-04 07:00 |  | TP Name | 04/02, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 72d | [5 empty] | 153291.1902 |  | 19.61% |  | 131691.1902 | 201042.271
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 30d | 34730.29 | 9600 | 10d | 0 | 0 | 34730.29 | 9600 | 75% | Started | 13130.29 | 15530.29 | 100 | 300 | 75 | 100 | 223.6294 | 75
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 |  | 0 | 0 | 13684.03 | 10d | 0 | 0 | 0 | 13684.03 | 0% | Not Started | 0 | 13684.03 | 100 |  | 0 | 100 |  | 0
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 |  | 0 | 0 | 53267.0508 | 10d | 0 | 0 | 0 | 53267.0508 | 0% | Not Started | 0 | 53267.0508 | 100 |  | 0 | 100 |  | 0
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 |  | 0 | 0 | 49507.8203 | 10d | 0 | 0 | 0 | 49507.8203 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 |  | 0 | 0 | 15810.8799 | 2d | 0 | 0 | 0 | 15810.8799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 |  | 0 | 0 | 21662.75 | 5d | 0 | 0 | 0 | 21662.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 |  | 0 | 0 | 24199.1299 | 8d | 0 | 0 | 0 | 24199.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2013-03-04 07:00 |  | TP Name | 04/03, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 92d | [5 empty] | 173695.2202 |  | 21.25% |  | 142655.2202 | 266360.9712
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 7d | 10804.03 | 7680 | 8d | 0 | 0 | 10804.03 | 7680 | 46.67% | Started | 8564.03 | 13684.03 | 100 | 70 | 46.6667 | 100 | 78.9536 | 46.6667
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 |  | 0 | 0 | 53267.0508 | 10d | 0 | 0 | 0 | 53267.0508 | 0% | Not Started | 0 | 53267.0508 | 100 |  | 0 | 100 |  | 0
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 |  | 0 | 0 | 49507.8203 | 10d | 0 | 0 | 0 | 49507.8203 | 0% | Not Started | 0 | 49507.8203 | 100 |  | 0 | 100 |  | 0
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 15810.8799
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 |  | 0 | 0 | 15810.8799 | 2d | 0 | 0 | 0 | 15810.8799 | 0% | Not Started | 0 | 15810.8799 | 100 |  | 0 | 100 |  | 0
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 |  | 0 | 0 | 21662.75 | 5d | 0 | 0 | 0 | 21662.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 |  | 0 | 0 | 24199.1299 | 8d | 0 | 0 | 0 | 24199.1299 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP6
| TP Status Date | 2013-04-01 07:00 |  | TP Name | 01/04, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 112d | [5 empty] | 232722.271 |  | 29.66% |  | 199122.2711 | 317849.2212
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 8d | 51347.0508 | 1920 | 2d | 0 | 0 | 51347.0508 | 1920 | 80% | Started | 51347.0509 | 53267.0508 | 100 | 80 | 80 | 100 | 96.3955 | 80
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 |  | 0 | 0 | 49507.8203 | 10d | 0 | 0 | 0 | 49507.8203 | 0% | Not Started | 0 | 49507.8203 | 100 |  | 0 | 100 |  | 0
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 |  | 0 | 0 | 15810.8799 | 2d | 0 | 0 | 0 | 15810.8799 | 0% | Not Started | 0 | 15810.8799 | 100 |  | 0 | 100 |  | 0
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 |  | 0 | 0 | 21662.75 | 5d | 0 | 0 | 0 | 21662.75 | 0% | Not Started | 0 | 21662.75 | 100 |  | 0 | 100 |  | 0
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 |  | 0 | 0 | 24199.1299 | 8d | 0 | 0 | 0 | 24199.1299 | 0% | Not Started | 0 | 24199.1299 | 100 |  | 0 | 100 |  | 0
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 5625.3701
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 5625.3701 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP7
| TP Status Date | 2013-05-06 07:00 |  | TP Name | 06/05, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 137d | [5 empty] | 341982.8511 |  | 45.93% |  | 308382.8511 | 386322.8828
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 7d | [5 empty] | 57832.7598 |  | 93.77% |  | 57832.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 5d | 20359.1299 | 3840 | 3d | 0 | 0 | 20359.1299 | 3840 | 62.5% | Started | 20359.1299 | 24199.1299 | 100 | 62.5 | 62.5 | 100 | 84.1317 | 62.5
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 |  | 0 | 0 | 5625.3701 | 2d | 0 | 0 | 0 | 5625.3701 | 0% | Not Started | 0 | 5625.3701 | 100 |  | 0 | 100 |  | 0
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 |  | 0 | 0 | 23526.2109 | 5d | 0 | 0 | 0 | 23526.2109 | 0% | Not Started | 0 | 23526.2109 | 100 |  | 0 | 100 |  | 0
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 |  | 0 | 0 | 19048.7305 | 8d | 0 | 0 | 0 | 19048.7305 | 0% | Not Started | 0 | 19048.7305 | 100 |  | 0 | 100 |  | 0
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 25897.7202
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 4936.26 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 15999.2402 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 4962.22 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP8
| TP Status Date | 2013-06-03 07:00 |  | TP Name | 03/06, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 157d | [5 empty] | 392744.1626 |  | 53.68% |  | 360424.1626 | 471056.0925
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 9d | [5 empty] | 46920.3115 |  | 100% |  | 48200.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 10d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 |  | 0 | 0 | 4936.26 | 2d | 0 | 0 | 0 | 4936.26 | 0% | Not Started | 0 | 4936.26 | 100 |  | 0 | 100 |  | 0
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 |  | 0 | 0 | 21119.2402 | 5d | 0 | 0 | 0 | 21119.2402 | 0% | Not Started | 0 | 21119.2402 | 100 |  | 0 | 100 |  | 0
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 |  | 0 | 0 | 8802.22 | 8d | 0 | 0 | 0 | 8802.22 | 0% | Not Started | 0 | 8802.22 | 100 |  | 0 | 100 |  | 0
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 1 | 5d | 0 | 0 | 0 | 1 | 0% | Not Started | 0 | 1 | 100 |  | 0 | 100 |  | 0
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 2379.53 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 30930.5508 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 42462.1289 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP9
| TP Status Date | 2013-07-01 07:00 |  | TP Name | 01/07, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 177d | [5 empty] | 427603.8828 |  | 58.88% |  | 395283.8828 | 564041.6394
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 100% |  | 48201.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 15d | [5 empty] | 34858.7202 |  | 93.61% |  | 34858.7202 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 100% | Finished | 4936.26 | 4936.26 | 100 | 100 | 100 | 100 | 100 | 100
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 100% | Finished | 21119.2402 | 21119.2402 | 100 | 100 | 100 | 100 | 100 | 100
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 100% | Finished | 8802.22 | 8802.22 | 100 | 100 | 100 | 100 | 100 | 100
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 |  | 0 | 0 | 2379.53 | 2d | 0 | 0 | 0 | 2379.53 | 0% | Not Started | 0 | 2379.53 | 100 |  | 0 | 100 |  | 0
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 |  | 0 | 0 | 30930.5508 | 5d | 0 | 0 | 0 | 30930.5508 | 0% | Not Started | 0 | 30930.5508 | 100 |  | 0 | 100 |  | 0
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 |  | 0 | 0 | 45342.1289 | 5d | 0 | 0 | 0 | 45342.1289 | 0% | Not Started | 0 | 45342.1289 | 100 |  | 0 | 100 |  | 0
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 |  | 0 | 0 | 97785.5469 | 25d | 0 | 0 | 0 | 97785.5469 | 0% | Not Started | 0 | 90105.5469 | 100 |  | 0 | 100 |  | 0
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP10
| TP Status Date | 2013-08-05 07:00 |  | TP Name | 05/08, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 202d | [5 empty] | 582921.6394 |  | 82.01% |  | 550601.6393 | 649303.4988
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 100% |  | 48201.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 17d | [5 empty] | 37238.2502 |  | 100% |  | 37238.2502 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 100% | Finished | 4936.26 | 4936.26 | 100 | 100 | 100 | 100 | 100 | 100
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 100% | Finished | 21119.2402 | 21119.2402 | 100 | 100 | 100 | 100 | 100 | 100
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 100% | Finished | 8802.22 | 8802.22 | 100 | 100 | 100 | 100 | 100 | 100
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 2013-07-01 07:00 | 2d | 2379.53 | 0 | 0 | 0 | 0 | 2379.53 | 0 | 100% | Finished | 2379.53 | 2379.53 | 100 | 100 | 100 | 100 | 100 | 100
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 2013-07-03 07:00 | 5d | 30930.5508 | 0 | 0 | 0 | 0 | 30930.5508 | 0 | 100% | Finished | 30930.5508 | 30930.5508 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-07-10 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 2013-07-17 07:00 | 3d | 76665.5469 | 21120 | 22d | 0 | 0 | 76665.5469 | 21120 | 12% | Started | 76665.5468 | 97785.5469 | 100 | 12 | 12 | 100 | 78.4017 | 12
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 77581.8594 | 100 |  | 0 | 100 |  | 0

## TP11
| TP Status Date | 2013-09-02 07:00 |  | TP Name | 02/09, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 222d | [5 empty] | 593481.6394 |  | 83.58% |  | 561161.6395 | 668503.4988
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 100% |  | 48201.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 17d | [5 empty] | 37238.2502 |  | 100% |  | 37238.2502 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 100% | Finished | 4936.26 | 4936.26 | 100 | 100 | 100 | 100 | 100 | 100
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 100% | Finished | 21119.2402 | 21119.2402 | 100 | 100 | 100 | 100 | 100 | 100
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 100% | Finished | 8802.22 | 8802.22 | 100 | 100 | 100 | 100 | 100 | 100
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 2013-07-01 07:00 | 2d | 2379.53 | 0 | 0 | 0 | 0 | 2379.53 | 0 | 100% | Finished | 2379.53 | 2379.53 | 100 | 100 | 100 | 100 | 100 | 100
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 2013-07-03 07:00 | 5d | 30930.5508 | 0 | 0 | 0 | 0 | 30930.5508 | 0 | 100% | Finished | 30930.5508 | 30930.5508 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-07-10 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 2013-07-17 07:00 | 14d | 87225.5469 | 10560 | 11d | 0 | 0 | 87225.5469 | 10560 | 56% | Started | 87225.5469 | 97785.5469 | 100 | 56 | 56 | 100 | 89.2009 | 56
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 |  | 0 | 0 | 99661.8594 | 40d | 0 | 0 | 0 | 99661.8594 | 0% | Not Started | 0 | 96781.8594 | 100 |  | 0 | 100 |  | 0

## TP12
| TP Status Date | 2013-10-07 07:00 |  | TP Name | 07/10, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 247d | [5 empty] | 677783.4988 |  | 96.14% |  | 645463.4983 | 671383.4988
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 100% |  | 48201.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 17d | [5 empty] | 37238.2502 |  | 100% |  | 37238.2502 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 100% | Finished | 4936.26 | 4936.26 | 100 | 100 | 100 | 100 | 100 | 100
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 100% | Finished | 21119.2402 | 21119.2402 | 100 | 100 | 100 | 100 | 100 | 100
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 100% | Finished | 8802.22 | 8802.22 | 100 | 100 | 100 | 100 | 100 | 100
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 2013-07-01 07:00 | 2d | 2379.53 | 0 | 0 | 0 | 0 | 2379.53 | 0 | 100% | Finished | 2379.53 | 2379.53 | 100 | 100 | 100 | 100 | 100 | 100
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 2013-07-03 07:00 | 5d | 30930.5508 | 0 | 0 | 0 | 0 | 30930.5508 | 0 | 100% | Finished | 30930.5508 | 30930.5508 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-07-10 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 2013-07-17 07:00 | 25d | 97785.5469 | 0 | 0 | 0 | 0 | 97785.5469 | 0 | 100% | Finished | 97785.5469 | 97785.5469 | 100 | 100 | 100 | 100 | 100 | 100
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 | 2013-09-18 07:00 | 13d | 73741.8594 | 25920 | 27d | 0 | 0 | 73741.8594 | 25920 | 32.5% | Started | 73741.8589 | 99661.8594 | 100 | 32.5 | 32.5 | 100 | 73.9921 | 32.5

## TP13
| TP Status Date | 2013-11-04 07:00 |  | TP Name | 04/11, 2013
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 267d | [5 empty] | 696983.4988 |  | 99% |  | 664663.4983 | 671383.4988
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 100% |  | 48201.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 17d | [5 empty] | 37238.2502 |  | 100% |  | 37238.2502 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 100% | Finished | 4936.26 | 4936.26 | 100 | 100 | 100 | 100 | 100 | 100
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 100% | Finished | 21119.2402 | 21119.2402 | 100 | 100 | 100 | 100 | 100 | 100
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 100% | Finished | 8802.22 | 8802.22 | 100 | 100 | 100 | 100 | 100 | 100
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 2013-07-01 07:00 | 2d | 2379.53 | 0 | 0 | 0 | 0 | 2379.53 | 0 | 100% | Finished | 2379.53 | 2379.53 | 100 | 100 | 100 | 100 | 100 | 100
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 2013-07-03 07:00 | 5d | 30930.5508 | 0 | 0 | 0 | 0 | 30930.5508 | 0 | 100% | Finished | 30930.5508 | 30930.5508 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-07-10 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 2013-07-17 07:00 | 25d | 97785.5469 | 0 | 0 | 0 | 0 | 97785.5469 | 0 | 100% | Finished | 97785.5469 | 97785.5469 | 100 | 100 | 100 | 100 | 100 | 100
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 | 2013-09-18 07:00 | 33d | 92941.8594 | 6720 | 7d | 0 | 0 | 92941.8594 | 6720 | 82.5% | Started | 92941.8589 | 99661.8594 | 100 | 82.5 | 82.5 | 100 | 93.2572 | 82.5

## TP14
| TP Status Date | 2013-12-02 07:00 |  | TP Name | Actual Schedule
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Railway Bridge (1) | 2012-10-25 07:00 | 2013-09-04 16:00 | 225d |  |  | 470743.4988 |  |  | 671383.4988 |  | 274d | [5 empty] | 703703.4988 |  | 100% |  | 671383.4988 | 671383.4988
1 | Voorbereidende studie | 2012-10-25 07:00 | 2012-11-15 16:00 | 16d |  | 0 | 10045.54 | 110 | 14080 | 24125.54 | 2012-10-25 07:00 | 16d | 24125.54 | 0 | 0 | 0 | 0 | 24125.54 | 0 | 100% | Finished | 24125.54 | 24125.54 | 100 | 100 | 100 | 100 | 100 | 100
2 | Goedkeuring controlebureau | 2012-11-21 16:00 | 2012-11-21 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-22 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
3 | Goedkeuring bedrijf | 2012-11-28 16:00 | 2012-11-28 16:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2012-11-29 07:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0 | 100 |  | 100 | 100 |  | 100
4 | Werfinrichting | 2012-11-12 07:00 | 2012-11-16 16:00 | 5d |  | 0 | 18573.9004 | 140 | 5600 | 24173.9004 | 2012-11-12 07:00 | 5d | 24173.9004 | 0 | 0 | 0 | 0 | 24173.9004 | 0 | 100% | Finished | 24173.9004 | 24173.9004 | 100 | 100 | 100 | 100 | 100 | 100
7 | Voorbereiding afbraak | 2012-11-15 07:00 | 2012-11-16 16:00 | 2d |  | 0 | 1844.28 | 180 | 2880 | 4724.28 | 2012-11-15 07:00 | 2d | 4724.28 | 0 | 0 | 0 | 0 | 4724.28 | 0 | 100% | Finished | 4724.28 | 4724.28 | 100 | 100 | 100 | 100 | 100 | 100
8 | Afbraak brug | 2012-11-16 07:00 | 2012-11-16 16:00 | 1d |  | 0 | 39759.0195 | 300 | 2400 | 42159.0195 | 2012-11-19 07:00 | 1d | 42159.0195 | 0 | 0 | 0 | 0 | 42159.0195 | 0 | 100% | Finished | 42159.0195 | 42159.0195 | 100 | 100 | 100 | 100 | 100 | 100
9 | Uitgraving bouwputten | 2012-11-19 07:00 | 2012-11-30 16:00 | 10d |  | 0 | 13778.1602 | 120 | 9600 | 23378.1602 | 2012-11-19 07:00 | 10d | 23378.1602 | 0 | 0 | 0 | 0 | 23378.1602 | 0 | 100% | Finished | 23378.1602 | 23378.1602 | 100 | 100 | 100 | 100 | 100 | 100
10 | Uitvoering paalfunderingen zijde A | 2012-12-10 07:00 | 2012-12-21 16:00 | 10d |  | 0 | 5930.29 | 120 | 9600 | 15530.29 | 2012-12-10 07:00 | 40d | 44330.29 | 0 | 0 | 0 | 0 | 44330.29 | 0 | 100% | Finished | 15530.29 | 15530.29 | 100 | 400 | 100 | 100 | 285.4441 | 100
11 | Uitvoering paalfunderingen zijde B | 2013-01-07 07:00 | 2013-01-18 16:00 | 10d |  | 0 | 4084.03 | 120 | 9600 | 13684.03 | 2013-02-21 07:00 | 15d | 18484.03 | 0 | 0 | 0 | 0 | 18484.03 | 0 | 100% | Finished | 13684.03 | 13684.03 | 100 | 150 | 100 | 100 | 135.0774 | 100
12 | Uitvoeren van funderingsbalken zijde A | 2013-01-21 07:00 | 2013-02-01 16:00 | 10d |  | 0 | 43667.0508 | 120 | 9600 | 53267.0508 | 2013-03-20 07:00 | 10d | 53267.0508 | 0 | 0 | 0 | 0 | 53267.0508 | 0 | 100% | Finished | 53267.0508 | 53267.0508 | 100 | 100 | 100 | 100 | 100 | 100
13 | Uitvoering van funderingsbalken zijde B | 2013-02-04 07:00 | 2013-02-15 16:00 | 10d |  | 0 | 39907.8203 | 120 | 9600 | 49507.8203 | 2013-04-08 07:00 | 10d | 49507.8203 | 0 | 0 | 0 | 0 | 49507.8203 | 0 | 100% | Finished | 49507.8203 | 49507.8203 | 100 | 100 | 100 | 100 | 100 | 100
31 | 1e fase brug | 2013-02-28 07:00 | 2013-03-27 16:00 | 20d |  |  | 41833.7598 |  |  | 61673.7598 |  | 15d | [5 empty] | 61673.7598 |  | 100% |  | 61673.7598 | 61673.7598
14 | Plaatsen bekisting | 2013-02-28 07:00 | 2013-03-01 16:00 | 2d |  | 0 | 12610.8799 | 200 | 3200 | 15810.8799 | 2013-04-25 07:00 | 2d | 15810.8799 | 0 | 0 | 0 | 0 | 15810.8799 | 0 | 100% | Finished | 15810.8799 | 15810.8799 | 100 | 100 | 100 | 100 | 100 | 100
15 | Wapening | 2013-03-06 07:00 | 2013-03-12 16:00 | 5d |  | 0 | 15262.75 | 160 | 6400 | 21662.75 | 2013-04-26 07:00 | 5d | 21662.75 | 0 | 0 | 0 | 0 | 21662.75 | 0 | 100% | Finished | 21662.75 | 21662.75 | 100 | 100 | 100 | 100 | 100 | 100
16 | Bekisting + beton | 2013-03-04 07:00 | 2013-03-13 16:00 | 8d |  | 0 | 13959.1299 | 160 | 10240 | 24199.1299 | 2013-04-26 07:00 | 8d | 24199.1299 | 0 | 0 | 0 | 0 | 24199.1299 | 0 | 100% | Finished | 24199.1299 | 24199.1299 | 100 | 100 | 100 | 100 | 100 | 100
17 | Uitharden | 2013-03-14 07:00 | 2013-03-27 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-05-08 07:00 | 6d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 60 | 100 | 100 | 100 | 100
32 | 2e fase brug | 2013-03-28 07:00 | 2013-04-24 16:00 | 20d |  |  | 28361.3115 |  |  | 48201.3115 |  | 19d | [5 empty] | 46921.3115 |  | 100% |  | 48201.3115 | 48201.3115
18 | Plaatsen bekisting | 2013-03-28 07:00 | 2013-03-29 16:00 | 2d |  | 0 | 2425.3701 | 200 | 3200 | 5625.3701 | 2013-05-21 07:00 | 2d | 5625.3701 | 0 | 0 | 0 | 0 | 5625.3701 | 0 | 100% | Finished | 5625.3701 | 5625.3701 | 100 | 100 | 100 | 100 | 100 | 100
19 | Wapening | 2013-04-01 07:00 | 2013-04-05 16:00 | 5d |  | 0 | 17126.2109 | 160 | 6400 | 23526.2109 | 2013-05-23 07:00 | 5d | 23526.2109 | 0 | 0 | 0 | 0 | 23526.2109 | 0 | 100% | Finished | 23526.2109 | 23526.2109 | 100 | 100 | 100 | 100 | 100 | 100
20 | Bekisting + beton | 2013-04-01 07:00 | 2013-04-10 16:00 | 8d |  | 0 | 8808.7305 | 160 | 10240 | 19048.7305 | 2013-05-23 07:00 | 7d | 17768.7305 | 0 | 0 | 0 | 0 | 17768.7305 | 0 | 100% | Finished | 19048.7305 | 19048.7305 | 100 | 87.5 | 100 | 100 | 93.2804 | 100
21 | Uitharden | 2013-04-11 07:00 | 2013-04-24 16:00 | 10d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-03 07:00 | 10d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
33 | 3e fase brug | 2013-04-29 07:00 | 2013-05-22 16:00 | 18d |  |  | 21238.2502 |  |  | 37238.2502 |  | 17d | [5 empty] | 37238.2502 |  | 100% |  | 37238.2502 | 37238.2502
22 | Plaatsen bekisting | 2013-04-29 07:00 | 2013-04-30 16:00 | 2d |  | 0 | 1736.26 | 200 | 3200 | 4936.26 | 2013-06-10 07:00 | 2d | 4936.26 | 0 | 0 | 0 | 0 | 4936.26 | 0 | 100% | Finished | 4936.26 | 4936.26 | 100 | 100 | 100 | 100 | 100 | 100
23 | Wapening | 2013-05-03 07:00 | 2013-05-09 16:00 | 5d |  | 0 | 14719.2402 | 160 | 6400 | 21119.2402 | 2013-06-12 07:00 | 5d | 21119.2402 | 0 | 0 | 0 | 0 | 21119.2402 | 0 | 100% | Finished | 21119.2402 | 21119.2402 | 100 | 100 | 100 | 100 | 100 | 100
24 | Bekisting + beton | 2013-05-02 07:00 | 2013-05-13 16:00 | 8d |  | 0 | 3682.22 | 80 | 5120 | 8802.22 | 2013-06-12 07:00 | 8d | 8802.22 | 0 | 0 | 0 | 0 | 8802.22 | 0 | 100% | Finished | 8802.22 | 8802.22 | 100 | 100 | 100 | 100 | 100 | 100
25 | Uitharden | 2013-05-14 07:00 | 2013-05-20 16:00 | 5d |  | 0 | 1 | 0 | 0 | 1 | 2013-06-24 07:00 | 5d | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | Finished | 1 | 1 | 100 | 100 | 100 | 100 | 100 | 100
26 | Ontkisten | 2013-05-21 07:00 | 2013-05-22 16:00 | 2d |  | 0 | 1099.53 | 80 | 1280 | 2379.53 | 2013-07-01 07:00 | 2d | 2379.53 | 0 | 0 | 0 | 0 | 2379.53 | 0 | 100% | Finished | 2379.53 | 2379.53 | 100 | 100 | 100 | 100 | 100 | 100
27 | Verbindingsbalken brug | 2013-05-23 07:00 | 2013-05-29 16:00 | 5d |  | 0 | 26130.5508 | 120 | 4800 | 30930.5508 | 2013-07-03 07:00 | 5d | 30930.5508 | 0 | 0 | 0 | 0 | 30930.5508 | 0 | 100% | Finished | 30930.5508 | 30930.5508 | 100 | 100 | 100 | 100 | 100 | 100
28 | Aanbrengen waterdichte rok | 2013-05-30 07:00 | 2013-06-05 16:00 | 5d |  | 0 | 40542.1289 | 120 | 4800 | 45342.1289 | 2013-07-10 07:00 | 5d | 45342.1289 | 0 | 0 | 0 | 0 | 45342.1289 | 0 | 100% | Finished | 45342.1289 | 45342.1289 | 100 | 100 | 100 | 100 | 100 | 100
29 | Aanvullingen en wegeniswerken | 2013-06-06 07:00 | 2013-07-10 16:00 | 25d |  | 0 | 73785.5469 | 120 | 24000 | 97785.5469 | 2013-07-17 07:00 | 25d | 97785.5469 | 0 | 0 | 0 | 0 | 97785.5469 | 0 | 100% | Finished | 97785.5469 | 97785.5469 | 100 | 100 | 100 | 100 | 100 | 100
30 | Afwerkingen | 2013-07-11 07:00 | 2013-09-04 16:00 | 40d |  | 0 | 61261.8594 | 120 | 38400 | 99661.8594 | 2013-09-18 07:00 | 40d | 99661.8594 | 0 | 0 | 0 | 0 | 99661.8594 | 0 | 100% | Finished | 99661.8594 | 99661.8594 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | Yes
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | No
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
05/11, 2012 | 2012-10-25 07:00 | 2012-11-05 07:00 | 16205.54 | 16205.54 | 16205.54 | 2012-11-02 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
03/12, 2012 | 2012-11-05 07:00 | 2012-12-03 07:00 | 118560.9001 | 118560.9001 | 118560.9001 | 2012-11-30 16:00 | 0 | 100% | 0 | 100% | 0 | 100% | 100% | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-04 16:00 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 671383.4988 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
07/01, 2013 | 2012-12-03 07:00 | 2013-01-07 07:00 | 134091.1902 | 126891.1902 | 134091.1902 | 2012-12-12 11:00 | -7200 | 94.63% | -7200 | 94.63% | -17d 4h | 66.35% | 100% | 2013-09-09 10:00 | 2013-09-23 14:00 | 2013-10-11 09:00 | 2013-09-09 14:00 | 2013-09-23 14:00 | 2013-10-08 09:00 | 2013-09-30 11:00 | 2014-02-12 08:00 | 2014-03-06 10:00 | 678583.4988 | 709478.8243 | 709478.8243 | 954775.2495 | 742127.1977 | 1001342.1169 | 709478.8243 | 746061.5091 | 0.66346 | 0.94631 | 0.94631 | 1 | -17.5 | 0.94631 | 1 | 0.66346 | 1
04/02, 2013 | 2013-01-07 07:00 | 2013-02-04 07:00 | 201042.271 | 131691.1902 | 153291.1902 | 2012-12-19 11:00 | -69351.0808 | 65.5% | -21600 | 85.91% | -32d 4h | 54.86% | 100% | 2013-10-08 09:00 | 2014-02-18 11:00 | 2014-05-07 15:00 | 2013-10-09 15:00 | 2014-02-18 11:00 | 2014-04-21 16:00 | 2013-10-21 11:00 | 2014-05-22 08:00 | 2014-08-07 12:00 | 692983.4988 | 781503.8763 | 977195.7141 | 1137034.1324 | 1112332.6029 | 1298387.7319 | 812834.5075 | 830449.6551 | 0.54861 | 0.85909 | 0.65504 | 1 | -32.5 | 0.85909 | 1 | 0.54861 | 1
04/03, 2013 | 2013-02-04 07:00 | 2013-03-04 07:00 | 266360.9712 | 142655.2202 | 173695.2202 | 2013-01-11 12:00 | -123705.751 | 53.56% | -31040 | 82.13% | -35d 3h | 61.55% | 100% | 2013-11-01 11:00 | 2014-06-05 08:00 | 2014-10-10 11:00 | 2013-11-04 14:00 | 2014-06-05 08:00 | 2014-09-12 11:00 | 2013-10-24 10:00 | 2014-03-20 12:00 | 2014-06-12 08:00 | 702423.4988 | 817468.1899 | 1160918.6638 | 1032732.7765 | 1375726.195 | 1219648.6545 | 865611.0542 | 851434.8887 | 0.61549 | 0.8213 | 0.53557 | 1 | -35.375 | 0.8213 | 1 | 0.61549 | 1
01/04, 2013 | 2013-03-04 07:00 | 2013-04-01 07:00 | 317849.2212 | 199122.2711 | 232722.271 | 2013-01-30 16:00 | -118726.9501 | 62.65% | -33599.9999 | 85.56% | -42d | 62.5% | 100% | 2013-10-30 14:00 | 2014-03-12 08:00 | 2014-06-04 14:00 | 2013-11-01 15:00 | 2014-03-12 08:00 | 2014-05-08 15:00 | 2013-11-01 16:00 | 2014-03-12 16:00 | 2014-05-09 15:00 | 704983.4987 | 784673.114 | 986569.9575 | 988340.2353 | 1113774.6245 | 1115843.6199 | 815911.2588 | 816122.735 | 0.625 | 0.85562 | 0.62647 | 1 | -42 | 0.85562 | 1 | 0.625 | 1
06/05, 2013 | 2013-04-01 07:00 | 2013-05-06 07:00 | 386322.8828 | 308382.8511 | 341982.8511 | 2013-03-11 16:00 | -77940.0317 | 79.83% | -33600 | 90.17% | -39d | 71.53% | 99.58% | 2013-10-11 08:00 | 2013-11-22 15:00 | 2014-01-06 12:00 | 2013-10-14 12:00 | 2013-11-22 15:00 | 2013-12-16 12:00 | 2013-10-29 16:00 | 2014-01-08 11:00 | 2014-02-04 15:00 | 704983.4988 | 744534.4068 | 796727.5173 | 849442.9402 | 846274.4384 | 904733.4952 | 753992.0399 | 761896.3677 | 0.71533 | 0.90175 | 0.79825 | 0.99585 | -39 | 0.90175 | 1 | 0.71533 | 1
03/06, 2013 | 2013-05-06 07:00 | 2013-06-03 07:00 | 471056.0925 | 360424.1626 | 392744.1626 | 2013-04-10 16:00 | -110631.9299 | 76.51% | -32320 | 91.77% | -37d | 76.43% | 100% | 2013-10-28 08:00 | 2013-12-11 08:00 | 2014-01-16 10:00 | 2013-10-25 15:00 | 2013-12-11 08:00 | 2013-12-27 10:00 | 2013-10-25 16:00 | 2013-12-11 10:00 | 2013-12-27 14:00 | 703703.4988 | 731587.8828 | 799152.2369 | 799582.6274 | 835595.7119 | 836064.6965 | 743241.7573 | 743305.7246 | 0.76433 | 0.91771 | 0.76514 | 1 | -37 | 0.91771 | 1 | 0.76433 | 1
01/07, 2013 | 2013-06-03 07:00 | 2013-07-01 07:00 | 564041.6394 | 395283.8828 | 427603.8828 | 2013-05-20 16:00 | -168757.7566 | 70.08% | -32320 | 92.44% | -29d | 83.62% | 100% | 2013-11-22 11:00 | 2014-01-16 16:00 | 2014-02-24 09:00 | 2013-11-18 16:00 | 2014-01-16 16:00 | 2014-02-03 15:00 | 2013-10-15 16:00 | 2013-11-06 08:00 | 2013-11-15 12:00 | 703703.4988 | 726278.5138 | 821578.155 | 757804.0992 | 853791.0759 | 784802.5969 | 741462.5608 | 732092.6756 | 0.83616 | 0.92442 | 0.70081 | 1 | -29 | 0.92442 | 1 | 0.83616 | 1
05/08, 2013 | 2013-07-01 07:00 | 2013-08-05 07:00 | 649303.4988 | 550601.6393 | 582921.6394 | 2013-06-10 16:00 | -98701.8594 | 84.8% | -32320.0001 | 94.46% | -39d | 80.69% | 100% | 2013-10-22 08:00 | 2013-10-31 10:00 | 2013-11-21 15:00 | 2013-10-17 14:00 | 2013-10-31 10:00 | 2013-11-05 16:00 | 2013-10-29 16:00 | 2013-11-19 15:00 | 2013-11-26 10:00 | 703703.4988 | 710793.3246 | 725355.0764 | 732602.2259 | 733715.8374 | 741388.3904 | 713462.5065 | 714631.4252 | 0.80693 | 0.94456 | 0.84799 | 1 | -39 | 0.94456 | 1 | 0.80693 | 1
02/09, 2013 | 2013-08-05 07:00 | 2013-09-02 07:00 | 668503.4988 | 561161.6395 | 593481.6394 | 2013-06-25 16:00 | -107341.8593 | 83.94% | -32319.9999 | 94.55% | -48d | 78.38% | 100% | 2013-10-24 16:00 | 2013-11-04 16:00 | 2013-11-26 11:00 | 2013-10-24 12:00 | 2013-11-04 16:00 | 2013-11-07 14:00 | 2013-11-11 16:00 | 2013-12-02 08:00 | 2013-12-05 15:00 | 703703.4987 | 710051.7061 | 724787.2979 | 734109.5289 | 732349.8228 | 742208.9659 | 712728.1606 | 714181.4336 | 0.78378 | 0.94554 | 0.83943 | 1 | -48 | 0.94554 | 1 | 0.78378 | 1
07/10, 2013 | 2013-09-02 07:00 | 2013-10-07 07:00 | 671383.4988 | 645463.4983 | 677783.4988 | 2013-07-29 16:00 | -25920.0005 | 96.14% | -32320.0005 | 95.23% | -49d | 80.16% | 100% | 2013-09-17 12:00 | 2013-09-17 16:00 | 2013-10-03 14:00 | 2013-10-18 11:00 | 2013-10-18 15:00 | 2013-10-21 10:00 | 2013-11-12 16:00 | 2013-11-21 12:00 | 2013-11-25 10:00 | 703703.4992 | 705001.3796 | 704744.3736 | 710118.0448 | 706094.3733 | 711737.1178 | 704949.5872 | 705890.9318 | 0.80162 | 0.95232 | 0.96139 | 1 | -49 | 0.95232 | 1 | 0.80162 | 1
04/11, 2013 | 2013-10-07 07:00 | 2013-11-04 07:00 | 671383.4988 | 664663.4983 | 696983.4988 | 2013-08-26 16:00 | -6720.0005 | 99% | -32320.0005 | 95.36% | -49d | 81.65% | 100% | 2013-09-09 09:00 | 2013-09-09 09:00 | 2013-09-24 10:00 | 2013-11-06 12:00 | 2013-11-06 14:00 | 2013-11-06 15:00 | 2013-11-12 16:00 | 2013-11-14 12:00 | 2013-11-14 16:00 | 703703.4992 | 704030.2667 | 703771.441 | 705213.9581 | 704101.5122 | 705614.1733 | 703976.9345 | 704238.9605 | 0.81648 | 0.95363 | 0.98999 | 1 | -49 | 0.95363 | 1 | 0.81648 | 1
Actual Schedule | 2013-11-04 07:00 | 2013-12-02 07:00 | 671383.4988 | 671383.4988 | 703703.4988 | 2013-09-04 16:00 | 0 | 100% | -32320 | 95.41% | -62d | 78.4% | 100% | 2013-09-04 16:00 | 2013-09-04 16:00 | 2013-09-19 15:00 | 2013-11-29 16:00 | 2013-11-29 16:00 | 2013-11-29 16:00 | 2013-11-29 16:00 | 2013-11-29 16:00 | 2013-11-29 16:00 | 703703.4988 | 703703.4988 | 703703.4988 | 703703.4988 | 703703.4988 | 703703.4988 | 703703.4988 | 703703.4988 | 0.78397 | 0.95407 | 1 | 1 | -62 | 0.95407 | 1 | 0.78397 | 1