## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House (2) | 1 |  |  | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 | 406.375
66 | Voorbereiding | 1.1 |  |  | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 | 36.375
1 | Werfinrichting/Werftoiletten | 1.1.1 |  | FS7 | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 1.375
2 | Voorbereiding oplevering | 1.1.2 |  | FS7 | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 0.375
3 | Transportkosten | 1.1.3 |  | FS7 | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 7.375
4 | Magazijn | 1.1.4 |  | FS7 | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 6.375
5 | Studiekosten projectontwikkelaar | 1.1.5 |  | FS7 | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 17.375
6 | Studiekosten aannemer | 1.1.6 |  | FS7 | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 36.375
67 | Funderingen | 1.2 |  |  | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 | 41.375
7 | Funderingen | 1.2.1 | 1FS;2FS;3FS;4FS;5FS;6FS | FS8 | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 41.375
68 | Ruwbouw | 1.3 |  |  | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 | 113.375
8 | Gewa/Metselwerk | 1.3.1 | 7FS | FS9;FS10 | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 | 29.375
9 | Gewelven/Structuur | 1.3.2 | 8FS | FS11 | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 | 3.375
10 | Uitbranden GEWA | 1.3.3 | 8FS | FS11 | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 | 0.375
11 | Isolatie | 1.3.4 | 9FS;10FS | FS12 | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 | 6.375
12 | Parament | 1.3.5 | 11FS | FS13 | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 | 47.375
13 | Ytong/Gipswanden | 1.3.6 | 12FS | FS14;FS15 | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 | 4.375
14 | Dorpels | 1.3.7 | 13FS | FS16 | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 | 1.375
15 | Voegwerk | 1.3.8 | 13FS | FS16 | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 | 9.375
16 | Stelling | 1.3.9 | 14FS;15FS | FS17 | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 | 6.375
17 | Karweien | 1.3.10 | 16FS | FS18 | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 | 0.375
69 | Dakwerken | 1.4 |  |  | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 | 49.375
18 | Daktimmer traditioneel/prefabkap | 1.4.1 | 17FS | FS19 | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 | 25.375
19 | Dakdekken | 1.4.2 | 18FS | FS20;FS21 | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 | 4.375
20 | Goten en afleiders | 1.4.3 | 19FS | FS22;FS23;FS24 | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 | 1.375
21 | Zonnepanelen | 1.4.4 | 19FS |  | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 | 0.375
22 | Afdichting/groendaken/plat dak | 1.4.5 | 20FS | FS25 | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 | 7.375
23 | Dakvlakramen | 1.4.6 | 20FS |  | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 | 12.375
24 | Karwei dakwerk | 1.4.7 | 20FS |  | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 | 7.375
70 | Buitenschrijnwerk | 1.5 |  |  | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 | 15.375
25 | Kader buitenschrijnwerk Wachtbuizen | 1.5.1 | 22FS | FS26 | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 | 0.375
26 | Buitenschrijnwerk plaatsen | 1.5.2 | 25FS | FS27;FS28;FS29;FS30;FS40;FS41 | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 | 11.375
27 | Elastische voegen | 1.5.3 | 26FS |  | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 0.375
28 | Ballustrades/Trapleuningen | 1.5.4 | 26FS |  | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 | 2.375
29 | Poort | 1.5.5 | 26FS |  | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2.375
30 | Karwei binnenschrijnwerk | 1.5.6 | 26FS |  | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 | 0.375
71 | Binnenafwerking | 1.6 |  |  | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 | 77.375
31 | Plakwerken | 1.6.1 | 50FS | FS32 | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 | 11.375
32 | Chapes | 1.6.2 | 31FS | FS43 | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 | 15.375
33 | Vloerisolatie | 1.6.3 | 43FS | FS34 | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 | 1.375
34 | Tegelwerken | 1.6.4 | 33FS | FS35;FS36;FS37;FS38;FS39;FS47 | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 | 28.375
35 | Buisbek/Zoldluik/Platen zold/Stijl | 1.6.5 | 34FS |  | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 | 2.375
36 | Binnendeuren/uitbekledingen | 1.6.6 | 34FS |  | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 | 6.375
37 | Trap | 1.6.7 | 34FS |  | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 | 9.375
38 | Luchtdichten | 1.6.8 | 34FS |  | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 | 1.375
39 | Keuken (laminaat, kasten) | 1.6.9 | 34FS |  | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 | 13.375
72 | Technieken | 1.7 |  |  | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 | 118.375
40 | UZL | 1.7.1 | 26FS | FS42 | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2.375
41 | Betonplexplaten | 1.7.2 | 26FS | FS42 | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2.375
42 | Slijpen technieken/boringen | 1.7.3 | 40FS;41FS | FS44 | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 4.375
43 | Bad en douche | 1.7.4 | 32FS | FS33 | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 | 0.375
44 | Leidingen ventilatie | 1.7.5 | 42FS | FS45 | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2.375
45 | Leidingen san/WP/CV | 1.7.6 | 44FS | FS46 | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 5.375
46 | Leidingen vloerverwarming | 1.7.7 | 45FS | FS50 | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 | 5.375
47 | Afwerken ventilatie | 1.7.8 | 34FS | FS48 | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 | 1.375
48 | Afwerken sanitair | 1.7.9 | 47FS | FS49 | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 | 1.375
49 | Afwerken CV/WP | 1.7.10 | 48FS | FS51 | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 | 3.375
50 | Leidingen electro | 1.7.11 | 46FS | FS31 | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 3.375
51 | Afwerken electro | 1.7.12 | 49FS | FS52;FS53;FS54 | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 | 6.375
52 | Verlichting | 1.7.13 | 51FS | FS55;FS56;FS59 | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 | 3.375
53 | Diepsondering, bron en aansluiting | 1.7.14 | 51FS | FS55;FS56;FS59 | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 | 4.375
54 | Karweien | 1.7.15 | 51FS | FS55;FS56;FS59 | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 | 3.375
73 | Omgevingswerken | 1.8 |  |  | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 | 34.375
55 | Opkuis werf (afvoer puin & afval) | 1.8.1 | 52FS;53FS;54FS | FS57;FS58 | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 | 6.375
56 | Grondafvoer | 1.8.2 | 52FS;53FS;54FS | FS57;FS58 | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 | 0.375
57 | Opritten en terassen | 1.8.3 | 55FS;56FS |  | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 | 27.375
58 | Tuinaanleg | 1.8.4 | 55FS;56FS |  | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 | 27.375
74 | Schilderwerken | 1.9 |  |  | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 | 34.375
59 | Schilderwerken | 1.9.1 | 52FS;53FS;54FS |  | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 | 34.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House (2) | 2328h |  |  |  |  | 99 | 100 | 101
66 | Voorbereiding | 216h |  |  |  |  | 99 | 100 | 101
1 | Werfinrichting/Werftoiletten | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Voorbereiding oplevering | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Transportkosten | 48h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Magazijn | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Studiekosten projectontwikkelaar | 112h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Studiekosten aannemer | 216h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
67 | Funderingen | 240h |  |  |  |  | 99 | 100 | 101
7 | Funderingen | 240h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
68 | Ruwbouw | 656h |  |  |  |  | 99 | 100 | 101
8 | Gewa/Metselwerk | 176h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Gewelven/Structuur | 32h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Uitbranden GEWA | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Isolatie | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Parament | 272h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Ytong/Gipswanden | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Dorpels | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Voegwerk | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Stelling | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Karweien | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
69 | Dakwerken | 288h |  |  |  |  | 99 | 100 | 101
18 | Daktimmer traditioneel/prefabkap | 160h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
19 | Dakdekken | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Goten en afleiders | 16h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
21 | Zonnepanelen | 8h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
22 | Afdichting/groendaken/plat dak | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
23 | Dakvlakramen | 72h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Karwei dakwerk | 48h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
70 | Buitenschrijnwerk | 96h |  |  |  |  | 99 | 100 | 101
25 | Kader buitenschrijnwerk Wachtbuizen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Buitenschrijnwerk plaatsen | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Elastische voegen | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Ballustrades/Trapleuningen | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Poort | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
30 | Karwei binnenschrijnwerk | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
71 | Binnenafwerking | 448h |  |  |  |  | 99 | 100 | 101
31 | Plakwerken | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
32 | Chapes | 96h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
33 | Vloerisolatie | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
34 | Tegelwerken | 168h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
35 | Buisbek/Zoldluik/Platen zold/Stijl | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
36 | Binnendeuren/uitbekledingen | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
37 | Trap | 64h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
38 | Luchtdichten | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
39 | Keuken (laminaat, kasten) | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
72 | Technieken | 680h |  |  |  |  | 99 | 100 | 101
40 | UZL | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
41 | Betonplexplaten | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
42 | Slijpen technieken/boringen | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
43 | Bad en douche | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
44 | Leidingen ventilatie | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
45 | Leidingen san/WP/CV | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
46 | Leidingen vloerverwarming | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
47 | Afwerken ventilatie | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
48 | Afwerken sanitair | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
49 | Afwerken CV/WP | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
50 | Leidingen electro | 32h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
51 | Afwerken electro | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
52 | Verlichting | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
53 | Diepsondering, bron en aansluiting | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
54 | Karweien | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
73 | Omgevingswerken | 200h |  |  |  |  | 99 | 100 | 101
55 | Opkuis werf (afvoer puin & afval) | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
56 | Grondafvoer | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
57 | Opritten en terassen | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
58 | Tuinaanleg | 160h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
74 | Schilderwerken | 200h |  |  |  |  | 99 | 100 | 101
59 | Schilderwerken | 200h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-05-20 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (2) | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 |  | 53d | [5 empty] | 25242 |  | 10.87% |  | 24235 | 24235
66 | Voorbereiding | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 |  | 25d | [5 empty] | 15972 |  | 100% |  | 15468 | 15468
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 2016-03-08 08:00 | 3d | 350 | 0 | 0 | 270 | 0 | 620 | 0 | 100% | Finished | 350 | 350 | 100 | 150 | 100 | 100 | 177.1429 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 2016-03-08 08:00 | 1d | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 100% | Finished | 187 | 187 | 100 | 100 | 100 | 100 | 100 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 2016-03-08 08:00 | 6d | 1725 | 0 | 0 | 24 | 0 | 1749 | 0 | 100% | Finished | 1725 | 1725 | 100 | 100 | 100 | 100 | 101.3913 | 100
4 | Magazijn | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 2016-03-08 08:00 | 5d | 1192 | 0 | 0 | 57 | 0 | 1249 | 0 | 100% | Finished | 1192 | 1192 | 100 | 100 | 100 | 100 | 104.7819 | 100
5 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 2016-03-08 08:00 | 15d | 4128 | 0 | 0 | 839 | 0 | 4967 | 0 | 100% | Finished | 4128 | 4128 | 100 | 107.1429 | 100 | 100 | 120.3246 | 100
6 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 2016-03-08 08:00 | 25d | 7886 | 0 | 0 | -686 | 0 | 7200 | 0 | 100% | Finished | 7886 | 7886 | 100 | 92.5926 | 100 | 100 | 91.301 | 100
67 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 |  | 28d | [5 empty] | 9270 |  | 100% |  | 8767 | 8767
7 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 2016-04-12 08:00 | 28d | 8767 | 0 | 0 | 503 | 0 | 9270 | 0 | 100% | Finished | 8767 | 8767 | 100 | 93.3333 | 100 | 100 | 105.7374 | 100
68 | Ruwbouw | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
8 | Gewa/Metselwerk | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 |  | 0 | 0 | 18103 | 22d | 0 | 0 | 0 | 18103 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Gewelven/Structuur | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 |  | 0 | 0 | 7328 | 4d | 0 | 0 | 0 | 7328 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Uitbranden GEWA | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 |  | 0 | 0 | 479 | 1d | 0 | 0 | 0 | 479 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Isolatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 |  | 0 | 0 | 4451 | 5d | 0 | 0 | 0 | 4451 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | Parament | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 |  | 0 | 0 | 19722 | 34d | 0 | 0 | 0 | 19722 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | Ytong/Gipswanden | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 |  | 0 | 0 | 2447 | 3d | 0 | 0 | 0 | 2447 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
14 | Dorpels | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 |  | 0 | 0 | 1065 | 2d | 0 | 0 | 0 | 1065 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Voegwerk | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 |  | 0 | 0 | 2246 | 8d | 0 | 0 | 0 | 2246 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Stelling | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 |  | 0 | 0 | 1836 | 5d | 0 | 0 | 0 | 1836 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Karweien | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 |  | 0 | 0 | 293 | 1d | 0 | 0 | 0 | 293 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
69 | Dakwerken | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Daktimmer traditioneel/prefabkap | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 |  | 0 | 0 | 11226 | 20d | 0 | 0 | 0 | 11226 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Dakdekken | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 |  | 0 | 0 | 2752 | 5d | 0 | 0 | 0 | 2752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Goten en afleiders | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 |  | 0 | 0 | 321 | 2d | 0 | 0 | 0 | 321 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Zonnepanelen | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 |  | 0 | 0 | 422 | 1d | 0 | 0 | 0 | 422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Afdichting/groendaken/plat dak | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 |  | 0 | 0 | 2677 | 6d | 0 | 0 | 0 | 2677 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Dakvlakramen | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 |  | 0 | 0 | 4783 | 9d | 0 | 0 | 0 | 4783 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Karwei dakwerk | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 |  | 0 | 0 | 1671 | 6d | 0 | 0 | 0 | 1671 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Buitenschrijnwerk | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 |  | 0 | 0 | 118 | 1d | 0 | 0 | 0 | 118 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Buitenschrijnwerk plaatsen | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 |  | 0 | 0 | 2256 | 8d | 0 | 0 | 0 | 2256 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Elastische voegen | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Ballustrades/Trapleuningen | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 |  | 0 | 0 | 710 | 3d | 0 | 0 | 0 | 710 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Poort | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 |  | 0 | 0 | 900 | 3d | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Karwei binnenschrijnwerk | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 |  | 0 | 0 | 250 | 1d | 0 | 0 | 0 | 250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Binnenafwerking | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Plakwerken | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 |  | 0 | 0 | 8700 | 10d | 0 | 0 | 0 | 8700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Chapes | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 |  | 0 | 0 | 4025 | 12d | 0 | 0 | 0 | 4025 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Vloerisolatie | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 |  | 0 | 0 | 2245 | 2d | 0 | 0 | 0 | 2245 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Tegelwerken | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 |  | 0 | 0 | 8951 | 21d | 0 | 0 | 0 | 8951 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 3d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnendeuren/uitbekledingen | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 |  | 0 | 0 | 1269 | 5d | 0 | 0 | 0 | 1269 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Trap | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 |  | 0 | 0 | 2312 | 8d | 0 | 0 | 0 | 2312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Luchtdichten | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 |  | 0 | 0 | 549 | 2d | 0 | 0 | 0 | 549 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Keuken (laminaat, kasten) | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 |  | 0 | 0 | 14493 | 10d | 0 | 0 | 0 | 14493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Technieken | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | UZL | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Betonplexplaten | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Slijpen technieken/boringen | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 |  | 0 | 0 | 1300 | 5d | 0 | 0 | 0 | 1300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Bad en douche | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen ventilatie | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 |  | 0 | 0 | 1926 | 3d | 0 | 0 | 0 | 1926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Leidingen san/WP/CV | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 |  | 0 | 0 | 2481 | 4d | 0 | 0 | 0 | 2481 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Leidingen vloerverwarming | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 |  | 0 | 0 | 2557 | 4d | 0 | 0 | 0 | 2557 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken ventilatie | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken sanitair | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Afwerken CV/WP | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Leidingen electro | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 |  | 0 | 0 | 2594 | 4d | 0 | 0 | 0 | 2594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Afwerken electro | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Verlichting | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 |  | 0 | 0 | 6653 | 2d | 0 | 0 | 0 | 6653 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 3d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 |  | 0 | 0 | 480 | 2d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Omgevingswerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werf (afvoer puin & afval) | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 |  | 0 | 0 | 1400 | 5d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Grondafvoer | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 |  | 0 | 0 | 280 | 1d | 0 | 0 | 0 | 280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opritten en terassen | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 |  | 0 | 0 | 6995 | 20d | 0 | 0 | 0 | 6995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Tuinaanleg | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 |  | 0 | 0 | 7158 | 20d | 0 | 0 | 0 | 7158 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 25d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-09-16 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (2) | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 |  | 138d | [5 empty] | 83287 |  | 36.89% |  | 82205 | 81912
66 | Voorbereiding | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 |  | 25d | [5 empty] | 15972 |  | 100% |  | 15468 | 15468
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 2016-03-08 08:00 | 3d | 350 | 0 | 0 | 270 | 0 | 620 | 0 | 100% | Finished | 350 | 350 | 100 | 150 | 100 | 100 | 177.1429 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 2016-03-08 08:00 | 1d | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 100% | Finished | 187 | 187 | 100 | 100 | 100 | 100 | 100 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 2016-03-08 08:00 | 6d | 1725 | 0 | 0 | 24 | 0 | 1749 | 0 | 100% | Finished | 1725 | 1725 | 100 | 100 | 100 | 100 | 101.3913 | 100
4 | Magazijn | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 2016-03-08 08:00 | 5d | 1192 | 0 | 0 | 57 | 0 | 1249 | 0 | 100% | Finished | 1192 | 1192 | 100 | 100 | 100 | 100 | 104.7819 | 100
5 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 2016-03-08 08:00 | 15d | 4128 | 0 | 0 | 839 | 0 | 4967 | 0 | 100% | Finished | 4128 | 4128 | 100 | 107.1429 | 100 | 100 | 120.3246 | 100
6 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 2016-03-08 08:00 | 25d | 7886 | 0 | 0 | -686 | 0 | 7200 | 0 | 100% | Finished | 7886 | 7886 | 100 | 92.5926 | 100 | 100 | 91.301 | 100
67 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 |  | 28d | [5 empty] | 9270 |  | 100% |  | 8767 | 8767
7 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 2016-04-12 08:00 | 28d | 8767 | 0 | 0 | 503 | 0 | 9270 | 0 | 100% | Finished | 8767 | 8767 | 100 | 93.3333 | 100 | 100 | 105.7374 | 100
68 | Ruwbouw | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 |  | 81d | [5 empty] | 58045 |  | 100% |  | 57970 | 57677
8 | Gewa/Metselwerk | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 | 2016-05-20 08:00 | 21d | 18103 | 0 | 0 | 96 | 0 | 18199 | 0 | 100% | Finished | 18103 | 18103 | 100 | 95.4545 | 100 | 100 | 100.5303 | 100
9 | Gewelven/Structuur | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 | 2016-06-20 08:00 | 5d | 7328 | 0 | 0 | 31 | 0 | 7359 | 0 | 100% | Finished | 7328 | 7328 | 100 | 125 | 100 | 100 | 100.423 | 100
10 | Uitbranden GEWA | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 | 2016-06-20 08:00 | 1d | 479 | 0 | 0 | -9 | 0 | 470 | 0 | 100% | Finished | 479 | 479 | 100 | 100 | 100 | 100 | 98.1211 | 100
11 | Isolatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 | 2016-06-27 08:00 | 5d | 4451 | 0 | 0 | -11 | 0 | 4440 | 0 | 100% | Finished | 4451 | 4451 | 100 | 100 | 100 | 100 | 99.7529 | 100
12 | Parament | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 | 2016-07-04 08:00 | 34d | 19722 | 0 | 0 | 169 | 0 | 19891 | 0 | 100% | Finished | 19722 | 19722 | 100 | 100 | 100 | 100 | 100.8569 | 100
13 | Ytong/Gipswanden | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 | 2016-08-19 08:00 | 3d | 2447 | 0 | 0 | 22 | 0 | 2469 | 0 | 100% | Finished | 2447 | 2447 | 100 | 100 | 100 | 100 | 100.8991 | 100
14 | Dorpels | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 | 2016-08-24 08:00 | 2d | 1065 | 0 | 0 | 5 | 0 | 1070 | 0 | 100% | Finished | 1065 | 1065 | 100 | 100 | 100 | 100 | 100.4695 | 100
15 | Voegwerk | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 | 2016-08-24 08:00 | 8d | 2246 | 0 | 0 | -171 | 0 | 2075 | 0 | 100% | Finished | 2246 | 2246 | 100 | 100 | 100 | 100 | 92.3865 | 100
16 | Stelling | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 | 2016-09-05 08:00 | 4d | 1836 | 0 | 0 | -57 | 0 | 1779 | 0 | 100% | Finished | 1836 | 1836 | 100 | 80 | 100 | 100 | 96.8954 | 100
17 | Karweien | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 | 2016-09-09 08:00 | 1d | 293 | 0 | 0 | 0 | 0 | 293 | 0 | 100% | Finished | 293 | 0 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
18 | Daktimmer traditioneel/prefabkap | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 |  | 0 | 0 | 11226 | 20d | 0 | 0 | 0 | 11226 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
19 | Dakdekken | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 |  | 0 | 0 | 2752 | 5d | 0 | 0 | 0 | 2752 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Goten en afleiders | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 |  | 0 | 0 | 321 | 2d | 0 | 0 | 0 | 321 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Zonnepanelen | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 |  | 0 | 0 | 422 | 1d | 0 | 0 | 0 | 422 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | Afdichting/groendaken/plat dak | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 |  | 0 | 0 | 2677 | 6d | 0 | 0 | 0 | 2677 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | Dakvlakramen | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 |  | 0 | 0 | 4783 | 9d | 0 | 0 | 0 | 4783 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Karwei dakwerk | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 |  | 0 | 0 | 1671 | 6d | 0 | 0 | 0 | 1671 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
70 | Buitenschrijnwerk | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 |  | 0 | 0 | 118 | 1d | 0 | 0 | 0 | 118 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Buitenschrijnwerk plaatsen | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 |  | 0 | 0 | 2256 | 8d | 0 | 0 | 0 | 2256 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
27 | Elastische voegen | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Ballustrades/Trapleuningen | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 |  | 0 | 0 | 710 | 3d | 0 | 0 | 0 | 710 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Poort | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 |  | 0 | 0 | 900 | 3d | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Karwei binnenschrijnwerk | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 |  | 0 | 0 | 250 | 1d | 0 | 0 | 0 | 250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Binnenafwerking | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Plakwerken | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 |  | 0 | 0 | 8700 | 10d | 0 | 0 | 0 | 8700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Chapes | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 |  | 0 | 0 | 4025 | 12d | 0 | 0 | 0 | 4025 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Vloerisolatie | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 |  | 0 | 0 | 2245 | 2d | 0 | 0 | 0 | 2245 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Tegelwerken | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 |  | 0 | 0 | 8951 | 21d | 0 | 0 | 0 | 8951 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 3d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnendeuren/uitbekledingen | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 |  | 0 | 0 | 1269 | 5d | 0 | 0 | 0 | 1269 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Trap | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 |  | 0 | 0 | 2312 | 8d | 0 | 0 | 0 | 2312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Luchtdichten | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 |  | 0 | 0 | 549 | 2d | 0 | 0 | 0 | 549 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Keuken (laminaat, kasten) | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 |  | 0 | 0 | 14493 | 10d | 0 | 0 | 0 | 14493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Technieken | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | UZL | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Betonplexplaten | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Slijpen technieken/boringen | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 |  | 0 | 0 | 1300 | 5d | 0 | 0 | 0 | 1300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Bad en douche | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen ventilatie | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 |  | 0 | 0 | 1926 | 3d | 0 | 0 | 0 | 1926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Leidingen san/WP/CV | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 |  | 0 | 0 | 2481 | 4d | 0 | 0 | 0 | 2481 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Leidingen vloerverwarming | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 |  | 0 | 0 | 2557 | 4d | 0 | 0 | 0 | 2557 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken ventilatie | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken sanitair | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Afwerken CV/WP | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Leidingen electro | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 |  | 0 | 0 | 2594 | 4d | 0 | 0 | 0 | 2594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Afwerken electro | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Verlichting | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 |  | 0 | 0 | 6653 | 2d | 0 | 0 | 0 | 6653 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 3d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 |  | 0 | 0 | 480 | 2d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Omgevingswerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werf (afvoer puin & afval) | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 |  | 0 | 0 | 1400 | 5d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Grondafvoer | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 |  | 0 | 0 | 280 | 1d | 0 | 0 | 0 | 280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opritten en terassen | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 |  | 0 | 0 | 6995 | 20d | 0 | 0 | 0 | 6995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Tuinaanleg | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 |  | 0 | 0 | 7158 | 20d | 0 | 0 | 0 | 7158 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 25d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-11-04 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (2) | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 |  | 173d | [5 empty] | 108630 |  | 48.65% |  | 108431 | 106175
66 | Voorbereiding | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 |  | 25d | [5 empty] | 15972 |  | 100% |  | 15468 | 15468
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 2016-03-08 08:00 | 3d | 350 | 0 | 0 | 270 | 0 | 620 | 0 | 100% | Finished | 350 | 350 | 100 | 150 | 100 | 100 | 177.1429 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 2016-03-08 08:00 | 1d | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 100% | Finished | 187 | 187 | 100 | 100 | 100 | 100 | 100 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 2016-03-08 08:00 | 6d | 1725 | 0 | 0 | 24 | 0 | 1749 | 0 | 100% | Finished | 1725 | 1725 | 100 | 100 | 100 | 100 | 101.3913 | 100
4 | Magazijn | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 2016-03-08 08:00 | 5d | 1192 | 0 | 0 | 57 | 0 | 1249 | 0 | 100% | Finished | 1192 | 1192 | 100 | 100 | 100 | 100 | 104.7819 | 100
5 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 2016-03-08 08:00 | 15d | 4128 | 0 | 0 | 839 | 0 | 4967 | 0 | 100% | Finished | 4128 | 4128 | 100 | 107.1429 | 100 | 100 | 120.3246 | 100
6 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 2016-03-08 08:00 | 25d | 7886 | 0 | 0 | -686 | 0 | 7200 | 0 | 100% | Finished | 7886 | 7886 | 100 | 92.5926 | 100 | 100 | 91.301 | 100
67 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 |  | 28d | [5 empty] | 9270 |  | 100% |  | 8767 | 8767
7 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 2016-04-12 08:00 | 28d | 8767 | 0 | 0 | 503 | 0 | 9270 | 0 | 100% | Finished | 8767 | 8767 | 100 | 93.3333 | 100 | 100 | 105.7374 | 100
68 | Ruwbouw | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 |  | 81d | [5 empty] | 58045 |  | 100% |  | 57970 | 57970
8 | Gewa/Metselwerk | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 | 2016-05-20 08:00 | 21d | 18103 | 0 | 0 | 96 | 0 | 18199 | 0 | 100% | Finished | 18103 | 18103 | 100 | 95.4545 | 100 | 100 | 100.5303 | 100
9 | Gewelven/Structuur | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 | 2016-06-20 08:00 | 5d | 7328 | 0 | 0 | 31 | 0 | 7359 | 0 | 100% | Finished | 7328 | 7328 | 100 | 125 | 100 | 100 | 100.423 | 100
10 | Uitbranden GEWA | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 | 2016-06-20 08:00 | 1d | 479 | 0 | 0 | -9 | 0 | 470 | 0 | 100% | Finished | 479 | 479 | 100 | 100 | 100 | 100 | 98.1211 | 100
11 | Isolatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 | 2016-06-27 08:00 | 5d | 4451 | 0 | 0 | -11 | 0 | 4440 | 0 | 100% | Finished | 4451 | 4451 | 100 | 100 | 100 | 100 | 99.7529 | 100
12 | Parament | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 | 2016-07-04 08:00 | 34d | 19722 | 0 | 0 | 169 | 0 | 19891 | 0 | 100% | Finished | 19722 | 19722 | 100 | 100 | 100 | 100 | 100.8569 | 100
13 | Ytong/Gipswanden | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 | 2016-08-19 08:00 | 3d | 2447 | 0 | 0 | 22 | 0 | 2469 | 0 | 100% | Finished | 2447 | 2447 | 100 | 100 | 100 | 100 | 100.8991 | 100
14 | Dorpels | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 | 2016-08-24 08:00 | 2d | 1065 | 0 | 0 | 5 | 0 | 1070 | 0 | 100% | Finished | 1065 | 1065 | 100 | 100 | 100 | 100 | 100.4695 | 100
15 | Voegwerk | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 | 2016-08-24 08:00 | 8d | 2246 | 0 | 0 | -171 | 0 | 2075 | 0 | 100% | Finished | 2246 | 2246 | 100 | 100 | 100 | 100 | 92.3865 | 100
16 | Stelling | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 | 2016-09-05 08:00 | 4d | 1836 | 0 | 0 | -57 | 0 | 1779 | 0 | 100% | Finished | 1836 | 1836 | 100 | 80 | 100 | 100 | 96.8954 | 100
17 | Karweien | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 | 2016-09-09 08:00 | 1d | 293 | 0 | 0 | 0 | 0 | 293 | 0 | 100% | Finished | 293 | 293 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 |  | 30d | [5 empty] | 22976 |  | 100% |  | 23852 | 23852
18 | Daktimmer traditioneel/prefabkap | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 | 2016-09-19 08:00 | 20d | 11226 | 0 | 0 | 0 | 0 | 11226 | 0 | 100% | Finished | 11226 | 11226 | 100 | 100 | 100 | 100 | 100 | 100
19 | Dakdekken | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 | 2016-10-10 08:00 | 4d | 2752 | 0 | 0 | -52 | 0 | 2700 | 0 | 100% | Finished | 2752 | 2752 | 100 | 80 | 100 | 100 | 98.1105 | 100
20 | Goten en afleiders | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 | 2016-10-14 08:00 | 2d | 321 | 0 | 0 | 0 | 0 | 321 | 0 | 100% | Finished | 321 | 321 | 100 | 100 | 100 | 100 | 100 | 100
21 | Zonnepanelen | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 | 2016-10-14 08:00 | 1d | 422 | 0 | 0 | -3 | 0 | 419 | 0 | 100% | Finished | 422 | 422 | 100 | 100 | 100 | 100 | 99.2891 | 100
22 | Afdichting/groendaken/plat dak | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 | 2016-10-18 08:00 | 3d | 2677 | 0 | 0 | -837 | 0 | 1840 | 0 | 100% | Finished | 2677 | 2677 | 100 | 50 | 100 | 100 | 68.7337 | 100
23 | Dakvlakramen | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 | 2016-10-18 08:00 | 9d | 4783 | 0 | 0 | 16 | 0 | 4799 | 0 | 100% | Finished | 4783 | 4783 | 100 | 100 | 100 | 100 | 100.3345 | 100
24 | Karwei dakwerk | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 | 2016-10-18 08:00 | 6d | 1671 | 0 | 0 | 0 | 0 | 1671 | 0 | 100% | Finished | 1671 | 1671 | 100 | 100 | 100 | 100 | 100 | 100
70 | Buitenschrijnwerk | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 |  | 10d | [5 empty] | 2367 |  | 55.42% |  | 2374 | 118
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 | 2016-10-21 08:00 | 1d | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 100% | Finished | 118 | 118 | 100 | 100 | 100 | 100 | 100 | 100
26 | Buitenschrijnwerk plaatsen | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 | 2016-10-24 08:00 | 8d | 2256 | 0 | 0 | -7 | 0 | 2249 | 0 | 100% | Finished | 2256 | 0 | 100 | 100 | 100 | 100 | 99.6897 | 100
27 | Elastische voegen | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 |  | 0 | 0 | 50 | 1d | 0 | 0 | 0 | 50 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
28 | Ballustrades/Trapleuningen | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 |  | 0 | 0 | 710 | 3d | 0 | 0 | 0 | 710 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Poort | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 |  | 0 | 0 | 900 | 3d | 0 | 0 | 0 | 900 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Karwei binnenschrijnwerk | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 |  | 0 | 0 | 250 | 1d | 0 | 0 | 0 | 250 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
71 | Binnenafwerking | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Plakwerken | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 |  | 0 | 0 | 8700 | 10d | 0 | 0 | 0 | 8700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Chapes | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 |  | 0 | 0 | 4025 | 12d | 0 | 0 | 0 | 4025 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Vloerisolatie | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 |  | 0 | 0 | 2245 | 2d | 0 | 0 | 0 | 2245 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Tegelwerken | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 |  | 0 | 0 | 8951 | 21d | 0 | 0 | 0 | 8951 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 3d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnendeuren/uitbekledingen | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 |  | 0 | 0 | 1269 | 5d | 0 | 0 | 0 | 1269 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Trap | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 |  | 0 | 0 | 2312 | 8d | 0 | 0 | 0 | 2312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Luchtdichten | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 |  | 0 | 0 | 549 | 2d | 0 | 0 | 0 | 549 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Keuken (laminaat, kasten) | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 |  | 0 | 0 | 14493 | 10d | 0 | 0 | 0 | 14493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Technieken | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
40 | UZL | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 |  | 0 | 0 | 888 | 3d | 0 | 0 | 0 | 888 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
41 | Betonplexplaten | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 |  | 0 | 0 | 625 | 3d | 0 | 0 | 0 | 625 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
42 | Slijpen technieken/boringen | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 |  | 0 | 0 | 1300 | 5d | 0 | 0 | 0 | 1300 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
43 | Bad en douche | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen ventilatie | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 |  | 0 | 0 | 1926 | 3d | 0 | 0 | 0 | 1926 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
45 | Leidingen san/WP/CV | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 |  | 0 | 0 | 2481 | 4d | 0 | 0 | 0 | 2481 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
46 | Leidingen vloerverwarming | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 |  | 0 | 0 | 2557 | 4d | 0 | 0 | 0 | 2557 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
47 | Afwerken ventilatie | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken sanitair | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Afwerken CV/WP | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Leidingen electro | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 |  | 0 | 0 | 2594 | 4d | 0 | 0 | 0 | 2594 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
51 | Afwerken electro | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Verlichting | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 |  | 0 | 0 | 6653 | 2d | 0 | 0 | 0 | 6653 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 3d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 |  | 0 | 0 | 480 | 2d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Omgevingswerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werf (afvoer puin & afval) | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 |  | 0 | 0 | 1400 | 5d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Grondafvoer | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 |  | 0 | 0 | 280 | 1d | 0 | 0 | 0 | 280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opritten en terassen | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 |  | 0 | 0 | 6995 | 20d | 0 | 0 | 0 | 6995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Tuinaanleg | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 |  | 0 | 0 | 7158 | 20d | 0 | 0 | 0 | 7158 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 25d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-12-14 08:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (2) | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 |  | 201d | [5 empty] | 126191 |  | 55.06% |  | 122712 | 122712
66 | Voorbereiding | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 |  | 25d | [5 empty] | 15972 |  | 100% |  | 15468 | 15468
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 2016-03-08 08:00 | 3d | 350 | 0 | 0 | 270 | 0 | 620 | 0 | 100% | Finished | 350 | 350 | 100 | 150 | 100 | 100 | 177.1429 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 2016-03-08 08:00 | 1d | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 100% | Finished | 187 | 187 | 100 | 100 | 100 | 100 | 100 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 2016-03-08 08:00 | 6d | 1725 | 0 | 0 | 24 | 0 | 1749 | 0 | 100% | Finished | 1725 | 1725 | 100 | 100 | 100 | 100 | 101.3913 | 100
4 | Magazijn | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 2016-03-08 08:00 | 5d | 1192 | 0 | 0 | 57 | 0 | 1249 | 0 | 100% | Finished | 1192 | 1192 | 100 | 100 | 100 | 100 | 104.7819 | 100
5 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 2016-03-08 08:00 | 15d | 4128 | 0 | 0 | 839 | 0 | 4967 | 0 | 100% | Finished | 4128 | 4128 | 100 | 107.1429 | 100 | 100 | 120.3246 | 100
6 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 2016-03-08 08:00 | 25d | 7886 | 0 | 0 | -686 | 0 | 7200 | 0 | 100% | Finished | 7886 | 7886 | 100 | 92.5926 | 100 | 100 | 91.301 | 100
67 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 |  | 28d | [5 empty] | 9270 |  | 100% |  | 8767 | 8767
7 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 2016-04-12 08:00 | 28d | 8767 | 0 | 0 | 503 | 0 | 9270 | 0 | 100% | Finished | 8767 | 8767 | 100 | 93.3333 | 100 | 100 | 105.7374 | 100
68 | Ruwbouw | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 |  | 81d | [5 empty] | 58045 |  | 100% |  | 57970 | 57970
8 | Gewa/Metselwerk | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 | 2016-05-20 08:00 | 21d | 18103 | 0 | 0 | 96 | 0 | 18199 | 0 | 100% | Finished | 18103 | 18103 | 100 | 95.4545 | 100 | 100 | 100.5303 | 100
9 | Gewelven/Structuur | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 | 2016-06-20 08:00 | 5d | 7328 | 0 | 0 | 31 | 0 | 7359 | 0 | 100% | Finished | 7328 | 7328 | 100 | 125 | 100 | 100 | 100.423 | 100
10 | Uitbranden GEWA | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 | 2016-06-20 08:00 | 1d | 479 | 0 | 0 | -9 | 0 | 470 | 0 | 100% | Finished | 479 | 479 | 100 | 100 | 100 | 100 | 98.1211 | 100
11 | Isolatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 | 2016-06-27 08:00 | 5d | 4451 | 0 | 0 | -11 | 0 | 4440 | 0 | 100% | Finished | 4451 | 4451 | 100 | 100 | 100 | 100 | 99.7529 | 100
12 | Parament | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 | 2016-07-04 08:00 | 34d | 19722 | 0 | 0 | 169 | 0 | 19891 | 0 | 100% | Finished | 19722 | 19722 | 100 | 100 | 100 | 100 | 100.8569 | 100
13 | Ytong/Gipswanden | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 | 2016-08-19 08:00 | 3d | 2447 | 0 | 0 | 22 | 0 | 2469 | 0 | 100% | Finished | 2447 | 2447 | 100 | 100 | 100 | 100 | 100.8991 | 100
14 | Dorpels | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 | 2016-08-24 08:00 | 2d | 1065 | 0 | 0 | 5 | 0 | 1070 | 0 | 100% | Finished | 1065 | 1065 | 100 | 100 | 100 | 100 | 100.4695 | 100
15 | Voegwerk | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 | 2016-08-24 08:00 | 8d | 2246 | 0 | 0 | -171 | 0 | 2075 | 0 | 100% | Finished | 2246 | 2246 | 100 | 100 | 100 | 100 | 92.3865 | 100
16 | Stelling | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 | 2016-09-05 08:00 | 4d | 1836 | 0 | 0 | -57 | 0 | 1779 | 0 | 100% | Finished | 1836 | 1836 | 100 | 80 | 100 | 100 | 96.8954 | 100
17 | Karweien | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 | 2016-09-09 08:00 | 1d | 293 | 0 | 0 | 0 | 0 | 293 | 0 | 100% | Finished | 293 | 293 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 |  | 30d | [5 empty] | 22976 |  | 100% |  | 23852 | 23852
18 | Daktimmer traditioneel/prefabkap | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 | 2016-09-19 08:00 | 20d | 11226 | 0 | 0 | 0 | 0 | 11226 | 0 | 100% | Finished | 11226 | 11226 | 100 | 100 | 100 | 100 | 100 | 100
19 | Dakdekken | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 | 2016-10-10 08:00 | 4d | 2752 | 0 | 0 | -52 | 0 | 2700 | 0 | 100% | Finished | 2752 | 2752 | 100 | 80 | 100 | 100 | 98.1105 | 100
20 | Goten en afleiders | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 | 2016-10-14 08:00 | 2d | 321 | 0 | 0 | 0 | 0 | 321 | 0 | 100% | Finished | 321 | 321 | 100 | 100 | 100 | 100 | 100 | 100
21 | Zonnepanelen | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 | 2016-10-14 08:00 | 1d | 422 | 0 | 0 | -3 | 0 | 419 | 0 | 100% | Finished | 422 | 422 | 100 | 100 | 100 | 100 | 99.2891 | 100
22 | Afdichting/groendaken/plat dak | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 | 2016-10-18 08:00 | 3d | 2677 | 0 | 0 | -837 | 0 | 1840 | 0 | 100% | Finished | 2677 | 2677 | 100 | 50 | 100 | 100 | 68.7337 | 100
23 | Dakvlakramen | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 | 2016-10-18 08:00 | 9d | 4783 | 0 | 0 | 16 | 0 | 4799 | 0 | 100% | Finished | 4783 | 4783 | 100 | 100 | 100 | 100 | 100.3345 | 100
24 | Karwei dakwerk | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 | 2016-10-18 08:00 | 6d | 1671 | 0 | 0 | 0 | 0 | 1671 | 0 | 100% | Finished | 1671 | 1671 | 100 | 100 | 100 | 100 | 100 | 100
70 | Buitenschrijnwerk | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 |  | 13d | [5 empty] | 4162 |  | 100% |  | 4284 | 4284
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 | 2016-10-21 08:00 | 1d | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 100% | Finished | 118 | 118 | 100 | 100 | 100 | 100 | 100 | 100
26 | Buitenschrijnwerk plaatsen | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 | 2016-10-24 08:00 | 8d | 2256 | 0 | 0 | -7 | 0 | 2249 | 0 | 100% | Finished | 2256 | 2256 | 100 | 100 | 100 | 100 | 99.6897 | 100
27 | Elastische voegen | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2016-11-04 08:00 | 1d | 50 | 0 | 0 | 5 | 0 | 55 | 0 | 100% | Finished | 50 | 50 | 100 | 100 | 100 | 100 | 110 | 100
28 | Ballustrades/Trapleuningen | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 | 2016-11-04 08:00 | 3d | 710 | 0 | 0 | -10 | 0 | 700 | 0 | 100% | Finished | 710 | 710 | 100 | 100 | 100 | 100 | 98.5915 | 100
29 | Poort | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2016-11-04 08:00 | 3d | 900 | 0 | 0 | -110 | 0 | 790 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 87.7778 | 100
30 | Karwei binnenschrijnwerk | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 | 2016-11-04 08:00 | 1d | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 100% | Finished | 250 | 250 | 100 | 100 | 100 | 100 | 100 | 100
71 | Binnenafwerking | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
31 | Plakwerken | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 |  | 0 | 0 | 8700 | 10d | 0 | 0 | 0 | 8700 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
32 | Chapes | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 |  | 0 | 0 | 4025 | 12d | 0 | 0 | 0 | 4025 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
33 | Vloerisolatie | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 |  | 0 | 0 | 2245 | 2d | 0 | 0 | 0 | 2245 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
34 | Tegelwerken | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 |  | 0 | 0 | 8951 | 21d | 0 | 0 | 0 | 8951 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
35 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 |  | 0 | 0 | 600 | 3d | 0 | 0 | 0 | 600 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
36 | Binnendeuren/uitbekledingen | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 |  | 0 | 0 | 1269 | 5d | 0 | 0 | 0 | 1269 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
37 | Trap | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 |  | 0 | 0 | 2312 | 8d | 0 | 0 | 0 | 2312 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
38 | Luchtdichten | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 |  | 0 | 0 | 549 | 2d | 0 | 0 | 0 | 549 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
39 | Keuken (laminaat, kasten) | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 |  | 0 | 0 | 14493 | 10d | 0 | 0 | 0 | 14493 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
72 | Technieken | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 |  | 28d | [5 empty] | 15766 |  | 32.95% |  | 12371 | 12371
40 | UZL | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-11-04 08:00 | 3d | 888 | 0 | 0 | 12 | 0 | 900 | 0 | 100% | Finished | 888 | 888 | 100 | 100 | 100 | 100 | 101.3514 | 100
41 | Betonplexplaten | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2016-11-04 08:00 | 2d | 625 | 0 | 0 | -330 | 0 | 295 | 0 | 100% | Finished | 625 | 625 | 100 | 66.6667 | 100 | 100 | 47.2 | 100
42 | Slijpen technieken/boringen | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 2016-11-08 08:00 | 5d | 1300 | 0 | 0 | 150 | 0 | 1450 | 0 | 100% | Finished | 1300 | 1300 | 100 | 100 | 100 | 100 | 111.5385 | 100
43 | Bad en douche | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 |  | 0 | 0 | 1152 | 1d | 0 | 0 | 0 | 1152 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
44 | Leidingen ventilatie | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2016-11-15 08:00 | 5d | 1926 | 0 | 0 | 1761 | 0 | 3687 | 0 | 100% | Finished | 1926 | 1926 | 100 | 166.6667 | 100 | 100 | 191.433 | 100
45 | Leidingen san/WP/CV | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 2016-11-22 08:00 | 7d | 2481 | 0 | 0 | 934 | 0 | 3415 | 0 | 100% | Finished | 2481 | 2481 | 100 | 175 | 100 | 100 | 137.6461 | 100
46 | Leidingen vloerverwarming | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 | 2016-12-01 08:00 | 5d | 2557 | 0 | 0 | 862 | 0 | 3419 | 0 | 100% | Finished | 2557 | 2557 | 100 | 125 | 100 | 100 | 133.7114 | 100
47 | Afwerken ventilatie | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 |  | 0 | 0 | 1899 | 2d | 0 | 0 | 0 | 1899 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
48 | Afwerken sanitair | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 |  | 0 | 0 | 2565 | 2d | 0 | 0 | 0 | 2565 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
49 | Afwerken CV/WP | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 |  | 0 | 0 | 6352 | 4d | 0 | 0 | 0 | 6352 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
50 | Leidingen electro | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 2016-12-08 08:00 | 4d | 2594 | 0 | 0 | 6 | 0 | 2600 | 0 | 100% | Finished | 2594 | 2594 | 100 | 100 | 100 | 100 | 100.2313 | 100
51 | Afwerken electro | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 |  | 0 | 0 | 3608 | 5d | 0 | 0 | 0 | 3608 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
52 | Verlichting | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 |  | 0 | 0 | 6653 | 2d | 0 | 0 | 0 | 6653 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
53 | Diepsondering, bron en aansluiting | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 |  | 0 | 0 | 2460 | 3d | 0 | 0 | 0 | 2460 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
54 | Karweien | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 |  | 0 | 0 | 480 | 2d | 0 | 0 | 0 | 480 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
73 | Omgevingswerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
55 | Opkuis werf (afvoer puin & afval) | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 |  | 0 | 0 | 1400 | 5d | 0 | 0 | 0 | 1400 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
56 | Grondafvoer | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 |  | 0 | 0 | 280 | 1d | 0 | 0 | 0 | 280 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
57 | Opritten en terassen | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 |  | 0 | 0 | 6995 | 20d | 0 | 0 | 0 | 6995 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
58 | Tuinaanleg | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 |  | 0 | 0 | 7158 | 20d | 0 | 0 | 0 | 7158 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
74 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
59 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 25d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP5
| TP Status Date | 2017-04-18 17:00 |  | TP Name | Tracking Period 5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House (2) | 2016-03-08 08:00 | 2017-04-18 17:00 | 291d |  |  | 222858 |  |  | 222858 |  | 291d | [5 empty] | 226285 |  | 100% |  | 222858 | 222858
66 | Voorbereiding | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  |  | 15468 |  |  | 15468 |  | 25d | [5 empty] | 15972 |  | 100% |  | 15468 | 15468
1 | Werfinrichting/Werftoiletten | 2016-03-08 08:00 | 2016-03-09 17:00 | 2d |  | 0 | 350 | 0 | 0 | 350 | 2016-03-08 08:00 | 3d | 350 | 0 | 0 | 270 | 0 | 620 | 0 | 100% | Finished | 350 | 350 | 100 | 150 | 100 | 100 | 177.1429 | 100
2 | Voorbereiding oplevering | 2016-03-08 08:00 | 2016-03-08 17:00 | 1d |  | 0 | 187 | 0 | 0 | 187 | 2016-03-08 08:00 | 1d | 187 | 0 | 0 | 0 | 0 | 187 | 0 | 100% | Finished | 187 | 187 | 100 | 100 | 100 | 100 | 100 | 100
3 | Transportkosten | 2016-03-08 08:00 | 2016-03-15 17:00 | 6d |  | 0 | 1725 | 0 | 0 | 1725 | 2016-03-08 08:00 | 6d | 1725 | 0 | 0 | 24 | 0 | 1749 | 0 | 100% | Finished | 1725 | 1725 | 100 | 100 | 100 | 100 | 101.3913 | 100
4 | Magazijn | 2016-03-08 08:00 | 2016-03-14 17:00 | 5d |  | 0 | 1192 | 0 | 0 | 1192 | 2016-03-08 08:00 | 5d | 1192 | 0 | 0 | 57 | 0 | 1249 | 0 | 100% | Finished | 1192 | 1192 | 100 | 100 | 100 | 100 | 104.7819 | 100
5 | Studiekosten projectontwikkelaar | 2016-03-08 08:00 | 2016-03-25 17:00 | 14d |  | 0 | 4128 | 0 | 0 | 4128 | 2016-03-08 08:00 | 15d | 4128 | 0 | 0 | 839 | 0 | 4967 | 0 | 100% | Finished | 4128 | 4128 | 100 | 107.1429 | 100 | 100 | 120.3246 | 100
6 | Studiekosten aannemer | 2016-03-08 08:00 | 2016-04-13 17:00 | 27d |  | 0 | 7886 | 0 | 0 | 7886 | 2016-03-08 08:00 | 25d | 7886 | 0 | 0 | -686 | 0 | 7200 | 0 | 100% | Finished | 7886 | 7886 | 100 | 92.5926 | 100 | 100 | 91.301 | 100
67 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  |  | 8767 |  |  | 8767 |  | 28d | [5 empty] | 9270 |  | 100% |  | 8767 | 8767
7 | Funderingen | 2016-04-14 08:00 | 2016-05-25 17:00 | 30d |  | 0 | 8767 | 0 | 0 | 8767 | 2016-04-12 08:00 | 28d | 8767 | 0 | 0 | 503 | 0 | 9270 | 0 | 100% | Finished | 8767 | 8767 | 100 | 93.3333 | 100 | 100 | 105.7374 | 100
68 | Ruwbouw | 2016-05-26 08:00 | 2016-09-16 17:00 | 82d |  |  | 57970 |  |  | 57970 |  | 81d | [5 empty] | 58045 |  | 100% |  | 57970 | 57970
8 | Gewa/Metselwerk | 2016-05-26 08:00 | 2016-06-24 17:00 | 22d |  | 0 | 18103 | 0 | 0 | 18103 | 2016-05-20 08:00 | 21d | 18103 | 0 | 0 | 96 | 0 | 18199 | 0 | 100% | Finished | 18103 | 18103 | 100 | 95.4545 | 100 | 100 | 100.5303 | 100
9 | Gewelven/Structuur | 2016-06-27 08:00 | 2016-06-30 17:00 | 4d |  | 0 | 7328 | 0 | 0 | 7328 | 2016-06-20 08:00 | 5d | 7328 | 0 | 0 | 31 | 0 | 7359 | 0 | 100% | Finished | 7328 | 7328 | 100 | 125 | 100 | 100 | 100.423 | 100
10 | Uitbranden GEWA | 2016-06-27 08:00 | 2016-06-27 17:00 | 1d |  | 0 | 479 | 0 | 0 | 479 | 2016-06-20 08:00 | 1d | 479 | 0 | 0 | -9 | 0 | 470 | 0 | 100% | Finished | 479 | 479 | 100 | 100 | 100 | 100 | 98.1211 | 100
11 | Isolatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 4451 | 0 | 0 | 4451 | 2016-06-27 08:00 | 5d | 4451 | 0 | 0 | -11 | 0 | 4440 | 0 | 100% | Finished | 4451 | 4451 | 100 | 100 | 100 | 100 | 99.7529 | 100
12 | Parament | 2016-07-08 08:00 | 2016-08-24 17:00 | 34d |  | 0 | 19722 | 0 | 0 | 19722 | 2016-07-04 08:00 | 34d | 19722 | 0 | 0 | 169 | 0 | 19891 | 0 | 100% | Finished | 19722 | 19722 | 100 | 100 | 100 | 100 | 100.8569 | 100
13 | Ytong/Gipswanden | 2016-08-25 08:00 | 2016-08-29 17:00 | 3d |  | 0 | 2447 | 0 | 0 | 2447 | 2016-08-19 08:00 | 3d | 2447 | 0 | 0 | 22 | 0 | 2469 | 0 | 100% | Finished | 2447 | 2447 | 100 | 100 | 100 | 100 | 100.8991 | 100
14 | Dorpels | 2016-08-30 08:00 | 2016-08-31 17:00 | 2d |  | 0 | 1065 | 0 | 0 | 1065 | 2016-08-24 08:00 | 2d | 1065 | 0 | 0 | 5 | 0 | 1070 | 0 | 100% | Finished | 1065 | 1065 | 100 | 100 | 100 | 100 | 100.4695 | 100
15 | Voegwerk | 2016-08-30 08:00 | 2016-09-08 17:00 | 8d |  | 0 | 2246 | 0 | 0 | 2246 | 2016-08-24 08:00 | 8d | 2246 | 0 | 0 | -171 | 0 | 2075 | 0 | 100% | Finished | 2246 | 2246 | 100 | 100 | 100 | 100 | 92.3865 | 100
16 | Stelling | 2016-09-09 08:00 | 2016-09-15 17:00 | 5d |  | 0 | 1836 | 0 | 0 | 1836 | 2016-09-05 08:00 | 4d | 1836 | 0 | 0 | -57 | 0 | 1779 | 0 | 100% | Finished | 1836 | 1836 | 100 | 80 | 100 | 100 | 96.8954 | 100
17 | Karweien | 2016-09-16 08:00 | 2016-09-16 17:00 | 1d |  | 0 | 293 | 0 | 0 | 293 | 2016-09-09 08:00 | 1d | 293 | 0 | 0 | 0 | 0 | 293 | 0 | 100% | Finished | 293 | 293 | 100 | 100 | 100 | 100 | 100 | 100
69 | Dakwerken | 2016-09-19 08:00 | 2016-11-07 17:00 | 36d |  |  | 23852 |  |  | 23852 |  | 30d | [5 empty] | 22976 |  | 100% |  | 23852 | 23852
18 | Daktimmer traditioneel/prefabkap | 2016-09-19 08:00 | 2016-10-14 17:00 | 20d |  | 0 | 11226 | 0 | 0 | 11226 | 2016-09-19 08:00 | 20d | 11226 | 0 | 0 | 0 | 0 | 11226 | 0 | 100% | Finished | 11226 | 11226 | 100 | 100 | 100 | 100 | 100 | 100
19 | Dakdekken | 2016-10-17 08:00 | 2016-10-21 17:00 | 5d |  | 0 | 2752 | 0 | 0 | 2752 | 2016-10-10 08:00 | 4d | 2752 | 0 | 0 | -52 | 0 | 2700 | 0 | 100% | Finished | 2752 | 2752 | 100 | 80 | 100 | 100 | 98.1105 | 100
20 | Goten en afleiders | 2016-10-24 08:00 | 2016-10-25 17:00 | 2d |  | 0 | 321 | 0 | 0 | 321 | 2016-10-14 08:00 | 2d | 321 | 0 | 0 | 0 | 0 | 321 | 0 | 100% | Finished | 321 | 321 | 100 | 100 | 100 | 100 | 100 | 100
21 | Zonnepanelen | 2016-10-24 08:00 | 2016-10-24 17:00 | 1d |  | 0 | 422 | 0 | 0 | 422 | 2016-10-14 08:00 | 1d | 422 | 0 | 0 | -3 | 0 | 419 | 0 | 100% | Finished | 422 | 422 | 100 | 100 | 100 | 100 | 99.2891 | 100
22 | Afdichting/groendaken/plat dak | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 2677 | 0 | 0 | 2677 | 2016-10-18 08:00 | 3d | 2677 | 0 | 0 | -837 | 0 | 1840 | 0 | 100% | Finished | 2677 | 2677 | 100 | 50 | 100 | 100 | 68.7337 | 100
23 | Dakvlakramen | 2016-10-26 08:00 | 2016-11-07 17:00 | 9d |  | 0 | 4783 | 0 | 0 | 4783 | 2016-10-18 08:00 | 9d | 4783 | 0 | 0 | 16 | 0 | 4799 | 0 | 100% | Finished | 4783 | 4783 | 100 | 100 | 100 | 100 | 100.3345 | 100
24 | Karwei dakwerk | 2016-10-26 08:00 | 2016-11-02 17:00 | 6d |  | 0 | 1671 | 0 | 0 | 1671 | 2016-10-18 08:00 | 6d | 1671 | 0 | 0 | 0 | 0 | 1671 | 0 | 100% | Finished | 1671 | 1671 | 100 | 100 | 100 | 100 | 100 | 100
70 | Buitenschrijnwerk | 2016-11-03 08:00 | 2016-11-18 17:00 | 12d |  |  | 4284 |  |  | 4284 |  | 13d | [5 empty] | 4162 |  | 100% |  | 4284 | 4284
25 | Kader buitenschrijnwerk Wachtbuizen | 2016-11-03 08:00 | 2016-11-03 17:00 | 1d |  | 0 | 118 | 0 | 0 | 118 | 2016-10-21 08:00 | 1d | 118 | 0 | 0 | 0 | 0 | 118 | 0 | 100% | Finished | 118 | 118 | 100 | 100 | 100 | 100 | 100 | 100
26 | Buitenschrijnwerk plaatsen | 2016-11-04 08:00 | 2016-11-15 17:00 | 8d |  | 0 | 2256 | 0 | 0 | 2256 | 2016-10-24 08:00 | 8d | 2256 | 0 | 0 | -7 | 0 | 2249 | 0 | 100% | Finished | 2256 | 2256 | 100 | 100 | 100 | 100 | 99.6897 | 100
27 | Elastische voegen | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 50 | 0 | 0 | 50 | 2016-11-04 08:00 | 1d | 50 | 0 | 0 | 5 | 0 | 55 | 0 | 100% | Finished | 50 | 50 | 100 | 100 | 100 | 100 | 110 | 100
28 | Ballustrades/Trapleuningen | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 710 | 0 | 0 | 710 | 2016-11-04 08:00 | 3d | 710 | 0 | 0 | -10 | 0 | 700 | 0 | 100% | Finished | 710 | 710 | 100 | 100 | 100 | 100 | 98.5915 | 100
29 | Poort | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 900 | 0 | 0 | 900 | 2016-11-04 08:00 | 3d | 900 | 0 | 0 | -110 | 0 | 790 | 0 | 100% | Finished | 900 | 900 | 100 | 100 | 100 | 100 | 87.7778 | 100
30 | Karwei binnenschrijnwerk | 2016-11-16 08:00 | 2016-11-16 17:00 | 1d |  | 0 | 250 | 0 | 0 | 250 | 2016-11-04 08:00 | 1d | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 100% | Finished | 250 | 250 | 100 | 100 | 100 | 100 | 100 | 100
71 | Binnenafwerking | 2016-12-19 08:00 | 2017-03-06 17:00 | 56d |  |  | 43144 |  |  | 43144 |  | 61d | [5 empty] | 44937 |  | 100% |  | 43144 | 43144
31 | Plakwerken | 2016-12-19 08:00 | 2016-12-30 17:00 | 10d |  | 0 | 8700 | 0 | 0 | 8700 | 2016-12-14 08:00 | 12d | 8700 | 0 | 0 | 780 | 0 | 9480 | 0 | 100% | Finished | 8700 | 8700 | 100 | 120 | 100 | 100 | 108.9655 | 100
32 | Chapes | 2017-01-02 08:00 | 2017-01-17 17:00 | 12d |  | 0 | 4025 | 0 | 0 | 4025 | 2016-12-30 08:00 | 14d | 4025 | 0 | 0 | 1104 | 0 | 5129 | 0 | 100% | Finished | 4025 | 4025 | 100 | 116.6667 | 100 | 100 | 127.4286 | 100
33 | Vloerisolatie | 2017-01-19 08:00 | 2017-01-20 17:00 | 2d |  | 0 | 2245 | 0 | 0 | 2245 | 2017-01-20 08:00 | 2d | 2245 | 0 | 0 | -244 | 0 | 2001 | 0 | 100% | Finished | 2245 | 2245 | 100 | 100 | 100 | 100 | 89.1314 | 100
34 | Tegelwerken | 2017-01-23 08:00 | 2017-02-20 17:00 | 21d |  | 0 | 8951 | 0 | 0 | 8951 | 2017-01-24 08:00 | 22d | 8951 | 0 | 0 | -219 | 0 | 8732 | 0 | 100% | Finished | 8951 | 8951 | 100 | 104.7619 | 100 | 100 | 97.5533 | 100
35 | Buisbek/Zoldluik/Platen zold/Stijl | 2017-02-21 08:00 | 2017-02-23 17:00 | 3d |  | 0 | 600 | 0 | 0 | 600 | 2017-02-23 08:00 | 3d | 600 | 0 | 0 | 26 | 0 | 626 | 0 | 100% | Finished | 600 | 600 | 100 | 100 | 100 | 100 | 104.3333 | 100
36 | Binnendeuren/uitbekledingen | 2017-02-21 08:00 | 2017-02-27 17:00 | 5d |  | 0 | 1269 | 0 | 0 | 1269 | 2017-02-23 08:00 | 6d | 1269 | 0 | 0 | 308 | 0 | 1577 | 0 | 100% | Finished | 1269 | 1269 | 100 | 120 | 100 | 100 | 124.2711 | 100
37 | Trap | 2017-02-21 08:00 | 2017-03-02 17:00 | 8d |  | 0 | 2312 | 0 | 0 | 2312 | 2017-02-23 08:00 | 8d | 2312 | 0 | 0 | 38 | 0 | 2350 | 0 | 100% | Finished | 2312 | 2312 | 100 | 100 | 100 | 100 | 101.6436 | 100
38 | Luchtdichten | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 549 | 0 | 0 | 549 | 2017-02-23 08:00 | 2d | 549 | 0 | 0 | 0 | 0 | 549 | 0 | 100% | Finished | 549 | 549 | 100 | 100 | 100 | 100 | 100 | 100
39 | Keuken (laminaat, kasten) | 2017-02-21 08:00 | 2017-03-06 17:00 | 10d |  | 0 | 14493 | 0 | 0 | 14493 | 2017-02-23 08:00 | 10d | 14493 | 0 | 0 | 0 | 0 | 14493 | 0 | 100% | Finished | 14493 | 14493 | 100 | 100 | 100 | 100 | 100 | 100
72 | Technieken | 2016-11-16 08:00 | 2017-03-14 17:00 | 85d |  |  | 37540 |  |  | 37540 |  | 93d | [5 empty] | 39090 |  | 100% |  | 37540 | 37540
40 | UZL | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 888 | 0 | 0 | 888 | 2016-11-04 08:00 | 3d | 888 | 0 | 0 | 12 | 0 | 900 | 0 | 100% | Finished | 888 | 888 | 100 | 100 | 100 | 100 | 101.3514 | 100
41 | Betonplexplaten | 2016-11-16 08:00 | 2016-11-18 17:00 | 3d |  | 0 | 625 | 0 | 0 | 625 | 2016-11-04 08:00 | 2d | 625 | 0 | 0 | -330 | 0 | 295 | 0 | 100% | Finished | 625 | 625 | 100 | 66.6667 | 100 | 100 | 47.2 | 100
42 | Slijpen technieken/boringen | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 1300 | 0 | 0 | 1300 | 2016-11-08 08:00 | 5d | 1300 | 0 | 0 | 150 | 0 | 1450 | 0 | 100% | Finished | 1300 | 1300 | 100 | 100 | 100 | 100 | 111.5385 | 100
43 | Bad en douche | 2017-01-18 08:00 | 2017-01-18 17:00 | 1d |  | 0 | 1152 | 0 | 0 | 1152 | 2017-01-19 08:00 | 1d | 1152 | 0 | 0 | -152 | 0 | 1000 | 0 | 100% | Finished | 1152 | 1152 | 100 | 100 | 100 | 100 | 86.8056 | 100
44 | Leidingen ventilatie | 2016-11-28 08:00 | 2016-11-30 17:00 | 3d |  | 0 | 1926 | 0 | 0 | 1926 | 2016-11-15 08:00 | 5d | 1926 | 0 | 0 | 1761 | 0 | 3687 | 0 | 100% | Finished | 1926 | 1926 | 100 | 166.6667 | 100 | 100 | 191.433 | 100
45 | Leidingen san/WP/CV | 2016-12-01 08:00 | 2016-12-06 17:00 | 4d |  | 0 | 2481 | 0 | 0 | 2481 | 2016-11-22 08:00 | 7d | 2481 | 0 | 0 | 934 | 0 | 3415 | 0 | 100% | Finished | 2481 | 2481 | 100 | 175 | 100 | 100 | 137.6461 | 100
46 | Leidingen vloerverwarming | 2016-12-07 08:00 | 2016-12-12 17:00 | 4d |  | 0 | 2557 | 0 | 0 | 2557 | 2016-12-01 08:00 | 5d | 2557 | 0 | 0 | 862 | 0 | 3419 | 0 | 100% | Finished | 2557 | 2557 | 100 | 125 | 100 | 100 | 133.7114 | 100
47 | Afwerken ventilatie | 2017-02-21 08:00 | 2017-02-22 17:00 | 2d |  | 0 | 1899 | 0 | 0 | 1899 | 2017-02-23 08:00 | 2d | 1899 | 0 | 0 | 0 | 0 | 1899 | 0 | 100% | Finished | 1899 | 1899 | 100 | 100 | 100 | 100 | 100 | 100
48 | Afwerken sanitair | 2017-02-23 08:00 | 2017-02-24 17:00 | 2d |  | 0 | 2565 | 0 | 0 | 2565 | 2017-02-27 08:00 | 2d | 2565 | 0 | 0 | 130 | 0 | 2695 | 0 | 100% | Finished | 2565 | 2565 | 100 | 100 | 100 | 100 | 105.0682 | 100
49 | Afwerken CV/WP | 2017-02-27 08:00 | 2017-03-02 17:00 | 4d |  | 0 | 6352 | 0 | 0 | 6352 | 2017-03-01 08:00 | 3d | 6352 | 0 | 0 | -1446 | 0 | 4906 | 0 | 100% | Finished | 6352 | 6352 | 100 | 75 | 100 | 100 | 77.2355 | 100
50 | Leidingen electro | 2016-12-13 08:00 | 2016-12-16 17:00 | 4d |  | 0 | 2594 | 0 | 0 | 2594 | 2016-12-08 08:00 | 4d | 2594 | 0 | 0 | 6 | 0 | 2600 | 0 | 100% | Finished | 2594 | 2594 | 100 | 100 | 100 | 100 | 100.2313 | 100
51 | Afwerken electro | 2017-03-03 08:00 | 2017-03-09 17:00 | 5d |  | 0 | 3608 | 0 | 0 | 3608 | 2017-03-06 08:00 | 4d | 3608 | 0 | 0 | -486 | 0 | 3122 | 0 | 100% | Finished | 3608 | 3608 | 100 | 80 | 100 | 100 | 86.5299 | 100
52 | Verlichting | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 6653 | 0 | 0 | 6653 | 2017-03-10 08:00 | 2d | 6653 | 0 | 0 | -29 | 0 | 6624 | 0 | 100% | Finished | 6653 | 6653 | 100 | 100 | 100 | 100 | 99.5641 | 100
53 | Diepsondering, bron en aansluiting | 2017-03-10 08:00 | 2017-03-14 17:00 | 3d |  | 0 | 2460 | 0 | 0 | 2460 | 2017-03-10 08:00 | 3d | 2460 | 0 | 0 | 138 | 0 | 2598 | 0 | 100% | Finished | 2460 | 2460 | 100 | 100 | 100 | 100 | 105.6098 | 100
54 | Karweien | 2017-03-10 08:00 | 2017-03-13 17:00 | 2d |  | 0 | 480 | 0 | 0 | 480 | 2017-03-10 08:00 | 2d | 480 | 0 | 0 | 0 | 0 | 480 | 0 | 100% | Finished | 480 | 480 | 100 | 100 | 100 | 100 | 100 | 100
73 | Omgevingswerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 15833 |  |  | 15833 |  | 25d | [5 empty] | 15833 |  | 100% |  | 15833 | 15833
55 | Opkuis werf (afvoer puin & afval) | 2017-03-15 08:00 | 2017-03-21 17:00 | 5d |  | 0 | 1400 | 0 | 0 | 1400 | 2017-03-15 08:00 | 5d | 1400 | 0 | 0 | 0 | 0 | 1400 | 0 | 100% | Finished | 1400 | 1400 | 100 | 100 | 100 | 100 | 100 | 100
56 | Grondafvoer | 2017-03-15 08:00 | 2017-03-15 17:00 | 1d |  | 0 | 280 | 0 | 0 | 280 | 2017-03-15 08:00 | 1d | 280 | 0 | 0 | 0 | 0 | 280 | 0 | 100% | Finished | 280 | 280 | 100 | 100 | 100 | 100 | 100 | 100
57 | Opritten en terassen | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 6995 | 0 | 0 | 6995 | 2017-03-22 08:00 | 20d | 6995 | 0 | 0 | 0 | 0 | 6995 | 0 | 100% | Finished | 6995 | 6995 | 100 | 100 | 100 | 100 | 100 | 100
58 | Tuinaanleg | 2017-03-22 08:00 | 2017-04-18 17:00 | 20d |  | 0 | 7158 | 0 | 0 | 7158 | 2017-03-22 08:00 | 20d | 7158 | 0 | 0 | 0 | 0 | 7158 | 0 | 100% | Finished | 7158 | 7158 | 100 | 100 | 100 | 100 | 100 | 100
74 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  |  | 16000 |  |  | 16000 |  | 25d | [5 empty] | 16000 |  | 100% |  | 16000 | 16000
59 | Schilderwerken | 2017-03-15 08:00 | 2017-04-18 17:00 | 25d |  | 0 | 16000 | 0 | 0 | 16000 | 2017-03-15 08:00 | 25d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 100 | 100 | 100 | 100 | 100 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-08 08:00 | 2016-05-20 08:00 | 24235 | 24235 | 25242 | 2016-05-19 17:00 | 0 | 100% | -1007 | 96.01% | 0 | 100% | 100% | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-05-05 09:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-05-02 16:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-05-02 16:00 | 223865 | 232118.0786 | 223865 | 223865 | 232118.0786 | 232118.0786 | 230413.0467 | 230413.0467 | 1 | 0.96011 | 1 | 1 | 0 | 0.96011 | 1 | 1 | 1
Tracking Period 2 | 2016-05-20 08:00 | 2016-09-16 08:00 | 81912 | 82205 | 83287 | 2016-09-16 09:00 | 293 | 100.4% | -1082 | 98.7% | 1h | 100.1% | 100% | 2017-04-18 14:00 | 2017-04-17 17:00 | 2017-04-21 15:00 | 2017-04-18 12:00 | 2017-04-17 17:00 | 2017-04-19 17:00 | 2017-04-18 16:00 | 2017-04-18 15:00 | 2017-04-20 15:00 | 223940 | 225791.3052 | 223438.6761 | 223812.7122 | 225283.3828 | 225662.3421 | 225314.4818 | 225391.1418 | 1.0009 | 0.98701 | 1.0036 | 1 | 0.125 | 0.98701 | 1 | 1.0009 | 1
Tracking Period 3 | 2016-09-16 08:00 | 2016-11-04 08:00 | 106175 | 108431 | 108630 | 2016-11-04 09:00 | 2256 | 102.1% | -199 | 99.82% | 1h | 100.1% | 100% | 2017-04-13 17:00 | 2017-04-10 17:00 | 2017-04-11 12:00 | 2017-04-13 11:00 | 2017-04-10 17:00 | 2017-04-11 09:00 | 2017-04-18 16:00 | 2017-04-18 15:00 | 2017-04-18 17:00 | 223057 | 223267.0043 | 220676.2481 | 222974.3812 | 220881.883 | 223184.2339 | 222739.3125 | 223208.3599 | 1.0007 | 0.99817 | 1.0212 | 1 | 0.125 | 0.99817 | 1 | 1.0007 | 1
Tracking Period 4 | 2016-11-04 08:00 | 2016-12-14 08:00 | 122712 | 122712 | 126191 | 2016-12-13 17:00 | 0 | 100% | -3479 | 97.24% | 0 | 100% | 100% | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-05-01 10:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-21 12:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-21 12:00 | 226337 | 229176.2328 | 226337 | 226337 | 229176.2328 | 229176.2328 | 228595.5797 | 228595.5797 | 1 | 0.97243 | 1 | 1 | 0 | 0.97243 | 1 | 1 | 1
Tracking Period 5 | 2016-12-14 08:00 | 2017-04-18 17:00 | 222858 | 222858 | 226285 | 2017-04-18 17:00 | 0 | 100% | -3427 | 98.49% | 0 | 100% | 100% | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-25 12:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 2017-04-18 17:00 | 226285 | 226285 | 226285 | 226285 | 226285 | 226285 | 226285 | 226285 | 1 | 0.98486 | 1 | 1 | 0 | 0.98486 | 1 | 1 | 1