## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Residential House Finishing Works (1) | 1 |  |  | 2016-03-11 08:00 | 2016-07-14 17:00 | 90d |  |  | 54577.7601 |  |  | 54577.7601 | 125.375
27 | Start uitv afwerking | 1.1 |  |  | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9025.5699 |  |  | 9025.5699 | 41.375
1 | F1 ventilatie | 1.1.1 |  | FS2 | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 6.375
2 | F1 san/cv | 1.1.2 | 1FS | FS3 | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 6.375
3 | F1 elektr | 1.1.3 | 2FS | FS4;FS5 | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 852.14 | 0 | 0 | 852.14 | 6.375
4 | Aansluiting water | 1.1.4 | 3FS |  | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 6.375
5 | Dakisolatie | 1.1.5 | 3FS | FS6 | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 13.375
6 | F1 pleister | 1.1.6 | 5FS | FS7;FS25 | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 6.375
28 | Fase 2 | 1.2 |  |  | 2016-04-22 08:00 | 2016-05-26 17:00 | 25d |  |  | 13051.47 |  |  | 13051.47 | 34.375
7 | Opm keuken | 1.2.1 | 6FS | FS8;FS9 | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 6.375
25 | F2 san/cv | 1.2.2 | 6FS | FS8;FS9 | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 6.375
8 | F2 ventilatie | 1.2.3 | 7FS;25FS |  | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 6.375
9 | Vloerisolatie | 1.2.4 | 7FS;25FS | FS10 | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3108.8701 | 0 | 0 | 3108.8701 | 6.375
10 | Chape | 1.2.5 | 9FS | FS11;FS12 | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1966.48 | 0 | 0 | 1966.48 | 6.375
11 | Opm Binnenschr | 1.2.6 | 10FS |  | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 6.375
12 | F2 elektr | 1.2.7 | 10FS | FS13 | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1278.21 | 0 | 0 | 1278.21 | 6.375
13 | openen E/G/W | 1.2.8 | 12FS | FS14 | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 318.75 | 0 | 0 | 318.75 | 6.375
29 | Fase 3 | 1.3 |  |  | 2016-05-27 08:00 | 2016-06-30 17:00 | 25d |  |  | 13380 |  |  | 13380 | 34.375
14 | F3 san/cv | 1.3.1 | 13FS | FS15 | 2016-05-27 08:00 | 2016-06-02 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 6.375
15 | Vloerwerken | 1.3.2 | 14FS | FS16 | 2016-06-03 08:00 | 2016-06-09 17:00 | 5d |  | 0 | 2072.5801 | 0 | 0 | 2072.5801 | 6.375
16 | Trappen | 1.3.3 | 15FS | FS17 | 2016-06-10 08:00 | 2016-06-16 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 | 6.375
17 | Binnenschrijnwerk | 1.3.4 | 16FS | FS18 | 2016-06-17 08:00 | 2016-06-23 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 6.375
18 | Keuken | 1.3.5 | 17FS | FS19;FS20 | 2016-06-24 08:00 | 2016-06-30 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 6.375
30 | Finale Afwerking | 1.4 |  |  | 2016-07-01 08:00 | 2016-07-14 17:00 | 10d |  |  | 19120.7202 |  |  | 19120.7202 | 13.375
19 | Afw ventilatie | 1.4.1 | 18FS | FS21;FS24;FS26 | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 6.375
20 | Afw elektr | 1.4.2 | 18FS | FS21;FS24 | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 2130.3501 | 0 | 0 | 2130.3501 | 6.375
21 | Afw san/cv | 1.4.3 | 19FS;20FS |  | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 6.375
26 | Afw vloer | 1.4.4 | 19FS |  | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 5181.4502 | 0 | 0 | 5181.4502 | 6.375
24 | Afw pleister | 1.4.5 | 19FS;20FS |  | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 3434.9199 | 0 | 0 | 3434.9199 | 6.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Residential House Finishing Works (1) | 720h |  |  |  |  | 99 | 100 | 101
27 | Start uitv afwerking | 240h |  |  |  |  | 99 | 100 | 101
1 | F1 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
2 | F1 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | F1 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | Aansluiting water | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Dakisolatie | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
6 | F1 pleister | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
28 | Fase 2 | 200h |  |  |  |  | 99 | 100 | 101
7 | Opm keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | F2 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | F2 ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
9 | Vloerisolatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
10 | Chape | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Opm Binnenschr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | F2 elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
13 | openen E/G/W | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
29 | Fase 3 | 200h |  |  |  |  | 99 | 100 | 101
14 | F3 san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Vloerwerken | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
16 | Trappen | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Binnenschrijnwerk | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | Keuken | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Finale Afwerking | 80h |  |  |  |  | 99 | 100 | 101
19 | Afw ventilatie | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
20 | Afw elektr | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | Afw san/cv | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Afw vloer | 40h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
24 | Afw pleister | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120

## Project Control - TP1
| TP Status Date | 2016-04-22 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (1) | 2016-03-11 08:00 | 2016-07-14 17:00 | 90d |  |  | 54577.7601 |  |  | 54577.7601 |  | 30d | [5 empty] | 11810.5699 |  | 16.54% |  | 9025.5699 | 9025.5699
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9025.5699 |  |  | 9025.5699 |  | 30d | [5 empty] | 11810.5699 |  | 100% |  | 9025.5699 | 9025.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 852.14 | 0 | 0 | 852.14 | 2016-03-25 08:00 | 5d | 852.14 | 0 | 0 | 476 | 0 | 1328.14 | 0 | 100% | Finished | 852.14 | 852.14 | 100 | 100 | 100 | 100 | 155.8594 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-01 08:00 | 10d | 2576.1899 | 0 | 0 | 908 | 0 | 3484.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 135.2458 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-15 08:00 | 5d | 2576.1899 | 0 | 0 | 689 | 0 | 3265.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 126.7449 | 100
28 | Fase 2 | 2016-04-22 08:00 | 2016-05-26 17:00 | 25d |  |  | 13051.47 |  |  | 13051.47 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 |  | 0 | 0 | 2231.25 | 5d | 0 | 0 | 0 | 2231.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 |  | 0 | 0 | 1932.83 | 5d | 0 | 0 | 0 | 1932.83 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 |  | 0 | 0 | 1158.75 | 5d | 0 | 0 | 0 | 1158.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3108.8701 | 0 | 0 | 3108.8701 |  | 0 | 0 | 3108.8701 | 5d | 0 | 0 | 0 | 3108.8701 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | Chape | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1966.48 | 0 | 0 | 1966.48 |  | 0 | 0 | 1966.48 | 5d | 0 | 0 | 0 | 1966.48 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | Opm Binnenschr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 |  | 0 | 0 | 1056.33 | 5d | 0 | 0 | 0 | 1056.33 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
12 | F2 elektr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1278.21 | 0 | 0 | 1278.21 |  | 0 | 0 | 1278.21 | 5d | 0 | 0 | 0 | 1278.21 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
13 | openen E/G/W | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 318.75 | 0 | 0 | 318.75 |  | 0 | 0 | 318.75 | 5d | 0 | 0 | 0 | 318.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
29 | Fase 3 | 2016-05-27 08:00 | 2016-06-30 17:00 | 25d |  |  | 13380 |  |  | 13380 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-27 08:00 | 2016-06-02 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-03 08:00 | 2016-06-09 17:00 | 5d |  | 0 | 2072.5801 | 0 | 0 | 2072.5801 |  | 0 | 0 | 2072.5801 | 5d | 0 | 0 | 0 | 2072.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-10 08:00 | 2016-06-16 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 |  | 0 | 0 | 2676.55 | 5d | 0 | 0 | 0 | 2676.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-17 08:00 | 2016-06-23 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 |  | 0 | 0 | 1584.49 | 5d | 0 | 0 | 0 | 1584.49 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-24 08:00 | 2016-06-30 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Finale Afwerking | 2016-07-01 08:00 | 2016-07-14 17:00 | 10d |  |  | 19120.7202 |  |  | 19120.7202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 2130.3501 | 0 | 0 | 2130.3501 |  | 0 | 0 | 2130.3501 | 5d | 0 | 0 | 0 | 2130.3501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 5181.4502 | 0 | 0 | 5181.4502 |  | 0 | 0 | 5181.4502 | 5d | 0 | 0 | 0 | 5181.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 3434.9199 | 0 | 0 | 3434.9199 |  | 0 | 0 | 3434.9199 | 5d | 0 | 0 | 0 | 3434.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-05-27 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (1) | 2016-03-11 08:00 | 2016-07-14 17:00 | 90d |  |  | 54577.7601 |  |  | 54577.7601 |  | 55d | [5 empty] | 27705.0399 |  | 40.45% |  | 22077.0399 | 22077.0399
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9025.5699 |  |  | 9025.5699 |  | 30d | [5 empty] | 11810.5699 |  | 100% |  | 9025.5699 | 9025.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 852.14 | 0 | 0 | 852.14 | 2016-03-25 08:00 | 5d | 852.14 | 0 | 0 | 476 | 0 | 1328.14 | 0 | 100% | Finished | 852.14 | 852.14 | 100 | 100 | 100 | 100 | 155.8594 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-01 08:00 | 10d | 2576.1899 | 0 | 0 | 908 | 0 | 3484.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 135.2458 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-15 08:00 | 5d | 2576.1899 | 0 | 0 | 689 | 0 | 3265.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 126.7449 | 100
28 | Fase 2 | 2016-04-22 08:00 | 2016-05-26 17:00 | 25d |  |  | 13051.47 |  |  | 13051.47 |  | 25d | [5 empty] | 15894.47 |  | 100% |  | 13051.47 | 13051.47
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 126.084 | 100
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 110.0371 | 100
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3108.8701 | 0 | 0 | 3108.8701 | 2016-04-29 08:00 | 5d | 3108.8701 | 0 | 0 | 367 | 0 | 3475.8701 | 0 | 100% | Finished | 3108.8701 | 3108.8701 | 100 | 100 | 100 | 100 | 111.8049 | 100
10 | Chape | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1966.48 | 0 | 0 | 1966.48 | 2016-05-06 08:00 | 5d | 1966.48 | 0 | 0 | 496 | 0 | 2462.48 | 0 | 100% | Finished | 1966.48 | 1966.48 | 100 | 100 | 100 | 100 | 125.2227 | 100
11 | Opm Binnenschr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-13 08:00 | 5d | 1056.33 | 0 | 0 | 322 | 0 | 1378.33 | 0 | 100% | Finished | 1056.33 | 1056.33 | 100 | 100 | 100 | 100 | 130.4829 | 100
12 | F2 elektr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1278.21 | 0 | 0 | 1278.21 | 2016-05-13 08:00 | 5d | 1278.21 | 0 | 0 | 714 | 0 | 1992.21 | 0 | 100% | Finished | 1278.21 | 1278.21 | 100 | 100 | 100 | 100 | 155.8594 | 100
13 | openen E/G/W | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-20 08:00 | 5d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 163.0588 | 100
29 | Fase 3 | 2016-05-27 08:00 | 2016-06-30 17:00 | 25d |  |  | 13380 |  |  | 13380 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
14 | F3 san/cv | 2016-05-27 08:00 | 2016-06-02 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 |  | 0 | 0 | 3221.3799 | 5d | 0 | 0 | 0 | 3221.3799 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
15 | Vloerwerken | 2016-06-03 08:00 | 2016-06-09 17:00 | 5d |  | 0 | 2072.5801 | 0 | 0 | 2072.5801 |  | 0 | 0 | 2072.5801 | 5d | 0 | 0 | 0 | 2072.5801 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
16 | Trappen | 2016-06-10 08:00 | 2016-06-16 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 |  | 0 | 0 | 2676.55 | 5d | 0 | 0 | 0 | 2676.55 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
17 | Binnenschrijnwerk | 2016-06-17 08:00 | 2016-06-23 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 |  | 0 | 0 | 1584.49 | 5d | 0 | 0 | 0 | 1584.49 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
18 | Keuken | 2016-06-24 08:00 | 2016-06-30 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 |  | 0 | 0 | 3825 | 5d | 0 | 0 | 0 | 3825 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
30 | Finale Afwerking | 2016-07-01 08:00 | 2016-07-14 17:00 | 10d |  |  | 19120.7202 |  |  | 19120.7202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 2130.3501 | 0 | 0 | 2130.3501 |  | 0 | 0 | 2130.3501 | 5d | 0 | 0 | 0 | 2130.3501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 5181.4502 | 0 | 0 | 5181.4502 |  | 0 | 0 | 5181.4502 | 5d | 0 | 0 | 0 | 5181.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 3434.9199 | 0 | 0 | 3434.9199 |  | 0 | 0 | 3434.9199 | 5d | 0 | 0 | 0 | 3434.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-01 08:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (1) | 2016-03-11 08:00 | 2016-07-14 17:00 | 90d |  |  | 54577.7601 |  |  | 54577.7601 |  | 80d | [5 empty] | 43422.0399 |  | 64.97% |  | 35457.0399 | 35457.0399
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9025.5699 |  |  | 9025.5699 |  | 30d | [5 empty] | 11810.5699 |  | 100% |  | 9025.5699 | 9025.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 852.14 | 0 | 0 | 852.14 | 2016-03-25 08:00 | 5d | 852.14 | 0 | 0 | 476 | 0 | 1328.14 | 0 | 100% | Finished | 852.14 | 852.14 | 100 | 100 | 100 | 100 | 155.8594 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-01 08:00 | 10d | 2576.1899 | 0 | 0 | 908 | 0 | 3484.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 135.2458 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-15 08:00 | 5d | 2576.1899 | 0 | 0 | 689 | 0 | 3265.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 126.7449 | 100
28 | Fase 2 | 2016-04-22 08:00 | 2016-05-26 17:00 | 25d |  |  | 13051.47 |  |  | 13051.47 |  | 25d | [5 empty] | 15894.47 |  | 100% |  | 13051.47 | 13051.47
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 126.084 | 100
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 110.0371 | 100
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3108.8701 | 0 | 0 | 3108.8701 | 2016-04-29 08:00 | 5d | 3108.8701 | 0 | 0 | 367 | 0 | 3475.8701 | 0 | 100% | Finished | 3108.8701 | 3108.8701 | 100 | 100 | 100 | 100 | 111.8049 | 100
10 | Chape | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1966.48 | 0 | 0 | 1966.48 | 2016-05-06 08:00 | 5d | 1966.48 | 0 | 0 | 496 | 0 | 2462.48 | 0 | 100% | Finished | 1966.48 | 1966.48 | 100 | 100 | 100 | 100 | 125.2227 | 100
11 | Opm Binnenschr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-13 08:00 | 5d | 1056.33 | 0 | 0 | 322 | 0 | 1378.33 | 0 | 100% | Finished | 1056.33 | 1056.33 | 100 | 100 | 100 | 100 | 130.4829 | 100
12 | F2 elektr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1278.21 | 0 | 0 | 1278.21 | 2016-05-13 08:00 | 5d | 1278.21 | 0 | 0 | 714 | 0 | 1992.21 | 0 | 100% | Finished | 1278.21 | 1278.21 | 100 | 100 | 100 | 100 | 155.8594 | 100
13 | openen E/G/W | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-20 08:00 | 5d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 163.0588 | 100
29 | Fase 3 | 2016-05-27 08:00 | 2016-06-30 17:00 | 25d |  |  | 13380 |  |  | 13380 |  | 25d | [5 empty] | 15717 |  | 100% |  | 13380 | 13380
14 | F3 san/cv | 2016-05-27 08:00 | 2016-06-02 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-27 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 110.0268 | 100
15 | Vloerwerken | 2016-06-03 08:00 | 2016-06-09 17:00 | 5d |  | 0 | 2072.5801 | 0 | 0 | 2072.5801 | 2016-06-03 08:00 | 5d | 2072.5801 | 0 | 0 | -286 | 0 | 1786.5801 | 0 | 100% | Finished | 2072.5801 | 2072.5801 | 100 | 100 | 100 | 100 | 86.2008 | 100
16 | Trappen | 2016-06-10 08:00 | 2016-06-16 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 | 2016-06-10 08:00 | 5d | 2676.55 | 0 | 0 | 817 | 0 | 3493.55 | 0 | 100% | Finished | 2676.55 | 2676.55 | 100 | 100 | 100 | 100 | 130.5244 | 100
17 | Binnenschrijnwerk | 2016-06-17 08:00 | 2016-06-23 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-17 08:00 | 5d | 1584.49 | 0 | 0 | 484 | 0 | 2068.49 | 0 | 100% | Finished | 1584.49 | 1584.49 | 100 | 100 | 100 | 100 | 130.5461 | 100
18 | Keuken | 2016-06-24 08:00 | 2016-06-30 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-24 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 126.1176 | 100
30 | Finale Afwerking | 2016-07-01 08:00 | 2016-07-14 17:00 | 10d |  |  | 19120.7202 |  |  | 19120.7202 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | Afw ventilatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 |  | 0 | 0 | 1931.25 | 5d | 0 | 0 | 0 | 1931.25 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | Afw elektr | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 2130.3501 | 0 | 0 | 2130.3501 |  | 0 | 0 | 2130.3501 | 5d | 0 | 0 | 0 | 2130.3501 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | Afw san/cv | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 |  | 0 | 0 | 6442.75 | 5d | 0 | 0 | 0 | 6442.75 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
26 | Afw vloer | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 5181.4502 | 0 | 0 | 5181.4502 |  | 0 | 0 | 5181.4502 | 5d | 0 | 0 | 0 | 5181.4502 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
24 | Afw pleister | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 3434.9199 | 0 | 0 | 3434.9199 |  | 0 | 0 | 3434.9199 | 5d | 0 | 0 | 0 | 3434.9199 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP4
| TP Status Date | 2016-07-14 17:00 |  | TP Name | Tracking Period 4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Residential House Finishing Works (1) | 2016-03-11 08:00 | 2016-07-14 17:00 | 90d |  |  | 54577.7601 |  |  | 54577.7601 |  | 90d | [5 empty] | 64526.7601 |  | 100% |  | 54577.7601 | 54577.7601
27 | Start uitv afwerking | 2016-03-11 08:00 | 2016-04-21 17:00 | 30d |  |  | 9025.5699 |  |  | 9025.5699 |  | 30d | [5 empty] | 11810.5699 |  | 100% |  | 9025.5699 | 9025.5699
1 | F1 ventilatie | 2016-03-11 08:00 | 2016-03-17 17:00 | 5d |  | 0 | 772.5 | 0 | 0 | 772.5 | 2016-03-11 08:00 | 5d | 772.5 | 0 | 0 | -22 | 0 | 750.5 | 0 | 100% | Finished | 772.5 | 772.5 | 100 | 100 | 100 | 100 | 97.1521 | 100
2 | F1 san/cv | 2016-03-18 08:00 | 2016-03-24 17:00 | 5d |  | 0 | 1288.55 | 0 | 0 | 1288.55 | 2016-03-18 08:00 | 5d | 1288.55 | 0 | 0 | 129 | 0 | 1417.55 | 0 | 100% | Finished | 1288.55 | 1288.55 | 100 | 100 | 100 | 100 | 110.0113 | 100
3 | F1 elektr | 2016-03-25 08:00 | 2016-03-31 17:00 | 5d |  | 0 | 852.14 | 0 | 0 | 852.14 | 2016-03-25 08:00 | 5d | 852.14 | 0 | 0 | 476 | 0 | 1328.14 | 0 | 100% | Finished | 852.14 | 852.14 | 100 | 100 | 100 | 100 | 155.8594 | 100
4 | Aansluiting water | 2016-04-01 08:00 | 2016-04-07 17:00 | 5d |  | 0 | 960 | 0 | 0 | 960 | 2016-04-01 08:00 | 5d | 960 | 0 | 0 | 605 | 0 | 1565 | 0 | 100% | Finished | 960 | 960 | 100 | 100 | 100 | 100 | 163.0208 | 100
5 | Dakisolatie | 2016-04-01 08:00 | 2016-04-14 17:00 | 10d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-01 08:00 | 10d | 2576.1899 | 0 | 0 | 908 | 0 | 3484.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 135.2458 | 100
6 | F1 pleister | 2016-04-15 08:00 | 2016-04-21 17:00 | 5d |  | 0 | 2576.1899 | 0 | 0 | 2576.1899 | 2016-04-15 08:00 | 5d | 2576.1899 | 0 | 0 | 689 | 0 | 3265.1899 | 0 | 100% | Finished | 2576.1899 | 2576.1899 | 100 | 100 | 100 | 100 | 126.7449 | 100
28 | Fase 2 | 2016-04-22 08:00 | 2016-05-26 17:00 | 25d |  |  | 13051.47 |  |  | 13051.47 |  | 25d | [5 empty] | 15894.47 |  | 100% |  | 13051.47 | 13051.47
7 | Opm keuken | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 2231.25 | 0 | 0 | 2231.25 | 2016-04-22 08:00 | 5d | 2231.25 | 0 | 0 | 582 | 0 | 2813.25 | 0 | 100% | Finished | 2231.25 | 2231.25 | 100 | 100 | 100 | 100 | 126.084 | 100
25 | F2 san/cv | 2016-04-22 08:00 | 2016-04-28 17:00 | 5d |  | 0 | 1932.83 | 0 | 0 | 1932.83 | 2016-04-22 08:00 | 5d | 1932.83 | 0 | 0 | 194 | 0 | 2126.83 | 0 | 100% | Finished | 1932.83 | 1932.83 | 100 | 100 | 100 | 100 | 110.0371 | 100
8 | F2 ventilatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 1158.75 | 0 | 0 | 1158.75 | 2016-04-29 08:00 | 5d | 1158.75 | 0 | 0 | -33 | 0 | 1125.75 | 0 | 100% | Finished | 1158.75 | 1158.75 | 100 | 100 | 100 | 100 | 97.1521 | 100
9 | Vloerisolatie | 2016-04-29 08:00 | 2016-05-05 17:00 | 5d |  | 0 | 3108.8701 | 0 | 0 | 3108.8701 | 2016-04-29 08:00 | 5d | 3108.8701 | 0 | 0 | 367 | 0 | 3475.8701 | 0 | 100% | Finished | 3108.8701 | 3108.8701 | 100 | 100 | 100 | 100 | 111.8049 | 100
10 | Chape | 2016-05-06 08:00 | 2016-05-12 17:00 | 5d |  | 0 | 1966.48 | 0 | 0 | 1966.48 | 2016-05-06 08:00 | 5d | 1966.48 | 0 | 0 | 496 | 0 | 2462.48 | 0 | 100% | Finished | 1966.48 | 1966.48 | 100 | 100 | 100 | 100 | 125.2227 | 100
11 | Opm Binnenschr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1056.33 | 0 | 0 | 1056.33 | 2016-05-13 08:00 | 5d | 1056.33 | 0 | 0 | 322 | 0 | 1378.33 | 0 | 100% | Finished | 1056.33 | 1056.33 | 100 | 100 | 100 | 100 | 130.4829 | 100
12 | F2 elektr | 2016-05-13 08:00 | 2016-05-19 17:00 | 5d |  | 0 | 1278.21 | 0 | 0 | 1278.21 | 2016-05-13 08:00 | 5d | 1278.21 | 0 | 0 | 714 | 0 | 1992.21 | 0 | 100% | Finished | 1278.21 | 1278.21 | 100 | 100 | 100 | 100 | 155.8594 | 100
13 | openen E/G/W | 2016-05-20 08:00 | 2016-05-26 17:00 | 5d |  | 0 | 318.75 | 0 | 0 | 318.75 | 2016-05-20 08:00 | 5d | 318.75 | 0 | 0 | 201 | 0 | 519.75 | 0 | 100% | Finished | 318.75 | 318.75 | 100 | 100 | 100 | 100 | 163.0588 | 100
29 | Fase 3 | 2016-05-27 08:00 | 2016-06-30 17:00 | 25d |  |  | 13380 |  |  | 13380 |  | 25d | [5 empty] | 15717 |  | 100% |  | 13380 | 13380
14 | F3 san/cv | 2016-05-27 08:00 | 2016-06-02 17:00 | 5d |  | 0 | 3221.3799 | 0 | 0 | 3221.3799 | 2016-05-27 08:00 | 5d | 3221.3799 | 0 | 0 | 323 | 0 | 3544.3799 | 0 | 100% | Finished | 3221.3799 | 3221.3799 | 100 | 100 | 100 | 100 | 110.0268 | 100
15 | Vloerwerken | 2016-06-03 08:00 | 2016-06-09 17:00 | 5d |  | 0 | 2072.5801 | 0 | 0 | 2072.5801 | 2016-06-03 08:00 | 5d | 2072.5801 | 0 | 0 | -286 | 0 | 1786.5801 | 0 | 100% | Finished | 2072.5801 | 2072.5801 | 100 | 100 | 100 | 100 | 86.2008 | 100
16 | Trappen | 2016-06-10 08:00 | 2016-06-16 17:00 | 5d |  | 0 | 2676.55 | 0 | 0 | 2676.55 | 2016-06-10 08:00 | 5d | 2676.55 | 0 | 0 | 817 | 0 | 3493.55 | 0 | 100% | Finished | 2676.55 | 2676.55 | 100 | 100 | 100 | 100 | 130.5244 | 100
17 | Binnenschrijnwerk | 2016-06-17 08:00 | 2016-06-23 17:00 | 5d |  | 0 | 1584.49 | 0 | 0 | 1584.49 | 2016-06-17 08:00 | 5d | 1584.49 | 0 | 0 | 484 | 0 | 2068.49 | 0 | 100% | Finished | 1584.49 | 1584.49 | 100 | 100 | 100 | 100 | 130.5461 | 100
18 | Keuken | 2016-06-24 08:00 | 2016-06-30 17:00 | 5d |  | 0 | 3825 | 0 | 0 | 3825 | 2016-06-24 08:00 | 5d | 3825 | 0 | 0 | 999 | 0 | 4824 | 0 | 100% | Finished | 3825 | 3825 | 100 | 100 | 100 | 100 | 126.1176 | 100
30 | Finale Afwerking | 2016-07-01 08:00 | 2016-07-14 17:00 | 10d |  |  | 19120.7202 |  |  | 19120.7202 |  | 10d | [5 empty] | 21104.7202 |  | 100% |  | 19120.7202 | 19120.7202
19 | Afw ventilatie | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 1931.25 | 0 | 0 | 1931.25 | 2016-07-01 08:00 | 5d | 1931.25 | 0 | 0 | -56 | 0 | 1875.25 | 0 | 100% | Finished | 1931.25 | 1931.25 | 100 | 100 | 100 | 100 | 97.1003 | 100
20 | Afw elektr | 2016-07-01 08:00 | 2016-07-07 17:00 | 5d |  | 0 | 2130.3501 | 0 | 0 | 2130.3501 | 2016-07-01 08:00 | 5d | 2130.3501 | 0 | 0 | 1190 | 0 | 3320.3501 | 0 | 100% | Finished | 2130.3501 | 2130.3501 | 100 | 100 | 100 | 100 | 155.8594 | 100
21 | Afw san/cv | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 6442.75 | 0 | 0 | 6442.75 | 2016-07-08 08:00 | 5d | 6442.75 | 0 | 0 | 647 | 0 | 7089.75 | 0 | 100% | Finished | 6442.75 | 6442.75 | 100 | 100 | 100 | 100 | 110.0423 | 100
26 | Afw vloer | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 5181.4502 | 0 | 0 | 5181.4502 | 2016-07-08 08:00 | 5d | 5181.4502 | 0 | 0 | -716 | 0 | 4465.4502 | 0 | 100% | Finished | 5181.4502 | 5181.4502 | 100 | 100 | 100 | 100 | 86.1815 | 100
24 | Afw pleister | 2016-07-08 08:00 | 2016-07-14 17:00 | 5d |  | 0 | 3434.9199 | 0 | 0 | 3434.9199 | 2016-07-08 08:00 | 5d | 3434.9199 | 0 | 0 | 919 | 0 | 4353.9199 | 0 | 100% | Finished | 3434.9199 | 3434.9199 | 100 | 100 | 100 | 100 | 126.7546 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-11 08:00 | 2016-04-22 08:00 | 9025.5699 | 9025.5699 | 11810.5699 | 2016-04-21 17:00 | 0 | 100% | -2785 | 76.42% | 0 | 100% | 100% | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-08-23 15:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-08-10 12:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-08-10 12:00 | 57362.7601 | 71418.6979 | 57362.7601 | 57362.7601 | 71418.6979 | 71418.6979 | 67953.8939 | 67953.8939 | 1 | 0.76419 | 1 | 1 | 0 | 0.76419 | 1 | 1 | 1
Tracking Period 2 | 2016-04-22 08:00 | 2016-05-27 08:00 | 22077.0399 | 22077.0399 | 27705.0399 | 2016-05-26 17:00 | 0 | 100% | -5628 | 79.69% | 0 | 100% | 100% | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-08-16 17:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-27 16:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-27 16:00 | 60205.7601 | 68491.0218 | 60205.7601 | 60205.7601 | 68491.0218 | 68491.0218 | 66512.4237 | 66512.4237 | 1 | 0.79686 | 1 | 1 | 0 | 0.79686 | 1 | 1 | 1
Tracking Period 3 | 2016-05-27 08:00 | 2016-07-01 08:00 | 35457.0399 | 35457.0399 | 43422.0399 | 2016-06-30 17:00 | 0 | 100% | -7965 | 81.66% | 0 | 100% | 100% | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-08-12 10:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-19 10:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-19 10:00 | 62542.7601 | 66838.0013 | 62542.7601 | 62542.7601 | 66838.0013 | 66838.0013 | 65831.2108 | 65831.2108 | 1 | 0.81657 | 1 | 1 | 0 | 0.81657 | 1 | 1 | 1
Tracking Period 4 | 2016-07-01 08:00 | 2016-07-14 17:00 | 54577.7601 | 54577.7601 | 64526.7601 | 2016-07-14 17:00 | 0 | 100% | -9949 | 84.58% | 0 | 100% | 100% | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-08-08 11:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 2016-07-14 17:00 | 64526.7601 | 64526.7601 | 64526.7601 | 64526.7601 | 64526.7601 | 64526.7601 | 64526.7601 | 64526.7601 | 1 | 0.84582 | 1 | 1 | 0 | 0.84582 | 1 | 1 | 1