## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Apartment Building Finishing Works (4) | 1 |  |  | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 362476 |  |  | 362476 | 114.375
24 | nivo +2 blok B | 1.1 |  |  | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 177539 |  |  | 177539 | 114.375
1 | pleisterwerken wanden 2B | 1.1.1 |  | SS2 | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 18.375
2 | pleisterwerken plafonds 2B | 1.1.2 | 1SS | FS3-1w;FS12 | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 11.375
3 | lichte scheidingswanden 2B | 1.1.3 | 2FS-1w | FS4 | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 11.375
4 | vloer uitvullingen 2B | 1.1.4 | 3FS | FS5 | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2.375
5 | chape 2B | 1.1.5 | 4FS | FS6+2w;FS8+6w | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 6.375
6 | plaatsen keramische tegels 2B | 1.1.6 | 5FS+2w | FS7-1w | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 13.375
7 | plaatsen faience 2B | 1.1.7 | 6FS-1w |  | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 13.375
8 | zachte vloerbekleding 2B | 1.1.8 | 5FS+6w | FS9;FS10;FS11 | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 13.375
9 | binnenschrijnwerk 2B | 1.1.9 | 8FS |  | 2016-06-16 08:00 | 2016-06-27 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 | 11.375
10 | schilderwerken wanden en plafonds 2B | 1.1.10 | 8FS |  | 2016-06-16 08:00 | 2016-07-13 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 | 27.375
11 | binnenmeubilair 2B | 1.1.11 | 8FS |  | 2016-06-16 08:00 | 2016-06-29 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 | 13.375
25 | nivo +3 blok B | 1.2 |  |  | 2016-04-04 08:00 | 2016-07-04 17:00 | 66d |  |  | 184937 |  |  | 184937 | 91.375
12 | pleisterwerken wanden 3B | 1.2.1 | 2FS | SS13 | 2016-04-04 08:00 | 2016-04-15 17:00 | 10d |  | 0 | 14596 | 0 | 0 | 14596 | 11.375
13 | pleisterwerken plafonds 3B | 1.2.2 | 12SS | FS14-1w | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 18767 | 0 | 0 | 18767 | 4.375
14 | lichte scheidingswanden 3B | 1.2.3 | 13FS-1w | FS15 | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 4796 | 0 | 0 | 4796 | 4.375
15 | vloer uitvullingen 3B | 1.2.4 | 14FS | FS16 | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3127 | 0 | 0 | 3127 | 2.375
16 | chape 3B | 1.2.5 | 15FS | FS17+2w;FS19+6w | 2016-04-14 08:00 | 2016-04-18 17:00 | 3d |  | 0 | 27108 | 0 | 0 | 27108 | 4.375
17 | plaatsen keramische tegels 3B | 1.2.6 | 16FS+2w | FS18-1w | 2016-05-03 08:00 | 2016-05-12 17:00 | 8d |  | 0 | 11364 | 0 | 0 | 11364 | 9.375
18 | plaatsen faience 3B | 1.2.7 | 17FS-1w |  | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 10426 | 0 | 0 | 10426 | 11.375
19 | zachte vloerbekleding 3B | 1.2.8 | 16FS+6w | FS20;FS21;FS22 | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 8340 | 0 | 0 | 8340 | 6.375
20 | binnenschrijnwerk 3B | 1.2.9 | 19FS |  | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 29193 | 0 | 0 | 29193 | 9.375
21 | schilderwerken wanden en plafonds 3B | 1.2.10 | 19FS | FS23 | 2016-06-07 08:00 | 2016-06-27 17:00 | 15d |  | 0 | 25022 | 0 | 0 | 25022 | 20.375
22 | binnenmeubilair 3B | 1.2.11 | 19FS |  | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 31278 | 0 | 0 | 31278 | 9.375
23 | opkuis voor oplevering blok B | 1.2.12 | 21FS |  | 2016-06-28 08:00 | 2016-07-04 17:00 | 5d |  | 0 | 920 | 0 | 0 | 920 | 6.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Apartment Building Finishing Works (4) | 664h |  |  |  |  | 99 | 100 | 101
24 | nivo +2 blok B | 664h |  |  |  |  | 99 | 100 | 101
1 | pleisterwerken wanden 2B | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | pleisterwerken plafonds 2B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | lichte scheidingswanden 2B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | vloer uitvullingen 2B | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | chape 2B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | plaatsen keramische tegels 2B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | plaatsen faience 2B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | zachte vloerbekleding 2B | 80h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | binnenschrijnwerk 2B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | schilderwerken wanden en plafonds 2B | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
11 | binnenmeubilair 2B | 80h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
25 | nivo +3 blok B | 528h |  |  |  |  | 99 | 100 | 101
12 | pleisterwerken wanden 3B | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | pleisterwerken plafonds 3B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | lichte scheidingswanden 3B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | vloer uitvullingen 3B | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
16 | chape 3B | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | plaatsen keramische tegels 3B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | plaatsen faience 3B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | zachte vloerbekleding 3B | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
20 | binnenschrijnwerk 3B | 64h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | schilderwerken wanden en plafonds 3B | 120h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | binnenmeubilair 3B | 64h | standard - skewed right | 80 | 90 | 120 | 80 | 90 | 120
23 | opkuis voor oplevering blok B | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2016-05-11 08:00 |  | TP Name | Tracking Period 1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (4) | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 362476 |  |  | 362476 |  | 37d | [5 empty] | 150373 |  | 37.07% |  | 134379 | 167133
24 | nivo +2 blok B | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 37d | [5 empty] | 72428 |  | 37.17% |  | 65985 | 76949
1 | pleisterwerken wanden 2B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-03-21 08:00 | 17d | 14082 | 0 | 0 | 475 | 0 | 14557 | 0 | 100% | Finished | 14082 | 14082 | 100 | 113.3333 | 100 | 100 | 103.3731 | 100
2 | pleisterwerken plafonds 2B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-03-21 08:00 | 12d | 18106 | 0 | 0 | 2859 | 0 | 20965 | 0 | 100% | Finished | 18106 | 18106 | 100 | 120 | 100 | 100 | 115.7903 | 100
3 | lichte scheidingswanden 2B | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-03-30 08:00 | 10d | 4627 | 0 | 0 | 222 | 0 | 4849 | 0 | 100% | Finished | 4627 | 4627 | 100 | 100 | 100 | 100 | 104.7979 | 100
4 | vloer uitvullingen 2B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-04-13 08:00 | 5d | 3017 | 0 | 0 | 454 | 0 | 3471 | 0 | 100% | Finished | 3017 | 3017 | 100 | 166.6667 | 100 | 100 | 115.0481 | 100
5 | chape 2B | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-04-20 08:00 | 5d | 26153 | 0 | 0 | 2433 | 0 | 28586 | 0 | 100% | Finished | 26153 | 26153 | 100 | 100 | 100 | 100 | 109.3029 | 100
6 | plaatsen keramische tegels 2B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 |  | 0 | 0 | 10964 | 10d | 0 | 0 | 0 | 10964 | 0% | Not Started | 0 | 10964 | 100 |  | 0 | 100 |  | 0
7 | plaatsen faience 2B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 |  | 0 | 0 | 10059 | 10d | 0 | 0 | 0 | 10059 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
8 | zachte vloerbekleding 2B | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 |  | 0 | 0 | 8047 | 10d | 0 | 0 | 0 | 8047 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
9 | binnenschrijnwerk 2B | 2016-06-16 08:00 | 2016-06-27 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 |  | 0 | 0 | 28165 | 8d | 0 | 0 | 0 | 28165 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | schilderwerken wanden en plafonds 2B | 2016-06-16 08:00 | 2016-07-13 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 |  | 0 | 0 | 24142 | 20d | 0 | 0 | 0 | 24142 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | binnenmeubilair 2B | 2016-06-16 08:00 | 2016-06-29 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 |  | 0 | 0 | 30177 | 10d | 0 | 0 | 0 | 30177 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | nivo +3 blok B | 2016-04-04 08:00 | 2016-07-04 17:00 | 66d |  |  | 184937 |  |  | 184937 |  | 25d | [5 empty] | 77945 |  | 36.98% |  | 68394 | 90184
12 | pleisterwerken wanden 3B | 2016-04-04 08:00 | 2016-04-15 17:00 | 10d |  | 0 | 14596 | 0 | 0 | 14596 | 2016-04-06 08:00 | 10d | 14596 | 0 | 0 | 817 | 0 | 15413 | 0 | 100% | Finished | 14596 | 14596 | 100 | 100 | 100 | 100 | 105.5974 | 100
13 | pleisterwerken plafonds 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 18767 | 0 | 0 | 18767 | 2016-04-06 08:00 | 5d | 18767 | 0 | 0 | 457 | 0 | 19224 | 0 | 100% | Finished | 18767 | 18767 | 100 | 100 | 100 | 100 | 102.4351 | 100
14 | lichte scheidingswanden 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 4796 | 0 | 0 | 4796 | 2016-04-06 08:00 | 5d | 4796 | 0 | 0 | -455 | 0 | 4341 | 0 | 100% | Finished | 4796 | 4796 | 100 | 100 | 100 | 100 | 90.5129 | 100
15 | vloer uitvullingen 3B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3127 | 0 | 0 | 3127 | 2016-04-13 08:00 | 5d | 3127 | 0 | 0 | 484 | 0 | 3611 | 0 | 100% | Finished | 3127 | 3127 | 100 | 166.6667 | 100 | 100 | 115.4781 | 100
16 | chape 3B | 2016-04-14 08:00 | 2016-04-18 17:00 | 3d |  | 0 | 27108 | 0 | 0 | 27108 | 2016-04-20 08:00 | 5d | 27108 | 0 | 0 | 8248 | 0 | 35356 | 0 | 100% | Finished | 27108 | 27108 | 100 | 166.6667 | 100 | 100 | 130.4264 | 100
17 | plaatsen keramische tegels 3B | 2016-05-03 08:00 | 2016-05-12 17:00 | 8d |  | 0 | 11364 | 0 | 0 | 11364 |  | 0 | 0 | 11364 | 8d | 0 | 0 | 0 | 11364 | 0% | Not Started | 0 | 11364 | 100 |  | 0 | 100 |  | 0
18 | plaatsen faience 3B | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 10426 | 0 | 0 | 10426 |  | 0 | 0 | 10426 | 8d | 0 | 0 | 0 | 10426 | 0% | Not Started | 0 | 10426 | 100 |  | 0 | 100 |  | 0
19 | zachte vloerbekleding 3B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 8340 | 0 | 0 | 8340 |  | 0 | 0 | 8340 | 5d | 0 | 0 | 0 | 8340 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
20 | binnenschrijnwerk 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 29193 | 0 | 0 | 29193 |  | 0 | 0 | 29193 | 8d | 0 | 0 | 0 | 29193 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
21 | schilderwerken wanden en plafonds 3B | 2016-06-07 08:00 | 2016-06-27 17:00 | 15d |  | 0 | 25022 | 0 | 0 | 25022 |  | 0 | 0 | 25022 | 15d | 0 | 0 | 0 | 25022 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
22 | binnenmeubilair 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 31278 | 0 | 0 | 31278 |  | 0 | 0 | 31278 | 8d | 0 | 0 | 0 | 31278 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
23 | opkuis voor oplevering blok B | 2016-06-28 08:00 | 2016-07-04 17:00 | 5d |  | 0 | 920 | 0 | 0 | 920 |  | 0 | 0 | 920 | 5d | 0 | 0 | 0 | 920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP2
| TP Status Date | 2016-06-08 08:00 |  | TP Name | Tracking Period 2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (4) | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 362476 |  |  | 362476 |  | 57d | [5 empty] | 195767 |  | 48.88% |  | 177192 | 279072
24 | nivo +2 blok B | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 57d | [5 empty] | 94313 |  | 49.01% |  | 87008 | 95055
1 | pleisterwerken wanden 2B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-03-21 08:00 | 17d | 14082 | 0 | 0 | 475 | 0 | 14557 | 0 | 100% | Finished | 14082 | 14082 | 100 | 113.3333 | 100 | 100 | 103.3731 | 100
2 | pleisterwerken plafonds 2B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-03-21 08:00 | 12d | 18106 | 0 | 0 | 2859 | 0 | 20965 | 0 | 100% | Finished | 18106 | 18106 | 100 | 120 | 100 | 100 | 115.7903 | 100
3 | lichte scheidingswanden 2B | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-03-30 08:00 | 10d | 4627 | 0 | 0 | 222 | 0 | 4849 | 0 | 100% | Finished | 4627 | 4627 | 100 | 100 | 100 | 100 | 104.7979 | 100
4 | vloer uitvullingen 2B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-04-13 08:00 | 5d | 3017 | 0 | 0 | 454 | 0 | 3471 | 0 | 100% | Finished | 3017 | 3017 | 100 | 166.6667 | 100 | 100 | 115.0481 | 100
5 | chape 2B | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-04-20 08:00 | 5d | 26153 | 0 | 0 | 2433 | 0 | 28586 | 0 | 100% | Finished | 26153 | 26153 | 100 | 100 | 100 | 100 | 109.3029 | 100
6 | plaatsen keramische tegels 2B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 2016-05-11 08:00 | 10d | 10964 | 0 | 0 | 825 | 0 | 11789 | 0 | 100% | Finished | 10964 | 10964 | 100 | 100 | 100 | 100 | 107.5246 | 100
7 | plaatsen faience 2B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 2016-05-18 08:00 | 10d | 10059 | 0 | 0 | 37 | 0 | 10096 | 0 | 100% | Finished | 10059 | 10059 | 100 | 100 | 100 | 100 | 100.3678 | 100
8 | zachte vloerbekleding 2B | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 |  | 0 | 0 | 8047 | 10d | 0 | 0 | 0 | 8047 | 0% | Not Started | 0 | 8047 | 100 |  | 0 | 100 |  | 0
9 | binnenschrijnwerk 2B | 2016-06-16 08:00 | 2016-06-27 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 |  | 0 | 0 | 28165 | 8d | 0 | 0 | 0 | 28165 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
10 | schilderwerken wanden en plafonds 2B | 2016-06-16 08:00 | 2016-07-13 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 |  | 0 | 0 | 24142 | 20d | 0 | 0 | 0 | 24142 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
11 | binnenmeubilair 2B | 2016-06-16 08:00 | 2016-06-29 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 |  | 0 | 0 | 30177 | 10d | 0 | 0 | 0 | 30177 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0
25 | nivo +3 blok B | 2016-04-04 08:00 | 2016-07-04 17:00 | 66d |  |  | 184937 |  |  | 184937 |  | 45d | [5 empty] | 101454 |  | 48.76% |  | 90184 | 184017
12 | pleisterwerken wanden 3B | 2016-04-04 08:00 | 2016-04-15 17:00 | 10d |  | 0 | 14596 | 0 | 0 | 14596 | 2016-04-06 08:00 | 10d | 14596 | 0 | 0 | 817 | 0 | 15413 | 0 | 100% | Finished | 14596 | 14596 | 100 | 100 | 100 | 100 | 105.5974 | 100
13 | pleisterwerken plafonds 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 18767 | 0 | 0 | 18767 | 2016-04-06 08:00 | 5d | 18767 | 0 | 0 | 457 | 0 | 19224 | 0 | 100% | Finished | 18767 | 18767 | 100 | 100 | 100 | 100 | 102.4351 | 100
14 | lichte scheidingswanden 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 4796 | 0 | 0 | 4796 | 2016-04-06 08:00 | 5d | 4796 | 0 | 0 | -455 | 0 | 4341 | 0 | 100% | Finished | 4796 | 4796 | 100 | 100 | 100 | 100 | 90.5129 | 100
15 | vloer uitvullingen 3B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3127 | 0 | 0 | 3127 | 2016-04-13 08:00 | 5d | 3127 | 0 | 0 | 484 | 0 | 3611 | 0 | 100% | Finished | 3127 | 3127 | 100 | 166.6667 | 100 | 100 | 115.4781 | 100
16 | chape 3B | 2016-04-14 08:00 | 2016-04-18 17:00 | 3d |  | 0 | 27108 | 0 | 0 | 27108 | 2016-04-20 08:00 | 5d | 27108 | 0 | 0 | 8248 | 0 | 35356 | 0 | 100% | Finished | 27108 | 27108 | 100 | 166.6667 | 100 | 100 | 130.4264 | 100
17 | plaatsen keramische tegels 3B | 2016-05-03 08:00 | 2016-05-12 17:00 | 8d |  | 0 | 11364 | 0 | 0 | 11364 | 2016-05-11 08:00 | 10d | 11364 | 0 | 0 | 245 | 0 | 11609 | 0 | 100% | Finished | 11364 | 11364 | 100 | 125 | 100 | 100 | 102.1559 | 100
18 | plaatsen faience 3B | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 10426 | 0 | 0 | 10426 | 2016-05-18 08:00 | 10d | 10426 | 0 | 0 | 1474 | 0 | 11900 | 0 | 100% | Finished | 10426 | 10426 | 100 | 125 | 100 | 100 | 114.1377 | 100
19 | zachte vloerbekleding 3B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 8340 | 0 | 0 | 8340 |  | 0 | 0 | 8340 | 5d | 0 | 0 | 0 | 8340 | 0% | Not Started | 0 | 8340 | 100 |  | 0 | 100 |  | 0
20 | binnenschrijnwerk 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 29193 | 0 | 0 | 29193 |  | 0 | 0 | 29193 | 8d | 0 | 0 | 0 | 29193 | 0% | Not Started | 0 | 29193 | 100 |  | 0 | 100 |  | 0
21 | schilderwerken wanden en plafonds 3B | 2016-06-07 08:00 | 2016-06-27 17:00 | 15d |  | 0 | 25022 | 0 | 0 | 25022 |  | 0 | 0 | 25022 | 15d | 0 | 0 | 0 | 25022 | 0% | Not Started | 0 | 25022 | 100 |  | 0 | 100 |  | 0
22 | binnenmeubilair 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 31278 | 0 | 0 | 31278 |  | 0 | 0 | 31278 | 8d | 0 | 0 | 0 | 31278 | 0% | Not Started | 0 | 31278 | 100 |  | 0 | 100 |  | 0
23 | opkuis voor oplevering blok B | 2016-06-28 08:00 | 2016-07-04 17:00 | 5d |  | 0 | 920 | 0 | 0 | 920 |  | 0 | 0 | 920 | 5d | 0 | 0 | 0 | 920 | 0% | Not Started | 0 | 0 | 100 |  | 0 | 100 |  | 0

## TP3
| TP Status Date | 2016-07-26 17:00 |  | TP Name | Tracking Period 3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Relative baseline duration | Relative actual duration | Percentage completed | Relative baseline cost | Relative actual cost | Percentage completed
0 | Apartment Building Finishing Works (4) | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 362476 |  |  | 362476 |  | 92d | [5 empty] | 383871 |  | 100% |  | 362476 | 362476
24 | nivo +2 blok B | 2016-03-21 08:00 | 2016-07-13 17:00 | 83d |  |  | 177539 |  |  | 177539 |  | 92d | [5 empty] | 187211 |  | 100% |  | 177539 | 177539
1 | pleisterwerken wanden 2B | 2016-03-21 08:00 | 2016-04-08 17:00 | 15d |  | 0 | 14082 | 0 | 0 | 14082 | 2016-03-21 08:00 | 17d | 14082 | 0 | 0 | 475 | 0 | 14557 | 0 | 100% | Finished | 14082 | 14082 | 100 | 113.3333 | 100 | 100 | 103.3731 | 100
2 | pleisterwerken plafonds 2B | 2016-03-21 08:00 | 2016-04-01 17:00 | 10d |  | 0 | 18106 | 0 | 0 | 18106 | 2016-03-21 08:00 | 12d | 18106 | 0 | 0 | 2859 | 0 | 20965 | 0 | 100% | Finished | 18106 | 18106 | 100 | 120 | 100 | 100 | 115.7903 | 100
3 | lichte scheidingswanden 2B | 2016-03-28 08:00 | 2016-04-08 17:00 | 10d |  | 0 | 4627 | 0 | 0 | 4627 | 2016-03-30 08:00 | 10d | 4627 | 0 | 0 | 222 | 0 | 4849 | 0 | 100% | Finished | 4627 | 4627 | 100 | 100 | 100 | 100 | 104.7979 | 100
4 | vloer uitvullingen 2B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3017 | 0 | 0 | 3017 | 2016-04-13 08:00 | 5d | 3017 | 0 | 0 | 454 | 0 | 3471 | 0 | 100% | Finished | 3017 | 3017 | 100 | 166.6667 | 100 | 100 | 115.0481 | 100
5 | chape 2B | 2016-04-14 08:00 | 2016-04-20 17:00 | 5d |  | 0 | 26153 | 0 | 0 | 26153 | 2016-04-20 08:00 | 5d | 26153 | 0 | 0 | 2433 | 0 | 28586 | 0 | 100% | Finished | 26153 | 26153 | 100 | 100 | 100 | 100 | 109.3029 | 100
6 | plaatsen keramische tegels 2B | 2016-05-05 08:00 | 2016-05-18 17:00 | 10d |  | 0 | 10964 | 0 | 0 | 10964 | 2016-05-11 08:00 | 10d | 10964 | 0 | 0 | 825 | 0 | 11789 | 0 | 100% | Finished | 10964 | 10964 | 100 | 100 | 100 | 100 | 107.5246 | 100
7 | plaatsen faience 2B | 2016-05-12 08:00 | 2016-05-25 17:00 | 10d |  | 0 | 10059 | 0 | 0 | 10059 | 2016-05-18 08:00 | 10d | 10059 | 0 | 0 | 37 | 0 | 10096 | 0 | 100% | Finished | 10059 | 10059 | 100 | 100 | 100 | 100 | 100.3678 | 100
8 | zachte vloerbekleding 2B | 2016-06-02 08:00 | 2016-06-15 17:00 | 10d |  | 0 | 8047 | 0 | 0 | 8047 | 2016-06-08 08:00 | 10d | 8047 | 0 | 0 | 224 | 0 | 8271 | 0 | 100% | Finished | 8047 | 8047 | 100 | 100 | 100 | 100 | 102.7836 | 100
9 | binnenschrijnwerk 2B | 2016-06-16 08:00 | 2016-06-27 17:00 | 8d |  | 0 | 28165 | 0 | 0 | 28165 | 2016-06-22 08:00 | 10d | 28165 | 0 | 0 | -372 | 0 | 27793 | 0 | 100% | Finished | 28165 | 28165 | 100 | 125 | 100 | 100 | 98.6792 | 100
10 | schilderwerken wanden en plafonds 2B | 2016-06-16 08:00 | 2016-07-13 17:00 | 20d |  | 0 | 24142 | 0 | 0 | 24142 | 2016-06-22 08:00 | 25d | 24142 | 0 | 0 | 4411 | 0 | 28553 | 0 | 100% | Finished | 24142 | 24142 | 100 | 125 | 100 | 100 | 118.2711 | 100
11 | binnenmeubilair 2B | 2016-06-16 08:00 | 2016-06-29 17:00 | 10d |  | 0 | 30177 | 0 | 0 | 30177 | 2016-06-22 08:00 | 10d | 30177 | 0 | 0 | -1896 | 0 | 28281 | 0 | 100% | Finished | 30177 | 30177 | 100 | 100 | 100 | 100 | 93.7171 | 100
25 | nivo +3 blok B | 2016-04-04 08:00 | 2016-07-04 17:00 | 66d |  |  | 184937 |  |  | 184937 |  | 70d | [5 empty] | 196660 |  | 100% |  | 184937 | 184937
12 | pleisterwerken wanden 3B | 2016-04-04 08:00 | 2016-04-15 17:00 | 10d |  | 0 | 14596 | 0 | 0 | 14596 | 2016-04-06 08:00 | 10d | 14596 | 0 | 0 | 817 | 0 | 15413 | 0 | 100% | Finished | 14596 | 14596 | 100 | 100 | 100 | 100 | 105.5974 | 100
13 | pleisterwerken plafonds 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 18767 | 0 | 0 | 18767 | 2016-04-06 08:00 | 5d | 18767 | 0 | 0 | 457 | 0 | 19224 | 0 | 100% | Finished | 18767 | 18767 | 100 | 100 | 100 | 100 | 102.4351 | 100
14 | lichte scheidingswanden 3B | 2016-04-04 08:00 | 2016-04-08 17:00 | 5d |  | 0 | 4796 | 0 | 0 | 4796 | 2016-04-06 08:00 | 5d | 4796 | 0 | 0 | -455 | 0 | 4341 | 0 | 100% | Finished | 4796 | 4796 | 100 | 100 | 100 | 100 | 90.5129 | 100
15 | vloer uitvullingen 3B | 2016-04-11 08:00 | 2016-04-13 17:00 | 3d |  | 0 | 3127 | 0 | 0 | 3127 | 2016-04-13 08:00 | 5d | 3127 | 0 | 0 | 484 | 0 | 3611 | 0 | 100% | Finished | 3127 | 3127 | 100 | 166.6667 | 100 | 100 | 115.4781 | 100
16 | chape 3B | 2016-04-14 08:00 | 2016-04-18 17:00 | 3d |  | 0 | 27108 | 0 | 0 | 27108 | 2016-04-20 08:00 | 5d | 27108 | 0 | 0 | 8248 | 0 | 35356 | 0 | 100% | Finished | 27108 | 27108 | 100 | 166.6667 | 100 | 100 | 130.4264 | 100
17 | plaatsen keramische tegels 3B | 2016-05-03 08:00 | 2016-05-12 17:00 | 8d |  | 0 | 11364 | 0 | 0 | 11364 | 2016-05-11 08:00 | 10d | 11364 | 0 | 0 | 245 | 0 | 11609 | 0 | 100% | Finished | 11364 | 11364 | 100 | 125 | 100 | 100 | 102.1559 | 100
18 | plaatsen faience 3B | 2016-05-06 08:00 | 2016-05-17 17:00 | 8d |  | 0 | 10426 | 0 | 0 | 10426 | 2016-05-18 08:00 | 10d | 10426 | 0 | 0 | 1474 | 0 | 11900 | 0 | 100% | Finished | 10426 | 10426 | 100 | 125 | 100 | 100 | 114.1377 | 100
19 | zachte vloerbekleding 3B | 2016-05-31 08:00 | 2016-06-06 17:00 | 5d |  | 0 | 8340 | 0 | 0 | 8340 | 2016-06-08 08:00 | 5d | 8340 | 0 | 0 | 741 | 0 | 9081 | 0 | 100% | Finished | 8340 | 8340 | 100 | 100 | 100 | 100 | 108.8849 | 100
20 | binnenschrijnwerk 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 29193 | 0 | 0 | 29193 | 2016-06-15 08:00 | 10d | 29193 | 0 | 0 | 1977 | 0 | 31170 | 0 | 100% | Finished | 29193 | 29193 | 100 | 125 | 100 | 100 | 106.7722 | 100
21 | schilderwerken wanden en plafonds 3B | 2016-06-07 08:00 | 2016-06-27 17:00 | 15d |  | 0 | 25022 | 0 | 0 | 25022 | 2016-06-15 08:00 | 15d | 25022 | 0 | 0 | -2133 | 0 | 22889 | 0 | 100% | Finished | 25022 | 25022 | 100 | 100 | 100 | 100 | 91.4755 | 100
22 | binnenmeubilair 3B | 2016-06-07 08:00 | 2016-06-16 17:00 | 8d |  | 0 | 31278 | 0 | 0 | 31278 | 2016-06-15 08:00 | 10d | 31278 | 0 | 0 | -113 | 0 | 31165 | 0 | 100% | Finished | 31278 | 31278 | 100 | 125 | 100 | 100 | 99.6387 | 100
23 | opkuis voor oplevering blok B | 2016-06-28 08:00 | 2016-07-04 17:00 | 5d |  | 0 | 920 | 0 | 0 | 920 | 2016-07-06 08:00 | 5d | 920 | 0 | 0 | -19 | 0 | 901 | 0 | 100% | Finished | 920 | 920 | 100 | 100 | 100 | 100 | 97.9348 | 100

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Tracking Period 1 | 2016-03-21 08:00 | 2016-05-11 08:00 | 167133 | 134379 | 150373 | 2016-05-02 17:00 | -32754 | 80.4% | -15994 | 89.36% | -6d | 83.78% | 100% | 2016-07-25 12:00 | 2016-08-11 10:00 | 2016-08-29 12:00 | 2016-07-25 10:00 | 2016-08-11 10:00 | 2016-08-23 09:00 | 2016-07-21 17:00 | 2016-08-05 09:00 | 2016-08-16 12:00 | 378470 | 405618.4638 | 434067.1479 | 422617.8065 | 467832.8717 | 455020.8116 | 410842.4079 | 408846.3506 | 0.83784 | 0.89364 | 0.80402 | 1 | -6 | 0.89364 | 1 | 0.83784 | 1
Tracking Period 2 | 2016-05-11 08:00 | 2016-06-08 08:00 | 279072 | 177192 | 195767 | 2016-05-30 17:00 | -101880 | 63.49% | -18575 | 90.51% | -6d | 89.47% | 100% | 2016-08-16 11:00 | 2016-09-19 15:00 | 2016-10-07 11:00 | 2016-08-11 15:00 | 2016-09-19 15:00 | 2016-09-29 12:00 | 2016-07-21 17:00 | 2016-07-27 15:00 | 2016-08-02 12:00 | 381051 | 400474.2827 | 487583.6534 | 402849.1176 | 518174.7316 | 424557.4924 | 413471.5581 | 400944.8821 | 0.89474 | 0.90512 | 0.63493 | 1 | -6 | 0.90512 | 1 | 0.89474 | 1
Tracking Period 3 | 2016-06-08 08:00 | 2016-07-26 17:00 | 362476 | 362476 | 383871 | 2016-07-13 17:00 | 0 | 100% | -21395 | 94.43% | -9d | 90.22% | 100% | 2016-07-13 17:00 | 2016-07-13 17:00 | 2016-07-20 16:00 | 2016-07-26 17:00 | 2016-07-26 17:00 | 2016-07-26 17:00 | 2016-07-26 17:00 | 2016-07-26 17:00 | 2016-07-26 17:00 | 383871 | 383871 | 383871 | 383871 | 383871 | 383871 | 383871 | 383871 | 0.90217 | 0.94427 | 1 | 1 | -9 | 0.94427 | 1 | 0.90217 | 1